| PART ONE | ITEM NO. |
| --- | --- |

REPORT OF THE

##### DIRECTOR OF CORPORATE SERVICES

To the: QUALITY & PERFORMANCE SCRUTINY AUDIT SUB COMMITTEE

On:	Monday 1st September 2003

TITLE: Internal Audit Plan Progress 2003/2004

RECOMMENDATIONS:
Members are asked to note the contents of the report.

EXECUTIVE SUMMARY:
The purpose of this report is to inform members of progress against the 2003/2004 Internal Audit Plan.

BACKGROUND DOCUMENTS:

None

ASSESSMENT OF RISK:

The internal audit plan is conducted under a risk-based methodology at both a planning and operational level.

THE SOURCE OF FUNDING IS:

N/A

LEGAL ADVICE OBTAINED:

N/A

FINANCIAL ADVICE OBTAINED:

N/A

CONTACT OFFICER:

Chris Griffiths Business Assurance Manager 0161 793 3217

WARD(S) TO WHICH REPORT RELATES:

N/A

KEY COUNCIL POLICIES:

N/A

DETAILS:

INTRODUCTION

This report summarises the progress relating to delivery of the Internal Audit Plan for 2003/2004.

NOTES TO THE REPORT

Plan delivery

The table below shows that in the period 1st April 2003 to 31st July 2003, 34% of the Salford Internal Audit element of the plan and 32% of the total plan (including Energy Audit and GMPA) has been delivered.

As reported to the June 2003 committee, 74 days relating to the 2002/2003 plan for Corporate Services were delivered in April 2003. The figure relating to Corporate Services in the table is, therefore, the net total of days relating to the 2003/2004 plan.

Staffing

The Principal Risk Auditor post on the Salford Team is currently vacant. Interviews are scheduled for 9th September 2003.

The Senior Auditor on the Salford team, who has been on long-term sick leave, returned to work on 4th August 2003. The sickness figure reported, totalling 85 days, includes 65 days in relation to this one long-term absence.

The vacant post of Senior Energy Officer will be re advertised shortly.

Some of the time lost to vacancies and sick leave is being recovered by the employment of one agency staff member, and one member of staff on a 12 month fixed term contract. It is planned to recruit one additional agency staff member, for a period of four months, to deliver some projects, which have been rescheduled during the vacancy of the Principal Risk Auditor. A planned figure of 195 days is included for vacancies in the table below.

Risk Management and Insurance staff are now based within BRC. Performance figures relating to these activities are not included in this report, but will be included in future plan progress reports to this committee.

Internal Audit Plan 2003-2004

Progress 1st April 2003to 31tst July 2003

| Organisation | Client | Actual Days (Total) | Annual Plan (Total) | % Achieved |
| --- | --- | --- | --- | --- |
| Chargeable Direct |  |  |  |  |
| Salford Mainstream | Chief Executive& Personnel | 17 | 131 | 13 |
|  | Community & Social Services | 41 | 243 | 17 |
|  | Corporate Services | 91 | 507 | 18 |
|  | Development Services | 0 | 72 | 0 |
|  | Education and Leisure | 177 | 313 | 57 |
|  | Environmental Services | 2 | 58 | 3 |
|  | Housing | 88 | 172 | 51 |
|  | To be allocated (PIR/Contingency) | 67 | 244 | 27 |
| Salford Mainstream Total | 483 | 1740 | 28 |
| Salford Specialist | Best Value/Irregularity | 180 | 660 | 27 |
|  | Computer | 199 | 294 | 68 |
|  | Contracts | 99 | 182 | 54 |
|  | NPHL | 50 | 130 | 38 |
| Salford Specialist Total |  | 528 | 1266 | 42 |
| Salford Audit Chargeable Direct Total | 1011 | 3006 | 34 |
| GMPA | 423 | 1530 | 28 |
| Energy Audit | 270 | 864 | 31 |
| Chargeable Direct Total | 1704 | 5400 | 32 |
| Chargeable Indirect |  |
|  | Internal Management | 226 | 352 | 64 |
|  | Leave | 284 | 998 | 28 |
|  | Maternity/Paternity leave | 0 | 90 | 0 |
|  | Vacancies | 143 | 195 | 73 |
|  | Sickness | 85 | 177 | 48 |
|  | Staffing | 30 | 167 | 18 |
|  | Training | 90 | 155 | 58 |
| Salford Chargeable Indirect Total | 858 | 2134 | 40 |
| GMPA Chargeable Indirect Total | 195 | 618 | 32 |
| Chargeable Indirect Total | 1053 | 2752 | 38 |
| Grand Total |  | 2757 | 8152 | 34 |