| QUALITY & PERFORMANCE SCRUTINY COMMITTEE | 24th March 2003 | PART 1 (OPEN TO THE PUBLIC) |
| --- | --- | --- |
| AUDIT SUB COMMITTEE |  | ITEM NO. |
| SUBJECT | : | INTERNAL AUDIT PLAN PROGRESS 2002/2003 | PERFORMANCE REVIEW MATTER |
| REPORT OF | : | THE DIRECTOR OF CORPORATE SERVICES | FOR INFORMATION |

A.  REPORT SUMMARY

- PURPOSE OF REPORT:

To inform members of progress against the Internal Audit Plan for 2002/2003.

- RECOMMENDATION

Members are asked to note the contents of the report.

- ROUTING:

Direct to Council.

- IMPLICATIONS:

| 4.1 | Resources (Financial/Staffing) | : | N/A |
| --- | --- | --- | --- |
| 4.2 | Performance Review | : | Adherence to Best Value principles will ensure that services match the best in quality and efficiency. |
| 4.3 | Environmental | : | N/A |
| 4.4 | Equal Opportunities | : | N/A |
| 4.5 | Community Strategy | : | N/A |
| 4.6 | Anti-Poverty Strategy | : | N/A |

| IF YOU HAVE ANY QUERIES PLEASE CONTACT | BACKGROUND DOCUMENTS |
| --- | --- |
| Chris Griffiths | 793 3217 |  |  |
| QUALITY CONTROL | Report prepared by | Chris Griffiths | 793 3217 |
|  | Checked by | Donald Simpson | 793 3290 |
| Corporate Services (Finance), Salford Civic Centre, Chorley Road, Swinton. M27 5AW |

B. REPORT DETAILS

5.	INTRODUCTION

  - This report summarises the progress relating to delivery of the Internal Audit Plan for 2002/2003.

6. 	NOTES TO THE REPORT

  - The report shows that after 11 months of the year 77% of the plan has been delivered. A number of factors have contributed to the plan being below target.

  - As previously reported, the delay in approving the new structure has had an adverse effect on delivery of the plan to date. During the year 1225 days have been lost to vacancies. Agency staff have been employed to cover some of the shortfall. In the period 1/4/02 to 28/2/03 agency staff have covered 620 days, leaving a net shortfall of 605 days.

  - In addition delivery of the plan has been affected by a higher level of sick leave, mainly due to two long term absences. The budgeted figure for sickness was 166 days, but 389 days have been lost to sickness during the year.

  - The actual figure for maternity leave in the year has been 228 days against a budgeted figure of 55 days.

  - Further time was lost by the secondment of a Principal Auditor to Accountancy for a period of six months. The secondment period is now complete. Other members of staff largely absorbed the post holder’s duties during the secondment.

  - Following approval of the new structure for Business Risk and Control, interviews have been held and appointments made to two vacant posts, one on the City of Salford Audit Team and one on the Energy Audit Team.

  - Further amendments to the structure, partially in response to the need to make budgetary savings have delayed recruitment to other vacant posts. Advertisements have now been placed and interviews scheduled. However any successful candidate will not be able to take up post until after the start of the new audit plan year

  - Whilst these factors have caused operational difficulties the situation has been managed on an ongoing basis to enable resources to be utilised to ensure the Organisations key business risks are addressed, as well as fulfilling all our managed audit commitments.

  - The units full SLA commitments to GMP will also be met, thus safeguarding our income level.

  - As indicated in paragraph 6.2 of this report, agency staff have covered approximately half of the days lost to vacancies. The cost differential in using agency staff means it is difficult to make up the full shortfall. Agency staff will cover further days until the end of the current plan year.

  - Some work relating to the review of key financial systems will be carried forward and completed in April.

  - The carry forward of some work to the new year, together with the use of agency staff for the remainder of the plan year will result in a likely final outturn of between 85% and 90%.

J. SPINK                      A. WESTWOOD

Head of Finance         Head of Corporate Service

Internal Audit Plan 2002-2003

Progress 1st April 2002 to 28th February 2003

| Organisation | Client | Actual Days (Total) | Annual Plan (Total) | % Achieved |
| --- | --- | --- | --- | --- |
| Chargeable Direct |  |  |  |  |
| Salford Mainstream | Chief Executive | 5 | 55 | 10 |
|  | Commty & Social Services | 264 | 260 | 102 |
|  | Corporate Services | 409 | 676 | 61 |
|  | Development Services | 65 | 151 | 43 |
|  | Education and Leisure | 162 | 269 | 60 |
|  | Environmental & Comm Serv | 24 | 73 | 33 |
|  | Housing | 145 | 251 | 58 |
|  | Personnel | 0 | 5 | 0 |
|  | Corporate | 182 | 183 | 99 |
| Salford Mainstream Total | 1256 | 1923 | 65 |
| Specialist / GMPA | Best Value | 644 | 735 | 88 |
|  | Computer | 463 | 517 | 90 |
|  | Contracts | 202 | 310 | 65 |
|  | External | 11 | 25 | 44 |
|  | GMPA | 1299 | 1530 | 85 |
| Specialist / GMPA Total |  | 2619 | 3117 | 84 |
| Audit Chargeable Direct Total | 3875 | 5040 | 77 |
| Energy Audit | 495 | 900 | 55 |
| Chargeable Direct Total | 4370 | 5940 | 74 |
| Chargeable Indirect |  |
|  | Internal Management | 678 | 312 | 217 |
|  | Leave | 1151 | 1575 | 73 |
|  | Maternity/Paternity leave | 228 | 55 | 415 |
|  | Net Vacancies | 605 | 80 | 756 |
|  | Sickness | 389 | 166 | 234 |
|  | Staffing | 211 | 211 | 100 |
|  | Training | 308 | 239 | 129 |
|  | Administration | 18 | 35 | 51 |
| Salford Total |  | 3588 | 2673 | 134 |
| Chargeable Indirect Total | 3588 | 2673 | 134 |
| Grand Total |  | 7958 | 8613 | 92 |