| PART ONE | ITEM NO.8 |
| --- | --- |

REPORT OF THE

##### DIRECTOR OF CORPORATE SERVICES

To the: QUALITY & PERFORMANCE SCRUTINY AUDIT SUB COMMITTEE

On:	Monday 19th January  2004

TITLE: Internal Audit Plan Progress 2003/2004

RECOMMENDATIONS:
Members are asked to note the contents of the report.

EXECUTIVE SUMMARY:
The purpose of this report is to inform members of progress against the 2003/2004 Internal Audit Plan.

BACKGROUND DOCUMENTS:

None

ASSESSMENT OF RISK:

The internal audit plan is conducted under a risk-based methodology at both a planning and operational level.

THE SOURCE OF FUNDING IS:

N/A

LEGAL ADVICE OBTAINED:

N/A

FINANCIAL ADVICE OBTAINED:

N/A

CONTACT OFFICER:

Chris Griffiths Business Assurance Manager 0161 793 3217

WARD(S) TO WHICH REPORT RELATES:

N/A

KEY COUNCIL POLICIES:

N/A

DETAILS:

INTRODUCTION

This report summarises the progress relating to delivery of the Internal Audit Plan for 2003/2004.

NOTES TO THE REPORT

Plan delivery

The table below shows that in the period 1st April 2003 to 30th November 2003, 71% of the Salford Internal Audit element of the plan and 65% of the total plan (including Energy Audit and GMPA) has been delivered.

Staffing

The Principal Risk Auditor post on the Salford Team is currently vacant. Interviews were held on 9th September 2003 but unfortunately an appointment was not made. The post was re-advertised with a closing date of 28th November 2003. On this occasion no suitable applications were received, so no candidates were invited for interview.

It is intended to utilise agency staff in the short term and re-advertise the post in approximately six months time.

An appointment has been made to the vacant post of Senior Energy Officer, with a proposed start date of February 2004.

Internal Audit Plan 2003-2004

Progress 1st April 2003to 30tst November 2003

| Organisation | Client | Actual Days (Total) | Annual Plan (Total) | % Achieved |
| --- | --- | --- | --- | --- |
| Chargeable Direct |  |  |  |  |
| Salford Mainstream | Chief Executive& Personnel | 27 | 131 | 21 |
|  | Community & Social Services | 118 | 266 | 44 |
|  | Corporate Services | 202 | 557 | 36 |
|  | Development Services | 0 | 72 | 0 |
|  | Education and Leisure | 445 | 346 | 129 |
|  | Environmental Services | 4 | 58 | 7 |
|  | Housing | 63 | 32 | 197 |
|  | To be allocated (PIR/Contingency) | 144 | 194 | 74 |
| Salford Mainstream Total | 1003 | 1656 | 61 |
| Salford Specialist | Best Value/Irregularity | 413 | 495 | 83 |
|  | Computer | 407 | 439 | 93 |
|  | Contracts | 224 | 209 | 107 |
|  | NPHL | 74 | 200 | 37 |
| Salford Specialist Total |  | 1118 | 1343 | 83 |
| Salford Audit Chargeable Direct Total | 2121 | 2999 | 71 |
| GMPA | 897 | 1534 | 58 |
| Energy Audit | 556 | 934 | 60 |
| NPHL | 82 | 140 | 59 |
| Chargeable Direct Total | 3656 | 5607 | 65 |
| Chargeable Indirect |  |
|  | Internal Management | 396 | 208 | 190 |
|  | Leave | 567 | 971 | 58 |
|  | Maternity/Paternity leave | 18 | 90 | 20 |
|  | Vacancies | 233 | 195 | 119 |
|  | Sickness | 190 | 125 | 152 |
|  | Staffing | 55 | 164 | 34 |
|  | Training | 175 | 258 | 67 |
| Salford Chargeable Indirect Total | 1634 | 2011 | 81 |
| GMPA Chargeable Indirect Total | 411 | 618 | 66 |
| Chargeable Indirect Total | 2045 | 2629 | 78 |
| Grand Total |  | 5701 | 8236 | 69 |