| PART ONE | ITEM NO.6 |
| --- | --- |

REPORT OF THE

##### DIRECTOR OF CORPORATE SERVICES

To the: QUALITY & PERFORMANCE SCRUTINY AUDIT SUB COMMITTEE

On:	Monday 19th April 2004

TITLE: Internal Audit Plan Progress 2003/2004

RECOMMENDATIONS:
Members are asked to note the contents of the report.

EXECUTIVE SUMMARY:
The purpose of this report is to inform members of progress against the 2003/2004 Internal Audit Plan.

BACKGROUND DOCUMENTS:

None

ASSESSMENT OF RISK:

Internal Audit projects are managed within the Unit’s risk based audit protocols aimed at giving assurance regarding the management of the City Council’s key business risks.

THE SOURCE OF FUNDING IS:

N/A

LEGAL ADVICE OBTAINED:

N/A

FINANCIAL ADVICE OBTAINED:

N/A

CONTACT OFFICER:

Andrew Waine - Audit Manager 0161 793 3357

WARD(S) TO WHICH REPORT RELATES:

N/A

KEY COUNCIL POLICIES:

N/A

DETAILS:

INTRODUCTION

This report summarises the progress relating to delivery of the Internal Audit Plan for 2003/2004.

NOTES TO THE REPORT

Plan delivery

The table below shows that in the period 1st April 2003 to 31st March 2004, 77% of the Salford Internal Audit element of the plan and 98% of the total plan (including Energy Audit and GMPA) had been delivered.

Staffing

A permanent appointment has been made to the post of Principal Auditor on the Salford Team, which had been vacant since May 2003. The Officer was appointed in early March 2004.

Agency staff have been utilised in the intervening period to cover for vacancies on the Team. An advertisement will be placed shortly for the vacant Senior Auditor post, which has come about as a result of internal staff transfers as a result of the restructure that came into effect from 1st February 2004.

Internal Audit Plan 2003-2004

Progress 1st April 2003 to 31tst March 2004

| Organisation | Client | Actual Days (Total) | Annual Plan (Total) | % Achieved |
| --- | --- | --- | --- | --- |
| Chargeable Direct |  |  |  |  |
| Salford Mainstream | Chief Executive & Personnel | 27 | 131 | 21 |
|  | Community & Social Services | 148 | 266 | 56 |
|  | Corporate Services | 395 | 577 | 68 |
|  | Development Services | 0 | 72 | 0 |
|  | Education and Leisure | 408 | 286 | 143 |
|  | Environmental Services | 4 | 58 | 7 |
|  | Housing | 65 | 97 | 67 |
|  | Corporate Management | 239 | 174 | 137 |
| Salford Mainstream Total | 1286 | 1661 | 77 |
| Salford Specialist | Best Value/Irregularity | 696 | 500 | 139 |
|  | Computer | 524 | 439 | 119 |
|  | Contracts | 316 | 209 | 151 |
|  | NPHL | 106 | 130 | 81 |
| Salford Specialist Total | 1642 | 1278 | 128 |
| Salford Audit Chargeable Direct Total | 2928 | 2939 | 100 |
| GMPA | 1447 | 1534 | 94 |
| Energy Audit | 863 | 934 | 92 |
| External | 35 | 0 | 0 |
| NPHL | 154 | 140 | 110 |
| Chargeable Direct Total | 5427 | 5547 | 98 |
| Chargeable Indirect |  |
|  | Internal Management/Administration/Planning/Meetings | 596 | 208 | 287 |
|  | Leave | 987 | 1091 | 90 |
|  | Sickness | 212 | 125 | 170 |
|  | Staffing inc vacancies/JE/Recruitment | 347 | 164 | 212 |
|  | Training | 466 | 318 | 147 |
| Salford Chargeable Indirect Total | 2608 | 1906 | 137 |
| GMPA Chargeable Indirect Total | 607 | 618 | 98 |
| Chargeable Indirect Total | 3215 | 2524 | 127 |
| Grand Total | 8642 | 8071 | 107 |