| PART ONE | ITEM NO. |
| --- | --- |

REPORT OF THE

##### DIRECTOR OF CORPORATE SERVICES

To the: QUALITY & PERFORMANCE AUDIT SUB COMMITTEE

On:	Monday 2nd June 2003

TITLE:  INTERNAL AUDIT PLAN 2002/2003 FINAL OUTTURN

RECOMMENDATIONS:
Members are asked to note the contents of  the report.

EXECUTIVE SUMMARY:
The purpose of this report is to inform members of the final outturn position relating to the Internal Audit Plan for 2002/2003.

BACKGROUND DOCUMENTS:
None

ASSESSMENT OF RISK:
N/A

THE SOURCE OF FUNDING IS:
N/A

LEGAL ADVICE OBTAINED:
N/A

FINANCIAL ADVICE OBTAINED:
N/A

CONTACT OFFICER:

Chris Griffiths Business Assurance Manager  0161 793 3217

WARD(S) TO WHICH REPORT RELATES:

N/A

KEY COUNCIL POLICIES:

N/A

DETAILS:

INTRODUCTION

This report details the final outturn position relating to delivery of the Internal Audit Plan for 2002/2003.

NOTES TO THE REPORT

The audit plan progress report submitted to the March Audit Committee stated that 77% of the plan had been delivered, and detailed a number of factors, which had contributed to the plan being below target.

The main factors were a high level of vacancies pending approval of the new structure, a higher than budgeted level of sickness and maternity leave and the secondment of a Principal Auditor to Accountancy for a period of six months.

Whilst these factors have caused operational difficulties the situation has been managed on an ongoing basis to enable resources to be utilised to ensure the Organisations key business risks are addressed, as well as fulfilling all our managed audit commitments.

It was reported that some work relating to the review of key financial systems will be carried forward and completed in April 2003.

It was forecast that the carry forward of some work to the new year, together with the use of agency staff for the remainder of the plan year would result in a likely final outturn of between 85% and 90%

The table below shows that the final outturn figure was 87%.

Internal Audit Plan 2002-2003

Final Outturn

| Organisation | Client | Actual Days (Total) | Annual Plan (Total) | % Achieved |
| --- | --- | --- | --- | --- |
| Chargeable Direct |  |  |  |  |
| Salford Mainstream | Chief Executive and Personnel | 14 | 60 | 23 |
|  | Community & Social Services | 269 | 260 | 103 |
|  | Corporate Services | 669 | 676 | 99 |
|  | Development Services | 65 | 151 | 43 |
|  | Education and Leisure | 164 | 269 | 61 |
|  | Environmental Services | 24 | 73 | 33 |
|  | Housing | 160 | 251 | 64 |
|  | Corporate | 204 | 183 | 111 |
| Salford Mainstream Total |  | 1569 | 1923 | 82 |
| Specialist / GMPA | Best Value | 685 | 735 | 93 |
|  | Computer | 527 | 517 | 102 |
|  | Contracts | 216 | 270 | 80 |
|  | External | 12 | 25 | 48 |
|  | NPHL | 57 | 40 | 143 |
| Specialist |  | 1497 | 1587 | 94 |
| Salford Audit Chargeable Direct Total |  | 3066 | 3510 | 87 |
| GMPA |  | 1442 | 1530 | 94 |
| Energy Audit |  | 551 | 900 | 61 |
| Chargeable Direct Total |  | 5059 | 5940 | 85 |
| Chargeable Indirect |  |  |  |  |
|  | Internal Management | 765 | 312 | 245 |
|  | Leave | 1221 | 1575 | 78 |
|  | Maternity/Paternity leave | 228 | 55 | 415 |
|  | Net Vacancies | 636 | 80 | 795 |
|  | Sickness | 442 | 166 | 266 |
|  | Staffing | 251 | 211 | 119 |
|  | Training | 339 | 239 | 142 |
|  | Administration | 18 | 35 | 51 |
| Chargeable Indirect Total |  | 3900 | 2673 | 146 |
| Grand Total |  | 8959 | 8613 | 104 |