## Appendix 2 - Local Authority Benchmarking Data- PSA performance

## Pilot LPSAs Achievement*of Targets to March 2004

| Authority | On Target | Not on target | 60% of target met |
| --- | --- | --- | --- |
| Birmingham | 5 | 4 | 3 |
| Blackburn with Darwen | 9 |  | 3 |
| Derbyshire | 8 | 4 |  |
| Kent | 8 | 1 | 3 |
| Lewisham | 4 | 3 |  |
| Milton Keynes | 3 | 9 |  |
| Newcastle | 6 | 3 | 3 |
| Sheffield | 4 | 4 | 4 |
| Stockton on Tees | 8 | 3 | 1 |
| Tameside | 9.5 | 2.5 |  |

NB. all figures are estimates

#### Progress of Local Authorities that finish in 2005

| Authority | On target* | Maybe** | Not on target*** |
| --- | --- | --- | --- |
| Bolton | 7 | 5 |  |
| Cheshire | 7 | 4 | 2 |
| Rochdale | 8 | 4 | 7 |
| Leicester | 8 | 2 | 2 |
| Salford | 6 | 1 | 5 |
| Staffordshire | 3 | 5 | 4 |

NB. These are estimates. Each authority is measuring ‘success’ slightly differenty:

*On target could refer to- 100% of target likely to be met, 100% of grant likely to be received

**Maybe could refer to- 60% of target likely to be met, part of grant likely to be received, May reach 100% of target

***Not on target could refer to- less than 60% of target likely to be met, no funding likely to be received, not going to meet 100% of target

Main Problems identified

- Definitions used needing clarification/ renegotiation

- Unrealistic targets

- Non delivery of freedoms and flexibilities

Key factors for success identified were:

- Additional investment for final year, especially in areas falling short of target

- Not wasting energy and resources on unreachable targets

- Renegotiation of counting methodology for example, re. Bus usage

- Positive energetic approach, driven by staff, service managers and leader, directors

- Robust monitoring system with quarterly reviews and “improvement clinics” with service managers and directors

Lessons learnt for the second generation LPSAs included:

- For next round: analyse targets and agree only targets where likelihood of success is high

- Take time to negotiate targets from outset

- Clarify what exactly is being measured and how

- Be rigorous on baseline settings

- Don’t waste time with freedom and flexibilities