APPENDIX A

Action Plan

| Action | Due Date | Responsibility? |
| --- | --- | --- |
| Prepare draft corporate risk register, based on outcomes of workshops and existing risk assessments, for agreement by Directors Team (and Cabinet/Audit Committee?) | Sept 02 | A Westwood |
| Prepare draft risk management strategy for agreement by Directors Team (and Cabinet/Audit Committee) | Sept 02 | A Westwood |
| Pilot facilitated half-day DMT meetings (with relevant Executive Member/members of Audit Committee) in Development Services to identify key operational risks and additional controls required | Oct 02 | D Simpson & B Taylor |
| Roll out DMT workshops across all directorates (with relevant Executive member/Audit Committee members) | No later than Mar 03 | D Simpson |
| Corporate risk register, revised in light of directorate outcomes, agreed by Directors (and Cabinet/Audit Committee) | July 03 | A Westwood |
| Identify and train risk management champions in directorates and Internal Audit (and in Cabinet/Scrutiny) | Sept 03 | A Westwood |
| Include risk management in training for all Executive Members/Deputies and scrutiny panel members | Sept 03 | A Eastwood |
| Review service planning process/format based on draft corporate risk register and outcomes of directorate workshops, to include explicit reference to risk management (detailing role of scrutiny) | No later than July 03 | D Simpson |
| Revise forms for recording key decisions taken under delegated powers to include explicit reference to risks and controls. | No later than Apr 03 | A Eastwood |
| Record identified risks and controls against decisions taken at Directors Team in minutes. | From Sept 02 | A Eastwood |
| Consider amending report template for Cabinet/Council etc to include section on risks and controls (highlighting risks of inaction as well as of actions) | No later than Apr 03 | A Eastwood |
| Establish Corporate Governance Risk Management Group with work programme and agree reporting mechanism to Directors Team | July 03 | A Westwood |