| QUALITY & PERFORMANCE SCRUTINY COMMITTEE | 11th DECEMBER 2000 | PART 1 (OPEN TO THE PUBLIC) |
| --- | --- | --- |
|  |  | ITEM NO. |
| SUBJECT | : | INTERNAL AUDIT PLAN 2000/2001 | PERFORMANCE REVIEW MATTER |
| REPORT OF | : | THE DIRECTOR OF CORPORATE SERVICES | FOR INFORMATION |

A.  REPORT SUMMARY

- PURPOSE OF REPORT:

To inform Members of  Internal Audit activity against the planned programme for the period 1st August 2000 to 31st October 2000.

- RECOMMENDATION

Members are asked to note the contents of the report.

- ROUTING:

Direct to Council.

- IMPLICATIONS:

| 4.1 | Resources (Financial/Staffing) | : | N/A |
| --- | --- | --- | --- |
| 4.2 | Performance Review | : | Adherence to Best Value principles will ensure that services match the best in quality and efficiency. |
| 4.3 | Environmental | : | N/A |
| 4.4 | Equal Opportunities | : | N/A |
| 4.5 | Community Strategy | : | N/A |
| 4.6 | Anti-Poverty Strategy | : | N/A |

| IF YOU HAVE ANY QUERIES PLEASE CONTACT | BACKGROUND DOCUMENTS |
| --- | --- |
| Donald Simpson | 793 3290 |  |  |
| QUALITY CONTROL | Report prepared by | Chris Griffiths | 793 3427 |
|  | Checked by | Donald Simpson | 793 3290 |
| Corporate Services (Finance), Salford Civic Centre, Chorley Road, Swinton. M27 5AW |

B. REPORT DETAILS

5. INTRODUCTION

This report summarises the progress against the Internal Audit plan for the period 1st April 2000 to 31st October 2000.

6. NOTES TO THE REPORT

6.1 	Progress during the period has seen 48% of the planned days for the year achieved. Continued progress at this rate would give a likely final outturn of 83%.

  - A disproportionate amount of time continues to be lost to vacancies, still to be resolved by the completion of filling the new audit structure, reported to the 11/9/2000 Scrutiny Committee. As at 31/10/2000 415 days have been lost. Continuation at this rate would give a final total of 711 days lost for the year compared to a planned figure of 200 days.

  - Staff are now in place in all but one of the posts on the new Best Value, Consultancy and Investigations Team. Great demands have been placed on the new team particularly relating to Special Investigations and Consultancy work. A summary of Special Investigations undertaken has been provided to this Committee. Consultancy work is also underway with other Local Authorities on an income-generating basis and a progress report will be provided to the next Committee.

  - The new Energy Audit Structure previously reported has now been filled. A report on the work of the team has been provided to this Committee.

  - The Purchasing function has now been transferred from Internal Audit to the new Financial Support Group. Reports on this function will therefore not form part of future Internal Audit progress reports.

J. SPINK              A. WESTWOOD

Head of Finance       Head of Corporate Services

| CLIENT | DEPARTMENT | 2000 PLAN | PROPORTION TO DATE | DAYS | VARIANCE TO PLANNED |
| --- | --- | --- | --- | --- | --- |
| SALFORD |  |  |  |  |  |
| Chief Executives | Chief Executives | 75 | 44 | 35 | -9 |
| Consortium | Consortium | 30 | 18 | 11 | -7 |
| Corporate Services | Finance | 249 | 145 | 121 | -24 |
| Corporate Services | I.T. Services | 65 | 38 | 11 | -27 |
| Corporate Services | Law & Administration | 54 | 32 | 12 | -20 |
| Development Services | Development Services | 138 | 81 | 43 | -38 |
| Development Services | Highway Services | 23 | 13 | 3 | -10 |
| Development Services | Valuation & Estates | 50 | 29 | 2 | -27 |
| Education & Leisure | City Leisure | 40 | 23 | 7 | -16 |
| Education & Leisure | Citywide | 86 | 50 | 4 | -46 |
| Education & Leisure | Education | 343 | 200 | 250 | 50 |
| Education & Leisure | Leisure | 56 | 33 | 63 | 30 |
| Env & Con Services | Cityclean | 51 | 30 | 14 | -16 |
| Env & Con Services | Env & Con Services | 80 | 47 | 10 | -37 |
| Env & Con Services | Outdoor Services | 28 | 16 | 23 | 7 |
| Housing Services | Building Services | 39 | 23 | 12 | -11 |
| Housing Services | Housing Services | 194 | 113 | 42 | -71 |
| Personnel | Personnel | 42 | 25 | 13 | -12 |
| Policy & Resources | Policy & Resources * | 1581 | 922 | 945 | 23 |
| Social Services | Social Services | 362 | 211 | 115 | -96 |
| SALFORD TOTAL |  | 3586 | 2092 | 1736 | -356 |
| GMPA TOTAL |  | 1743 | 1017 | 754 | -263 |
| Group Total |  | 5329 | 3109 | 2490 | -619 |
| Audit General |  | 3284 | 1916 | 2479 | 563 |
| Group Total |  | 8613 | 5024 | 4969 | -55 |
| * Policy and Resources includes Corporate specialist audit time for the following groups: - |
|  | Computer |  |  |  |  |
|  | Contracts |  |  |  |  |
|  | Energy |  |  |  |  |
|  | Irregularity |  |  |  |  |
|  | VFM |  |  |  |  |
|  | Purchasing |  |  |  |  |

| GROUP | 2000 PLAN | PROPORTION TO DATE | DAYS | VARIANCE TO PLANNED |
| --- | --- | --- | --- | --- |
| SALFORD |  |  |  |  |
| Computer | 442 | 258 | 181 | -77 |
| Contracts | 258 | 151 | 106 | -45 |
| Energy | 537 | 313 | 303 | -10 |
| Irregularity/VFM | 358 | 209 | 274 | 65 |
| Mainstream | 1633 | 953 | 615 | -338 |
| Purchasing | 358 | 209 | 257 | 48 |
| Salford Group Total | 3586 | 2092 | 1736 | -356 |
| GMPA Group Total | 1743 | 1017 | 754 | -263 |
| Group Total | 5329 | 3109 | 2490 | -619 |
| AUDIT GENERAL |  |  |  |  |
| Audit Development | 107 | 62 | 126 | 64 |
| Audit Management | 741 | 432 | 382 | -50 |
| Clerical & Administration | 247 | 144 | 229 | 85 |
| Consultancy | 111 | 65 | 65 | 0 |
| Leave | 1403 | 818 | 724 | -94 |
| Non Audit Work | 59 | 34 | 107 | 73 |
| Reduced Hours | 63 | 37 | 62 | 25 |
| Sickness | 180 | 105 | 178 | 73 |
| Training | 173 | 101 | 191 | 90 |
| Vacancies | 200 | 117 | 415 | 298 |
| Audit General Total | 3284 | 1916 | 2479 | 563 |
| Grand Total | 8613 | 5024 | 4969 | -55 |