Appendix A

PERSONNEL SERVICES - SERVICE PLAN 2000/2001

REVIEW OF ACHIEVEMENTS - SERVICE PLAN PART 1

Overview

Details of the work of the Directorate’s functional groups were set out in the Service Plan.  It should be borne in mind that a number of initiatives will involve the whole Directorate.  These include:-

- Implementation of Single Status

- Implementation of Attendance Management arrangements

- Implementation of Fair Funding for services to Schools

- Implementation of e-merge / Information Society initiatives

- Best Value Inspection Improvement Plans (NEW WORK)

These are not separated out here but are reported on within each of the following sections.

Operational Management - Planned Work

| Objective | Achievement |
| --- | --- |
| Continued implementation of the Single Status Agreement - 1st to 4th quarters | Negotiations concluded Communications strategy developed and implemented Employee ballot held Implementation date revised to September 2000 Contracts of employment amended as needed Some implementation issues will continue into 2001 / 02 plan year. |
| Re-tender for the external advertising contract - 3rd quarter | Views of customers sought Discussions held with Media Unit Discussions held with other local authorities Plans on hold pending outcome of those discussions Improvements made to existing arrangements until position clarified |
| Development of the Directorate's intranet / extranet web pages -1st to 4th quarters | Website available Jobs bulletin published both internally and externally Special events pages published as and when necessary |

Operational Management - Additional Work Undertaken

In addition to the work outlined in the Service Plan the Team has been involved in some work which was unforeseen. Major items are set out below:

| Criminal Records Bureau (Criminal records checks on people in sensitive positions) | Respond to consultation paper produced by the Bureau on its future operation Consult with interested parties inside and outside the City Council Liase with other local authorities |
| --- | --- |
| Best Value Review of Strategic Options for Support Services | Best Value review of Personnel Outstations increased to include the whole of Personnel Focus Groups held with employees Customer consultation exercise conducted |
| Call Centre (Transfer of function) | Contribution to Business Process Reengineering exercise Formulation of options / recommendations Consultation with employees concerned |

Police and Management Services Group - Planned Work

| Objective | Achievement |
| --- | --- |
| Agreeing an annual programme of work with clients | Programme agreed Programme reflected in Service Level Agreements |
| Prepare for the introduction of a Job Evaluation Scheme - ongoing work programmed for two years | Options evaluated Initial training undertaken |
| Assisting with Best Value Reviews | Contribute to the work of the Best Value Review Panel for Personnel Outstations Provide support / analysis for other reviews as required |

Police and Management Services Group - Additional Work Undertaken

In addition to the work outlined in the Service Plan the Teams have been involved in some work which was unforeseen. Major items are set out below:

| Best Value Review | Best Value review of Personnel Outstations increased to include the whole of Personnel Services and other support services Contribution to consultation process Contribution to tenderer evaluation process Assistance with analysis of information |
| --- | --- |
| Single Status | Support to negotiations by provision of information Analysis of information produced Development of options for negotiations |
| Improvement Plans | Development of Improvement Plans from Best Value Inspection process (Procurement and Crime reviews) |

Consultancy Services Group - Planned Work

| Objective | Achievement |
| --- | --- |
| Develop and implement the revised attendance management arrangements - completion 4th quarter | Arrangements developed and agreed with trade unions Information pack developed and launched with briefing sessions in each Directorate Letters and leaflet campaign to inform employees Monitoring arrangements put in place |
| Introduce improved secure storage arrangements for medical records - completion 4th quarter | Planned subject to finance No funding available therefore not achieved Alternatives being examined |
| Contribute to fair funding arrangements - completion 4th quarter | Service Level Agreements signed with all schools for Personnel support Monitoring arrangements developed Revised SLA's to go to schools ready for next academic year |

Consultancy Services Group - Planned Work (cont'd)

| Objective | Achievement |
| --- | --- |
| Assist the Environmental Services Directorate in developing a comprehensive Human Resources Plan - completion 4th quarter | Assistance provided with development of revised refuse collection arrangements Assistance provided with staff discussions Implementation will continue into 2001 / 02 plan year |

Consultancy Services Group - Additional Work Undertaken

In addition to the work outlined in the Service Plan the Teams have been involved in some work which was unforeseen. Major items are set out below:

| Revised Disciplinary Procedure for Schools | Revised procedure drafted Agreed with Professional Associations Awaiting adoption by Governing Bodies |
| --- | --- |
| School closures | Communications issues Production of information to assist planning process Dealing with redeployment, compensation, welfare etc. |
| Implementation of SAP | Member of Steering Group and various working parties Leading on implementation on transfer to monthly pay Communication / training work undertaken |
| Housing Area Offices | Development of organisation structure Production of support information Discussions with Trade Unions Implementation of revised arrangements |
| Community & Social Services | Reshaping service provision Home Care and Elderly sectors Development and implementation of revised staffing arrangements |
| The Lowry | Provision of advice on Health and Safety issues This work produced some external income |

Organisation Development and Equalities Group - Planned Work

| Objective | Achievement |
| --- | --- |
| Implementing equality policies and provision of advice primarily to Directorates to support good practice in terms of employment and service delivery; | Officer Working Group established Equality of Service Delivery Policy developed and implemented Process for monitoring reports of racist incidents developed and implemented Training strategy developed and publicised Training programme established and publicised |

| Advising and consulting with Directorates to ensure accessible services for the whole community paying particular attention to the needs of disabled people; | Progress delayed by non-availability of Access Officer post Accessibility criteria established Criteria being applied by Development Services Directorate so as to draw up a priority list |
| --- | --- |
| To provide training and development opportunities that enable employees to make an enhanced contribution within their respective area of service; | Corporate programme - 62 courses provided Most employees within appraisal scheme 29 training events to support management competencies Annual training plan produced |
| To develop a programme of training for Elected Members which will provide support and development into the new political arrangements and beyond; | Annual training plan produced 236 attendances at Elected Member training events Training provided on new technology and new political arrangements |
| To ensure that the Authority continues to offer high quality training opportunities through schemes such as Modern Apprenticeships, New Deal etc.; | IiP promoted in all Directorates 29 modern apprenticeships provided 37 New Deal opportunities provided |
| Introduction of a number of initiatives to promote a staff care package for employees. | Counselling Service introduced Weight Watchers sessions provided Passport to Leisure scheme promoted Changes to working arrangements as part of Single Status to improve flexibility |
| To develop the culture of the City Council and support change | Partnerships at Work Organisational Development model published 74 days OD consultancy provided 25 days Team Development work provided |

Organisation Development and Equalities Group - Additional Work Undertaken

| NVQ Assessments | Revised arrangements for assessment of admin trainees Individual coaching for Assessors |
| --- | --- |
| Assessment Centre | Growing use of Assessment / Development Centres |
| Change Management | Involvement in implementation of FSG staffing arrangements Community Strategy developments Involvement with call centre development |