| QUALITY & PERFORMANCE SCRUTINY COMMITTEE | 17th DECEMBER 2001 | PART 1 (OPEN TO THE PUBLIC) |
| --- | --- | --- |
|  |  | ITEM NO. |
| SUBJECT | : | INTERNAL AUDIT PLAN PROGRESS 2001/2002 | PERFORMANCE REVIEW MATTER |
| REPORT OF | : | THE DIRECTOR OF CORPORATE SERVICES | FOR INFORMATION |

A.  REPORT SUMMARY

- PURPOSE OF REPORT:

To inform members of progress against the Internal Audit Plan for 2001/2002.

- RECOMMENDATION

Members are asked to note the contents of the report.

- ROUTING:

Direct to Council.

- IMPLICATIONS:

| 4.1 | Resources (Financial/Staffing) | : | N/A |
| --- | --- | --- | --- |
| 4.2 | Performance Review | : | Adherence to Best Value principles will ensure that services match the best in quality and efficiency. |
| 4.3 | Environmental | : | N/A |
| 4.4 | Equal Opportunities | : | N/A |
| 4.5 | Community Strategy | : | N/A |
| 4.6 | Anti-Poverty Strategy | : | N/A |

| IF YOU HAVE ANY QUERIES PLEASE CONTACT | BACKGROUND DOCUMENTS |
| --- | --- |
| Donald Simpson | 793 3290 |  |  |
| QUALITY CONTROL | Report prepared by | Chris Griffiths | 793 3217 |
|  | Checked by | Donald Simpson | 793 3290 |
| Corporate Services (Finance), Salford Civic Centre, Chorley Road, Swinton. M27 5AW |

B. REPORT DETAILS

5.	INTRODUCTION

  - This report summarises the progress relating to delivery of the Internal Audit Plan for 2001/2002.

6. 	NOTES TO THE REPORT

  - The report shows that 64% of the Salford plan has been delivered to date.

  - Some amendments have been made to the planned days for individual Directorates in line with the flexible plan now operated.

  - Planned days have also been adjusted in some instances between audit teams to utilise specialist skills where required.

  - Planned days for the year have already been achieved or are on target in a number of Directorates. Directorates where the plan is behind target have projects planned for the remainder of the year.

  - The most notable shortfall is currently in Development Services, as a result of the majority of the work for this Directorate being programmed for the final quarter of the year.

J. SPINK                      A. WESTWOOD

Head of Finance         Head of Corporate Service

Internal Audit Plan Progress From 1st April 2001 to 2nd December 2001

| Client | 2001 Plan (Days) | Actual to Date (Days) | Percent of plan achieved (Proportion for period 67%) |
| --- | --- | --- | --- |
| Salford Chargeable Direct |  |  |  |
| Chief Executive | 42 | 26 | 63% |
| Commty & Social Services | 233 | 113 | 48% |
| Corporate Services | 568 | 337 | 59% |
| Development Services | 152 | 3 | 2% |
| Education and Leisure | 276 | 273 | 99% |
| Environmental & Comm Serv | 37 | 45 | 122% |
| Housing | 142 | 72 | 50% |
| Personnel | 0 | 0 | 0% |
| Policy and Resources | 170 | 49 | 29% |
| Sub Total | 1620 | 918 | 57% |
| Add Specialist Groups |  |  |  |
| BVCI | 647 | 419 | 65% |
| Computer | 432 | 347 | 80% |
| Contracts | 314 | 153 | 49% |
| Energy | 909 | 656 | 72% |
| Salford Chargeable Direct | 3922 | 2493 | 64% |
| External | 105 | 62 | 59% |
| GMPA | 1530 | 907 | 59% |
| Total Chargeable Direct | 5557 | 3462 | 62% |
| Chargeable Indirect |  |  |  |
| Audit Development | 80 | 84 | 106% |
| Administration and Management | 499 | 440 | 88% |
| Leave | 1198 | 638 | 53% |
| Other paid Leave | 28 | 37 | 132% |
| Policy and Resources | 27 | 10 | 38% |
| Sickness | 130 | 155 | 119% |
| Staffing and Vacancies | 123 | 157 | 127% |
| Training | 307 | 170 | 55% |
| GMPA Forcewide | 648 | 593 | 91% |
| Chargeable Indirect Total | 3040 | 2284 | 75% |
| TOTAL PLAN | 8597 | 5746 | 67% |