| QUALITY & PERFORMANCE SCRUTINY COMMITTEE | 26th MARCH 2001 | PART 1 (OPEN TO THE PUBLIC) |
| --- | --- | --- |
|  |  | ITEM NO. |
| SUBJECT | : | PROGRESS AGAINST INTERNAL AUDIT PLAN 2000/2001 | PERFORMANCE REVIEW MATTER |
| REPORT OF | : | THE DIRECTOR OF CORPORATE SERVICES | FOR INFORMATION |

A.  REPORT SUMMARY

- PURPOSE OF REPORT:

To inform members of progress against the Internal Audit Plan for 2000/2001

- RECOMMENDATION

Members are asked to note the contents of the report.

- ROUTING:

Direct to Council.

- IMPLICATIONS:

| 4.1 | Resources (Financial/Staffing) | : | N/A |
| --- | --- | --- | --- |
| 4.2 | Performance Review | : | Adherence to Best Value principles will ensure that services match the best in quality and efficiency. |
| 4.3 | Environmental | : | N/A |
| 4.4 | Equal Opportunities | : | N/A |
| 4.5 | Community Strategy | : | N/A |
| 4.6 | Anti-Poverty Strategy | : | N/A |

| IF YOU HAVE ANY QUERIES PLEASE CONTACT | BACKGROUND DOCUMENTS |
| --- | --- |
| Donald Simpson | 793 3290 |  |  |
| QUALITY CONTROL | Report prepared by | Chris Griffiths | 793 3217 |
|  | Checked by | Donald Simpson | 793 3290 |
| Corporate Services (Finance), Salford Civic Centre, Chorley Road, Swinton. M27 5AW |

B. REPORT DETAILS

5.	INTRODUCTION

  - This report summarises the progress against the Internal Audit Plan for 2000/2001

6. 	NOTES TO THE REPORT

  - Progress against the plan after 11 months of the year stands at 69%.

  - As previously reported a disproportionate amount of time has been lost to vacancies and sickness. To date 535 days have been lost to vacancies and 378 days to sickness.

  - Recent problems in filling the new structure have now been resolved and the process is now progressing with interviews for the next stage imminent.

  - Approval has also been obtained to recruit five temporary members of staff, two internally and three from a recruitment agency, to allow a significant degree of the plan shortfall to be made up. These staff will not be in place before the end of 2000/2001, but it is planned to carry some projects from the current plan into the New Year. The recruitment of additional staff will allow important outstanding reviews, such as the new Payroll, Creditors and Debtors Systems to be completed, whilst not compromising the commencement of the new four year plan presented to this Committee.

  - The extension of the plan into 2001/2002 should result in a final outturn of approximately 80%.

J. SPINK                      A. WESTWOOD

Head of Finance         Head of Corporate Service

| GROUP | 2000 PLAN | PROPORTION TO DATE | DAYS | VARIANCE TO PLANNED |
| --- | --- | --- | --- | --- |
| SALFORD |  |  |  |  |
| Computer | 450 | 413 | 276 | -137 |
| Contracts | 258 | 237 | 203 | -34 |
| Energy | 557 | 511 | 570 | 59 |
| Best Value | 422 | 387 | 461 | 74 |
| Mainstream | 1,977 | 1,812 | 1,093 | -719 |
| Purchasing | 358 | 327 | 257 | -70 |
| Salford Group Total | 4,022 | 3,687 | 2,860 | -827 |
| GMPA Group Total | 1,743 | 1,598 | 1,252 | -346 |
| Group Total | 5,765 | 5,285 | 4,112 | -1,173 |
| AUDIT GENERAL |  |  |  |  |
| Audit Development | 109 | 100 | 183 | 83 |
| Audit Management | 324 | 297 | 303 | 6 |
| Clerical & Administration | 247 | 226 | 365 | 139 |
| Consultancy | 111 | 102 | 77 | -25 |
| Leave | 1,405 | 1,288 | 1,098 | -190 |
| Non Audit Work | 73 | 67 | 82 | 15 |
| Reduced Hours | 63 | 58 | 96 | 38 |
| Sickness | 180 | 165 | 378 | 213 |
| Training | 173 | 158 | 292 | 134 |
| Vacancies | 200 | 183 | 536 | 353 |
| Audit General Total | 2,885 | 2,644 | 3,410 | 766 |
| Grand Total | 8,650 | 7,929 | 7,522 | -407 |

| CLIENT | DEPARTMENT | 2000 PLAN | PROPORTION TO DATE | DAYS | VARIANCE TO PLANNED |
| --- | --- | --- | --- | --- | --- |
| SALFORD |  |  |  |  |  |
| Chief Executives | Chief Executives | 75 | 69 | 48 | -21 |
| Consortium | Consortium | 30 | 27 | 11 | -16 |
| Corporate Services | Finance | 249 | 228 | 180 | -48 |
| Corporate Services | I.T. Services | 65 | 60 | 36 | -24 |
| Corporate Services | Law & Administration | 54 | 49 | 31 | -18 |
| Development Services | Development Services | 138 | 127 | 88 | -39 |
| Development Services | Highway Services | 23 | 21 | 3 | -18 |
| Development Services | Valuation & Estates | 50 | 46 | 2 | -44 |
| Education & Leisure | City Leisure | 40 | 37 | 7 | -30 |
| Education & Leisure | Citywide | 86 | 79 | 31 | -48 |
| Education & Leisure | Education | 343 | 314 | 239 | -75 |
| Education & Leisure | Leisure | 56 | 51 | 118 | 67 |
| Env & Con Services | Cityclean | 51 | 47 | 64 | 17 |
| Env & Con Services | Env & Con Services | 80 | 73 | 13 | -60 |
| Env & Con Services | Outdoor Services | 28 | 26 | 35 | 9 |
| Housing Services | Building Services | 39 | 36 | 13 | -23 |
| Housing Services | Housing Services | 194 | 178 | 120 | -58 |
| Personnel | Personnel | 42 | 39 | 16 | -23 |
| Policy & Resources | Policy & Resources * | 2,144 | 1,965 | 1,630 | -335 |
| Social Services | Social Services | 235 | 215 | 175 | -40 |
| SALFORD TOTAL |  | 4,022 | 3,687 | 2,860 | -827 |
| GMPA TOTAL |  | 1,743 | 1,598 | 1,252 | -346 |
| Group Total |  | 5,765 | 5,285 | 4,112 | -1,173 |
| Audit General |  | 2,885 | 2,644 | 3,410 | 766 |
| Group Total |  | 8,650 | 7,929 | 7,522 | -407 |

Policy and Resources includes Corporate specialist audit time for the following groups: -

Computer

Contracts

Energy

Irregularity

VFM

Purchasing