| Part 1 (Open to the Public) | ITEM NO. |
| --- | --- |
| Report of the Assistant Chief Executive and Strategic Director of Sustainable Regeneration |
| Regeneration Initiatives Cabinet Working Group 18th May 2009 |
| TITLE: Update on regeneration projects and programmes. |
| RECOMMENDATIONS: That the report is noted. |
| EXECUTIVE SUMMARY: This report provides an update on key regeneration programmes, projects and developing strategies. It outlines progress against milestones and highlights emerging issues. |
| BACKGROUND DOCUMENTS AND KEY COUNCIL POLICY (Available for public inspection): Making the vision real; Salford's Community Plan for 2006 - 2016 Central Salford Vision and Regeneration Framework Salford West Strategic Regeneration Framework and Action Plan Regenerating a Great City, Salford's Neighbourhood Renewal Strategy Regeneration Report for Regeneration Initiatives Cabinet Working Group (16/03/09) |
| ASSESSMENT OF RISK: Risk is assessed and addressed within individual projects and programmes. In the current economic climate, risk levels associated with key developments have increased and require regular review and mitigation. |
| SOURCE OF FUNDING: Funding sources and applications identified. |
| COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative): Each of the projects involves property transactions and a range of property issues as well as legal, financial and human resource implications. These transactions and issues are addressed within individual projects and approved as appropriate within each project. |
| CONTACT OFFICER: Maura Carey, Group Leader, Regeneration Strategy and Co-ordination, 793 2903 Nilima Misra, Senior Project Officer, Regeneration Strategy and Co-ordination, 793 3449 Lynne Braid, Trainee Project Officer, Regeneration Strategy and Co-ordination, 793 3444 |
| WARD(S) TO WHICH REPORT RELATE(S): All |
| DETAILS: Information on regeneration projects is set out according to Community Committee areas. The report also includes regeneration programmes, a list of developing strategies and a summary of key developments. |

| Project | Key developments |
| --- | --- |
| Building Schools for the Future | The closing date for potential bidders to submit their proposals to build schools in the £182m BSF programme was 27/03/09. The shortlisted bidders are: Catalyst Lend Lease – Catalyst Lend Lease, Bovis Lend Lease, Redstone Communications Transformational Learning Partnerships – Laing O’Rourke, Hochtief, RM Education Bidders are competing to be the Preferred Partner to enter into a Local Education Partnership with Wigan MBC and Salford City Council in October 2009. |
| Port Salford | Planning application considered by the Planning and Transportation Regulatory Panel. Planning Panel requested further information. This will be presented to Planning Panel in late May/ early June 2009. |
| Salford Forest Park | Public inquiry by Secretary of State to determine future application opened on 21/04/09 for 4 -5 weeks. |
| Buile Hill Park | Proposals for the new visitor centre are being displayed for public viewing at Height Library, Swinton Civic Centre, Unity House and the Cornerstone. A planning application for the centre is expected to be submitted in May 2009. A decision on the Buile Hill Park round 1 bid submitted to the Heritage Lottery Fund is expected in June 2009. |
| Charlestown Riverside Masterplan | The Charlestown Riverside Masterplan was approved by the Pathfinder Sounding Board on 31/03/09. The masterplan was presented to Lead Members for Planning and Housing on 05/05/09. |
| Salford Central Development Framework | The Development Framework will be recommended to Lead Members for Planning and Housing for approval on 19/05/09, following incorporation of preferred option for Islington Estate. |
| Pendleton PFI | Outline solutions received from five bidders by 26/03/09 deadline. Evaluation process is underway. Shortlist of a maximum of three bidders to be determined May 2009. Bidders will be asked to submit detailed solutions by 19/05/09. |

| Ordsall Regeneration | First phase housing at Hulton Square (72 homes) completed in March 2009. |
| --- | --- |
| MediaCityUK | The BBC’s learning centre in Salford based at the former Moorside Community Learning Centre in Swinton opened on 31/03/09. The new facility marks the BBC’s physical presence in Salford prior to its move to MediaCityUK in 2011. The facility will run free workshops on using multimedia and new technology in teaching and learning. A planning application associated with the new Metrolink development approved 07/05/09. |

| Development sites |  | Buile Hill Park |
| --- | --- | --- |
| Development sites in the Claremont Weaste area: The Pendlebury Children’s Hospital. Former site of Oakwood High School declared surplus to educational requirements and earmarked for sale. The Willows site, currently home to the Salford Reds. For more information: www.salford.gov.uk/claremont-weaste |  | An improvement and restoration project is underway at Buile Hill Park, a Grade II listed park of national historic importance. Funding has been applied for through the ‘Parks for People’ project, funded by the Heritage Lottery Fund and Big Lottery Fund, to support improvements to park and the educational elements of the proposed visitor centre. In addition planning consent for conversion of a mansion and former stables into hotel and leisure suite has been approved. For more information: www.salford.gov.uk/builehill |
| Lead officers | Dave Greenfield, Sustainable Regeneration Peter Openshaw, Urban Vision |  | Contact officer | Alan Rowley, Environment Directorate |
| Funding sources | Private sector, Salford City Council officer resources |  | Funding sources | SCC capital receipts - £175,000 Insurance settlement - £100,000 for Skills Centre Section 106, SSCF |
| Pledge | Enhancing life |  | Pledge | Enhancing life |
| Pendlebury Children’s Hospital | Timescales |
| Royal Manchester Children’s Hospital in Pendlebury to close. | June 2009 |
| Former site of Oakwood High School | Timescales |
| Informal report to Lead Member for Planning to update on progress and seek guidance on way forward based on current market conditions. Choices will be to either test the market now or to mothball the site until market conditions improve. | 19/05/09 |
| The Willows site | Timescales |
| Discussions on the Willows site (including the Variety Club) and surrounding lands, will progress once position on the new stadium is clear. Discussions have focused on family housing provision. | Ongoing |

| Progress | Timescales |
| --- | --- |
| Negotiations with the prospective leaseholder for Buile Hill Mansion and former stable courtyard area. Project on hold until negotiations are complete. | Ongoing |
| Proposals for the new visitor centre displayed for public viewing at Height Library, Swinton Civic Centre, Unity House and Cornerstone. | April 2009 |
| Buile Hill Park round 1 bid submitted to the Heritage Lottery Fund. | 06/03/09 |
| Future milestones | Timescales |
| Planning permission for new visitor centre to be submitted. | May 2009 |
| HLF decision on round 1 bid expected. | June 2009 |

| Charlestown & Lower Kersal New Deal for Communities (NDC) |  | Salford Innovation Park |
| --- | --- | --- |
| NDC programme for the North Irwell area with the following priorities: Building Communities; Crime and Community Safety; Education; Children and Young People; Physical Environment; Health; Business, Employment and Skills. For more information: www.chalk-ndc.info. NDC summary in the Programme section of this report outlines expenditure and key achievements to date. |  | Salford Innovation Park (SIP) encompasses the Salford Innovation Forum (SIF) building, Salford University Technology House and surrounding business units to promote the growth of knowledge based industries. For more information: www.innovation-forum.co.uk |
| Lead officers | Tim Field, New Deal for Communities Kevin Brady, Assistant Chief Executive |  | Lead officer | Matthew Lynn, Sustainable Regeneration Rob Pickering, Sustainable Regeneration |
| Funding sources | SCC officer resources |  | Funding sources | ERDF 3.4m; NWDA £5.9m; NDC £300K; Total capital receipts £9.6m Salford Innovation |
| Pledges | All |  | Pledges | Creating prosperity |
| Progress | Date |
| Charlestown Riverside masterplan approved by Lead Member for Housing subject to the resolution of Urban Design issues, and the future submission of technical reports. The masterplan was also sent to Lead Member for Planning for noting. | 05/05/09 |
| Pulse Regeneration presented detailed succession arrangements to Partnership Board. | March 2009 |
| Future milestones | Timescale |
| Phase 3 environmental works in Lower Kersal completed. | June 2009 |
| Board workshop to discuss Succession Plan. | 10/06/09 |
| Submit outline planning application for masterplan. | July / August 2009 |
| Open day for residents to view CR masterplan. | July / August 2009 |
| Progress | Date |
| Discussions held with The University of Salford regarding incorporating the SIP project within The University of Salford masterplanning process. | March/ April 2009 |
| Salford City Council legal and procurement advice sought on future of the SIP model. | February 2009 |
| Discussions on tender selection, taking into account advice on the restructuring of the park. | January 2009 |
| Future milestones | Timescale |
| Dialogue commences with chosen management company for SIF. The chosen company will also own and manage the two adjacent assets. | May/ June 2009 |

| Lower Broughton |  | Broughton Green |
| --- | --- | --- |
| The transformation of 75 hectares in the Lower Broughton area over the next 10 to 15 years to provide over 3,500 mixed-tenure homes and a range of community facilities and services. Residents Association established by Contour Housing, with regular monthly meetings, for affected residents via steering group. Work in progress on sites. For more information: www.salford.gov.uk/broughton-regeneration.htm |  | An innovative community development through the regeneration of a 30 acre site in Higher Broughton. Aimed at creating approximately 700 new homes of mixed tenure (family homes and apartments) with comprehensive community facilities/ services over the next seven years. Partners are working together to mitigate impact of current economic climate. www.salford.gov.uk/broughton-regeneration |
| Lead officers | Sarah Clayton, Sustainable Regeneration Richard Wynne, Urban Vision |  | Lead officers | Sarah Clayton, Sustainable Regeneration |
| Funding sources | HMRF 2006/07, HCP, private sector |  | Funding sources | HCP, HMRF |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Developers, HCA and other key partners working together to mitigate impact of current economic climate, in particular the impact on other schemes such as the proposed new school on the Wheatersfield Site. | Ongoing |
| Discussion between the council and Countryside on future development phases (Mocha Parade, land adjoining the Meadows and land east of Great Clowes Street). | Ongoing |
| Spike Island Estate regeneration to concentrate on retaining existing stock. Review of Decent Homes improvements, environment and access to Crescent Meadows, to include underused sites. Part of estate being considered for inclusion in Environment Agency supported project around environmentally resilient communities. | Ongoing |
| Future milestones | Timescale |
| Phase 2 to commence following demolition at Countess Grove and agreement of financial measures. | July 2009 |
| Building phase 2 and 4 expected to be completed. | 2011 |
| Progress | Date |
| Further 19 properties acquired in January – March 2009. 20 properties still to be acquired. | Ongoing |
| Developers drafting business plans for redevelopment of the whole site. | Ongoing |
| 12 HCA funded properties sold to a Registered Social Landlord. | February 2009 |
| Visits to all remaining owner occupiers undertaken. | February 2009 |
| Future milestones | Timescales |
| Working with partners on remaining 40+ properties. | June 2009 |
| Whole clearance project expected to be complete. | September 2010 |

| Higher Broughton Community Hub |  | Broughton Renewal Area |
| --- | --- | --- |
| Following withdrawal of the earlier planning application submitted for a new two storey community centre on Wellington Street East, discussions have continued with the local community and a revised location agreed slightly to the south of the previous location. Facilities are still to comprise of office accommodation, library, children’s centre, youth club, fitness lounge, trampoline club, community rooms together with associated car parking. |  | The development and implementation of an action plan, in consultation with residents and stakeholders for the Broughton area bounded by Camp Street to the south, the River Irwell to the west, Bury New Road to the east and the Kersal border to the north. The area was declared a renewal area in 2006 for five years. For more information: www.salixhomes.org/broughton |
| Lead officers | Bob Osborne, Sustainable Regeneration Andy Howitt, Community Health and Social Care |  | Lead officer | John Wooderson, Sustainable Regeneration |
| Funding sources | Unsupported borrowing/ partnership receipts |  | Funding sources | HCP, HMRF |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Community consultation. | Ongoing |
| Negotiations for disposal of land at Wellington Street East commenced. | March 2009 |
| Future milestones | Timescales |
| End of community consultation. | June 2009 |
| Report to Lead Member for Planning. | June 2009 |
| Submit revised planning application. | July 2009 |
| Start of pre-commencement works, advertising. | November 2009 |
| Start on site construction works. | December 2009 |
| Completion of hub construction. | Summer 2010 |
| Progress | Date |
| Work to bring forward alley greening. Further bid to Grass Roots fund for £5000 in progress. | April 2009 |
| 75% response rate achieved on the expressions of interest letters sent to Gainsborough Street. | March 2009 |
| Rock and Hill Street alley gates installed. Work with residents group underway to green alleys with £2,300 funding identified. | January 2009 |
| Funding for Gainsborough Street block improvements confirmed. | December/ January 2009 |
| Future milestones | Timescale |
| Gating of remaining alleys in the Wellington Street West area to start. | Summer 2009 |
| Report on Gainsborough Street block improvements to Lead Member for Planning. | Summer 2009 |
| Work anticipated to start on Wellington Street West area and Gainsborough Street improvements. | September/ October 2009 |

| Crescent Masterplan/ Crescent Railway Station |  | Salford Museum & Art Gallery |
| --- | --- | --- |
| Regeneration of the southern side of The Crescent will link the regeneration of Chapel Street with the University and Pendleton town centre. The masterplan will underpin the development of a residential led mixed-use development. The masterplan is linked to the outcomes of several pieces of work including the Salford University masterplan. For more information: www.centralsalford.com. |  | The vision for the Salford Museum & Art Gallery is to establish the museum as a regional and national resource for the understanding of social history. It will also become a focal point promoting innovation and enterprise amongst the city’s growing creative industries. A masterplan and delivery plan for the museum was agreed in December 2007. For more information: www.salford.gov.uk/salfordmuseum |
| Lead officers | David Evans, Sustainable Regeneration Nik Puttnam, Central Salford URC |  | Lead officer | Andy Howitt, Community Health & Social Care |
| Funding sources | CSURC, British Waterways |  | Funding sources | Salford Council Capital programme for phase 1 project development work |
| Pledges | Enhancing life |  | Pledges | Encouraging learning, leisure and creativity |
| Progress | Date |
| Network Rail’s appointed consultants undertaking a technical feasibility study looking at two options for Crescent Railway Station. | Ongoing |
| University masterplan (Estate Strategy) presented to Cabinet. | 24/02/09 |
| Future milestones | Timescale |
| Technical feasibility study complete. The outcome of this study may impact on both the University masterplan and draft Crescent masterplan. | May 2009 |
| Development framework for the University and Crescent areas completed. | March 2010 |

| Progress | Date |
| --- | --- |
| Continued technical work associated with the museums collections, exhibitions, conservation and building. | February 2009 |
| Future milestones | Timescale |
| Presentation to Corporate Management Team and/or Cabinet Briefing on the concept design report and proposed capital investment programme for the museum. | May 2009 |
| Exploration of funding opportunities. | 2009 – summer 2010 |

| Springfield Lane |  |  |
| --- | --- | --- |
| Redevelopment for residential and mixed use scheme with Urban Splash. The scheme includes 450 apartments, 20,000 square feet of commercial space on the lower levels of the apartment blocks, an office building of approximately 50-70,000 square feet on the corner of Trinity Way/ Springfield Lane and 400 car parking spaces. Due to the current market, Urban Splash is unable to progress the proposed redevelopment at the current time. Meetings have been held between Urban Splash, the city council and Central Salford URC. |  |  |
| Lead officers | David Evans, Sustainable Regeneration Stephen Gwatkin, Urban Vision |  |  |  |
| Funding sources | Private sector, potential public sector funding for affordable housing |  |  |  |
| Pledges | Enhancing life |  |  |  |
| Progress | Date |
| Legal advice being sought, as to city council options in relation to Development Agreement, prior to update report being submitted to Lead Member for Planning. | Ongoing |
| Future milestones | Timescale |
| Urban Splash, the city council and Central Salford URC meeting. | 13/05/09 |
| Report to Lead Member for Planning. | Tbc |

| Bridgewater Canal Corridor (BCC) |  | Bridgewater Way |
| --- | --- | --- |
| A priority project in the Salford West SRF, to transform the canal and environs into a leisure destination for visitors and residents. This includes physical works as well as community involvement, educational and heritage interpretation. Consultants appointed in October 2008 to develop an Audience Development Plan, Audit Plan and Conservation Management Plan. For more information: www.salford.gov.uk/salfordwest |  | The Bridgewater Way will enhance and regenerate 65km of historic canal routes linking communities, the National Cycle and footpath networks and create a more accessible leisure asset. 8km of the towpath will connect communities across the west of Salford. The project is part of the Bridgewater Canal Corridor scheme. For more information: www.bridgewatercanal.co.uk. |
| Lead officers | Susan Wildman, Chief Executive’s Directorate Paul Gill, Sustainable Regeneration |  | Lead officers | Darren Findley, Sustainable Regeneration Janet Roberts, Bridgewater Trust |
| Funding sources | Salford City Council (Salford West Framework), private sector, external funding bodies |  | Funding sources | NWDA, Manchester Ship Canal, Salford City Council (Salford West Framework), Block 3 Local Transport Plan (£75,000) |
| Pledges | Encouraging learning, leisure and creativity |  | Pledges | Enhancing life |

| Progress | Date |
| --- | --- |
| Expression of Interest submitted to Visitor Attraction Fund. | 01/05/09 |
| Lowry Walkabout event held in Barton. | 05/04/09 |
| Future milestones | Timescale |
| Final reports for Audience Development Plan, Access Audit and Conservation Management plan. | May 2009 |
| Masterplan for BCC commissioned. | Late May 2009 |
| Masterplan for BCC completed. | November 2009 |
| Progress | Date |
| Phase 3 funding from Salford West Framework approved. | April 2009 |
| Opening of phase one and two (Liverpool Road to M602). | 11/06/08 |
| Future milestones | Timescale |
| Local Transport Plan funding announcement expected. | June 2009 |
| Physical works begin on phase 3 of Bridgewater Way - M602 to 500m beyond Monton. | Summer 2009 onwards |
| 250th anniversary of the Bridgewater Canal. | 2011 |

| Liverpool Road Corridor Strategy |  | Eccles Town Centre |
| --- | --- | --- |
| Implementation of environmental improvements and promotion of social and economic cohesion along the Eccles section of the Liverpool Road Corridor. The ten year strategy, approved in June 2008, is a priority in the Salford West Framework. The Liverpool Road Corridor Task Group is working with local businesses to implement shopfront and streetscene improvements: www.salford.gov.uk/liverpool-road-corridor |  | Promote and enhance vitality of the town centre. A Task Group was established in July 2008 to progress improvements to the three Salford West town centres via the Salford West Framework. Eccles Town Centre is the priority town centre. For more information: www.salford.gov.uk/salfordwest. |
| Lead officers | David Evans, Sustainable Regeneration Lyndsey Priestley, Sustainable Regeneration |  | Lead officers | Rob Pickering, Sustainable Regeneration Paul Gill, Sustainable Regeneration |
| Funding sources | Capital budget (Salford West) 2009/10 £724,000 (for Irlam, Cadishead and Eccles), Private sector contributions £100,000 |  | Funding sources | Private, Salford City Council (Salford West) |
| Pledges | Enhancing life and creating prosperity |  | Pledges | Enhancing life and creating prosperity |
| Progress | Date |
| Crown Theatre agent progressing pre implementation work and reconsidering use of ground floor units. | Ongoing |
| Patricroft Bridge masterplan appointment signed off by Lead Member for Customer and Support Services. URBED announced as preferred contractor. | 11/05/09 |
| Patricroft Bridge masterplan appointment signed off by Lead Member for Planning. | 05/05/09 |
| Applications for shopfront grants submitted. | March/April 2009 |
| Future milestones | Timescale |
| Work on shopfront improvements starts on site. | May/ June 2009 |
| Consultation on streetscene improvements. | Summer 2009 |
| Masterplan for Patricroft Bridge completed. | May 2010 |
| Progress | Date |
| Eccles town centre vision being developed. | March-May 2009 |
| Planning application submitted by Aldi to demolish existing public house and erect a single storey side extension to existing store. | 03/04/09 |
| Footpath improvements completed. | March 2009 |
| Planning application received for partial demolition of existing retail units (4,484sqm gross) and replace with retail food store (8,213sqm gross) on West One Retail Park, including new footbridge over Gilda Brook Road. | 23/02/09 |
| Future milestones | Timescales |
| Planning application for new Tesco at West One expected to go to Planning Panel. | Summer 2009 |
| Eccles Town Centre Vision and Action Plan presented to Salford West Partnership Board for approval. | July 2009 |

| Magistrates Court and Justice Centre |  |  |
| --- | --- | --- |
| Establishment of a new courthouse at John William Street. The building will contain eight Magistrates Courts and four county courts as well as offices for staff and solicitors, with an adjacent circa 300 space car park. The car park will be built by selected bidder with Salford City Council retaining ownership. |  |  |
| Lead officers | Dave Greenfield, Sustainable Regeneration Richard Wynne, Urban Vision |  |  |  |
| Funding sources | PFI funding of approximately £20million confirmed via HMCS |  |  |  |
| Pledges | Creating prosperity and reducing crime |  |  |  |

| Progress | Date |
| --- | --- |
| Looking at interim parking solutions. | Ongoing |
| Two bids submitted for the car park construction. | 07/08/08 |
| Future milestones | Timescale |
| Selection of preferred bidder to be announced. | June 2009 |
| Multi-storey car park construction starts. | March 2010 |
| Courthouse construction starts. | December 2010 |
| Completion of Magistrates Courthouse (subject to review by HMCS). | December 2012 |

| Barton Strategic Site - Salford Reds Stadium |  | Barton Strategic Site - Port Salford |
| --- | --- | --- |
| Secretary of State outline approval given 03/11/06 to Salford Reds for a new 20,000 seat stadium with associated development. Following Red City Developments going into administration in July 2008 discussions have been taking place to determine the appropriate way forward. The current proposal incorporates a potential facility for Salford City College (details under development). |  | The development of a multi modal freight terminal; to include 2-berth port, rail freight terminal and 200,000 sq m warehousing. Concerns of the Highway Agency were resolved in December 2008. |
| Lead officers | Chris Findley, Sustainable Regeneration Matthew Lamb, Urban Vision |  | Lead officers | David Evans, Sustainable Regeneration Simon Wood & Andrew Fuller, Urban Vision |
| Funding sources | Private |  | Funding sources | Private |
| Pledges | N/A |  | Pledges | N/A |

| Progress | Date |
| --- | --- |
| Legal advice sought on whether a new application could be submitted in the form of a reserved matters under the outline planning permission, or whether a full planning application will be required. | March 2009 |
| Discussions on how the scheme will be taken forward once the administrator completes task. | Ongoing |
| Future milestones | Timescale |
| Revised planning application will be determined by the Planning and Transportation Regulatory Panel, at which point site remediation and construction could commence (subject to discharge of relevant pre-commencement conditions). | tbc |
| Progress | Date |
| Legal agreements under discussion. | Ongoing |
| Joint Eccles, Irlam and Cadishead Community Committee meeting held. | 14/04/09 |
| Planning application considered by the Planning and Transportation Regulatory Panel. Planning Panel requested more information be presented at a future meeting on highways and pollution issues associated with the scheme. | 16/04/09 |
| Future milestones | Timescale |
| Planning Panel expected to consider planning application. | Late May/ early June 2009 |

.

| Chat Moss Visioning |  | Liverpool Road Corridor Strategy |
| --- | --- | --- |
| An assessment of the Mosslands project area to produce a long term vision that will promote the “best fit” for competing land uses establishing sustainable land use patterns, and to maximise the value of the mossland landscape as an accessible leisure, health and local heritage resource for tourists, visitors and local communities. A Mossland Action Group has been set up and meets regularly. For more information: www.salford.gov.uk/chatmoss |  | Implementation of environmental improvements and promotion of social and economic cohesion along the Irlam and Cadishead section of the Liverpool Road Corridor. The ten year strategy, approved in June 2008, is a priority in the Salford West Framework. The Liverpool Road Corridor Task Group is working with local businesses and residents to implement shop front, street scene and highways improvements in key areas. For more information: www.salford.gov.uk/liverpool-road-corridor |
| Lead officers | Will Horsfall, Sustainable Regeneration |  | Lead officers | David Evans, Sustainable Regeneration Lyndsey Priestley, Sustainable Regeneration |
| Funding sources | Biffaward |  | Funding sources | Capital budget (Salford West) 2009/10 £724,000 (for Irlam, Cadishead and Eccles), Private sector contributions £100,000, Highways Block 3 (£310,000) |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Considering Core Strategy responses received in setting out a preferred way forward. | Ongoing |
| Lancashire Wildlife Trust secured funding to employ project workers to promote peat restoration projects and to advise on management practices. The Trust also has funding to acquire key sites. | February 2009 |
| Core Strategy Issues and Options consultation included a section setting out the options for taking forward the Mosslands Vision for creating a Mosslands Heartland. | October 2008 - January 2009 |
| Future milestones | Timescale |
| Undertake further work to establish the hydrological zone width to protect bog restoration areas on Chat Moss. | Summer 2009 |
| Progress | Date |
| Landscape improvements around Cadishead Bridge (near library) started on site. | April 2009 |
| Applications for shopfront improvements grants submitted. | March/ April 2009 |
| Informal Shopfront Design Guide drafted. | October 2008 |
| Future milestones | Timescale |
| Shopfront improvements start on site. | May / June 2009 |
| Draft designs for streetscene improvement proposals (New Moss Road to Brinnell Drive) completed. | June 2009 |
| Highways resurfacing (Cadishead) starts. | Summer 2009 |
| Consultation of streetscene improvements proposals. | Summer 2009 |

| Walkden Town Centre |  | Cutacre site |
| --- | --- | --- |
| Town centres have been identified as a key issue in the Salford West Framework. Salford City Council officers will work with Walkden town centre management to progress improvement. Work in Walkden in 2009 will focus on events and promotion to draw in a higher footfall. For more information: www.salford.gov.uk/salfordwest |  | Site of coal extraction (Bolton, Wigan and Salford – Little Hulton). The terms of the permission require that the site be restored for a mixture of amenity, agriculture and woodland uses by 2011. Bolton MBC is proposing 144ha of land at Cutacre for a strategic employment site development as part of its Core Strategy Preferred Options. The council is supportive of proposals subject to addressing issues of improving public transport and green belt concerns. Three of the four options within Salford’s Core Strategy Options report identify potential for 10 hectares of land in Salford to be part of larger employment site. |
| Lead officers | Rob Pickering, Sustainable Regeneration Paul Gill, Sustainable Regeneration |  | Lead officers | Graham Gentry, Sustainable Regeneration Stephen Birnie, Urban Vision |
| Funding sources | Private, Salford City Council (Salford West Framework) |  | Funding sources | Private |
| Pledges | Enhancing life and creating prosperity |  | Pledges | Creating prosperity |

| Progress | Date |
| --- | --- |
| Salford City Council officers attending meetings with town centre management. Current work focuses on supporting community events programme. | Ongoing |
| Highway improvements on Walkden Road completed. | April 2009 |
| Work commenced on Tesco development. | January 2009 |
| Consultation with Political Executive on issues and priorities and proposed quick wins. | 30/10/08 |
| Future milestones | Timescale |
| Tesco due to vacate current premises and move into temporary buildings on Ellesmere Retail Park. | May 2009 |
| Tesco development completed. | 2011 |
| Progress | Date |
| Coaling of Area F (Little Hulton) progressing, progressive backfill and restoration. Excavation and Coaling of Area G (Cutacre Tip) progressing. | April 2009 |
| 440,220 tonnes of coal off site. | March 2009 |
| Future milestones | Timescale |
| Begin reduction of Cutacre Colliery Tip. | April - June 2009 |
| Coaling of Area F (Little Hulton) finished. | June 2009 |
| Publication of Salford’s Core Strategy Preferred Options Report. | October 2009 |

| Salford Central Planning Guidance and Development Framework |  | Islington Estate |
| --- | --- | --- |
| The Salford Central Planning Guidance was adopted by the city council in March 2008. Following its adoption, CSURC commissioned Urban Initiatives to prepare a more detailed Development Framework for the Salford Central area. The Framework will set out how the principles in the Planning Guidance will be reflected in the five character areas and on individual sites. This is being steered by a Project Team comprising CSURC, Salford City Council, Salix Homes and English Cities Fund (ECf). The Development Framework will incorporate the preferred option for Islington Estate regeneration (emerging from neighbourhood plan process). For more information: www.centralsalford.com. |  | Development of a Neighbourhood Plan for the Islington Estate to outline the future of the area in the context of the wider regeneration of the Chapel Street area. The process will explore the future options of the council’s commitment to bring homes up to the government’s Decent Homes Standard over the next 5 years. Consultation with local communities is ongoing, looking at issues around housing, the environment, crime and anti social behaviour. For more information: www.salixhomes.org/chapelstreet. |
| Lead officer | Peter Baker, Central Salford URC |  | Lead officers | Sarah Clayton, Sustainable Regeneration Neil Mawson, Salix Homes |
| Funding sources | CSURC, Salford City Council |  | Funding sources | Salford City Council, ECf, CSURC, Salix Homes |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Detailed analysis of consultation results complete. | April 2009 |
| Meetings between city council, Salix Homes and Central Salford URC to discuss options complete. | April 2009 |
| Full resident consultation on the options to redevelop the estate completed. | 28/02/09 |
| Future milestones | Timescales |
| PFI round 6 application approval anticipated. | May / June 2009 |
| Final option for the estate put forward to Lead Members for Housing and Planning for approval. | June 2009 |
| Final exhibition for residents to be presented. | Early summer |
| Progress | Date |
| Full report on responses to draft development framework consultation to be published. | February 2009 |
| Consultation on draft Development Framework. | May/ June 2008 |
| Future milestones | Timescale |
| Development framework recommended to Lead Members for Planning and Housing for adoption, following incorporation of preferred option for the Islington Estate. | 19/05/09 |
| Submission of outline planning application for ECf Development Agreement area. | July 2009 |

| Salford Central Station |  | Greengate |
| --- | --- | --- |
| Improvements to the station and approaches. Phase 1 improvements (including new enclosed forecourt, refurbished concourse, lift and improved facilities) completed February 2008. Study undertaken by Austin Smith Lord Architects to review the design, cost and implementation of future phases. Funding now being sought to move these phases forward. Following a review of Network Rail’s plans for the region over the next five years, their proposals for Salford Central Station are not as extensive as hoped, with only minor repair works expected. |  | Redevelopment of 13 hectares of former industrial land/ property. Based on a point in time when the residential market was more buoyant Greengate would have delivered 2,600 homes, over 85,000 m2 of commercial floorspace and a high quality public realm (including a new bridge across the River Irwell), with the potential to attract over £580 million of private sector investment. Given current market conditions these outputs may be reduced significantly. For more information: www.centralsalford.com |
| Lead officer | Peter Baker, Central Salford URC |  | Lead officers | David Evans, Sustainable Regeneration Nik Puttnam, Central Salford URC |
| Funding sources | Funding being sought for future phases. Awaiting ERDF decision. Possible opportunities to fund some elements through private sector funding. |  | Funding sources | English Partnerships, Private Sector, SCC |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Planning application and Listed Building Consent for Phase 1 of Greengate public realm scheme (the Urban Cove and the Link) submitted and registered by Salford. Awaiting registration of the planning application and listed building consent from Manchester. | 03/04/09 |
| Future milestones | Timescale |
| Salford City Council to serve notice on tenant of former Victoria Bus Station site. | July 2009 |
| Phase 1 works: Urban Cove /footbridge commence | November 2009 |
| Completion of phase 1 public realm design works. | March 2011 |
| Progress | Date |
| Station being integrated into wider regeneration proposals by ECf. Three arches identified to provide pedestrian linkages between sites north and south of the station. | Ongoing |
| Final report on the study on future improvements incorporated the proposals for the new bus interchange at Gore Street. | February 2009 |
| Future milestones | Timescale |
| Submission of outline planning application for ECf Development Agreement area including some of the Central Station arches. | July 2009 |
| Decision on GMPTE transport priorities following review of Regional Centre Transport Strategy (following the TIF referendum decision). | Summer 2009 |

| Progress | Date |
| --- | --- |
| The majority of residents due to be rehoused from Seedley South clearance area have now been relocated or have identified a relocation property. There are two Irwell Valley tenants, one private tenant and one owner occupier remaining. CPO action will be needed to pick up problematic acquisitions. | Ongoing |
| Council in discussion with Urban Splash regarding development on land adjacent to current development. | Ongoing |
| Future milestones | Timescale |
| Completion of block improvements scheme for 173 homes including 15 empty SCC owned properties. | May 2009 |
| Urban Splash development complete. | May 2009 |
| Completion of mixed use scheme on Langworthy Road including 25 apartments for rent, church and community facilities. | January 2010 |

| Seedley Village |  | Proposed Food Store Development - Shopping City |
| --- | --- | --- |
| To create a sustainable neighbourhood of choice that offers a safe and attractive place to live for the existing community and encourages newcomers and private investment. 318 units on the Chimney Pot Park scheme will have been completed by May 2009. Salford City Council has supported a bid to the Homes and Communities for 10 units to be made available for intermediate rent. For more information: www.salixhomes.org/seedley. |  | New food store and associated retail development on land adjacent to Pendleton Way, near Salford Shopping City, to support the centre and enhance retail facilities in the area. |
| Lead officer | John Wooderson, Sustainable Regeneration |  | Lead officers | Graham Gentry, Sustainable Regeneration Peter Openshaw, Urban Vision |
| Funding sources | NWDA, ERDF, HMRF, English Partnerships and Housing Capital Programme. |  | Funding sources | Private |
| Pledges | Enhancing life |  | Pledges | N/A |
| Progress | Date |
| Negotiations ongoing with all parties. Ideally a financial resolution will be reached. In the absence of agreement with PCP, the council will look to enter into an early exchange of contracts with Tesco which may result in a revised scheme to that contained within PCP/Tesco masterplan. | Ongoing |
| Future milestones | Timescale |
| Report to Lead Member for Planning/ Cabinet setting out way forward. | June 2009 |

| Middlewood |  | Pendleton Housing Private Finance Initiative (PFI) |
| --- | --- | --- |
| Made up of two sites: - Valley and Vale owned land has permission for mixed-use development accommodating residential (142,697 sqm of floorspace), commercial (67,773 sqm of B1 floorspace), leisure (27,191 sqm) uses. Outline planning permission (access only) was granted in 2007 and is valid until 2014. No reserved matters approvals have been applied for or granted. - Granada owned land has outline planning approval granted for a mixed-use development comprising of residential (15,509 sqm), commercial (15,587 sqm of Class B1 floorspace), and leisure uses (1,692 sqm). |  | The regeneration of Pendleton will be a key part of transforming Central Salford, improving the area for local residents and attracting new residents. There will be a wider variety of housing, facilities and shops as well as attractive and safe public spaces. Pendleton will be well connected to opportunities including MediaCityUK. The outline business case approved and confirmation of £121 million investment received from DCLG in October 2008. For more information: www.salford.gov.uk/pfi |
| Lead officers | David Evans, Sustainable Regeneration Matthew Lamb, Urban Vision |  | Lead officers | Paul Longshaw, Sustainable Regeneration Barry Whitmarsh, Sustainable Regeneration |
| Funding sources | Private |  | Funding sources | DCLG (£121 million PFI) |
| Pledges | N/A |  | Pledges | Enhancing life |
| Progress | Date |
| Outline solutions submitted from five bidders. Evaluation process is well underway. Shortlist of at most three bidders to be determined May 2009. | 26/03/09 |
| Pre-qualification stage complete, long-list of bidders identified. Bidders invited to submit outline solutions. | 09/02/09 |
| Future milestones | Timescale |
| Bidders invited to submit detailed solutions. | 19/05/09 |
| Salford City Council to confirm preferred bidder. | August 2010 |
| Work starts in Pendleton. | 2011 |

| Progress | Date |
| --- | --- |
| Outline planning application for land owned by Granada approved. | 02/10/08 |
| Salford City Council met with ITV to discuss proposals. | August 2008 |
| Future milestones Timescale |
| In the current situation, no development is considered imminent. Valley and Vale have looked at disposal, which has not proceeded. They have approached the city council seeking advice regarding alternative uses (e.g. temporary car parking) and propose to engage a local team to review the options for their site. |

| IrweIl City Park |  | Ordsall Regeneration Framework |
| --- | --- | --- |
| Irwell City Park (ICP) encompasses an 8km stretch between Salford Quays and The Meadows. The project, a cross boundary collaboration with Manchester City Council, Trafford Metropolitan Borough Council and Central Salford Urban Regeneration Company, has been set up to transform an important urban waterway into an exciting city park with an accessible, attractive and vibrant waterfront at the heart of the regional centre. ICP covers the Ordsall / Irwell Riverside area. For more information: www.salford.gov.uk/irwellcitypark |  | Regeneration and development within Ordsall estate. Developments to date include new homes at Radclyffe Mews and Hulton Square, the refurbishment of Monmouth Park and a new access road to serve Hulton Square. First phase of Hulton Square has mostly sold off plan. Several properties sold under “Launchpad” and “First Time Buyers Initiative” schemes. For more information: www.salford.gov.uk/ordsallregeneration |
| Lead officers | Paul Walker, Sustainable Regeneration Elaine Davis, Central Salford URC |  | Lead officer | Barry Whitmarsh, Sustainable Regeneration |
| Funding sources | NWDA 498,000 for 2008/09 - 2009/10 £600,000 match-funding from SCC, MCC; TMBC. |  | Funding sources | Private sector-led development, predominantly on council-owned land, infrastructure works funded from land values, HCP, gap funding to be sought. |
| Pledges | Enhancing life |  | Pledges | Enhancing life |
| Progress | Date |
| Strategic Review phase completed. | 30/04/09 |
| ICP project given commendation in the BURA Waterways Renaissance awards 2009. | 31/03/09 |
| All consultant teams appointed to support delivery of pre-implementation phase. | January 2009 |
| Future milestones | Timescale |
| Pre-implementation phase. | January 2009 – April 2010 |
| Identity and branding of ICP reviewed. | July 2009 |

| Progress | Date |
| --- | --- |
| First phase housing at Hulton Square (72 homes) completed. | March 2009 |
| Extension to length of development partnership approved. | December 2008 |
| Construction of 260 dwellings at Hulton Square commenced September 2007. | Ongoing |
| Retail application from LPC still under discussion. | Ongoing |
| Future milestones | Timescale |
| Opening of new retail centre. | 2012 |

| Ordsall Riverside |  | MediaCityUK – Public sector programme |
| --- | --- | --- |
| Transformation of riverside employment area to vibrant waterside mixed use area. Planning guidance was adopted in June 2008. For more information: www.salford.gov.uk/ordsall-riverside. |  | Creation of a hub of media, creative industries and support industries on Dock 9, Salford Quays. Includes the relocation, from London and Manchester, of key BBC Departments such as Children’s, Sport and Radio Five Live. The University of Salford has become the second anchor tenant with plans for an innovative higher education centre. The public sector support programme is targeted on 3 themes - Place, Sector & Economy and People & Communities. The council is leading on the People & Communities programme, in conjunction with CSURC. |
| Lead officer | Barry Whitmarsh, Sustainable Regeneration |  | Lead officers | Alan Westwood, Customer and Support Services Jane Deane, Public Sector Programme Director |
| Funding sources | Private sector led, Section 106 (For infrastructure works), CSURC seeking public funding for infrastructure elements, such as proposed Cornbrook bridge (part of Irwell City Park) |  | Funding sources | BBC, NWDA, private sector and Salford City Council |
| Pledges | Enhancing life |  | Pledges | Creating prosperity |

| Progress | Date |
| --- | --- |
| URC looking at design, development and potential short term use of the acquired Vanguard Textiles site on Ordsall Lane. | Ongoing |
| Development of 260 apartments by Lowry Homes at Taylorson Street completed. | December 2008 |
| Future milestones | Timescale |
| Planning application to be submitted and considered by Planning Panel for public realm work that will open up access between Ordsall Hall and River Irwell. This work is part of Irwell City Park. | By summer 2010 |
| Progress | Date |
| Tours for BBC staff. | Ongoing |
| Planning application for provision of detail around the Metrolink extension into MediaCityUK considered at Planning Panel. | 05/05/09 |
| Planning application permitted for revised junction arrangements at MediaCityUK (the new Broadway Link road and Daniel Adamson Way). | 05/02/09 |
| Future milestones | Timescale |
| Work to start on the Broadway Link Road. | May / June 2009 |
| Metrolink service improvements to the Quays completed. | 2010 |
| Completion date for Quays Point. | 2012 |

| Progress | Date |
| --- | --- |
| Match funding being pursued. | Ongoing |
| £100,000 match funding confirmed from Country Homes Foundation. | May 2009 |
| Ordsall Hall closed & building contract awarded. | 23/02/09 |
| HLF approved stage 2 bid for £4.1 million. | 30/09/08 |
| Future milestones | Timescale |
| Further funding bids to be submitted. | Spring 2009 |
| Building works commence. | 18/05/09 |
| Building work complete. | September 2010 |
| Landscaping and fitting out undertaken. | September 2010- Spring 2011 |
| Ordsall Hall reopens. | Easter 2011 |

| Ordsall Hall Museum |  |  |
| --- | --- | --- |
| Major restoration and conservation work on Ordsall Hall to improve the visitor experience. The work will include opening up areas of the building previously not accessible to the public, fitting out of interactive exhibition areas, and the provision of a fully equipped education resource and community room. The grounds will also be landscaped to reflect the building’s heritage. Total project costs estimated at £6.5m. For more information: www.salford.gov.uk/ordsallhall |  |  |
| Lead officer | Robin Culpin, Community Health & Social Care |  |  |  |
| Funding sources | Heritage Lottery Fund (£4.1 million); match funding (£2.4 million) |  |  |  |
| Pledges | Encouraging learning, leisure and creativity |  |  |  |

| Croal Irwell Regional Park / Lower Irwell Valley Improvement Area |  | Swinton Town Centre |
| --- | --- | --- |
| Over 200 hectares identified for reclamation in the Irwell Valley. Site suffered from significant contamination as a result of past industrial uses. A programme of works assessed contamination and restored land for recreational uses (8,000m of footpath creation, new events space, two new play facilities and wildflower/ tree planting). The Forestry Commission has lead responsibility for the delivery of Croal/ Lower Irwell Valley Improvement Area scheme on behalf of the council. For more information: www.salford.gov.uk/land-reclamation -programmes.htm. |  | Town centres have been identified as a key issue in the Salford West Framework. Salford City Council officers will work with Swinton town centre management to progress improvement. A baseline and environmental audit have been undertaken. Work in Swinton in 2009 will focus on events and promotion to draw in a higher footfall. For more information: www.salford.gov.uk/salfordwest. |
| Lead officer | Neil Hook, Sustainable Regeneration Tim Oliver, Forestry Commission Mike Savage, Red Rose Forest |  | Lead officers | Rob Pickering, Sustainable Regeneration Paul Gill, Sustainable Regeneration |
| Funding sources | £4.75m approved in 2003. Match funding from a variety of sources. |  | Funding sources | Private, Salford City Council (Salford West Framework), Salford PCT |
| Pledges | Enhancing life |  | Pledges | Enhancing life and creating prosperity |

| Progress | Date |
| --- | --- |
| Forestry Commission leading on proposals for a rolling programme of additional capital works in LIVIA with input from the city council. | Ongoing |
| Future milestones | Timescale |
| Regional Parks Exchange and Red Rose Forest to hold stakeholder meetings on the future of Croal Irwell Regional Park, followed by the development of future proposals. | July 2009 |
| Regular meetings with the Forestry Commission, Red Rose Forest and the Regional Parks Exchange to develop future plans for the regional park. | To be determined |
| Progress | Date |
| Regular meetings set up with Swinton Town Centre manager. Discussions focus on developing an events programme and making environmental improvements. | Ongoing |
| Notification of the company that owns the precinct going into receivership. | 23/03/09 |
| Future milestones | Timescale |
| Officers to meet with new receivers (GVA Grimley) for Swinton Shopping Limited. | 18/05/09 |

| Clifton Country Park |  | Former Swinton Sewage Treatment Works |
| --- | --- | --- |
| Clifton Country Park covers 50 hectares of scenic urban countryside within the Irwell Valley and is home to the Wet Earth Colliery, part of the city’s industrial archaeology. The Country Park has been a Green Flag Award site for the last three years. The Country Park attracts around 100,000 visits every year. On site there are opportunities for walking, fishing, horse riding and cycling. The ranger team deliver a varied programme of activities. Improvements to facilities are ongoing. |  | The city council’s Core Strategy (Issues & Options Report) identifies the desire to retain and improve the former sewage works (including appropriate reclamation) greenspace recreational purposes Extensive discussions with the local community and site owners United Utilities (UU) have been taking place since the Inspector's report of the Unitary Development Plan public inquiry was published. UU have indicated a desire for some enabling built development on at least part of the site. |
| Lead officer | Annie Surtees, Environment Directorate |  | Lead officers | David Evans, Sustainable Regeneration |
| Funding sources | Heritage Lottery Fund, Salford City Council, Greater Manchester Ecological Unit, Section 106, Greening Greater Manchester |  | Funding sources | To be determined |
| Pledges | Enhancing life |  | Pledges | Enhancing life, Improving health |

| Progress | Date |
| --- | --- |
| Discussions taking place on next phase of interpretation. | Ongoing |
| Development of joint projects with Clifton House Farm in 2008 was limited. Plans to develop further in 2009. | Ongoing |
| Wet Earth Colliery interpretation project completed. | October 2008 |
| Future milestones | Timescale |
| Completion of play ground improvements. | June 2009 |
| Progress | Date |
| The UU representation on the Core Strategy Issues & Options Consultation was supportive of greenspace improvements but indicated that to remediate site issues (including dealing with land contamination) and make the scheme financially viable, some enabling development will be required. | January 2009 |
| Future milestones | Timescale |
| Confirm the type and scale of enabling development that United Utilities envisage. | July 2009 |

| Bridgewater Canal Corridor (BCC) |  | Salford Forest Park |
| --- | --- | --- |
| A priority project in the Salford West SRF, to transform the canal and environs into a leisure destination for visitors and residents. This includes physical works as well as community involvement, educational and heritage interpretation. Consultants appointed in October 2008 to develop an Audience Development Plan, Audit Plan and Conservation Management Plan. For more information: www.salford.gov.uk/salfordwest. |  | The masterplan for the site includes a racecourse with floodlights, all weather track and grandstand; an equestrian centre; 80 bed hotel; a golf course and clubhouse; a forest park centre comprising timber initiative centre, woodland wildlife centre, exhibition space, a demonstration eco-village, camping and woodland play area. A network of footpath, riding trails and cycle paths are proposed. A number of new roads are proposed including a link to J13 of the M60. Extensive landscaping, including ground remodelling, the creation of water bodies and woodland is also proposed. Peel Holdings Ltd has submitted an expression of interest for residual waste facility through the Waste Development Plan Document process. |
| Lead officers | Susan Wildman, Chief Executive’s Paul Gill, Sustainable Regeneration |  | Lead officers | Chris Findley, Sustainable Regeneration Lydia Lewis, Urban Vision |
| Funding sources | Salford West Framework, private sector, external funding |  | Funding sources | Private |
| Pledges | Encouraging learning, leisure and creativity |  | Pledges | N/A |
| Progress | Date |
| Public inquiry by Secretary of State to determine future of application opened for 4 - 5 weeks. | 21/04/09 |
| Future Milestones | Timescale |
| Secretary of State decision. | Tbc |

| Progress | Date |
| --- | --- |
| Expression of Interest submitted to Visitor Attraction Fund. | 01/05/09 |
| Phase 1 habitat survey complete for Worsley Delph. | April 2009 |
| Hydrological assessment for Old Warke Dam phase 2 completed. | March 2009 |
| Future milestones | Timescale |
| Final reports for Audience Development Plan, Access Audit and Conservation Management plan. | May 2009 |
| Masterplan for BCC commissioned. | Late May 2009 |
| Submit bid to Young Roots. | Autumn 2009 |

| Housing Market Renewal Fund (HMRF) |
| --- |
| This programme is restructuring the housing market in Central Salford. There are four major intervention areas: the NDC area, Seedley & Langworthy, Higher and Lower Broughton. |
| Lead officer | Bob Osborne, Sustainable Regeneration Directorate |
| Start date | 02/10/03 | End date | 2013 |
| Key outputs | Target 08/09 | April – March 2009 |
| Homes constructed | 725 | Awaiting figures which are being verified by Planning. |
| Homes acquired | 204 | 118 |
| Homes refurbished | 798 | 476 |
| Households assisted with relocation | 109 | 50 |
| Progress | Date |
| Reconfigure programme to meet allocation and reflect actual 2009 / 10 investment. | 25/05/09 |
| Leaders and Lead Members of Housing for Manchester and Salford council met to agree future of programme and incorporation of growth point. Further work around governance was commissioned. | 06/05/09 |
| Confirmation of 2009/10 Pathfinder allocation at 90% of the level applied for. | March 2009 |
| Audit Commission inspections completed. Salford pathfinder assessed as ‘performing strongly’. | October 2008 |
| Expenditure | Q1 | Q2 | Q3 | Q4 | Total Spend |
| Projected Spend 2008/09 | 1,686,000 | 4,033,000 | 4,236,000 | 7,293,000 | 17,248,000 |
| Actual Spend 2008/09 | 1,686,000 | 3,645,000 | 5,393,000 | 6,524,000 | 17,248,000 |
| Total Approved Spend 2008/2009 | 17,248,000 |

| Kickstart Programme |
| --- |
| Kickstart Housing Delivery is a £400 million programme, targeted at currently stalled sites, to support the construction of high quality mixed tenure housing developments. The package to kickstart stalled sites was announced in the 2009 budget. It includes up front investment support for infrastructure and development costs complemented by support for affordable housing and Homebuy Direct. Funding will be available to a range of organisations who control land, including housing associations and private sector developers. They will need to put forward housing led schemes with a minimum of 50 homes. Sites should have detailed planning consent in place or the ability to achieve this by the beginning of September 2009. Sites should also have their other funding in place. |
| Lead officers | Sarah Clayton, Sustainable Regeneration |
| Future milestones | Timescales |
| Officers to brief Lead Members for Housing and Planning and Leader. | Week commencing 18/05/09 |
| Strategic Housing Partnership Executive to meet and discuss prioritisation of sites for bidding. | Week commencing 18/05/09 |
| Registered Social Landlords and developer partners to submit initial bids to Salford City Council. | Week commencing 25/05/09 |
| Expressions of Interest submitted to Homes and Communities Agency. | 08/06/09 |
| Announcement of shortlist and reserve list. | Late July 2009 |
| Due diligence and pre-qualification of non pre-qualified bidders. | Tbc |
| Rolling programme of decision-making on final allocations. | Tbc |

| New Deal for Communities (NDC) |
| --- |
| The programme delivers the following improvements in the North Irwell Riverside areas: building communities, crime and community safety, education, children and young people, physical environment, health, business, employment and skills. www.chalk-ndc.info/ and www.salford.gov.uk/ndc.htm |
| Lead officer | Tim Field, NDC Chief Executive |
| Start date | April 2001 | End date | March 2011 |
| Programme Projects |
| Housing redevelopment in riverside location and at former Kersal High School site. Remodelling and renewal of existing housing public and private estates. Supporting Schools GEARS+ (automotive project with young people); young people’s filming projects Burglary reduction, alleygating schemes, public realm improvements, shop parade improvements Community Health Action Partnership Business Support (special grants for expansion) Skills and Work Centre (formerly Job Shop) |
| Key achievements |
| The improvement of 438 private dwellings and 259 public sector houses, with a further 479 private dwellings and 62 further public sector dwellings currently being improved. A new £1.5 million Beacon Youth Centre. A new £4.5 million Sports Village complex developed in partnership with Salford City Council, Manchester FA and Sport England. 20 grants to business in 2007-08, and 18 approved so far in 2008-09. Over 600 people supported into employment. Three new Healthy Living Centres opened including one dedicated to mental health support projects. NDC ‘In Bloom’ group achieved awards in 2008 Northwest In Bloom ceremony. 79 alleygates have been erected, benefiting over 1,000 homes in the area, and support has been given for the formation of 12 new residents groups as a result. Supporting over 2,262 children from disadvantaged backgrounds into play, sports and community activity. Over 150 community grants given out to community and voluntary sector groups. The appointment of 2 new NDC area dedicated Police Community Support Officers who won an award for their work in the community (August 2008). The establishment of NDC office at Cromwell House as a hate crime reporting centre. Around 450 young people accessing specific advice on drugs and alcohol. New Neighbourhood Park created and three new community gardens created with residents groups. Six new community enterprises developed and supported. Support for the development of a new £9 million Innovation Forum in partnership with SCC, NWDA and EU. Salford Mini Soccer Festivals held in 2006, 2007 and 2008. Green Streets Initiative. There are approximately 70 young volunteers aged 13-15 between the two high schools, 20 have already completed 25 hours of volunteering. NDC developer partner Miller Homes won the Regeneration Award, at the prestigious North West Business Insider Property Awards, for its Unity Quarter development in Lower Kersal. The Social Media Centre at the Innovation Forum is up and running and successfully engaging local residents in media activities, filming and reporting on local events. |
| Expenditure (08/09) | Q1 | Q2 | Q3 | Q4 | Total Spend |
| Projected Spend 2008/09 | 923,339 | 1,381,720 | 1,553,295 | 2,881,646 | 6,740,000 |
| Actual Spend 2008/09 | 898,463 | 1,518,947 | 2,090,320 | 2,484,033 | 6,991,763 |
| Total Approved Spend 08/09 | £6,990,000 (Please note increase in NDC grant allocation by bringing forward £250,000 from 2009-10 allocation) |

| North West Operational Programme (NWOP) European Regional Development Fund (ERDF) 2007-2013 |
| --- |
| The NWOP allocation for the North West excluding Merseyside is £308 million, which will support the European Union 'Growth and Jobs' agenda and align to the North West Regional Economic Strategy. The programme has four priorities: Priority 1 - Stimulating enterprise and supporting growth in target markets Priority 2 - Exploiting innovation and knowledge Priority 3 - Creating the conditions for sustainable growth Priority 4 - Growing and accessing employment |
| Lead officer | Dee Carroll, Sustainable Regeneration |
| Start date | 2007 | End date | 2013 |
| Future milestones | Timescale |
| Priority 1: Salford City Council to procure delivery of service from NWDA approved list via mini tender process. | July 2009 |
| Delivery of the Priority 1 Intensive Start Up Support (ISUS) project scheduled to commence. | June 2009 |
| NWDA to announce a list of organisations/ consortia to deliver the ISUS project. Salford has an annual allocation approved of £478,500: NWDA/ ERDF £288,500 which will be matched with Area Based Grant £115,000 and NW Coalfields Programme £75,000 | May 2009 |
| Progress | Date |
| Priority 1: NWDA Intensive Start Up Support (ISUS) Project A4e has been selected to provide a regional project management service for the ISUS project on behalf of NWDA. | February 2009 |
| Priority 4: Five projects have been invited to progress to concept stage applications: Irwell City Park Salford Central station Salford Crescent station Creative Industries Incubation Hub (Islington Mill) Irwell Pedestrian Footbridge | Ongoing |

| Salford’s Health Investment for Tomorrow (SHIFT) |
| --- |
| The SHIFT programme is a long-term service improvement initiative to help Salford residents to access healthcare and linked social care services. For more information: www.shiftprogramme.co.uk. Hospital Redevelopment (Salford Royal NHS Foundation Trust/ SRFT) Redevelopment of Hope Hospital site valued at £135 million PFI contract and a further £55 million modernisation investment. This initiative replaces the old Victorian ward blocks on the hospital site. The scheme also includes demolition of the tower blocks on Eccles Old Road, the creation of a multi-storey car park and a separate education and research block. Start date: 2007 End date: 2012 Information Management and Technology The local deployment of the NHS National programme for IT / NHS Connecting for Health in Salford. The project includes a range of initiatives, from electronic prescription transfers, new patient record systems, technology to support Choose and Book, integration of healthcare records across primary and secondary care, etc. Workforce and Education Focused on developing an integrated NHS workforce in Salford to ensure effective collaboration across healthcare sectors. Also seeking to encourage and increase local employment in healthcare. |
| Lead officers | Alan Westwood, Community, Health and Social Care Janet Roberts, Salford PCT |
| Funding sources | Salford PCT and other commissioners / NHS |
| Start date | April 2001 | End date | 2012 |
| Future milestones | Timescales |
| Handover and completion of SRFT site. | 2012 |
| Progress | Date |
| Demolition of two former accommodation blocks, Webb and Worthington House, at Salford Royal commenced. A new treatment centre, called Hope Building, will be built on the site of the demolished buildings. | April 2009 |
| Work on Eccles Old Road and Stott Lane Road improvements. | Ongoing |
| Multi storey car park completed. | 2009 |
| Topping out ceremony for new education building. | 20/06/09 |

| Local Improvement Finance Trust (LIFT) |
| --- |
| A city wide building initiative to improve the quality of the primary healthcare facilities and establish a new range of services. Salford's LIFT centres will bring public services together under one roof, working together to improve the health and wellbeing of the people of Salford. Whilst the services available in each LIFT centre will differ, in general the centres are a partnership between health (Salford Primary Care NHS Trust, Salford Royal Hospitals NHS Trust) and Salford City Council. |
| Lead officer | Alan Westwood, Customer and Support Services Directorate |
| Funding sources | PCT/ NHS - Capital investment to date £36 million Revenue costs £1.18 million |
| Progress | Date |
| PCT at early stages of planning LIFT phase 2 schemes in Salford. | Spring 2009 |
| Pendleton £16.2m Gateway Centre opened www.shiftprogramme.co.uk/gatewaycentres/pendleton/ | 16/02/09 |
| Eccles £10.7m Gateway Centre opened www.shiftprogramme.co.uk/gatewaycentres/eccles/ | 10/11/08 |
| Walkden £9.1m Gateway Centre opened www.shiftprogramme.co.uk/gatewaycentres/walkden/ | September 2008 |
| Lower Kersal Gateway Centre complete. http://www.shiftprogramme.co.uk/lift/lowerkersal.htm | November 2006 |
| Charlestown Gateway Centre completed. www.shiftprogramme.co.uk/gatewaycentres/charlestown/ | October 2005 |

| Building Schools for the Future (BSF) |
| --- |
| The BSF vision is to create buildings for the 21st century with choice and a greater range of services at each secondary school. The timescales indicated below are drawn from the outline business case and are subject to review once procurement process underway. www.salford.gov.uk/learning/secondary/bsf.htm |
| Lead officer | Stephen Bradbury, Children’s Services Directorate |
| Funding sources | BSF – over £150 million |
| Start date | January 2006 | End date | September 2012 |
| Future milestones | Timescales |
| Remaining schools, expected to be completed: St Ambrose Barlow to be rebuilt for 1,050 pupils and relocated to the Wardley site. This will include sixth form provision. St Patrick’s to be rebuilt on current site. All Hallows to be rebuilt on existing site of Oasis academy:MediaCityUK. One new high school to replace the Swinton and Moorside High Schools on the playing fields of Moorside High for 1,350 pupils. Wentworth High School to be rebuilt for 750 pupils on existing site. | September 2012 |
| Proposed Oasis academy: MediaCityUK Salford Quays site completed (Phase 2). | March 2012 |
| Proposed Irlam and Cadishead Community High School to be rebuilt on its existing site (Phase 1A). | September 2011 |
| Proposed new build Walkden High School completed (Phase 1A). | September 2011 |
| Preferred bidder to enter into a Local Education Partnership (Shadow LEP in June 2009 and LEP in October 2009) with Wigan MBC and Salford City Council. | June and October 2009 |
| Planning applications expected to be submitted for Walkden High School and Irlam and Cadishead Community High School. | June 2009 |
| Progress | Date |
| Cabinet meeting on proposals for three Roman Catholic Schools, St Ambrose Barlow, St Patricks and All Hallows, with the closure of St Georges. | 05/05/09 |
| Statutory Notice published inviting proposals to run the new school (Moorside and Swinton High), under competition rules. This notice runs until 26/08/09. | 26/03/09 |
| Competitive dialogue and submission of final bids completed. Procurement process still on track to deliver schools to the above programme. Revised programme in development. | 27/03/09 |
| Six weeks consultation period on Roman Catholic school proposals completed. Statutory notice published. Consultation finished. | 20/03/09 |

| Primary Capital Programme (PCP) |
| --- |
| A long term strategic capital investment programme for all primary schools in England which aims to create schools that are equipped for 21st century learning and are at the heart of their communities with children’s services in reach of every family. Improvements range from new schools to refurbished buildings (including ICT) and improved playing fields. Received notification from DCSF on 12/11/08 that Salford’s primary strategy for change had been approved subject to minor modification. DCSF have released the first year’s allocation of £4.1million. Salford City Council resubmitted Salford’s Primary Capital for Change to DCSF on 30/03/09. DCSF will review amendments. The notification of outcome from DCEF is expected in May. For more info: www.salford.gov.uk/primarycapitalprogramme Current investment projects include: A new community primary school on the Wheatersfield site A new community primary school on the Glendinning Street site A new Roman Catholic primary school (Holy Family) on present Langworthy Road primary school site A new school on an extended Lewis Street site. |
| Lead officer | Bob McIntyre, Children’s Services |
| Key milestones | Proposed timescales |
| Wheatersfield site (East Salford) |
| New school to open. | September 2011 |
| Contractor on site. | January 2010 |
| Planning application expected to go to Planning Panel. | Summer 2009 |
| Planning application submitted. | 06/04/09 |
| Glendinning site (Ordsall and Langworthy) |
| New school to open. | September 2010 |
| Contractor (G and J Seddon) commenced work on new ‘green’ school. | January 2009 |
| Holy Family Roman Catholic Primary School |
| New school to open. | September 2010 |
| Contractor on site. | August 2009 |
| Planning application approved subject to additional conditions, including the achievement of a very good BREEM rating. | 16/04/09 |
| Lewis Street site (Eccles) |
| Cabinet report to commence statutory process. | June 2009 |

| Salford West Strategic Regeneration Framework and Action Plan |
| --- |
| The Salford West Framework will drive investment and regeneration across the western two thirds of Salford for the next 20 years. 2008-11 priorities are town centres, Liverpool Road Corridor and Bridgewater Canal Corridor. Covers 13 wards (Cadishead, Irlam, Winton, Barton, Eccles, Boothstown & Ellenbrook, Worsley, Swinton North, Swinton South, Pendlebury, Walkden North, Walkden South, Little Hulton). For more information: www.salford.gov.uk/salfordwest |
| Lead officers | Bob Osborne, Sustainable Regeneration Directorate Maura Carey, Sustainable Regeneration Directorate |
| Funding sources | Salford City Council capital programme and grant allocations Private sector |
| Future milestones | Timescales |
| Salford West Partnership Board. | 14/10/09 |
| Salford West Partnership Board. | 07/07/09 |
| Salford West business dinner. | 22/06/09 |
| Progress | Date |
| Salford West Partnership Board agreed spend 2009/10. | 21/04/09 |
| Salford West Partnership Board agrees priority actions for 2009/10 State of Salford West indicators report. | 30/01/09 |
| Salford West Partnership Board meeting – Funding plan and output/ outcomes plan agreed. Presentation and discussion on the Core Strategy. | 20/10/08 |
| Salford West business breakfast held. | 16/10/08 |
| Project contract letters distributed. | 15/09/08 |
| Salford West Partnership Board meeting – Terms of Reference for Partnership Board agreed. Communications and Engagement Plan agreed. Task Group membership and indicative actions agreed. | 21/07/08 |
| Liverpool Road Corridor, town centres and tourism product development task groups initiated. | May 2008 |

| Sustainable Community Strategy |
| --- |
| Salford’s Sustainable Community Strategy: Connecting People to Opportunities is currently being developed. It will replace the current Community Plan and will include priorities and objectives developed as part of the negotiation process for the Salford Agreement 2008-11. The Sustainable Community Strategy sets the framework within which the partnership will operate. Our objectives will be delivered through mainstream business plans and the Salford Agreement 2008-2011. |
| Lead officer | Sheila Murtagh, Chief Executive’s Directorate |
| Milestones | Timescales |
| Final strategy to Council. | 20/05/09 |
| Progress | Timescales |
| Final draft to Cabinet Briefing. | 28/04/09 |
| Final draft to SSP Executive. | 25/03/09 |
| Draft text to Leader’s Briefing. | 16/03/09 |
| Draft strategy published on the partners in Salford website for comment and consultation. | January -20/02/09 |
| New LAA2 priorities agreed at the joint Cabinet/ Executive meeting providing the foundation for our new Sustainable Community Strategy. | 26/02/08 |
| Set of measures finalised at a Partnership Executive meeting. | 26/03/08 |
| Anticipated approval | 20/05/09 |

| Central Salford Integrated Transport Strategy |
| --- |
| A strategy for taking forward transport improvements to enable the delivery of the Vision for Central Salford. |
| Lead officer | Darren Findley, Sustainable Regeneration |
| Milestones | Timescales |
| Draft strategy out to stakeholder consultation. | February / March 2009 |
| Progress | Timescales |
| Draft strategy presented to the Salford Travel Partnership. | 04/02/09 |
| Anticipated approval | July 2009 |

| Strategic Economic Development Plan (SEDP) and Employment Land Review (ELR) |
| --- |
| Commissioned in partnership by Salford council and the URC. The Employment Land Review (ELR) considered the potential future demand for employment land and premises within the city over the period 2007-2026, along with the capacity of available supply. The outcome of the study needs careful consideration to decide how best to take forward. This evidence will inform future economic activity and will feed into key strategies including the Strategic Economic Development Plan and the Core Strategy process. The Strategic Economic Development Plan (SEDP) will provide a strategic framework for future economic activity. |
| Lead officers | Chris Marsh, Central Salford URC Rob Pickering, Sustainable Regeneration |
| Milestones | Timescales |
| ELR: To be discussed at Strategy and Regeneration Scrutiny Committee. | 01/06/09 |
| SEDP: Presented to Cabinet for approval and actions to be integrated into business plans. | Summer 2009 |
| Progress | Timescales |
| ELR: Report presented to Cabinet Members for approval with particular consideration given to those sites categorised as ‘swing’. Referred to Scrutiny and Regeneration Committee. | 28/04/09 |
| SEDP: Strategy to be refreshed to reflect the economic downturn and the Manchester Independent Economic Review (MIER) findings. | May 2009 |
| Anticipated approval | Summer 2009 |

| Local Development Framework |
| --- |
| The Local Development Framework is a portfolio of inter-related planning policy documents that includes, amongst other things, the Core Strategy, the Greater Manchester Joint Waste Development Plan Document, the proposed Allocations Development Plan Document and a range of Supplementary Planning Documents. The Core Strategy is the principal document within the Local Development Framework and will set out the long term spatial vision for Salford, along with implications for other plans and strategies on the development and use of land in the city. The Core Strategy needs to conform with the Regional Spatial Strategy. The Core Strategy Issues and Options report, the first stage in the development of the vision and strategy, has undergone a public consultation exercise. Responses from the consultation will be taken into consideration in developing a Preferred Option for the Core Strategy, which will be subject to public consultation later in the year www.salford.gov.uk/core-strategy The Greater Manchester Joint Waste Development Plan Document will set out a planning policy framework for provision of waste management facilities at AGMA level. Initial public consultation has already been undertaken on Issues and Options surrounding the provision of built waste facilities and residual landfill sites (i.e. sites with potential to accommodate landfill or land raising operations). The results of these various consultation exercises will inform the production of later stages of the document www.gmwastedpd.co.uk The proposed Allocations Development Plan Document will be informed by the Core Strategy and will allocate land for specific purposes. Work on the document is due to start late in 2010. A number of Supplementary Planning Documents currently exist, which augment planning policies set out in the Unitary Development Plan. These will need to be reviewed to ensure that they align with the Core Strategy and consideration will be given to the need for any additional documents. An Employment Land Supplementary Planning Document is currently being prepared and will help to interpret employment policies in the UDP in the light of the Employment Land Study. |
| CORE STRATEGY |
| Lead officer | David Percival, Sustainable Regeneration |
| Milestones | Timescales |
| Consult on the Core Strategy Preferred Option. | Oct – December 2009 |
| “Draft” Core Strategy published. Period for representations. | August – October 2010 |
| Submit Core Strategy to Secretary of State. | November 2010 |
| Public examination. | February - March 2011 |
| Expected adoption. | September 2011 |
| Progress | Timescales |
| Consultation on the alternative options suggested in response to the Issues and Options Consultation report. | 14/04/09 – 29/05/09 |
| Representations received on the Issues and Options report published. | April 2009 |
| GREATER MANCHESTER JOINT WASTE DEVELOPMENT PLAN DOCUMENT |
| Lead officer | Graham Gentry, Sustainable Regeneration |
| Milestones | Timescales |
| Consultation on Preferred Options. | Dec 09 – January 2010 |
| Publication on full draft document. | November 2010 |
| Submission to Secretary of State. | February 2011 |
| Public examination. | June 2011 |
| Expected adoption. | January 2012 |
| Progress | Timescales |
| Representation submitted in respect of potential residual waste site at Vicars Hall Lane, identified in Issues and Options Consultation | May 2009 |
| Representation submitted in respect of potential provision of built facilities at Swinton Hall Road, identified in Issues and Options Consultation. | April 2009 |
| Anticipated approval | January 2012 |
| ALLOCATIONS DEVELOPMENT PLAN DOCUMENT |
| Lead officer | Graham Gentry, Sustainable Regeneration |
| Milestones | Timescales |
| Initial consultation. | Aug – July 2011 |
| Publication for consultation. | May 2013 |
| Submission to Secretary of State. | August 2013 |
| Public examination. | December 2013 |
| Progress | Timescales |
| Discussions regarding overall timetable for production with Government Office North West (may have implications for milestones given above. | Ongoing |
| Anticipated approval | July 2014 |
| EMPLOYMENT LAND SUPPLEMENTARY PLANNING DOCUMENT |
| Lead officer | Jim McManus, Sustainable Regeneration |
| Milestones | Timescales |
| Preparation of draft document. | June – September 2009 |
| Public consultation. | Nov - December 2009 |
| Progress | Timescales |
| Scoping of the document. | Ongoing |
| Anticipated approval | May 2010 |

| Regional Spatial Strategy |
| --- |
| The Regional Spatial Strategy provides an important context for the Local Development Framework, setting out regional policies which the Core Strategy and other documents within the Local Development Framework must be in conformity with. The current Regional Spatial Strategy was published in September 2008 but is currently the subject of a partial review covering Parking Standards, Gypsies and Travellers, and travelling showpeople. www.northwestplanpartialreview.org.uk In due course it is proposed that a Single Integrated Regional Strategy will replace both the Regional Spatial Strategy and the Regional Economic Strategy. Arrangements for this are still to be formalised via the Local Democracy, Economic Development and Construction Bill. NWDA have recently commenced work on “RS2010 Regional Strategy for England’s Northwest” with publication of a Principles and Issues Paper. |
| REGIONAL SPATIAL STRATEGY PARTIAL REVIEW |
| Lead officer | David Percival, Sustainable Regeneration |
| Milestones | Timescales |
| Public consultation on submitted draft policies. | July – October 2009 |
| Public examination. | October 09 – May 2010 |
| Publication of examination panel report. | May 2010 |
| Consultation on Secretary of State’s proposed changes. | Autumn 2010 |
| Progress | Timescales |
| AGMA comments submitted in response to informal consultation. | March 2009 |
| Anticipated approval | December 2010 |
| SINGLE INTEGRATED REGIONAL STRATEGY (RS2010) |
| Lead officer | David Percival, Sustainable Regeneration |
| Milestones | Timescales |
| Still to be determined in detail although consultation on a Draft Strategy is anticipated towards the end of 2009. | To be determined |
| Progress | Timescales |
| AGMA response to Principles and Issues Paper. | April 2009 |

AGMA		Association of Greater Manchester Authorities

BCC		Bridgewater Canal Corridor

BSF		Building Schools for the Future

CSURC	Central Salford Urban Regeneration Company

CPO		Compulsory Purchase Order

DCLG		Department for Communities and Local Government

DCSF		Department for Children Schools and Families

ECf		English Cities Fund

ELR		Employment Land Review

ERDF		European Regional Development Fund

GONW	Government Office North West

HCA		Homes and Communities Agency

HLF		Heritage Lottery Fund

HMCS		Her Majesty’s Courts Service

HMRF		Housing Market Renewal Fund

ICP		Irwell City Park

LAA		Local Area Agreement

LDF		Local Development Framework

LIFT		Local Investment Finance Trust

LIVIA		Lower Irwell Valley Improvement Area

LRC		Liverpool Road Corridor

MAA		Multi Area Agreement

MBBC		Manchester, Bury and Bolton Canal

MIER		Manchester Independent Economic Review

MSP		Manchester Salford Pathfinder

NDC		New Deal for Communities

NRF		Neighbourhood Renewal Fund

NWDA		North West Development Agency

OJEU		Official Journal of the European Union

PCP		Primary Capital Programme

PCT		Primary Care Trust

PFI 		Private Finance Initiative

RSL		Registered Social Landlord

SCS		Sustainable Community Strategy

SEDP		Strategic Economic Development Plan

SHIFT		Salford Health Investment for Tomorrow

SIF		Salford Innovation Forum

SSP		Salford Strategic Partnership

TIF		Transport Innovation Fund

# Text boxes

###### Contents

Irlam and Cadishead						15

Barton Strategic Site						15	Salford Reds City of Salford Stadium		15	Port Salford						15

Chat Moss Visioning						16

Liverpool Road Corridor Strategy				16

Little Hulton and Walkden						17	Walkden Town Centre 					17	Cutacre site							17

Ordsall and Langworthy						18

Salford Central Planning Guidance and Development	18

Framework

Islington Estate						18

Salford Central Station					19

Greengate							19

Seedley Village						20

Proposed food store development	- Shopping City	20

Middlewood							21

Pendleton Housing Private Finance Initiative 		21

Irwell City Park 						22

Ordsall Regeneration Framework				22

Ordsall Riverside						23

MediaCityUK 	- Public sector programme			23

Ordsall Hall Museum						24

Summary of key developments				4

Claremont and Weaste					6

Development sites					6

Pendlebury Children’s Hospital		6		Former site of Oakwood High School	6

The Willows					6

Buile Hill Park						6

East Salford 							7

New Deal for Communities				7

Salford Innovation Park				7

Lower Broughton					8

Broughton Green 					8

Higher Broughton Community Hub			9

Broughton Renewal Area				9

Crescent Masterplan/ Crescent Railway Station	10

Salford Museum and Art Gallery			10

Springfield Lane					11

Eccles							12

Bridgewater Canal Corridor				12

Bridgewater Way					12

Liverpool Road Corridor Strategy			13

Eccles Town Centre					13

Magistrates Court and Justice Centre Initiative	14

Swinton								25				51

Croal Irwell Regional Park / Lower Irwell Valley 		25

Improvement Area

Swinton Town Centre					25

Clifton Country Park						26

Former Swinton Sewage Works				26

Worsley and Boothstown						27	Bridgewater Canal Corridor					27	Salford Forest Park						27

Programmes								28 	Housing Market Renewal Fund (HMRF)			28

Kickstart Programme						29

New Deal for Communities (NDC)				30

North West Operational Programme (ERDF)		32	Salford’s Health Improvement for Tomorrow (SHIFT)	33

Local Improvement Finance Trust (LIFT)			34

Building Schools for the Future (BSF)			35

Primary Capital Programme (PCP)				36

Salford West Strategic Regeneration Framework		37

Developing strategies						38

Sustainable Community Strategy				38

Central Salford Integrated Transport Strategy		38

Strategic Economic Development Plan and 		39

Employment Land Review

Local Development Framework				40

Regional Spatial Strategy					42

Glossary								43

###### Summary of key developments

###### Claremont and Weaste

###### East Salford

###### Eccles

###### Irlam and Cadishead

###### Little Hulton and Walkden

###### Ordsall and Langworthy

###### Swinton

###### Worsley and Boothstown

###### Programmes

###### Developing strategies

###### Glossary