|  | Part 1 (Open to the Public) | ITEM NO. |
| --- | --- | --- |
| Report of the Assistant Chief Executive and Deputy Director of Housing and Planning |  |  |
| Regeneration Initiatives Cabinet Working Group 23rd June 2008 |  |  |
| TITLE: Update on regeneration projects and programmes. |  |  |
| RECOMMENDATIONS: That the report is noted. |  |  |
| EXECUTIVE SUMMARY: This report provides an update on key regeneration programmes, projects and developing strategies. It outlines progress against milestones and highlights emerging issues. |  |  |
| BACKGROUND DOCUMENTS AND KEY COUNCIL POLICY (Available for public inspection): - Central Salford Vision and Regeneration Framework - Salford West Strategic Regeneration Framework and Action Plan - Making the vision real; Salford's Community Plan for 2006 - 2016 - Regenerating a Great City, Salford's Neighbourhood Renewal Strategy - Regeneration Report for Regeneration Initiatives Cabinet Working Group (19/05/08) |  |  |
| ASSESSMENT OF RISK: Risk is assessed and addressed within individual projects and programmes. |  |  |
| SOURCE OF FUNDING: Key funding sources are identified throughout the report. Current applications for funding are also indicated in the report. |  |  |
| COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative): - LEGAL IMPLICATIONS: N/A - FINANCIAL IMPLICATIONS: N/A - PROPERTY: N/A - HUMAN RESOURCES: N/A |  |  |
| CONTACT OFFICER: Cath Inchbold, Assistant Director, Regeneration Strategy and Co-ordination, 0161 793 3796 Nilima Misra, Senior Project Officer, Regeneration Strategy and Co-ordination, 0161 793 3449 Lynne Braid, Trainee Project Officer, Regeneration Strategy and Co-ordination, 0161 793 3444 |  |  |
| WARD(S) TO WHICH REPORT RELATE(S): All |  |  |
| DETAILS: Information on regeneration projects is set out according to Community Committee areas. The report also includes programmes, a list of developing strategies and a summary of key developments. |  |  |

Contents

Summary of key developments								4

Claremont and Weaste									6	Claremont Weaste Neighbourhood Plan						6

Weaste Renewal Area								7

Eccles New Road Neighbourhood Renewal Area					8

Development sites									9

Pendlebury Children’s Hospital

Former site of Oakwood High School

East Salford 											10

New Deal for Communities								10

SPOTlighting in Charlestown and Lower Kersal					11

SPOTlighting in East Salford							12

Higher Broughton – Homeswap to new build					13

Higher Broughton and Higher Broughton Community Hub			14

Broughton Renewal Area								15

Lower Broughton									16

Duchy and Pendlebury Renewal Area						17

Salford Innovation Park including the Salford Innovation Forum			18

Salford Museum and Art Gallery							19

Springfield Lane									20

Eccles											21

Bridgewater Way									21

Liverpool Road Corridor Strategy							22

Eccles town centre									23

Crown Theatre

Magistrates Court and Justice Centre Initiative					24

Irlam and Cadishead									25

Barton Strategic Site									25

Salford Reds City of Salford Stadium

Port Salford

Chat Moss Visioning									26

Liverpool Road Corridor Strategy 							27

Little Hulton and Walkden									28

Ashton’s Field									28

SPOTlighting in Little Hulton								28

Cutacre site										29

Walkden town centre									30

Ordsall and Langworthy									31

Islington Estate									31

Salford Central Planning Guidance and Development Framework 		32

Salford Central Station								33

Crescent Masterplan/ Crescent Railway Station					34

Former Police Headquarters

Salford University – Estates masterplan

Greengate										35

Restoration of the Manchester, Bury and Bolton Canal (MBBC)			36

Middlewood										37

Pendleton Housing Private Finance Initiative (PFI)				38

Pendleton Planning Guidance							39

Proposed food store development							40

Seedley Village									41

Ordsall Regeneration Framework							42

Ordsall Riverside									43

MediaCityUK 										44

Ordsall Hall Museum – Heritage Lottery Fund (HLF) project			45

SPOTlighting in Ordsall and Langworthy						46

Swinton											47

Croal Irwell Regional Park – Lower Irwell Valley Improvement Area (LIVIA)	47

Agecroft Commerce Park								48

Swinton town centre									49

Worsley and Boothstown									50

Old Warke Dam and Worsley Delph						50

Salford Forest Park									51

Programmes											52

Housing Market Renewal Fund (HMRF)						52

New Deal for Communities (NDC)							53

North West Objective 2 – Priority 2							55

North West Objective 2 – Priority 3							56

Salford’s Health Improvement for Tomorrow (SHIFT)				57

Local Improvement Finance Trust (LIFT)						58

Building Schools for the Future (BSF						59

Proposed primary school developments						60

Irwell City Park (ICP)									61

Salford West Strategic Regeneration Framework					62

Transport Innovation Fund (TIF)							63

Parks for People									64

Developing strategies									65

Glossary											70

###### Summary of key developments

| Project | Key developments |
| --- | --- |
| Ministerial Visit | Ministerial visit of Iain Wight MP, Parliamentary Under Secretary of State, Department for Communities and Local Government (DCLG), was hosted in Lower Broughton on 12/06/08 on behalf of the Manchester Salford Pathfinder. |
| Transport Innovation Fund (TIF) | Following a bid jointly submitted by the AGMA authorities and the Greater Manchester Passenger Transport Authority (GMPTA) to the Department for Transport (DfT) in July 2007, confirmation of “Programme Entry" status was granted on 09/06/08. A 12 week consultation will take place in the near future. |
| Think Family Pathfinder | Think Family Pathfinder application was approved by the Department for Children, Schools and Families (DCSF) on 30/04/08. Funding available to each pathfinder is £780,000 phased: £180,000 2008/09, £300,000 2009/10 and £300,000 2010/11. DCSF will shortly be setting up a meeting to discuss how the proposal will be taken forward. |
| Post Office Network Change Programme | Announcement made on proposed closures 10/06/08. Post offices in Langworthy, Adelphi and Patricroft proposed for closure. Meeting of AGMA to take place 16/06/08. A six week local public consultation will run from 10/06/08 to 21/07/08. |
| New Deal for Communities (NDC) | NDC developer partner Miller Homes won the Regeneration Award, at the prestigious North West Business Insider Property Awards in May 2008, for its Unity Quarter development in Lower Kersal. Salford Green Streets initiative launched on 06/06/08. Salford Mini Soccer Festival took place on the 07/06/08 and 08/06/08 at the Sports Village. Almost 240 teams participated. |
| Higher Broughton | Second phase of demolitions on Turner Street and King Street to be undertaken June/July 2008. Formal marketing of Devonshire Street housing site development commenced June 2008. |
| Liverpool Road Corridor | Greening work will be completed by end of June 2008. |
| Port Salford | Highways Agency holding direction extended to 13/08/08. |
| Proposed food store | Meeting between Salford City Council and the Salford Shopping Precinct owner and agents held 11/06/08 to agree way forward following recent financial discussions. A deadline for resolution of land deal is set for week commencing 16/06/08. Discussions have also taken place between the council and the food store regarding land removal costs. The food store has been advised that its figures need to be reduced. A response is awaited. |
| Greengate | British Standard Construction (BSC) Canopus scheme put on hold, following recent reports in MEN about the company going into receivership. URC contacting bank/receiver. |
| Salford Central Development Framework | Consultation on the draft Development Framework took place between 13/05/08 to 03/06/08. The Framework is being redrafted and will be presented to the council for adoption in January 2009. |
| Buile Hill Mansion | Planning application approved on 05/06/08. Discussions to finalise the legal sale agreement and associated financial details are progressing and a response from the purchaser is awaited. |
| Walkden | Work started on street scene improvements in May 2008 with work around the station to start in June 2008. |
| Former Enersys site, Clifton | Strategic land company Ainscough Johnstone Ltd. acquired the 45 acre former Enersys site in Clifton with a view to developing the site for industrial use. Salford City Council officers met with the company in May 2008 to discuss planning details and proposals for the site. |
| Old Warke Dam | Work to start on second set of silt traps in late June 2008. Ecological surveys and design work underway. |
| Glendinning site | Salford City Council has served Compulsory Purchase Orders (CPO) for seven properties. The period for objections ended on 23/05/08. The council has been advised verbally that there have been no objections to the CPO. Discussions are now taking place between DCSF and the council to determine the best route to obtain confirmation of the CPO. |
| Finding the Talent - Youth Culture Offer | Salford City Council bid submitted 07/04/08 was unsuccessful. Feedback has been sought. Council officers within Culture and Leisure and Children’s Services will take forward these proposals. |
| Conservation Areas | The Cliff and the Crescent Conservation Areas Appraisal documents were formally adopted by Council in May 2008. |
| Housing Growth Point | Announcement of bidders delayed until July 2008. |
| Strategic Housing Position Statement | Drivers Jonas appointed by Central Salford Urban Regeneration Company (CSURC) and the city council to prepare the Salford Strategic Housing Position Statement. Stage 1 report completed. A market analysis and consultation will be undertaken. The findings of the study will be reported to the city council and CSURC summer 2008. |
| Salford Business Awards | The first Salford Business Awards were held at The Lowry in April 2008. Business of the Year was awarded to HD Cable. |

###### Claremont and Weaste

Project: Claremont Weaste Neighbourhood Plan

Pledge: Enhancing Life

| Area Covered | Claremont and Weaste Community Committee area |  |
| --- | --- | --- |
| Lead Officers | Dave Greenfield, Housing and Planning Directorate Maura Carey, Chief Executive Directorate |  |
| Summary | Plan will set out a vision for the neighbourhood area highlighting potential for investment. |  |
| Priorities and Milestones |  | Timescales |
| Final draft plan presented to Council. |  | 16/07/08 |
| Final draft plan presented to Cabinet Briefing. |  | 24/06/08 |
| Final draft plan presented to Lead Member for Planning. |  | 17/06/08 |
| Progress |  | Date |
| Neighbourhood Plan Advisory Group met. |  | 07/05/08 |
| Consultation on the draft Claremont Weaste Neighbourhood Plan completed. The consultation consisted of: a special Community Committee meeting (22/01/08); four resident drop in sessions (08/02/08, 21/02/08, 28/02/08 and 25/02/08); and a series of youth consultations at local schools and the Height youth centre. |  | 07/03/08 |
| Funding sources | Salford City Council staff resources |  |
| Publicity to date | Consultation report and summary Consultation posters and copies of plan displayed in public buildings Salford City Council website Article in Advertiser about consultation (24/01/08) |  |

Project: Weaste Renewal Area

Pledge: Enhancing Life

| Area Covered | Areas of Weaste |  |
| --- | --- | --- |
| Lead Officer | John Wooderson, Housing and Planning Directorate |  |
| Summary | To provide a strategic framework for the physical, social and economic renewal of the neighbourhood; securing its long-term sustainability by making the area a more attractive and safer place to live, more desirable place to visit and more inviting area for private sector investment. This will build on a strong local identity and aspiration, involving local communities and other stakeholders. |  |
| Priorities and Milestones |  | Timescales |
| Draft review document circulated to key stakeholders. |  | Late September 2008 |
| Review of Renewal Area completed. |  | Autumn 2008 |
| Complete review baseline and undertake consultation. |  | Summer 2008 |
| Progress |  | Date |
| Review of Renewal Area as per statutory requirement. |  | Ongoing |
| Funding sources | Private Sector Housing Capital Programme (HCP) Housing Market Renewal Fund (HMRF) European Regional Development Fund (ERDF) |  |
| Publicity to date | Weaste Phase 5 newsletters Salford City Council website |  |

Project: Eccles New Road Neighbourhood Renewal Area

##### Pledge: Enhancing life

| Area Covered | Nelson Street, Cemetery Road and Bridston Street |  |
| --- | --- | --- |
| Lead Officer | John Wooderson, Housing and Planning Directorate |  |
| Summary | To provide a strategic framework for the physical, social and economic renewal of the neighbourhood; securing its long-term sustainability by making the area a more attractive and safer place to live, more desirable place to visit and more inviting area for private sector investment. This will build on a strong local identity and aspiration, involving local communities and other stakeholders. |  |
| Priorities and Milestones |  | Timescales |
| Draft review document circulated to key stakeholders. |  | Late September 2008 |
| EKOS to use the finalised Renewal Area Review and Claremont Weaste Neighbourhood Plan to assist in the creation of future plans for the Eccles New Road area where suitable. |  | Summer/ Autumn 2008 |
| Review of Renewal Area completed. |  | Autumn 2008 |
| Complete review baseline and undertake consultation. |  | Summer 2008 |
| Demolition of two remaining properties on Nelson Street completed. |  | End of June 2008 |
| Progress |  | Date |
| Review of Renewal Area as per statutory requirement. |  | Ongoing |
| Demolition of properties on Bridson Street completed. |  | February 2008 |
| Funding sources | Housing Capital Programme Housing Market Renewal Funding |  |
| Publicity to date | Claremont Weaste Community Committee newsletter Salford City Council website |  |

Project: Development sites

Pledge: Enhancing life

| Area Covered | Claremont and Weaste Community Committee Area |  |
| --- | --- | --- |
| Lead Officer | Dave Greenfield, Housing and Planning Directorate Peter Openshaw, Urban Vision |  |
| Summary | This section highlights development sites within the Claremont Weaste area including: - The Pendlebury Children’s Hospital - Former site of Oakwood High School which has been declared surplus to educational requirements and earmarked for sale. The receipt of the land has been ring fenced for educational purposes. |  |
| Pendlebury Children’s Hospital |  |  |
| Priorities and Milestones |  | Timescales |
| Hospital closes. |  | 2009 |
| Planning application submitted for redevelopment of the site. |  | Summer 2008 |
| Site being considered for inclusion in the Housing Growth Point bid. |  | Ongoing |
| Consultants appointed by Health Trust with a view to submitting a planning application for the redevelopment of the site. |  | Ongoing |
| Planning guidance being drafted. |  | Ongoing |
| Future of the site considered as part of the Claremont Weaste Neighbourhood Plan consultation. |  | Spring 2008 |
| Former site of Oakwood High School |  |  |
| Priorities and Milestones |  | Timescales |
| Lead Member for Planning approved an application to the High Court for a declaratory judgement, which if successful would ensure any houses built on the land could be occupied. The application for declaratory judgement is now considered unnecessary as a bill is progressing through parliament that will overcome previous ambiguity. Once the bill has received its final approvals the marketing of the site will commence. |  | Spring 2008 |
| Funding sources | Private, SCC officer time |  |
| Publicity to date | Workshops and consultation events as part of Claremont Weaste Neighbourhood Plan consultation |  |

###### East Salford

## Programme: Charlestown and Lower Kersal New Deal for Communities

##### Pledges: All

| Area Covered | North Irwell Riverside |  |
| --- | --- | --- |
| Lead Officers | Tim Field, New Deal for Communities Kevin Brady, Chief Executive Directorate Cath Inchbold, Chief Executive Directorate |  |
| Summary | Priorities: - Building Communities - Crime and Community Safety - Education, Children and Young People - Physical Environment - Health - Business, Employment and Skills NDC programme summary outlines expenditure and key achievements to date. |  |
| Priorities and Milestones |  | Timescales |
| Community information day on the Charlestown Riverside masterplan. |  | Summer 2008 |
| Progress |  | Date |
| Salford mini soccer festival took place at the Sports Village with around 240 teams participating. |  | 07/06/08 and 08/06/08 |
| Salford Green Streets initiative launched at the Student Union Building. |  | 06/06/08 |
| NDC Succession Strategy finalised. |  | May 2008 |
| Phase 1 residents from clearance areas moved into new Unity Quarter homes. |  | April 2008 |
| Consultation with community and wide range of stakeholders on NDC succession strategy. |  | March/ April 2008 |
| 30 homes completed in Unity Quarter. |  | March 2008 |
| Draft NDC Succession Strategy approved by NDC Board. |  | February 2008 |
| NDC Charlestown Riverside masterplan agreed by NDC board. The development of this masterplan has included an exhibition with over 150 people attending. This led to the formation of a People’s Panel, consisting of up to 20 residents who reviewed the process and fed back their findings. |  | 28/01/08 |
| Publicity to date | NDC newsletter & website www.chalk-ndc.info, coverage in partner publications to be promoted |  |

Project: SPOTlighting in Charlestown and Lower Kersal

Pledge: Enhancing Life

| Area Covered | Charlestown and Lower Kersal |  |
| --- | --- | --- |
| Lead Officer | Steve Hobbs, Children’s Services Directorate |  |
| Summary | This SPOTlight concentrates on young people not in education, employment or training (NEET) in the Charlestown and Lower Kersal area. The project plan is targeted at effective early intervention. |  |
| Priorities and Milestones |  | Timescales |
| First phase delivery of action completed. |  | July 2008 |
| All young people identified to have Common Assessment Framework (CAF) completed and intervention plans. |  | July 2008 |
| Young people at risk of becoming NEET identified by feeder primary schools. |  | June 2008 |
| Progress |  | Date |
| Early intervention programme to improve year 6 to year 7 transition of young people at risk of becoming NEET. |  | May 2008 |
| Actions to reduce post 16 NEET and incorporate preventative measures for 13-16 year olds embedded in 13-19 planning reporting to the Children and Young People’s Strategic Board. |  | April 2008 |
| Proposals to develop a Locality Commissioning model and to ensure more effective intelligence gathering and collaboration identified as common to all SPOTlights. |  | Ongoing |
| Funding sources | Resources will be identified as part of the intervention plans |  |
| Publicity to date | Two SPOTlight newsletters produced and distributed Resident sheet summarising project and findings distributed |  |

Project: SPOTlighting in East Salford

Pledge: Enhancing Life

| Area Covered | East Salford area |  |
| --- | --- | --- |
| Lead Officer | Emily Kynes, Chief Executive Directorate Matthew Ainsworth, Chief Executive Directorate |  |
| Summary | Concentrates on worklessness in the East Salford area. |  |
| Priorities and Milestones |  | Timescales |
| Presentation on learning from SPOTlight will be delivered at the Centre for Economic and Social Inclusion (CESI) Welfare to Work Convention. |  | 25/06/08-26/06/08 |
| Progress |  | Date |
| Project plan being developed to deliver programme of activities. |  | Ongoing |
| Delivery started on seven innovative community-based engagement and support activities. |  | May 2008 |
| Registered Social Landlords (RSL) working group established to work on their role in supporting the tackling worklessness agenda. |  | May 2008 |
| Contracts in place between PCT and three GP cluster leads to advise and signpost patients to employment and skills support. Further training being developed to roll out good practice across all GP practices in Salford. |  | May 2008 |
| East Salford management team and local task group co-ordinated targeted activities in Mandley Park area, including perceptions study of attitudes towards worklessness using a ‘community reporters’ approach delivered by the Manchester Community Information Network (MCIN) and the Broughton Trust. |  | May 2008 |
| Progress made to adapt Skills and Work services to meet the needs of the Orthodox Jewish community. |  | May 2008 |
| Funding sources | Salford City Council Primary Care Trust (Local Enhanced Services) |  |
| Publicity to date | Two SPOTlight newsletters produced and distributed |  |

Project: Higher Broughton Regeneration Initiative – Homeswap to new build

Pledge: Enhancing life

| Area Covered | Higher Broughton Partnership area |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Reuben Flynn, Salix Homes |  |
| Summary | This will provide access to new properties in the redevelopment for owners living in the clearance area. |  |
| Priorities and Milestones |  | Timescales |
| Second phase of remedials being brought to the attention of developers. |  | Ongoing |
| Progress |  | Date |
| Full evaluation of the ‘homeswap to new build’ project completed. Lessons will be taken into account in future phases of development. |  | April 2008 |
| Residents interested in moving to refurbished property on Top Streets being consulted on developing the existing proposals. Lessons learnt from resident feedback have been discussed. |  | January 2008 |
| Funding sources | Housing Market Renewal Programme (HMRF) Housing Capital Programme (HCP) |  |
| Publicity to date | MEN article The Broughton newsletter has featured publicity on homeswap to new build at Vincent Street |  |

# Project: Higher Broughton

## Pledge: Enhancing life

| Area Covered | Higher Broughton Partnership area |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Reuben Flynn, Salix Homes |  |
| Summary | Maintain and support existing communities whilst seeking opportunities for new development through a range of interventions. |  |
| Higher Broughton |  |  |
| Progress/ Priorities/ Milestones |  | Date |
| Second phase of demolitions on Turner Street and King Street to take place. |  | June/July 2008 |
| Results of Gainsborough Street surveys presented to the community. |  | June 2008 |
| Construction of the 52 new units on Devonshire Street completed. Marketing of the site being undertaken by the Higher Broughton Partnership and Contour Housing. Formal marketing has commenced. |  | June 2008 |
| Good progress being made on re-housing from the CPO area. Where whole or half blocks are assembled, further demolitions will take place if planning permission is approved. |  | Ongoing |
| Analysis of survey information from the Gainsborough Street area presented to the council and partner organisations. |  | May 2008 |
| Salford City Council continues to take possession of properties in the priority area of Top Streets. To date six separate vesting declarations including around 50 properties have taken place. |  | May 2008 |
| Higher Broughton Community Hub |  |  |
| Potential start of hub construction if planning application granted. |  | Spring 2009 |
| Planning application to be submitted subject to positive outcome of costing checks for hub construction. |  | June 2008 |
| Urban Vision quantity surveyors finalising costs for material and construction costs. |  | May/June 2008 |
| Meetings with all users to sign off building layout for their particular area. Negotiations ongoing with a user regarding their space in the building. |  | May 2008 |
| Discussions undertaken with main construction partner Laing O’Rourke Northern Limited. Carrying out cost check to ensure building affordable and may be built within budget. |  | May 2008 |
| Grass seeding, knee railing and cleaning completed. |  | April 2008 |
| Funding sources | Housing Market Renewal Fund (HMRF) 2006/07 Housing Capital Programme (HCP). Community Hub - unsupported borrowing/Partnership receipts |  |
| Publicity to date | Publicity to maximise this opportunity at appropriate time. |  |

# Project: Broughton Renewal Area

## Pledge: Enhancing life

| Area Covered | Broughton area bounded by Camp Street to the south, the River Irwell to the west, Bury New Road to the east and the Kersal border to the north. |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Reuben Flynn, Salix Homes |  |
| Summary | To develop and implement an action plan, in consultation with residents and stakeholders, for the Broughton Renewal Area. Renewal Area Plan available at: www.salford.gov.uk/living/housing/marketrenewal/broughton_regeneration/neighbour-renewal-area.htm |  |
| Priorities and Milestones |  | Timescales |
| Gating of remaining alleys in the Rock and Hill Street area complete. |  | Mid July 2008 |
| Short term action plan for Cliffside area to be drawn up. |  | June 2008 |
| Evaluation of the block improvement scheme in Great Cheetham Street West complete. |  | End June 2008 |
| Progress |  | Date |
| Partial handover of the block improvement scheme from Seddon back to Urban Vision pending completion of snagging items. This will be followed by an evaluation of scheme. |  | May 2008 |
| Analysis of consultation (Hill Street and Rock Street) complete. Considerable support for action to improve the area among residents. Report to Lead Member requesting permission to go ahead with option development in partnership with Contour Housing deferred until August 2008 pending the outcome of decisions re: funding. |  | May 2008 |
| Planning approval in place for gating order for Rock and Hill Street area. Written objection for one alley received during initial consultation but no further objections received. Awaiting decision from legal as to whether order can be sealed or if a panel decision is required. |  | May 2008 |
| Work on gardens in Great Cheetham Street West commenced. |  | May 2008 |
| Funding sources | Housing Capital Programme and HMRF |  |
| Publicity to date | Formal declaration notice – MEN and Salford Advertiser (18/05/06) |  |

# Project: Lower Broughton

Pledge: Enhancing life

| Area Covered | Lower Broughton |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Richard Wynne, Urban Vision |  |
| Summary | The transformation of an area of 74 hectares over the next ten to fifteen years. The project is anticipated to cost just over £500 million. The project will provide over 3,500 mixed-tenure homes and a range of community facilities and services. Work started in 2004 and a Development Agreement between SCC and Countryside Properties was agreed in March 2005. |  |
| Priorities and Milestones |  | Timescales |
| Completion of site in Lucy Street at the junction of Camp Street and Great Clowes Street. |  | Autumn 2008 |
| Properties on site L (moving phase 2 residents are relocating) handed over. |  | July to September 2008 |
| Demolition of clearance area properties complete. |  | End summer 2008 |
| Discussion to be undertaken between the council and Countryside on future development following the completion of Mocha Parade phase. Countryside to be asked to concentrate on land to the east of Great Clowes Street. |  | Summer 2008 |
| Progress |  | Date |
| Spike Island Estate regeneration to concentrate on retaining existing stock. A review of Decent Homes improvements and environmental works to include underused sites in the estate. Consideration of the access to Crescent Meadows will be included in this review. |  | Ongoing |
| Demolition of clearance area properties. |  | Ongoing |
| Work in progress on sites T (Camp Street site), U (Fenney Street site) and L (Lucy Street site). |  | Ongoing |
| One-to-one consultation continues with Phase 4 (moving phase 2) residents and fortnightly workshops have been set up with effect from 03/04/08. |  | Ongoing |
| Residents Association established by Contour Housing for phase 1 residents and is formalising a constitution. Regular monthly meetings set up. |  | Ongoing |
| Planning applications for approval of reserved matters for Phases 2, 3 and 5 submitted. |  | 04/04/08 |
| Funding sources | HMRF, HCP and Private |  |
| Publicity to date | Publication of newsletters and moving leaflets Advertising campaign by Countryside |  |

Project: Duchy & Pendlebury Renewal Area

##### Pledge: Enhancing life

| Area Covered | Duchy and Pendlebury |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Reuben Flynn, Salix Homes |  |
| Summary | To provide a strategic framework for the physical, social and economic renewal of the area; securing its long-term sustainability by making the areas more attractive and safer places to live, more desirable places to visit and more inviting areas for private sector investment; building on a strong local identity and aspiration and involving the communities and other stakeholders. |  |
| Priorities and Milestones |  | Timescales |
| Draft review document circulated to key stakeholders. |  | Late September 2008 |
| Review of renewal area complete. |  | Autumn 2008 |
| CPO area scheduled to be cleared. |  | Summer 2008 |
| Work on alleygating scheme adjoining the Asten’s Fold Development (formally Duchy Bank) completed. |  | End of June 2008 |
| Complete review baseline and undertake consultation. |  | Summer 2008 |
| Progress |  | Date |
| Negotiations to secure vacant possession of three properties. |  | Ongoing |
| Phased demolition programme (114 properties) ongoing (82% of all properties had been cleared by May 2008). |  | Ongoing |
| Off-street parking scheme implemented. |  | May 2008 |
| Asten’s Fold (Duchy Bank) housing development completed. All residents choosing to relocate from the adjoining clearance area have now moved in. |  | January 2008 |
| Funding sources | Housing Capital Programme and HMRF |  |
| Publicity to date | - Asten’s Fold Development formally opened by Rt Hon Hazel Blears, MP - Media coverage of successful development & housing design in local & regional press and in housing & development trade magazines - Development has been entered into a regional design award competition - Newsletter updates |  |

## Project: Salford Innovation Park including the Salford Innovation Forum

##### Pledge: Creating prosperity in Salford

| Area Covered | North Irwell Riverside |  |
| --- | --- | --- |
| Lead Officers | Matthew Lynn, Chief Executive Directorate Bernie Vaudrey, Chief Executive Directorate |  |
| Summary | Salford Innovation Park encompasses the Salford Innovation Forum (SIF) Building, Salford University Technology House and surrounding business units to promote the growth of knowledge based industries. |  |
| Priorities and Milestones |  | Timescales |
| Commence contract negotiations with chosen management company for SIF who will also own and manage the two adjacent assets. |  | November 2008 |
| Deadline for return of second stage tenders. |  | 21/07/08 |
| Progress |  | Date |
| The Salford Innovation Park OJEU tender Pre Qualification Questionnaire (PQQ) was advertised for a company to manage the Forum and own two adjacent assets (Salford University Business Park and Technology House).Two companies invited to tender for second stage. |  | Spring 2008 |
| Forum has 16 tenants. |  | April 2008 |
| Funding sources | £3.4m ERDF £5.9m NWDA £300K NDC £9.6m Total capital costs |  |
| Publicity to date | Press release dated 27/09/06 |  |

## Project: Salford Museum & Art Gallery

## Pledge: Enhancing life

| Area Covered | Whole city |  |
| --- | --- | --- |
| Lead Officer | Andy Howitt, Community Health & Social Care Directorate |  |
| Summary | Salford City Council approved a broad vision for Salford Museum & Art Gallery in June 2006. It consisted of: - A museum that will be a regional and national resource for the understanding of social history - A focal point promoting innovation and enterprise amongst the city’s growing creative industries - A facility which, in partnership with Salford University, will provide learning and educational opportunities from pre-school to Higher Education, research and the general public - A setting that can be used for events and conferences - A building and public space that is a catalyst for, and integral to, the development of the ‘Crescent Heritage/Cultural Quarter’ - A facility which achieves universal physical and intellectual access |  |
| Priorities and Milestones |  | Timescales |
| Complete development phase – (provisional date). |  | September 2009 |
| Submission of initial funding bids. |  | December 2008 |
| Investigations and technical development of the masterplan scheduled to complete. |  | September 2008 |
| Progress |  | Date |
| Investigations and technical development of the masterplan commenced. |  | March 2008 |
| Delivery Plan agreed. |  | December 2007 |
| Masterplan completed. |  | December 2007 |
| Funding sources | Currently unknown |  |

Project: Springfield Lane

##### Pledges: Enhancing life / Creating prosperity in Salford

| Area Covered | Springfield Lane |  |
| --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate Stephen Gwatkin, Urban Vision |  |
| Summary | Redevelopment for residential and mixed use scheme with Urban Splash. The scheme includes 450 apartments, 20,000 square feet of commercial space on the lower levels of the apartment blocks, an office building of approximately 50-70,000 square feet on the corner of Trinity Way / Springfield Lane and 400 car parking spaces. |  |
| Priorities and Milestones |  | Timescales |
| Planning for phase 1 expected to start. |  | September 2008 |
| Report to Lead Member for Planning. |  | June/July 2008 |
| Progress |  | Date |
| Forecasts indicate first phase of scheme will not produce land receipt and overall forecast is less than expected. Lead Member report being developed in consultation with Central Salford URC to highlight position and seek guidance on way forward. |  | June 2008 |
| Funding sources | Private sector Possible public sector in relation to affordable housing |  |
| Publicity to date | Urban Splash coverage |  |

###### Eccles

Project: Bridgewater Way

## Pledge: A city that is good to live in

| Area Covered | Covers 65km of towpath covering eight local authorities. |  |
| --- | --- | --- |
| Lead Officer | Darren Findley, Housing and Planning Directorate Janet Roberts, Bridgewater Trust |  |
| Summary | The Bridgewater Way will enhance and regenerate 65km of the areas historic canal routes linking communities and the National Cycle and footpath network. Approximately 8km of the towpath will connect communities across the west of Salford. It is hoped that the regeneration of the canal will create a more accessible leisure asset, bring an additional 0.5 million visitors per annum, create 225 indirect jobs and 24 direct jobs and create £5.8 million annual total net benefit. |  |
| Priorities and Milestones |  | Timescales |
| 250th anniversary of the Bridgewater Canal. |  | 2011 |
| Response to bid for European funding for interpretation and lighting along the canal. |  | July 2008 |
| Progress |  | Date |
| Opening of phase one and two (Liverpool Road to M602). |  | 11/06/08 |
| £75,000 funding allocated from Block 3 Local Transport Plan 2008/09. |  | June 2008 |
| Funding for third phase (route into Monton) being sought. |  | Ongoing |
| New booklet produced by Bridgewater Canal Trust to publicise ongoing work. |  | May 2008 |
| Booklet publicising a walk along Bridgewater Way in Salford distributed. |  | March 2008 |
| Surface work for phase one and two completed (Liverpool Road to M602). |  | March 2008 |
| A marketing programme is being drawn up for the Eccles to Monton section (from Liverpool Road to the M602). |  | January 2008 |
| Funding sources | NWDA Manchester Ship Canal Salford City Council (Salford West Regeneration Framework) Block 3 LTP The overall project is estimated to cost £8 million |  |
| Publicity to date | Salford City Council publication of trail along the Bridgewater canal ‘Monton & Roe Green Loopline Heritage Trail’. Leaflets, website and press releases. www.bridgewatercanal.co.uk |  |

Liverpool Road Corridor Strategy

## Pledge: Creating prosperity in Salford

| Area Covered | Eccles |  |
| --- | --- | --- |
| Lead Officer | David Evans, Housing & Planning Directorate Lyndsey Priestley, Chief Executive Directorate |  |
| Summary | Implementation of environmental improvements and promotion of social and economic cohesion along the Liverpool Road Corridor (LRC). The strategy has been integrated into the Salford West Strategic Regeneration Framework delivery structure. |  |
| Priorities and Milestones |  | Timescales |
| Masterplan for Patricroft Bridge completed. |  | May 2009 |
| Eccles Area Regeneration Study completed. |  | Dec 2008 |
| Draft three year implementation plan presented to the Salford West Board. |  | July 2008 |
| Completion of greening scheme work. |  | End June 2008 |
| 2008/09 priority action plan drafted. |  | June 2008 |
| Progress |  | Date |
| Liverpool Road Corridor strategy presented to Salford West Board for comments. |  | 15/04/08 |
| Liverpool Road Corridor Task Group established and a three year implementation plan is being developed. |  | April 2008 |
| Greening scheme underway. |  | April 2008 |
| Work on the Eccles Area Regeneration Study started. |  | April 2008 |
| Business front improvement scheme in development. |  | April 2008 |
| Funding sources | ## Capital budget (Salford West) 2008/09 - £475,000 (Funding for LRC will fund activity in both Eccles and Irlam & Cadishead) Private Sector Contributions – TBC |  |
| Publicity to date | - Press release in MEN re: Ministerial visit - Article in the Salford Advertiser – February 2007 - Further publicity planned |  |

Project: Eccles town centre

Pledge: Creating prosperity in Salford

| Area Covered | Eccles |  |
| --- | --- | --- |
| Lead Officer | Cath Inchbold, Chief Executive Directorate Richard Wynne, Urban Vision |  |
| Summary | Various interventions to promote and enhance the town centre. A cross Directorate Task Group will progress development of town centres via the Salford West Framework implementation. |  |
| Priorities and Milestones |  | Timescales |
| Eccles Gateway Centre (LIFT) due to open. |  | November 2008 |
| Town centre stakeholder workshop. |  | Autumn 2008 |
| Following clarification around the Crown Theatre, the application will be presented to Planning Panel. |  | June/ July 2008 |
| Progress |  | Date |
| Town centre task group compiling baseline data. |  | May/ June 2008 |
| Leader, Deputy Leader and Chief Executive met with owners of West One Retail Park. |  | 19/05/08 |
| Report on Eccles town centre presented to Leader’s Briefing. |  | 14/04/08 |
| Listed Building Consent for the partial demolition of a listed building (Crown Theatre) submitted. Application awaiting clarification on outstanding matters around sustainable design, scheme viability and waste management. |  | 14/01/08 |
| Funding sources | Private Salford City Council PCT |  |
| Publicity to date | Press coverage of LIFT proposal |  |

##### Project: Magistrates Court and Justice Centre Initiative

##### Pledge: Enhancing life

| Area Covered | Eccles |  |
| --- | --- | --- |
| Lead Officer | David Greenfield, Housing and Planning Directorate Richard Wynne, Urban Vision |  |
| Summary | Establishment of new courthouse at John William Street. The building will contain eight Magistrates Courts and four country courts as well as officers for staff and solicitors, with an adjacent 308 space five-storey car park. The car park will be built by selected bidder with Urban Vision retaining ownership. |  |
| Priorities and Milestones |  | Timescales |
| Completion of Magistrates Courthouse. |  | November 2011 (subject to review) |
| Multi-storey car park/ Courthouse construction starts. |  | July 2009 (subject to review) |
| Submission of bids. |  | Early August 2008 |
| Discussions to be held with each bidder. |  | May – July 2008 |
| Progress |  | Date |
| Negotiations between SCC and HMCS to secure final agreement to the Head of Terms for both the land transaction and car park terms and conditions completed. |  | May 2008 |
| Funding sources | PFI funding of approximately £20million confirmed via HMCS |  |
| Publicity to date | Press coverage of Magistrate Court proposal |  |

###### Irlam & Cadishead

Project: Barton Strategic Site

Salford Reds Stadium

| Area Covered | Barton |  |  |
| --- | --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate Matthew Lamb, Urban Vision |  |  |
| Summary | The Secretary of State gave approval to Salford Reds new 20,000 seat stadium with retail, hotel and catering support 03/11/06. The council is working with the applicant on a phased approach to implementing the scheme that will comprise site clearance, site remediation and implementation stages. Application for approval of Reserved Matters approval is in preparation. |  |  |
| Priorities and Milestones |  |  | Timescales |
| Reserved matters planning application will potentially be determined by the Planning and Transportation Regulatory Panel, at which point site remediation and construction could commence (subject to discharge of relevant pre-commencement conditions). |  |  | Summer 2008 |
| A Reserved Matters application is expected for all outstanding elements (design, scale and landscaping) for the stadium, hotel, conference facilities, ancillary offices, bars and stand alone retail units for the stadium and retail units. |  |  | Summer 2008 |
| Progress |  |  | Date |
| Preliminary archaeological dig has been extended as remains of an ancient settlement were found. Due to location at entrance of site these are not expected to delay works. |  |  | Ongoing |
| Outline planning permission granted with reserved matters. |  |  | December 2007/ January 2008 |
| Funding sources |  | Private |  |
| Publicity to date |  | Press coverage. Salford Reds website |  |

Port Salford

| Area Covered | Barton |  |  |
| --- | --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate Jonathan Pennick, Urban Vision |  |  |
| Summary | Port Salford: multi modal freight terminal; to include 2-berth port, rail freight terminal, and 200,000 sq m warehousing. |  |  |
| Priorities and Milestones |  |  | Timescales |
| Highways Agency holding direction in place, and is reviewed on a month-by-month basis as necessary. Direction is extended to 18/08/08. |  |  | 18/08/08 |
| Funding sources |  | Private |  |
| Publicity to date |  | Press coverage |  |

Project: Chat Moss Visioning

Pledge: Enhancing Life

| Area Covered | Chat Moss (in Salford); Rixton and Risley Mosses (in Warrington) and Astley Moss (in Wigan) |  |
| --- | --- | --- |
| Lead Officer | Nick Lowther, Housing and Planning Directorate |  |
| Summary | To carry out an assessment of the Mossland project area to produce a long term vision that will promote the “best fit” for competing land uses and establish sustainable land use patterns with a view to: - understanding mossland habitat and landscape in order to deliver maximum public benefit. - secure long term economic viability of mosslands based around agriculture, establishment of local markets, specialist products and creation of jobs for local people. - recognise unique potential of mossland to deliver rare and significant amounts of mossland habitat of high biodiversity value. - maximise value of mossland landscape as an accessible leisure, health and local heritage resource for tourists, visitors and local communities. |  |
| Priorities and Milestones |  | Timescales |
| Undertake further work to establish the hydrological zone width to protect bog restoration areas on Chat Moss. |  | During 2008/09 |
| Further consultation with residents is being considered as part of the future Core Strategy issues and options. |  | Autumn/ Winter 2008 |
| Progress |  | Date |
| Hydrological Protection Zone report finalised. Report recommends a narrow pilot zone established without crops installation of dipwells in study area, followed by one year water level monitoring to verify peat permeability values. |  | May 2008 |
| Land use survey field work completed. |  | March 2008 |
| Completion of bog restoration work undertaken by Lancashire Wildlife Trust and funded through Biffaward. |  | February 2008 |
| Funding sources | Salford West Action Plan - £10,000 (Hydrological Study) Biffaward Section 106 |  |
| Publicity to date | n/a |  |

Liverpool Road Corridor Strategy

## Pledge: Creating prosperity in Salford

| Area Covered | Irlam and Cadishead |  |
| --- | --- | --- |
| Lead Officers | David Evans, Housing & Planning Directorate Lyndsey Priestley, Chief Executive Directorate |  |
| Summary | Implementation of environmental improvements and promotion of social and economic cohesion along the Liverpool Road Corridor. The Strategy has been integrated into Salford West Strategic West Regeneration Framework delivery structure. |  |
| Priorities and Milestones |  | Timescales |
| Carriageway/ streetscape improvements works expected to start on site following consultation. |  | November 2008 |
| Draft three year implementation plan presented to the Salford West Board. |  | 21/07/08 |
| #### Completion of greening scheme. |  | June 2008 |
| Progress |  | Date |
| Three year implementation plan is being developed. |  | Ongoing |
| Council officers met with Network Rail, Northern Rail and GMPTE at Irlam Station to discuss potential improvements around car parking and access, particularly at the station approach junction with Liverpool Road. |  | June 2008 |
| Public consultation on carriageway/ streetscape improvements. |  | June 2008 |
| Liverpool Road Corridor strategy presented to Salford West Board for comments. |  | 15/04/08 |
| Greening scheme underway. |  | April 2008 |
| Company set up to purchase and renovate run down properties along Liverpool Road. |  | April 2008 |
| Funding sources | ## Capital budget (Salford West) 2008/09 - £475,000 (Funding for LRC and will fund activity in both Eccles and Irlam & Cadishead) Private Sector – TBC Highways – TBC |  |
| Publicity to date | Press Release in MEN re: Ministerial visit Article in the Salford Advertiser – February 2007 Further publicity planned |  |

###### Little Hulton & Walkden

Project: Ashton’s Field Site

Pledge: Creating prosperity in Salford

| Area Covered | Little Hulton |  |  |
| --- | --- | --- | --- |
| Lead Officer | Matthew Lynn, Chief Executive Directorate |  |  |
| Summary | Attract prospective developers to the Ashton’s Field site. |  |  |
| Priorities and Milestones |  |  | Timescales |
| Engage with private sector developers (and the landowners NWDA) to release the commercial element of the site for B1 B2 B8 uses. |  |  | November 2008 |
| Progress |  |  | Date |
| Rok Developments have confirmed that they will re-submit planning application following further discussions with NWDA, the landowner. Date of resubmission to be confirmed. |  |  | Ongoing |
| Several enquiries from inward investors handled by Economic Development. |  |  | May 2008 |
| Planning application for 10 general industrial units for the Ashton field site, Little Hulton, was submitted by Rok Developments Limited. The application was refused on the grounds of a lack of flood risk assessment. |  |  | April 2008 |
| Funding sources |  | NWDA EP |  |
| Publicity to date |  | NWDA Press Release June 2005 |  |

Project: SPOTlighting in Little Hulton

Pledge: Enhancing Life in Salford

| Area Covered | Little Hulton |  |  |
| --- | --- | --- | --- |
| Lead Officer | Emily Kynes, Matthew Ainsworth, Chief Executive Directorate |  |  |
| Summary | Tackling worklessness through a series of support measures to lone parents. |  |  |
| Priorities and Milestones |  |  | Timescales |
| Presentation of analysis, consultation and challenges to Children’s Services Management Team. |  |  | 01/07/08 |
| Action planning workshop for partners. |  |  | 20/06/08 |
| Progress |  |  | Date |
| Project plan developed from Action Planning Workshop. |  |  | Ongoing |
| Presentation to panel. |  |  | 24/04/08 |
| Develop project plan. |  |  | July 2008 |
| Funding sources |  | Salford City Council |  |
| Publicity to date |  | SPOTlight newsletters and feedback |  |

Project: Cutacre Site

Pledge: Creating prosperity in Salford

| Area Covered | Cutacre Site, Little Hulton |  |
| --- | --- | --- |
| Lead Officers | Graham Gentry, Housing and Planning Directorate Stephen Birnie, Urban Vision |  |
| Summary | Reclamation and restoration of the land, following coal extraction, for a mixture of amenity, agriculture and woodland uses. The coal extraction programme has a 4 year timetable. |  |
| Priorities and Milestones |  | Timescales |
| Completed restoration of land following coal extraction. |  | 2011 |
| Water treatment lagoons to be implemented in areas F (south east corner – Salford) and G (south east corner – Salford and Bolton) subject to dry weather conditions. |  | Summer 2008 |
| Progress |  | Date |
| Archaeological works began at Wharton Hall. This included provision of site compound. |  | 03/06/08 |
| Site clearance to east of Cutacre Tip (Salford) completed. |  | May 2008 |
| Soil stripping commenced. |  | May 2008 |
| 176,276 tonnes of coal removed from site. |  | March 2008 |
| Bond signed by Salford CC, Wigan MBC and Bolton MBC. |  | 05/03/08 |
| Funding sources | Private funding |  |
| Publicity to date | Liaison meetings with Ward Councillors and residents take place every few months. Given the size of the site, it has been split into areas A-H which will be worked as separate phases (some of which overlap). |  |

Project: Walkden town centre

Pledges: All

| Area Covered | Walkden town centre and Walkden Station area |  |
| --- | --- | --- |
| Lead Officer | Cath Inchbold, Chief Executive Directorate Kurt Partington, Urban Vision Partnership |  |
| Summary | Interventions to promote or enhance the town centre. A cross directorate Task Group will progress development of town centres via Salford West framework implementation. |  |
| Priorities and Milestones |  | Timescales |
| Walkden Gateway centre complete. |  | September 2008 |
| Town Centre stakeholder workshops. |  | Autumn 2008 |
| Work due to commence on Walkden Station. |  | June 2008 |
| Progress |  | Date |
| Town centre task group compiling baseline data. |  | May/ June 2008 |
| Two options for work around Walkden Station were presented to the Little Hulton and Walkden Devolved Highways Budget Group. Option 1, to enhance the street scene and highway safety in the area without the creation of a new pedestrian crossing chosen. |  | 08/05/08 |
| Report on Walkden town centre presented to Leader’s Briefing. |  | 21/04/08 |
| Planning application submitted to demolish existing Tesco food store and replace with a new supermarket together with new atrium, additional retail units and car park alternations and access. The application is expected to be considered by planning panel in July 2008. |  | 28/03/08 |
| Funding sources | Private |  |
| Publicity to date | Press articles |  |

###### Ordsall & Langworthy

##### Project: Islington Estate

Pledge: Enhancing life

| Area Covered | Islington Estate |  |
| --- | --- | --- |
| Lead Officer | John Wooderson, Housing & Planning Directorate Christine Duffin, Salix Homes |  |
| Summary | Development of a neighbourhood Plan for the Islington Estate to outline the future of the area in the context of the wider regeneration of the Chapel Street area. The process will explore the future options of the council’s commitment to bring homes up to the government’s Decent Homes Standard over the next 5 years. The Salford Central Development Framework will look at the wider area around Islington Estate. Consultation will take place during spring/ summer to look at issues around housing, the environment, crime and anti social behaviour. |  |
| Priorities and Milestones |  | Timescales |
| Open day planned to look at preferred option. |  | September 2008 |
| Progress |  | Date |
| Moving Forward event to identify next steps and consult with residents on generating options for investment in the area. |  | 31/05/08 |
| Community consultation on estate started. |  | 06/05/08 |
| Funding sources | SCC ECF CSURC Salix Homes |  |
| Publicity to date | Local media and consultation media |  |

##### Project: Salford Central Planning Guidance and Development Framework

##### Pledge: Creating prosperity in Salford

| Area Covered | Chapel Street |  |
| --- | --- | --- |
| Lead Officer | Peter Baker, CSURC |  |
| Summary | The Salford Central Planning Guidance was adopted by the city council in March 2008. The CSURC has commissioned Urban Initiatives to undertake the preparation of a Development Framework for the Salford Central area. The Framework will set out in detail how the principles in the planning guidance will be reflected within development in the five character areas and on individual sites. This is being steered by a project team comprising of Salford City Council, Salix Homes and English Cities Fund. |  |
| Priorities and Milestones |  | Timescales |
| Adoption of Development Framework by city council. |  | January 2009 |
| Progress |  | Date |
| Consultation on draft Development Framework. |  | 13/05/08 to 03/06/08 |
| Planning Guidance adopted. |  | 19/03/08 |
| Funding sources | CSURC and SCC |  |
| Publicity to date | Publicity about adoption of Planning Guidance on Salford City Council website. |  |

##### Project: Salford Central Station

##### Pledge: Creating prosperity in Salford

| Area Covered | Chapel Street |  |
| --- | --- | --- |
| Lead Officer | Peter Baker, CSURC |  |
| Summary | Improvements to the station and approaches will provide a major transport interchange for surrounding developments in Chapel Street and Manchester City Centre. Phase 1 has been completed and there is a further study currently underway to review the design, cost and phasing of future phases. |  |
| Milestones |  |  |
| Completion of design review study. |  | July 2008 |
| Progress |  | Date |
| CSURC with partners GMPTE, Salford City Council, Network Rail, Northern Rail and English Cities Fund (ECf) has commissioned a study to review the design, cost and phasing of further station improvements. This is being undertaken by Austin Smith Lord Architects. |  | May 2008 |
| Phase 1 improvements completed. Improvements include the creation of a new enclosed forecourt, a refurbished concourse and new lift access to the upper level platforms. There were also improvements to facilities such as the ticket office, toilets and information systems. |  | February 2008 |
| Funding sources | Phase 1: EDZ £1,080,848 GMPTE £3,352,442 |  |
| Publicity to date | Various press coverage about completion of Phase 1 works. |  |

Project: Crescent Masterplan/ Crescent Railway Station

##### Pledge: Enhancing life in Salford/ Creating prosperity in Salford

| Area Covered | Crescent Masterplan/ Crescent Railway Station |  |
| --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate Nik Puttnam, CSURC |  |
| Summary | The regeneration of the southern side of The Crescent will serve to link the regeneration of the Chapel Street Corridor with the University Quarter and Pendleton town. The Masterplan will underpin the development of a residential led mixed-use development, focused around the re-opened Manchester Bury Bolton Canal and an expanded University. The masterplan has been put on hold pending outcome of several other pieces of work including the Salford University masterplan. |  |
| Priorities and Milestones |  | Timescales |
| Short term measures to address overcrowding and safety issues at Salford Crescent Station implemented. |  | December 2008 |
| Revisit the Crescent Masterplan and incorporate the findings of the various other studies. |  | September 2008 |
| Completion of Salford University Masterplan and Estates Strategy. |  | September 2008 |
| Progress |  | Date |
| A report summarising the Former Police Headquarters Feasibility Study and suggesting ways forward is being prepared for consideration by Members. |  | Ongoing |
| Urban Initiatives, the masterplanning consultant appointed by Salford University, have circulated initial delivery options in relation to the University’s estates following a consultation event in May 2008. |  | June 2008 |
| Network Rail has programmed the redevelopment of Crescent Railway Station into their future work plan. Salford Crescent Station Study complete. Further development work on two sites taking place. |  | Ongoing |
| The URC and British Waterways considering the deliverability of the phase 2 re-opening the Manchester Bury Bolton Canal and discussions held on delivery options. |  | Ongoing |
| Funding sources | CSURC, British Waterways |  |
| Publicity to date | Project websites |  |

##### Project: Greengate

##### Pledges: Enhancing life in Salford/ Creating prosperity in Salford

| Area Covered | Greengate area |  |
| --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate Nik Puttnam, CSURC |  |
| Summary | Greengate represents the redevelopment of 13 hectares of vacant/underused former industrial land and property. Exchange Greengate Planning Guidance adopted by council on 17/01/07. The redevelopment of Greengate is underpinned by the delivery of 1.9 hectare of public realm including new public space and a pedestrian bridge link across the River Irwell. This forms part of Irwell City Park. The new public realm will be the catalyst to the delivery of 2,600 homes and over 85,000 m2 of commercial floorspace, including hotels and leisure use. The scheme has the potential to deliver over £650 million of private sector investment and will be delivered over the next 10 -15 years. CSURC project manage the overall process. Northwest Regional Development Agency’s (NWDA) Framework Panel will appoint a separate project management and quantity surveying team. |  |
| Priorities and Milestones |  | Timescales |
| ASK/ Network Rail to start development of Phase 1. |  | Spring 2009 |
| Centre for Construction Innovation (CCI) will project manage the OJEU procurement to appoint a preferred civil contractor. |  | 28/10/08 |
| Salford City Council to serve notice on tenant of former Victoria Bus Station site giving six months notice to vacate. |  | 21/10/08 |
| English Partnership’s Landscape Architect Framework Panel to appoint design team. |  | July 2008 |
| Progress |  | Date |
| Tenders received for phase 1 detailed design works. |  | 16/06/08 |
| British Standard Construction (BSC) Canopus scheme put on hold, following recent reports in MEN about the company going into receivership. URC chasing up with the bank/ receiver. |  | May 2008 |
| CSURC finalised the procurement route for phase 1 detailed design works and preferred contractor. CSURC short-listed Design Team Pre-qualification Questionnaires. Five practices invited to tender. |  | May/ June 2008 |
| Funding sources | English Partnerships, Private Sector and SCC Section 106. |  |
| Publicity to date | Publicity in local press and professional journals about various planning applications and public realm proposals. |  |

## Project: Restoration of Manchester, Bury & Bolton Canal (MBBC)

## Pledge: Enhancing life in Salford

| Area Covered | Line of the Canal from the River Irwell Trinity Way / Hampson Street to Clifton Junction (and on into Bury & Bolton). |  |
| --- | --- | --- |
| Lead Officers | David Evans, Housing and Planning Directorate |  |
| Summary | To drive the restoration of the canal to navigation, which will act as a catalyst to regeneration & redevelopment along its line. Phase one of the restoration is concentrated around the Middlewood area. |  |
| Priorities and Milestones |  | Timescales |
| Financial completion of phase 1. |  | May/ June 2008 (commissioning may extend into summer period). |
| Installation of pumps and phase 1 finishing off. |  | Summer 2008 |
| Progress |  | Date |
| Breakthrough into the river. |  | June 2008 |
| Land adjacent to phased 1 restoration work has been acquired for potential redevelopment. |  | April 2008 |
| The URC and British Waterways have started to look at the deliverability of the phase 2 re-opening and are discussing delivery vehicle options. |  | Ongoing |
| Funding sources | Phase 1 ERDF £2,039,362 NWDA £1,100,000 S106/ SCC £1,354,000 Private sector £1,000,000 (contribution of land) |  |
| Publicity to date | Press releases Website |  |

Project: Middlewood

Pledge: Enhancing life in Salford

| Area Covered | Middlewood area |  |
| --- | --- | --- |
| Lead Officer | David Evans, Housing and Planning Directorate Matthew Lamb, Urban Vision |  |
| Summary | The below sites make up the Middlewood area in its entirety: Valley and Vale owned land: This scheme comprises a mixed-use development accommodating residential (142,697 sqm of floorspace), commercial (67,773 sqm of B1 floorspace), leisure and retail (27,191 sqm of Class A1, A2, A3, A4, and D2) uses. Outline planning permission (access only) has been granted. Granada owned land: This application seeks outline approval for a mixed-use development comprising of residential (15,509 sqm), commercial (15,587 sqm of Class B1 floorspace), and leisure/ retail uses (1,692 sqm of Class A1, A2, A3, and A4), together with associated car parking, landscaping, and infrastructure. |  |
| Priorities and Milestones |  | Timescales |
| Outline planning application for land owned by Granada expected to be considered by Planning and Transportation Regulatory Panel. |  | 03/07/08 |
| Progress |  | Date |
| Outline planning permission (access only) relating to land currently within the ownership of Valley and Vale, granted. This is valid until April 2014. To date no applications for approval of reserved matters and no requests for formal pre-application advice have been made. |  | April 2007 |
| Planning application for land owned by Granada submitted. |  | 20/12/2006 |
| Funding sources | Private |  |
| Publicity to date |  |  |

Project: Pendleton Housing Private Finance Initiative (PFI)

Pledge: Enhancing life in Salford

| Area Covered | Pendleton |  |
| --- | --- | --- |
| Lead Officer | Rob Pickering, Housing and Planning Directorate |  |
| Summary | DCLG approval was given in December 2006 to proceed with developing the Outline Business Case for the Pendleton PFI scheme by the end of 2007. Maximum credit allocation available £102m. |  |
| Priorities and Milestones |  | Timescales |
| DCLG decision on the outline business case for PFI. |  | November 2008 |
| Planned bidders day. |  | November 2008 |
| Outline business case for Pendleton PFI to DCLG. |  | June 2008 |
| Progress |  | Date |
| Gateway review complete. |  | May 2008 |
| Marketing prospectus is being developed by CSURC and Salford City Council incorporating the Pendleton Planning Guidance to seek a private sector PFI partner. |  | April 2008 |
| Funding sources | DCLG |  |
| Publicity to date | Various, associated with AAP consultation. MEN press coverage of PFI announcement Dec 06. Newsletter Spring 07 Newsletter Winter 07 |  |

Project: Pendleton Planning Guidance

Pledge: Enhancing life in Salford

| Area Covered | Pendleton and Langworthy |  |
| --- | --- | --- |
| Lead Officer | Graham Gentry, Housing and Planning Directorate |  |
| Summary | A non-statutory Draft Planning Guidance Document for the Pendleton area is being prepared by Urban Vision. This will build upon work already undertaken on the former Area Action Plan (Consultation on Preferred Options completed 26/07/07). The Guidance will sit outside the Local Development Framework (LDF). |  |
| Priorities and Milestones |  | Timescales |
| Public consultation on the draft Planning Guidance document. |  | 05/09/08 to 16/10/08 |
| Progress |  | Date |
| Updated draft Planning Guidance discussed at informal Planning Lead Member. |  | 01/04/08 |
| Funding sources | SCC |  |
| Publicity to date | Various publicity associated with Area Action Plan consultation. PAAP Newsletter Feb 2006. |  |

Project: Proposed food store development – Shopping City

Pledges: Creating prosperity in Salford/ Enhancing life in Salford

| Area Covered | Land adjacent to Pendleton Way |  |
| --- | --- | --- |
| Lead Officers | Graham Gentry, Housing and Planning Directorate Peter Openshaw, Urban Vision |  |
| Summary | New food store and associated retail development at Salford Shopping City to support the centre and enhance retail facilities in the area. |  |
| Priorities and Milestones |  | Timescales |
| Once financial resolution agreed between the council, Shopping Centre owner and food store agents, contracts can be exchanged and the CPO/ planning application taken forward. |  | Summer 2008 |
| Meeting between the council and the food store to agree a final figure and its impact on sales price. A revised Lead Member approval will be required following resolution of the land deal issues. |  | June 2008 |
| Progress |  | Timescales |
| Shopping Centre owner has been advised by the council that resolution of the land deal is needed asap with an absolute deadline in week commencing 16/06/08. |  | June 2008 |
| Food store response to the council’s position on land removal costs is awaited. |  | June 2008 |
| Funding sources | Private |  |

Project: Seedley Village

Pledges: All

| Area Covered | Seedley Village |  |
| --- | --- | --- |
| Lead Officers | John Wooderson, Housing and Planning Directorate Gill Finlay, Salix Homes |  |
| Summary | To create a sustainable neighbourhood of choice that offers a safe and attractive place to live for the existing community and encourages newcomers and private investment. |  |
| Priorities and Milestones |  | Timescales |
| Urban Splash development complete. |  | March 2010 |
| Completion of a mixed use development including a new church, apartments, offices and community facilities on Langworthy Road. |  | Summer 2009 |
| Completion of block improvements scheme in Seedley South. |  | February 2009 |
| Progress |  | Date |
| Negotiations between church client group and contractors regarding completion of the scheme. If negotiations are successful work could re-commence on site in July 2008. If unsuccessful there would be a need to go to competitive tender in July/August 2008. |  | Ongoing |
| Discussions with residents to identify their re-housing needs from the proposed Seedley South clearance area. |  | Ongoing |
| Building on the church has stopped leading to a three month delay in completing the scheme. |  | April 2008 |
| 160 units on the Chimney Pot Park scheme completed (March 2007 to March 2008). All of the 91 ‘First Time Buyer’ units funded via English Partnerships have been sold. |  | March 2008 |
| Block improvements scheme for 173 homes started including refurbishment of 15 empty SCC owned properties starts. |  | January 2008 |
| Funding sources | NWDA, ERDF, HMRF, English Partnerships and Housing Capital Programme. |  |
| Publicity to date | Chimney Pot Park press coverage Launch of First Time Buyers Initiative in October 2006 |  |

## Project: Ordsall Regeneration Framework

## Pledge: Enhancing life in Salford

| Area Covered | Ordsall |  |
| --- | --- | --- |
| Lead Officer | Barry Whitmarsh, Housing and Planning Directorate |  |
| Summary | Regeneration and development within the Ordsall estate. |  |
| Priorities and milestones |  | Timescales |
| Opening of new retail centre. |  | Spring 2010 |
| Planning application for new retail centre expected to be considered at planning panel. |  | Summer 2008 |
| Public consultation on development proposals for existing district centre and former St Clements School sites. |  | July 2008 |
| Completion of environmental improvements to Monmouth Park. |  | June 2008 |
| Progress |  | Date |
| Planning application for 19 dwellings at Robert Hall Street approved. |  | 17/04/08 |
| Planning application for new retail centre and 282 dwellings at former Radclyffe school site submitted. |  | April 2008 |
| Construction on 33 dwellings at Radclyffe Mews completed and occupied. |  | April 2008 |
| Construction of 260 dwellings at Hulton Square commenced September 2007. First phase sold off plan. Marketing of second phase underway. Several properties sold under “Launchpad” and “First Time Buyers Initiative” schemes. |  | Ongoing |
| Funding sources | Private sector-led development, predominantly on Council-owned land. Infrastructure works funded from land values. Sources of gap funding to be identified. Housing Capital Programme. |  |
| Publicity to date | - Ordsall Regeneration Framework shortlisted for RICS North West Award for Regeneration. - Quay 5 development won the 'Your New Home ' magazine 'Best Development for 1st Time Buyers' award (March 2007) - Press articles following completion of development agreement. - Press releases issued in respect of consultation event. - Quarterly newsletter for local residents. |  |

Project: Ordsall Riverside

Pledges: Creating prosperity in Salford/ Enhancing life in Salford

| Area Covered | Ordsall Riverside |  |
| --- | --- | --- |
| Lead Officer | Barry Whitmarsh, Housing and Planning Directorate |  |
| Summary | Transformation of riverside employment area to vibrant waterside mixed use area. |  |
| Priorities and Milestones |  | Timescales |
| Planning Guidance presented to council for adoption. |  | July 2008 |
| Progress |  | Date |
| Development of 260 apartments by Lowry Homes at Taylorson Street nearing completion. |  | June 2008 |
| Planning application for 290 apartments by Bellway homes at Woden Street being considered. |  | June 2008 |
| Consultation report and revised Planning Guidance drafted. |  | May 2008 |
| Consultation on draft Planning Guidance completed. |  | March 2008 |
| Draft of Planning Guidance approved for consultation by Lead Member for Planning. |  | January 2008 |
| Funding sources | Private sector-led development. Most infrastructure works expected to be funded via section 106 contributions. CSURC seeking public funding for key infrastructure elements, such as proposed Cornbrook bridge through Irwell City Park programme. |  |

## Project: MediaCityUK

## Pledges: Creating prosperity in Salford / Enhancing life in Salford

| Area Covered | Salford Quays – Dock 9 |  |
| --- | --- | --- |
| Lead Officers | Alan Westwood, Customer and Support Services Directorate Jane Deane, Public Sector Programme Director |  |
| Summary | Relocation, from London and Manchester, of key BBC Departments such as Children’s, Sport and Radio Five Live. Creation of a hub of media and creative industries and support industries. The public sector support programme is targeted on 3 themes - Place, Sector & Economy and People & Communities. SCC is leading on the People and Communities programme, in conjunction with CSURC and building up a programme of measures to connect Salford people and communities to the development. |  |
| Priorities and Milestones |  | Timescales |
| Completion date for Quays Point. |  | 2012 |
| Metrolink service improvements to the Quays completed. |  | 2010 |
| Progress |  | Date |
| Closing date for advanced media apprenticeship applications. |  | 20/06/08 |
| SCC meeting with various partners, including BBC, to follow up actions under the People and Communities programme, school/ education and skills/ employability workstreams. |  | May/ June 2008 |
| Reserved matters planning application for the public realm and landscaping approved. |  | 17/04/08 |
| Planning permission granted for the Broadway Link Road. |  | 03/04/08 |
| Grant funding agreements in place with NWDA to secure funding for public realm work and metrolink. |  | April 2008 |
| Stakeholder event held. |  | March 2008 |
| Studio block and multi-storey car park planning applications approved. |  | 07/02/08 |
| Number of jobs transferring to MediaCityUK increased from 1,500 to over 1,620. |  | January 2008 |
| Funding sources | BBC / NWDA / private sector / SCC |  |
| Publicity to date | BBC relocation local and national press coverage. |  |

Project: Ordsall Hall Museum – Heritage Lottery Fund (HLF) project

## Pledge: Enhancing life in Salford

| Area Covered | Ordsall |  |
| --- | --- | --- |
| Lead Officer | Robin Culpin, Community Health & Social Care Directorate |  |
| Summary | The project aims to: - conserve the building, rather than restore it, - use the building and the grounds to reflect the phases of Salford’s history into the 21st century, - create a resource, which is a hub for the Ordsall community, a schools resource as well as a visitor destination, and - ensure that the Hall is a valuable addition to the visitor offer in Salford and key factor in the place shaping of Ordsall, the Quays and the Irwell City Park. |  |
| Priorities and Milestones |  | Timescales |
| Ordsall Hall reopens. |  | Easter 2011 |
| Building works commence. |  | Easter 2009 |
| HLF Stage 2 decision expected. |  | September 2008 |
| Progress |  | Date |
| HLF stage two bid submitted. |  | April 2008 |
| Match funding of £850,000 being pursued through a variety of sources. Funding has been received from the Garfield Weston Foundation, Shaw Trust, the Booth Foundation, the D’Oyly Carte Charitable Trust, the Pilgrims Trust, Glazers Trust and the Wolfson Foundation. Further bid decisions are awaited and new bids are to be submitted. Potential short fall. |  | Ongoing |
| The Heritage Lottery Fund (HLF) approved the bid for £4.1m for Ordsall Hall based on a successful stage two bid. A development grant was awarded. |  | 20/03/07 |
| Funding sources | HLF, SCC, charities, donations |  |
| Publicity to date | - Numerous features in the press - www.salford.gov.uk/ordsallhall |  |

Project: SPOTlighting in Ordsall and Langworthy

Pledge: Enhancing Life in Salford

| Area Covered | Ordsall and Langworthy |  |
| --- | --- | --- |
| Lead Officer | Diana Martin, Community Health and Social Care Directorate |  |
| Summary | Focus on safe, clean and green issues. |  |
| Priorities and Milestones |  | Timescales |
| Project plan with local indicators being developed. |  | Ongoing |
| Progress |  | Date |
| Police partnership vehicle crime 'operation lira' undertaken, with main focus on Salford Quays. The 20 arrests made have contributed to the vehicle crime reduction target being reached city wide. |  | April 2008 |
| Integrated Youth Support Service being piloted to engage statutory and voluntary provision to meet local need. |  | April 2008 |
| Additional police resources allocated to the neighbourhood. |  | April 2008 |
| Funding sources | Salford City Council SSP partners |  |
| Publicity to date | SPOTlight newsletters and community feedback |  |

###### Swinton

Project: Croal Irwell Regional Park - Lower Irwell Valley Improvement Area (LIVIA)

Pledge: Enhancing life in Salford

| Area Covered | LIVIA area |  |
| --- | --- | --- |
| Lead Officer | Neil Hook, Housing and Planning Directorate |  |
| Summary | Over 200 hectares identified for reclamation in the Irwell Valley. Site suffers from significant contamination from a wide range of past industrial uses. Focus of the programme will be to assess contamination, treat it where possible and restore the land for soft-end and recreational after uses. The Forestry Commission has taken lead responsibility for the delivery of this programme on behalf of the council. NWDA recognises the Croal Irwell Regional Park as a priority. |  |
| Priorities and Milestones |  | Timescales |
| NWDA decision on bid submission expected. |  | Late 2008 |
| An open day and presentation to community groups and Elected Members is being developed to begin process of developing a masterplan. |  | Late summer 2008 |
| Progress |  | Date |
| Completion of 8000m of footpath creation, new events space near Silverdale, two new play facilities and wildflower and tree planting. |  | April 2008 |
| Report presented to Lead Member for Planning providing an update on site works and proposals for future development. |  | 25/04/08 |
| Red Rose Forest has commissioned consultants to look at the links between Croal Irwell Regional Park and Irwell City Park. |  | November 2007 |
| The Bolton, Bury and Salford Newlands 2 bid, submitted by Manchester Enterprises to the North West Development Agency (NWDA), is through to the second round. |  | September 2007 |
| Funding sources | £4.75m approved in 2003. Approximately £1.5m of this will provide at least 15 years management and maintenance. Match funding has been secured from a number of sources including: - Coalfield Communities fund, Environment Agency landfill tax credits, S106 agreements, council capital receipts, Home Office ‘Gate-It’ funding. |  |
| Publicity to date | Coverage in MEN |  |

##### Project: Agecroft Commerce Park

## Pledge:  Creating Prosperity in Salford

| Area Covered | Swinton |  |
| --- | --- | --- |
| Lead Officer | Matthew Lynn, Chief Executive Directorate Bernie Vaudrey, Chief Executive Directorate |  |
| Summary | Site is cleared with development plots serviced by an access road constructed in 2005 by NWDA. In planning policy terms the end use is for employment generation B1 business, B2 general industrial or B8 storage or distribution. The site is 16.5 hectares and is owned by the North West Development Agency (NWDA) and marketed by DTZ (Manchester Office). The aim is to encourage investment and developer interest in Phase III, which will mean that all phases are up to full occupancy and maximum economic capacity. |  |
| Priorities and Milestones |  | Timescales |
| Launch of Invest IN Salford employment sites publication covering Salford West. Agecroft is identified as a key site. |  | November 2008 |
| Progress |  | Date |
| Revised proposal for public art piece under preparation/ consultation. Discussions taking place with the city council’s Arts Development team, with a view to consulting with residents and Members when designs are finalised. |  | On going |
| Tour of Agecroft as part of a MIDAS tour of the city. |  | May 2008 |
| Continued developer interest in Phase III. Urban Vision recently handled enquiries for one of the five plots available. |  | December 2007 |
| Funding sources | NWDA and RSI |  |
| Publicity to date | Article in Manchester Evening News 11/01/07. |  |

##### Project: Swinton Town Centre

## Pledge:  Enhancing life in Salford

| Area Covered | Swinton |  |
| --- | --- | --- |
| Lead Officers | Cath Inchbold, Chief Executive Directorate Perry Twigg, Urban Vision |  |
| Summary | Overall improvement of town centre. Cross directorate group set up to progress development of town centres via Salford West Framework implementation. |  |
| Priorities and milestones |  | Timescales |
| Stakeholder workshops. |  | Autumn 2008 |
| LIFTCo complete design scheme for a Swinton LIFT. |  | Summer 2008 |
| Meeting between SCC and town centre owners. |  | July 2008 |
| Progress |  | Date |
| Town centre task group compiling baseline data. |  | May/ June 2008 |
| Report on Swinton town centre presented to Leader’s Briefing. |  | 28/04/08 |
| A meeting between SCC and the new shopping centre owners took place. |  | December 2007 |
| Funding sources | Private Salford City Council Salford PCT |  |
| Publicity to date | n/a |  |

###### Worsley & Boothstown

Project: Old Warke Dam and Worsley Delph

Pledge: Enhancing Life in Salford

| Area Covered | Old Warke Dam and Worsley Delph |  |
| --- | --- | --- |
| Lead Officers | Cath Inchbold, Chief Executive Directorate |  |
| Summary | Restore Old Warke Dam and enhance the environmental and leisure assets in the area. The project will be delivered in stages. The first stage involves fitting four silt traps to avoid the dam silting up. This action is being delivered through the Salford West Framework and Action Plan. |  |
| Priorities and milestones |  | Timescales |
| Old Warke Dam ecological report. |  | September 2008 |
| Completion of final two silt traps. |  | August 2008 |
| Work on second set of silt traps to start. |  | Late June 2008 |
| Analysis of silt composition at Worsley Delph anticipated. |  | June 2008 |
| Progress |  | Date |
| First two silt traps completed. |  | June 2008 |
| Ecological studies started. |  | May 2008 |
| Initial site investigations complete. |  | March 2008 |
| Work on first two silt traps starts. |  | March 2008 |
| Phase two objectives agreed with the Environment Agency. |  | 20/03/2008 |
| Planning application for silt traps approved. |  | 21/02/08 |
| Group set up to consider future of Worsley Delph. |  | January 2008 |
| Old Warke Dam project team set up. |  | December 2007 |
| Funding sources | Private Sector Salford West |  |
| Publicity to date | Community Committee letters |  |

Project: Salford Forest Park

| Area Covered | Worsley/ Boothstown |  |
| --- | --- | --- |
| Lead Officers | Chris Findley, Housing and Planning Directorate Jonathan Pennick, Urban Vision |  |
| Summary | The Masterplan for the site includes the provision of a racecourse with floodlit all weather track and grandstand; an equestrian centre; 80 bed hotel; a golf course and clubhouse; a forest park centre comprising timber initiative centre, woodland wildlife centre, exhibition space, a demonstration eco-village, camping and woodland play area. A network of footpath, riding trails and cycle paths are proposed. A number of new roads are proposed including a link to J13 of the M60. Extensive landscaping, including ground remodelling, the creation of water bodies and woodland is also proposed. |  |
| Priorities and Milestones |  | Timescales |
| Highways Agency holding direction deadline. |  | 16/07/08 |
| Progress |  | Date |
| The Highways Agency has a holding direction in place until 16/07/08 following an extension in May. This directs that the Local Authority cannot grant planning permission before the Highways Agency is satisfied with the new highways proposals. The Highways Agency is currently considering new junction arrangements. SCC continues to consider the application. |  | Ongoing |
| Funding sources | Private Sector |  |

###### Programmes

## Programme: Housing Market Renewal Fund (HMRF)

| Area Covered | Central Salford |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer | Bob Osborne, Housing and Planning Directorate Cath Inchbold, Chief Executive Directorate |  |  |  |  |  |  |
| Summary | This programme is restructuring the housing market in Central Salford. There are four major intervention areas: the NDC area, Seedley & Langworthy, Higher and Lower Broughton. |  |  |  |  |  |  |
| Start Date | 02/10/03 |  |  | End Date |  |  | 2013 |
| Key Outputs |  |  |  | Target 08/09 |  |  | April 2008 – March 2009 |
| Homes constructed |  |  |  | 659 |  |  | 0 |
| Homes acquired |  |  |  | 159 |  |  | 0 |
| Homes refurbished |  |  |  | 660 |  |  | 0 |
| Households assisted with relocation |  |  |  | 47 |  |  | 0 |
| Milestones |  |  |  |  |  |  | Date |
| Impact of current market conditions on programme and associated risk management under review. |  |  |  |  |  |  | Ongoing |
| Progress |  |  |  |  |  |  | Date |
| Ministerial visit by Iain Wright MP hosted in Lower Broughton. |  |  |  |  |  |  | 12/06/08 |
| Appraisal for major investment areas, areas of stabilisation, private rented sector and delivery approved subject to conditions, by MSP Programmes and Scrutiny Sub Committee. |  |  |  |  |  |  | 12/06/08 |
| Detailed discussion on 2008/11 programme held at Strategy and Regeneration Scrutiny Sub Committee. |  |  |  |  |  |  | May 2008 |
| Manchester Salford Pathfinder (MSP) allocation for 2008/09 and indicative allocations of 2009/10 and 2010/11 announced. The allocation for Salford over the next three years is approximately £43.97 million (excluding secretariat costs). |  |  |  |  |  |  | 29/02/08 |
| HMR Business Plan approved. |  |  |  |  |  |  | February 2008 |
| Expenditure |  | Q1 | Q2 |  | Q3 | Q4 | Total Spend |
| Projected Spend 2008/09 |  | 1,816,000 | 4,033,000 |  | 4,236,000 | 7,221,000 | 17,306,000 |
| Actual Spend 2008/09 |  | 0 | 0 |  | 0 | 0 | 0 |
| Total Approved Spend 2008/2009 |  | 17,306,000 |  |  |  |  |  |

# Programme: New Deal for Communities (NDC)

| Area Covered | North Irwell Riverside |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer | Tim Field, NDC Chief Executive |  |  |  |  |  |  |  |
| Summary | This programme concentrates on delivering improvements in the following areas: building communities, crime and community safety, education, children and young people, physical environment, health, business, employment and skills. |  |  |  |  |  |  |  |
| Start Date | April 2001 |  |  | End Date |  | March 2011 |  |  |
| Programme Projects |  |  |  |  |  |  |  |  |
| - Housing redevelopment in riverside locations and at former Kersal High School site - Remodelling and renewal of existing housing public and private estates. - Salford Innovation Park hub - Supporting Schools - GEARS+ (Automotive project with Young People) - Burglary Reduction - Community Health Action Partnership - Alleygating - Public realm improvements - Pendleton Gateway - CRASY sports development - Targeted policing - Business Support (special grants for expansion) - Shop Parade improvements - Summer Fun - Skills and Work Centre (formerly Job Shop) - Young people’s filming projects |  |  |  |  |  |  |  |  |
| Key achievements (April 2001 - April 2008) |  |  |  |  |  |  |  |  |
| - The improvement of 438 private dwellings and 259 public sector houses, with a further 479 private dwellings and 73 further public sector dwellings currently being improved. - A new £1.5 million Beacon Youth Centre. - A new £4.5 million Sports Village complex developed in partnership with Salford City Council, Manchester FA and Sport England. - 20 grants to business in 2007-08. - Over 600 people supported into employment. - Three new Healthy Living Centres opened including one dedicated to mental health support projects. - The NDC ‘In Bloom’ group achieved 4 small-area awards and also recognition in the North West Urban Regeneration category in 2007. - 79 alleygates have been erected, benefiting over 1,000 homes in the area, and support has been given for the formation of 12 new residents groups as a result. - Supporting over 2,262 children from disadvantaged backgrounds into play, sports and community activity. - 149 community grants given out to community and voluntary sector groups. - The appointment of 2 new NDC area dedicated Police Community Support Officers. - The establishment of a domestic violence project with Relate. - The establishment of the NDC office at Cromwell House as a hate crime reporting centre. - 426 young people accessing specific advice on drugs and alcohol. - A local young person’s group formed and supported. Group short-listed for the RENEW North West awards in 2006. The young people have now formed their own Management Committee. - The NDC Supporting Schools project has contributed to excellent GCSE results for Albion High School pupils in 2007 – 55% achieving A-C grades compared to just 22% in 2005. Very few pupils are leaving without qualifications. - Albion High School has done well compared to other similar schools on Key Stages 2-4, with a score of 1012 against a target of 1,000 which puts it in the top 25% nationally, compared to the 2006 score of 984.6 against a target of 1,000 which was in the lowest 20-30% nationally. - New Neighbourhood Park created and three new community gardens created with residents groups. - Six new community enterprises developed and supported. - Support for the development of a new £9 million Innovation Forum in Partnership with Salford City Council, Northwest Regional Development Agency and European Union. - Salford Mini Soccer Festivals held in 2006, 2007 and 2008. - Green Streets Initiative launched. - There are approximately 70 young volunteers aged 13-15 between the two high schools, 20 have already completed 25 hours of volunteering. - NDC developer partner Miller Homes won the Regeneration Award, at the prestigious North West Business Insider Property Awards, for its Unity Quarter development in Lower Kersal. |  |  |  |  |  |  |  |  |
| Website |  | www.chalk-ndc.info |  |  |  |  |  |  |
| Expenditure (07/08) |  | Q1 | Q2 |  | Q3 |  | Q4 | Total Spend |
| Projected Spend 2007/08 |  | 1,445,428 | 1,153,482 |  | 1,417,982 |  | 2,365,460 | 6,382,352 |
| Actual Spend 2007/08 |  | 884,676 | 985,125 |  | 1,016,312 |  | 3,646,274 | 6,532,387 |
| Total Approved Spend 07/08 |  | 6,382,352 * |  |  |  |  |  |  |

* Following discussion, the final allocation for 2007-08 was confirmed by DCLG as being £6,382,352. Following work with Salford City Council across match funded programmes to maximise charges to NDC grant funding within the approvals and grant regulations, this allocation was met with a small revenue overspend which had been the subject of in principle approval from DCLG.

| Expenditure (08/09) | Q1 | Q2 | Q3 | Q4 | Total Spend |
| --- | --- | --- | --- | --- | --- |
| Projected Spend 2008/09 | 923,339 | 1,381,720 | 1,553,295 | 2,881,646 | 6,740,000 |
| Actual Spend 2008/09 | 0 | 0 | 0 | 0 | 0 |
| Total Approved Spend 08/09 | £6,740,000 |  |  |  |  |

Programme: North West European Objective 2 Programme Priority 2

‘Manchester Salford Sustaining Neighbourhoods Initiative’

| Area Covered | Central Salford wards |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer | Dee Carroll, Chief Executive Directorate |  |  |  |  |  |  |
| Summary | The Programme supports the process of transformation in a limited number of Priority 2 wards surrounding the regional centre. The action plan utilises European Regional Development Fund adding value to Housing Market Renewal to create sustainable neighbourhoods through: - targeted streetscape and environmental enhancements - alleyway treatments and alley-gating - associated neighbourhood planning and ward co-ordination. |  |  |  |  |  |  |
| Start Date | October 2004 |  |  | End Date |  |  | December 2008 |
| Key Outputs |  |  |  |  |  |  | April-January 2007 * |
| Community safety initiatives. |  |  |  |  |  |  | 1 |
| Community organisations provided with capacity support. |  |  |  |  |  |  | 7 |
| Environmental initiatives. |  |  |  |  |  |  | 0 |
| Expenditure |  | Q1 | Q2 |  | Q3 | Q4 | Total Spend |
| Projected Spend 2007/2008 |  | 95,989 | 105,227 |  | 91,929 | 169,392 | 462,537 |
| Actual Spend 2007/2008 |  | 95,989 | 105,227 |  | 91,929 | 129,749 | 422,894 |
| Total approved spend January 2000 to December 2008 |  | 2,484,013 |  |  |  |  |  |
| Expenditure |  | Q1 | Q2 |  | Q3 | Q4 | Total Spend |
| Projected Spend 2008/2009 |  | £107,208** | Programme completed |  |  |  | £107,208 |
| Actual Spend 2008/2009 |  |  |  |  |  |  |  |
| Total approved spend January 2000 to December 2008 |  | 2,484,013 |  |  |  |  |  |

* Key outputs to be updated at end of Q1 2008/09.

** Carried forward from 2007/08 and claimed in Q1 2008/09.

Programme: North West Objective 2 Programme –

Priority 3 ‘Irwell Corridor Economic Development Zones’

| Area Covered | Ordsall/ Broughton |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer | Dee Carroll, Chief Executive Directorate |  |  |  |  |  |  |
| Summary | To develop employment sites and realise the economic potential of natural, built, cultural or industrial heritage assets to create significant number of jobs, that are accessible to residents from ‘communities in need’. This will be delivered through 3 themes: - Developing Strategic Employment Opportunities. - Maximising the economic potential of the Region’s Natural, Cultural Assets. - Connecting with communities in need. |  |  |  |  |  |  |
| Start Date | January 2000 |  |  | End Date |  |  | December 2008 |
| Actions |  |  |  |  |  |  | Date |
| Work on Manchester, Bury and Bolton Canal nearing completion. Installation of pumps and phase 1 finishing off to be completed summer 2008. Financial completion of phase 1 by end of June 2008, although commissioning may extend into summer period. |  |  |  |  |  |  | June 2008 |
| Phase 1 Salford Central Station improvements completed. |  |  |  |  |  |  | December 2007 |
| Expenditure |  | Q1 | Q2 |  | Q3 | Q4 | Total Spend |
| Projected Spend 2007/08 |  | 1,049,145 | 1,455,265 |  | 3,127,191 | 2,379,476 | 8,011,077 |
| Actual Spend 2007/08 |  | 1,049,145 | 1,455,265 |  | 3,339,988 | 1,641,251 | 7,485,649 |
| Total approved spend January 2000 to December 2008 |  | 8,011,077 |  |  |  |  |  |

# Programme: Salford’s Health Investment for Tomorrow (SHIFT)

| Area Covered |  | Salford community and hospital NHS services |  |  |
| --- | --- | --- | --- | --- |
| Lead Officers |  | Alan Westwood, Community, Health and Social Care Directorate Janet Roberts, Salford PCT |  |  |
| Summary |  | Service Change Management & Delivery: Redesign of health services to provide integrated primary, hospital and, when appropriate, social care services, provided in the most suitable location: hospital, in the community or at home. Four project areas are: Unscheduled Care; Diagnostics and Planned Care; Long Term Conditions; and Children’s Services. Start date: 2006 End date: End of 2008 Hospital Redevelopment (Salford Royal NHS Foundation Trust/SRFT): Redevelopment of Hope Hospital site valued at £135 million PFI contract and a further £55 million modernisation investment. This initiative replaces the old Victorian ward blocks on the hospital site, which are no longer compatible with contemporary healthcare. Also included in the scheme are the demolition of the tower blocks on Eccles Old Road, the creation of a multi-storey car park and a separate education and research block. Start date: 2007 End date: 2012 Information Management and Technology: This is the local deployment of the NHS National Programme for IT / NHS Connecting for Health in Salford. This project includes a range of initiatives, from electronic prescription transfers, new patient record systems, technology to support Choose and Book, integration of healthcare records across primary and secondary care, etc. Workforce and Education: Focused on developing an integrated NHS workforce in Salford, which ensures effective collaboration across healthcare sectors. Also seeking to encourage and increase local employment in healthcare. LIFT Developments: Please see next section. |  |  |
| Start Date |  | April 2001 | End Date | 2012 |
| Priorities and Milestones |  |  |  | Timescales |
| Handover and completion of SRFT site. |  |  |  | December 2011 |
| Handover and completion of SRFT Education Block. |  |  |  | March 2009 |
| Roll-out of use of electronic prescriptions technology. |  |  |  | December 2008 |
| Progress |  |  |  | Date |
| Work underway on Eccles Old Road and Stott Lane road improvements. |  |  |  | April 2008 |
| SRFT Hospital Redevelopment - Financial close and start of construction. |  |  |  | September 2007 |
| Funding sources | Salford PCT and other commissioners / NHS |  |  |  |

# Programme: Local Improvement Finance Trust (LIFT)

| Area Covered | Citywide |  |
| --- | --- | --- |
| Lead Officer | Alan Westwood, Customer and Support Services Directorate |  |
| Summary | This is a building initiative to improve the quality of the primary healthcare facilities and establish a new range of services. Salford's LIFT (Local Improvement Finance Trust) centres will bring public services together under one roof, working together to improve the health and wellbeing of the people of Salford. Whilst the services available in each LIFT centre will differ slightly, in general the centres are a partnership between health (Salford Primary Care NHS Trust, Salford Royal Hospitals NHS Trust) and Salford City Council. |  |
| Priorities and Milestones |  | Timescales |
| Pendleton £16.2m Gateway Centre completion www.shiftprogramme.co.uk/lift/pendleton.htm |  | January 2009 |
| Walkden £9.1m Gateway Centre completion www.shiftprogramme.co.uk/lift/walkden.htm |  | September 2008 |
| Eccles £10.7m Gateway Centre completion www.shiftprogramme.co.uk/lift/eccles.htm |  | November 2008 |
| Completion of LiftCo’s proposed Swinton LIFT scheme. |  | Summer 2008 |
| Progress |  | Date |
| Eccles Gateway Centre topping out ceremony. |  | January 2008 |
| Commissioning of services and equipment/ technology/ facilities management to support service delivery. |  | Ongoing |
| PCT assessing options for phase 2. |  | Ongoing |
| Lower Kersal Gateway Centre complete. http://www.shiftprogramme.co.uk/lift/lowerkersal.htm |  | November 2006 |
| Charlestown Gateway Centre completed. http://www.shiftprogramme.co.uk/lift/charlestown.htm |  | October 2005 |
| Funding sources | PCT/ NHS - Capital investment to date is £36million. Revenue costs come to £1.18million. |  |
| Publicity to date | SHIFT website updates www.shiftprogramme.co.uk New publicity materials for Gateway Centres due to open later this year |  |

Programme: Building Schools for the Future (BSF)

| Area Covered | City Wide |  |  |  |
| --- | --- | --- | --- | --- |
| Lead Officer | Stephen Bradbury, Children’s Services Directorate |  |  |  |
| Start Date | January 2006 | End Date | 2012 |  |
| Summary | The BSF vision is to create buildings for the 21st century with choice and a greater range of services at each secondary school. Supporting the vision is an investment of over £150 million from Government's BSF programme. The timescales indicated below are drawn from the Outline Business Case and are subject to review once the procurement process is underway. |  |  |  |
| Milestones |  |  |  | Proposed timescales |
| Proposed Academy in Salford Quays completed (Phase 1B). |  |  |  | September 2011 |
| Proposed Irlam and Cadishead Community High School refurbishment completed (Phase 1A). |  |  |  | September 2011 |
| Proposed new build Walkden High School completed (Phase 1A). |  |  |  | September 2011 |
| The preferred bidder will enter into a Local Education Partnership with Wigan MBC and Salford City Council. |  |  |  | May 2009 |
| Select Preferred Bidder. |  |  |  | December 2008 |
| Opening of the Academy within the existing Hope High School building. |  |  |  | September 2008 |
| Designs for phase 1a schools to be presented by the two short listed bidders. |  |  |  | Summer 2008 |
| Cabinet report to consider the outcome of the Roman Catholic school consultation exercise and further development proposals. |  |  |  | By end June 2008 |
| Actions |  |  |  | Date |
| The following proposals/timescales are under review: Roman Catholic School proposals, proposed refurbishment of St Ambrose RC, Proposed St Patrick’s RC refurbishment. Proposed new school in Swinton to replace Moorside and Swinton, proposed new Wentworth High and the proposed new school in Central Salford to replace All Hallows. |  |  |  | On going |
| Two bidders have been short listed to design, build and refurbish selected high schools across Salford and Wigan. |  |  |  | January 2008 |
| Funding sources | BSF – over £150 million |  |  |  |
| Publicity to date | Consultation sessions held across the city Dedicated pages have been set up on Salford City Council web site |  |  |  |

Programme: Primary school developments

| Area Covered | City wide |  |
| --- | --- | --- |
| Lead Officer | Irene Heald, Children’s Services Directorate |  |
| Summary | The following primary school developments will create school buildings for the 21st century. The developments include the proposals for: - A new primary school on the Wheatersfield site - Replacing Christ Church CE and Lewis Street primary school - A new community primary school on the Glendinning Street site - A new Roman Catholic primary school for the present site of the Langworthy Road primary school (This is to be built on the playing fields of Langworthy Road primary school, following the clearance of land for the new community primary school on Glendinning site) |  |
| Milestones |  | Proposed timescales |
| Wheatersfield site (East Salford) |  |  |
| New school to open. |  | September 2010 |
| Proposed new school given approval by the Schools’ Adjudicator. |  | 28/02/08 |
| Eccles |  |  |
| The council is considering the feasibility of replacing Christ Church CE and Lewis Street primary schools with one new school. |  | Ongoing |
| Glendinning site (Ordsall and Langworthy) |  |  |
| New school to open. |  | September 2010 |
| Salford City Council served Compulsory Purchase Orders for seven properties. The period for objections ended on 23/05/08. The council has been advised verbally that there have been no objections to the CPO. Discussions are now taking place between DCSF and the council to determine the best route to obtain early confirmation of the CPO. |  | May 2008 |
| Present site of Langworthy Road School (Ordsall and Langworthy) |  |  |
| New school to open. |  | September 2010 |
| Funding sources | Salford City Council DCSF capital grant |  |
| Publicity to date | Consultation taken place as part of statutory process Future publicity plans under development |  |

Programme: Irwell City Park (ICP) Living Landmarks Lottery Bid

| Area Covered | Ordsall / Irwell Riverside |  |
| --- | --- | --- |
| Lead Officers | Kevin Brady, Assistant Chief Executive, SCC Cath Inchbold, Chief Executive Directorate Elaine Davis, Central Salford URC |  |
| Summary | Restore the River Irwell as an important urban waterway and create an exciting city park at the heart of the regional centre. |  |
| Priorities and Milestones |  | Timescales |
| Pre-Implementation package of works to commence |  | October 2008 |
| Project approval anticipated. |  | October 2008 |
| Full NWDA application to be submitted. |  | June 2008 |
| Progress |  | Date |
| Economic appraisal, revised business case and NWDA application/s to be produced by project and consultant Team. |  | April- June 2008 |
| NWDA concept application - pre-implementation works – submitted. |  | 15/04/08 |
| Salford City Council has approved a policy to dedicate 50% of Section 106 monies within the park boundary to deliver the scheme. |  | March 2008 |
| ICP planning guidance approved by Trafford Metropolitan Borough Council, Manchester City Council and Salford City Council. |  | March 2008 |
| Following Big Lottery decision, the Project Board has confirmed all partners' commitment to delivering ICP. |  | December 2007 |
| Funding sources | £1.44 m being sought from NWDA to support pre-implementation works 2008/09 - 2009/10 |  |
| Publicity to date | ICP website Series of summer exhibitions A feedback document for local residents distributed Articles in MEN and Advertiser (July/ August/ September/ October 2007) |  |

Programme - Salford West Strategic Regeneration Framework and Action Plan

| Area Covered | Covers 13 wards (Cadishead, Irlam, Winton, Barton, Eccles, Boothstown & Ellenbrook, Worsley, Swinton North, Swinton South, Pendlebury, Walkden North, Walkden South, Little Hulton). |  |
| --- | --- | --- |
| Lead Officer | Bob Osborne, Housing & Planning Directorate Maura Carey, Chief Executive Directorate |  |
| Summary | Develop Strategic Regeneration Framework and Action Plan that will drive investment and regeneration across the area for the next 20 years. |  |
| Priorities and Milestones |  | Timescales |
| Business event. |  | October 2008 |
| Salford West Board meeting. |  | 21/07/08 |
| Agree Task Group action plans. |  | July 2008 |
| Progress |  | Date |
| Liverpool Road Corridor, town centres and tourism product development task groups initiated. |  | May 2008 |
| Project and programme management arrangements finalised. |  | April 2008 |
| First Salford West Board meeting. |  | 15/04/08 |
| Salford West business dinner. |  | 19/03/08 |
| Funding sources | City council capital programme and grant allocations. Private sector. |  |
| Publicity to date | Dedicated pages have been set up on the council's web site Coverage in Community Committee newsletters and meetings Mail outs and distribution of marketing materials Public events and consultation |  |

Programme – Transport Innovation Fund (TIF) bid

| Area Covered | Greater Manchester |  |
| --- | --- | --- |
| Contact Officer | Darren Findley, Strategic Transportation Manager |  |
| Summary | The bid is for £1.25 billion of Government funding, towards a full package amounting to just under £3 billion. The remaining £1.75 billion of funding would be borrowed, and then repaid through funding raised via a congestion charge, to be applied during the am & pm peak periods. The bid comprises a range of schemes & initiatives throughout the GM area. The main schemes for Salford are: - Leigh, Salford, Manchester Quality Bus Corridor; - Route 8 QBC along A666; - Rail capacity improvements; - A fleet of yellow school buses for the GM area; - Extension of Metrolink to the airport, Oldham & Rochdale; - £26m towards local cycling & pedestrian route improvements. |  |
| Priorities and Milestones |  | Timescales |
| A 12 week consultation period is under development. |  | Ongoing |
| Progress |  | Date |
| Decision from Department for Transport (DfT) to grant "Programme Entry" status. |  | 09/06/08 |
| TIF bid jointly submitted to the DfT by the AGMA authorities and the Greater Manchester Passenger Transport Authority (GMPTA). |  | July 2007 |
| Funding sources | DfT – to be confirmed |  |
| Publicity to date | Press releases. |  |

Programme - Parks for People

| Area Covered | City wide |  |
| --- | --- | --- |
| Lead Officer | Alan Rowley, Environment Directorate |  |
| Summary | To make public parks more inviting and welcoming by improving facilities and park environment, masterplans have been developed for six key parks across the city. Parks include: Eccles Recreation Ground, Peel Park, Ordsall Park, Mandley Park, Cadishead Park and Albert Park. District Park status will be sought for all six parks. |  |
| Priorities and Milestones |  | Timescales |
| Cadishead Park – completion of all works (yet to be determined). |  | Summer 2009 |
| Peel Park, Little Hulton - achieve district standard, including access and security improvements; development of new communal building; new putting green; rejuvenate bowling green and create summer events area. |  | March 2009 |
| Peel Park, Little Hulton - New greens and events area completed. |  | March 2009 |
| Peel Park - New community building completed. |  | Autumn 2008 |
| Submit bid to the Heritage Lottery Fund for restoration of Buile Hill Park. |  | September 2008 |
| Cadishead Park - Detailed scheme produced. |  | Summer 2008 |
| Cadishead Park – achieve the district standard, including a refurbished playground. |  | July 2008 |
| Consultation on draft revised masterplan for Buile Hill Park with Community Committees. |  | July 2008 |
| Progress |  | Date |
| Buile Hill Park- Developing bid for Heritage Lottery. Stakeholder workshops held. |  | May 2008 |
| Access and security improvements to Peel Park completed. |  | March 2008 |
| Car park and playground improvements completed at Clifton Country Park. |  | March 2008 |
| Publicity to date | www.salford.gov.uk/parksforpeople |  |

###### Developing strategies

| Strategy | Lead Officer(s) | Summary | Progress | Milestones | Adoption Date |
| --- | --- | --- | --- | --- | --- |
| Sustainable Community Strategy | Sheila Murtagh, Chief Executive Directorate | The Sustainable Community Strategy (SCS) will replace the Community Plan 2006-2016. The second generation Local Area Agreement (LAA2) will act as the main delivery plan for the SCS. | Currently developing our Sustainable Community Strategy using the current Community Plan and the Salford Agreement as the foundation. We also need to ensure that we are incorporating the issues identified in recent government guidance. New LAA2 priorities were agreed at the joint Cabinet/Executive meeting on 26/02/08. Set of measures finalised at a Partnership Executive meeting on 26/03/08. Discussions are ongoing with Government Office North West to finalise targets. | The current timescales around the Sustainable Community Strategy are being extended to ensure strategic alignment and support for the place shaping agenda and to allow for wider consultation. An updated timeframe is being developed. | TBC |
| Strategic Economic Development Plan (SEDP) and Employment Land Review (ELR) | Bernie Vaudrey, Chief Executive Directorate Emily Kynes, Chief Executive Directorate Chris Marsh, Central Salford URC | The Employment Land Review (ELR) is a key piece of work for the city; it will feed into and influence the production of the Local Development Framework documents (Core Strategy) as well as informing future economic development activity. A Strategic Economic Development Plan (SEDP) for Salford will replace the Economic Development Strategy. Given the linkages between the two areas of work; the ELR and the SEDP have been commissioned in partnership by Salford City Council and the URC. | ELR: Detailed site appraisals ongoing. SEDP: Overall completion of the SEDP is timetabled for July 2008. | Final SEDP incorporating ELR scheduled for July 2008. | July/August 2008 |
| Core Strategy | David Percival, Housing and Planning Directorate. | The Core Strategy will provide the strategic planning framework for Salford, and all other planning documents that the city council produces will need to be consistent with it. The Core Strategy will need to consider the full range of issues affecting the city, and will need to identify: - The various roles of the city and its constituent neighbourhoods, and how these should evolve over the next 20 years, including the relationship with surrounding areas. - The overall scale of development that needs to be planned for within the city over the next 20 years, and how this should be distributed. - How the city's environmental and heritage assets will be protected and enhanced. - How contributions to climate change will be minimised, and the effects of that change adapted to. - The strategic development control policies that will be used in determining planning applications. The implications of other plans and strategies on the development and use of land in the city. | Issues and Options report is being developed. | Issues and Options Report (October/ December 2008). | September 2011 |
|  |  |  |  | Preferred Options Report (The Government is proposing to delete this stage in the process) |  |
|  |  |  |  | Full Draft Core Strategy and consultation (January/February 2010) |  |
|  |  |  |  | Public examination (December 2010/January 2011) |  |
| Primary Strategy for Change | Irene Heald Children’s Services Directorate | - To consider the needs of all primary schools, including: all types (e.g., community, voluntary controlled, voluntary aided, primary age special schools in the authority’s boundaries) and pupil referral units covering primary age pupils. This 13 year investment programme should: - Rebuild, remodel or refurbish at least 50% of our primary education provision; - Support national policy agenda: Children’s Plan, world class standards, ECM, diversity and responsiveness, extended services, and personalisation; - Targeted to address deprivation nationally and in every local authority; - Provide primary schools at the heart of the community, with ICT and children’s services in reach of every family; - Improve links between schools and early years settings; and - Deliver facilities equipped to provide 21st century learning. | Issues and option appraisal report is being developed. A Project Team which meets fortnightly has been established. Primary Capital Programme Strategy Co-ordinator in place. Consultants appointed to help deliver the Primary Strategy for Change by the deadline date of the 16/06/08. Consultations with all stakeholders including schools and the dioceses have commenced. ‘Wicked Issues’ to various Cabinet Briefing sessions before May 2008. Full Strategy to Cabinet May 2008. Submission of Strategy to the Department for Children, Schools and Families on 16/06/08. | Funding confirmed in September 2008, subject to a robust ‘Primary Strategy For Change’. Draw down of funds as from April 2009 to 2021. | June 2008 |
| Parenting Strategy | Jane Middleton, Children’s Services Directorate | To co-ordinate a diverse range of responses to parent and family need, in line with the Every Child Matters (ECM) and Respect Agendas. | Family Pathfinder bid has been approved (April 2008 to March 2011) up to £180K in 2008-2009; £300K in 2009-2010; £300K in 2010-2011. Parenting Strategy will link with and support the wider Family Support and Think Family Strategies. The strategy group is being restructured to involve more partners, and to meet monthly to overlook the development and implementation of the three strategies. Strategy presented to Corporate Management Team (CMT). | Strategy presented to Cabinet (July/ August 2008). Parenting Handbook will be printed for parents and professionals (end June 2008). Handbook will be distributed during launch day and local parenting events (July-Sept 2008). Contracts for four Parenting Support Workers extended to end Sept 2008. Funding for the four posts to be confirmed after June 2008. Stakeholder Forum made up of key partners established will meet quarterly after the strategy approved. Stakeholders will be invited to the launch day and local parenting events. (July-Sept 2008). | August 2008 |
| Children and Young People's Participation Strategy | Cath Connor, Children’s Services Directorate | This will assist agencies in incorporating participation into strategic planning and service delivery. Participation of children and young people across Salford will be monitored and evaluated on a regular basis to ensure that we constantly learn from good practice. The strategy will provide a practical guide to map, plan and most importantly monitor the outcomes of participation by children and young people. It is suggested that Salford adopts the ‘Hear By Right’ standards framework to help secure sustained and beneficial participation. | A draft implementation plan has been submitted for consideration by leadership team and Lead Member for Children’s Services. A cross-directorate working group has been established. | Contribute to NI 4 of Local Area Agreement. (NI 4 - % of people who feel they can influence local decision-making) | TBC |
| Salford City Council Housing Strategy | Sarah Clayton Housing and Planning Directorate | Salford strategic approach to future housing, encompassing Fit For Purpose criteria and Audit Commission recommendations. | A completed Strategy was considered at Cabinet briefing on the 26/03/08 and agreed as a draft. Some further amendments to be made following Audit Commission comments. | Final approval will be sought after Cabinet away day in June 2008. | July 2008 |
| Community Cohesion Strategy | Shaun Clydesdale Community, Health and Social Care Directorate | The strategy identifies how partners in the city can work together to make Salford a place where people from different backgrounds get on well together | Strategy was presented to Cabinet Briefing on 26/02/08 and agreed. Strategy was presented to SSP Executive 07/05/08 and agreed. | Strategy to be presented to Cabinet. | TBC |

###### Glossary

ABG		Area Based Grant

AGMA	Association of Greater Manchester Authorities

BLF		Big Lottery Fund

BSF		Building Schools for the Future

CCI		Centre for Construction Innovation

CESI		Centre for Economic and Social Inclusion

CLG		Department for Communities and Local Government

CSURC	Central Salford Urban Regeneration Company

CPO		Compulsory Purchase Order

CYPPB	Children and Young People’s Strategic Partnership Board

DCLG	Department for Communities and Local Government

DCSF	Department for Children Schools and Families

DfT		Department for Transport

DPD		Development Plan Document

ECf		English Cities Fund

ECM		Every Child Matters

ELR		Employment Land Review

ERDF	European Regional Development Fund

GMPTA	Greater Manchester Passenger Transport Authority

GMPTE	Greater Manchester Passenger Transport Executive

GMWDA	Greater Manchester Waste Disposal Authority

GONW	Government Office North West

HLF		Heritage Lottery Fund

HMCS	Her Majesty’s Courts Service

HMRF	Housing Market Renewal Fund

ICP		Irwell City Park

LAA		Local Area Agreement

LDF		Local Development Framework

LIFT		Local Investment Finance Trust

LIVIA	Lower Irwell Valley Improvement Area

LRC		Liverpool Road Corridor

LTP		Local Transport Plan

MBBC	Manchester, Bury and Bolton Canal

MBC		Metropolitan Borough Council

MCIN	Manchester Community Information Network

MEN		Manchester Evening News

MKC		Manchester Knowledge Capital

MSP		Manchester Salford Partnership

NDC		New Deal for Communities

NEET	Not in Education, Employment or Training

NRF		Neighbourhood Renewal Fund

NWDA	Northwest Regional Development Agency

OBC		Outline Business Case

OJEU	Official Journal of the European Union

PCP		Primary Capital Programme

PCT		Primary Care Trust

PFI 		Private Finance Initiative

PQQ		Pre Qualification Questionnaire

RSL		Registered Social Landlord

SCS		Sustainable Community Strategy

SEDP	Strategic Economic Development Plan

SHIFT	Salford Health Investment for Tomorrow

SIF		Salford Innovation Forum

SSP		Salford Strategic Partnership

TIF		Transport Innovation Fund