|  | PART I (OPEN TO THE PUBLIC) | ITEM NO. 4 |
| --- | --- | --- |

| REPORT of the Chief Executive |
| --- |
| TO Regeneration Initiatives Cabinet Working Group ON Monday 19 February 2007 |
| TITLE : Single Regeneration Budget Round 5 (SRB5) Integrating and Sustaining Communities – Final Evaluation Report |
| RECOMMENDATIONS : That consideration be given to the report and the Summary Evaluation. |
| EXECUTIVE SUMMARY : Quaternion Research and Consulting were appointed in February 2005 to undertake a final evaluation of the SRB5 Integrating and Sustaining Communities Programme and to work with individual SRB projects to assist them in developing their forward strategies. Quaternion has now completed the evaluation of the programme. The evaluation report includes an analysis of spend, outputs, outcomes, learning and good practice for each of the 3 themes and for the programme as a whole. It includes the views of stakeholders, beneficiaries and local residents. Spend targets have been met, the majority of output targets have been met and in many cases exceeded. The overall impact of the programme has been viewed positively by stakeholders. A stakeholder workshop has been arranged on the afternoon of 19 February to discuss the findings of the evaluation. |
| BACKGROUND DOCUMENTS (available for public inspection): Integrating and Sustaining Communities : Salford’s bid to round 5 of the Government’s Single Regeneration Budget |
| ASSESSMENT OF RISK : Not Applicable |
| SOURCES OF FUNDING : SRB5, Housing Market Renewal Fund, Single Capital Pot, other public and private funding |
| COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative) Not applicable |
| 1. LEGAL IMPLICATIONS | Provided by : | Not Applicable |
| 2. FINANCIAL IMPLICATIONS | Provided by : | Not Applicable |
| PROPERTY (if applicable): Not Applicable |
| HUMAN RESOURCES (if applicable): Not Applicable |
| CONTACT OFFICER : Sue Ford, Group Leader, Regeneration Strategy and Co-ordination – 793 3443 |
| WARD(S) TO WHICH REPORT RELATE(S) : City wide |
| KEY COUNCIL POLICIES : Making the Vision Real; Salford’s Community Plan 2006-16, Regenerating a Great City – Salford’s Neighbourhood Renewal Strategy, Salford‘s Housing Strategy |
| DETAILS |

- Purpose of Report

In 1999 Salford City Council were successful in obtaining £25 million SRB5 funding to carryout the seven year programme of regeneration activities which were set out in the SRB5 Sustaining and Integrating Communities Plan.  As part of the conditions for receiving this money, through the North West Development Agency, an end of scheme evaluation had to be carried out. The programme came to an end in March 2006.

Following a tendering process, Quaternion Research and Consulting were appointed in February 2005. They worked with the SRB5 Team until the end of the programme to undertake a final evaluation of the SRB5 Integrating and Sustaining Communities Programme and with individual SRB projects to assist them in developing their forward strategies.

- Final Report

Quaternion has now completed the evaluation of the programme.

As members are aware the SRB5 programme covered:

- The comprehensive regeneration of Seedley and Langworthy.

And two city-wide themes for:

- Economic Development

- Social Inclusion

The Evaluation Summary report is attached for information. The report includes an analysis of spend, outputs, outcomes and learning for each of the 3 themes and for the programme as a whole. It also includes a summary of the views of stakeholders, beneficiaries and local residents.

Overall the programme has performed well, meeting it’s spend target, drawing in additional match funding, achieving the majority of outcomes and in many areas exceeding output targets.

- Spending Targets

Actual SRB spend for the programme totalled £24,984,000 against a planned spend at the outset of the programme of £25,000,000 – a 99.9% spend. This funding drew in £61million in match funding compared to a planned figure of £53 million – a leverage rate of 2.46. A more detailed breakdown is given below:

Spending Achievements – Lifetime Programme

| Source | Final Spend £ | Planned Spend £ | % achieve |
| --- | --- | --- | --- |
| ESF | 1,726,000 | 300,000 | 575% |
| SRB - Cap | 11,987,000 | 12,000,000 | 100% |
| SRB - Rev | 12,997,000 | 13,000,000 | 100% |
| SRB - Tot | 24,984,000 | 25,000,000 | 100% |
| Other Public | 18,031,000 | 10,443,000 | 173% |
| Private | 10,637,756 | 34,000,000 | 31% |
| New Deal | 563,000 | 0 |  |
| Voluntary | 1,681,000 | 180,000 | 934% |
| City Council | 10,538,000 | 4,000,000 | 263% |
| ERDF | 7,046,500 | 2,700,000 | 261% |
| NWDA | 1,804,000 | 1,640,000 | 110% |
| HMRF | 9,337,000 | 0 |  |
| Total | 86,348,256 | 78,263,000 | 110% |

- Output Targets

Outputs were also exceeded in a number of areas including jobs created and people accessing employment. The main area where outputs were not achieved was in the number of new dwellings completed and empty dwellings brought back into use. These outputs are attributable to the Seedley and Langworthy programme where the physical programme has taken longer than anticipated to deliver. The physical regeneration of Seedley and Langworthy is continuing with funding provided by HMRF, English Partnerships and the City Council. We are therefore continuing to monitor the physical outputs in the area beyond the life of SRB5 through the Housing Market Renewal (HMR) programme.

Key Output Targets

| Planned Key Output Targets | Actual Lifetime Outputs |
| --- | --- |
| 1,000 new jobs created | 2,018 |
| 300 pupils benefiting from projects to improve attainment | 9,416 |
| 1,200 people trained obtaining qualifications | 5,721 |
| 1,000 young people benefiting from personal and social development | 22,286 |
| 1,000 from disadvantaged groups obtaining a job | 3,356 |
| 5,000 given access to new community/health facilities | 9,286 |
| 5,000 people given access to new community/cultural facilities | 20,647 |
| 50 voluntary organisations supported | 726 |
| 50 community groups supported | 1,854 |
| 400 private sector dwellings completed | 0 (370) |
| 675 private sector dwellings improved | 636 |
| 300 dwellings included in new management arrangements | 200 |
| 350 empty dwellings brought back into use | 129 (529) |
| 100 new business start ups in the city | 938 |
| 100 new businesses established | 259 |
| 500 businesses advised | 9145 |
| 7,000 benefiting from community safety initiatives | 20,960 |
| 575 dwellings where security is upgraded | 2,328 |
| 25 new community safety initiatives | 362 |
| 8 youth crime prevention initiatives with 1,000 young people attending | 1,324 |

Figure in brackets indicate the position once the current build activity on site in Seedley and Langworthy is completed.

- Programme Outcomes

Key outcomes for the programme were exceeded in all areas except permanent exclusions. This outcome was set at the beginning of the programme and was not an area that the SRB programme partnerships chose to focus on during its lifetime.

- Stakeholders Views

Seedley and Langworthy Residents

During the evaluation local people’s views were gathered to assess the impact of the programme. This was done in two ways – through a questionnaire managed by the Seedley and Langworthy Trust (SALT) and through a series of focus groups held across the area.

Feedback from this has demonstrated the positive impact that the programme has made. This included improvements to the physical environment but also to improvements in community well-being, reductions in crime, improved access to training and employment and the increased involvement of local people in improving their area. However, it has also confirmed areas where improvement can be made to the process of regeneration, for example in the area of community consultation.

Other Stakeholders

There have been a wide range of other stakeholders involved in the development, implementation and management of the SRB5 programme. The Seedley and Langworthy Board, Economic Development Forum, Social Inclusion Forum and SRB5 Executive, all multi-agency groups, have had responsibility for overseeing the delivery of the programme. Many public, voluntary and community organisations have been responsible for developing and implementing projects.

It was important that stakeholder views on the programme were also incorporated into the evaluation process. Various workshops and individual interviews were held in order to capture their views.

Feedback here confirmed the positive impact of the programme in Seedley and Langworthy and in other areas of the city-wide programmes.

- Learning

There were several key learning points which the evaluation raised which were particular to the process of regeneration and programme development. These are summarised as follows:

Overall

- Networking and sharing good practice is essential in attaining a more co-ordinated programme.

- Strong partnerships are vital – working as a team and taking responsibility for issues, whilst recognising individual partners organisational constraints.

- Partnerships need to concentrate on delivering the vision rather than micro-managing the programme.

- Early forward strategies based on accurate analysis are needed. Projects that developed early forward strategies generally had better developed succession strategies.

- Inviting bids can create an unco-ordinated programme. A move to commissioning ensured a more comprehensive approach.

Seedley and Langworthy

- The process of regeneration is a stressful life event for those it affects. Accurate, timely and open communication with residents is therefore important particularly communicating changes to plans after consultation on specific options has taken place. It is important to understand that it takes a long time to win the confidence of the community and resources need to be made available to achieve this.

- The amount of effort that members of the community put into the process should be recognised. People need to be enabled to participate effectively. Robust training is needed to support individuals to participate to provide the skills, knowledge and confidence they need to fulfil their roles, for example, as Board members.

- Softer outputs, for example, confidence building, improved communication skills, can lead to enhancement of hard outputs. For example In Bloom brought the alleyways to life following the installation of alleygates.

Economic Development

- The networking that resulted from the establishment of the Economic Development Forum was fundamental to the success of the Economic Development Programme.

- Realistic targets need to be set at the outset of a programme. A better analysis of sector trends will allow better targeting of activity for example training, maximising private sector investment in workforce training.

- The development of the third sector emerged as a priority during the programme and pointed to the need for a distinct service tailored to this sector in order to maximise its future potential.

Social Inclusion

- Different approaches and levels of support should be taken to the development of proposals depending on the organisations involved. For example more support needs to be given to developing community enterprise projects.

- Many projects felt that the appraisal process was too complicated and onerus for the level of funding required and that the programme should be more flexible to meet the changing needs of projects. Whilst there is a need for flexibility this has to be balanced with the requirement for projects to be accountable and for the programme to deliver its outputs/outcomes.  Establishing the needs of project managers and  programme managers at the outset and maintaining open communication will ensure this is overcome.

- Next Steps

A workshop event has been organised for 19 February 2007 at the Harold Riley Suite, Salford University. A wide range of stakeholders, including local residents in Seedley and Langworthy, have been invited to attend. This will include a series of short presentations on the evaluation and on the future direction of the 3 themes. Presentations will be followed by workshops at which attendees will be able to discuss the evaluation and put forward their views. A summary report of the conference will be produced and circulated to attendees.

The Final Evaluation Report will then be submitted to the North West Development Agency. It is intended that the learning and good practice identified in the evaluation be used to inform the development of future regeneration programmes in the City.