| Part one (open to the public) | Item 9 |
| --- | --- |

Report of the Chief Executive

To Regeneration Initiatives Cabinet Working Group On Monday 19 February 2007

Recommendation: 1. Members are asked to note progress to date. 2. Members are requested to consider the four strands of the Futures Report as a basis for stage two consultation.

Executive Summary: This report outlines progress in developing a Strategic Regeneration Framework and Action Plan for Salford West. This includes producing the baseline and issues report and a round of consultation looking at the role of the area. Members attention is drawn to the four key strands of the Futures Report and stage two consultation looking to shape the Action Plan.

Background Document: (Available for public inspection) Regenerating a Great City: Salford’s Neighbourhood Renewal Strategy

Assessment of Risk: Low

Source of Funding: NRF

Comments of the Strategic Director of Customer and Support Services (or their representative) Legal implications Provided by: n/a Financial implications Provided by: n/a Property: n/a Human Resources: n/a

Contact Officer: Cath Inchbold, Assistant Head of Service, Regeneration Strategy and Co-ordination, 0161 793 3796 Maura Carey, Group Leader, Regeneration Strategy and Co-ordination, 0161 793 2903

Ward(s) to which the report relate(s): All wards in Salford West: Little Hulton, Walkden North, Walkden South, Worsley, Boothstown & Ellenbrook, Pendlebury, Swinton North, Swinton South, Eccles, Winton, Barton, Irlam, Cadishead.

Key Council Policies: Salford Community Plan: 2006 – 2016 Regenerating a Great City: Salford’s Neighbourhood Renewal Strategy

DETAILS:

1.	Background

1.1	As you will be aware Salford City Council is mid-way through the process of developing a Strategic Regeneration Framework and Action Plan for Salford West.  This will complement the framework that exists in Central Salford and will drive investment in the west of the city.  It is a key document for the future of the area, linking opportunities for investment across a variety of sectors.

1.2	The Framework and Action Plan will identify, co-ordinate and prioritise opportunities 	for major development and investment.  It will target resources (where available) at 	pockets of deprivation.

2.	Progress to Date

2.1	A consultant team led by Building Design Partnership (BDP) began work in 	October.   The team includes specialists in transport, commercial property, 	economic development and planning.

2.2	SCC provided the consultant team with a wide range of background data.

2.3 	The consultant team held a series of interviews with key partners in October and 	November.  This included the Primary Care Trust, developers and MIDAS amongst 	others.

2.4 	Analysis of the baseline data and intelligence from the interviews was drawn 	together to form the draft baseline and issues report.  This was circulated in 	December and formed the basis of stage one consultations.

3.	Stage One Consultation

3.1	A series of consultation events were held in 	December to conclude the first part of the process.  Attendees were asked to look at the following issues;

- the future role of Salford West,

- the key strategic issues facing Salford West, and

- the key opportunities for the area.

3.2	Over 80 people attended the following  events;

7/12/06	Public Sector Workshop,

8/12/06	Private Sector Workshop,

11/12/06 	Councillors and Community Stakeholders Discussion,

13/12/06 	Councillors and Community Stakeholders Workshop.

3.3	In addition, information and questionnaires were circulated to Councillors who could 	not attend these events.  A section for comments and questions has also been 	posted on the Salford West pages in the Council's website.

4.	Results of Stage One Consultation

4.1	Each of the events generated in-depth discussion.  All participants were enthusiastic about the future of Salford West.  While the emphasis was different in each of the groups, common themes did emerge.  The executive summary of the results of stage one consultation is attached.

4.2 	The main roles for Salford West at a regional and local level, as highlighted by 	stakeholders, were for Salford West to be,

- a desirable place to live,

- a quality destination for leisure and tourism, and

- a source of future employment opportunities.

4.3	The key issues identified through discussions were;

- transport,

- town and neighbourhood centres,

- housing,

- employment opportunities and worklessness, and

- community safety.

4.4	The final report, with all the results of consultation will be posted on the Council's website in February.  An e-mail will be sent to all consultees advising them when the report has been posted.

5.	Futures Report

5.1	The Futures Report builds on the results of stage one consultation.  It translates the role for the area into a future vision with four key strands.  The Salford West Executive Board agreed the four key strands on the 23/01/07.  They are;

- a successful local economy,

- a network of high quality residential neighbourhoods,

- an outstanding leisure and recreation asset,

- a well connected component of the city region.

5.2 	This report will be the basis of the stage two consultation.  This consultation will move the process from vision to action, examining how we make the best of the opportunities offered the area in order to address the issues it faces.

6.	Next Steps

6.1 	This round of consultation will again involve Councillors, the private sector and 	public agencies.  It will also include the Regeneration Scrutiny Committee, the 	Youth Panel and neighbouring authorities.  We will also run a series of drop in 		sessions across the area, inviting local interested parties to call in and let us know 	how they think Salford West should be shaped into the future.

6.2	Members of RI CWG are invited to the following workshop.

Salford West Strategic Regeneration Framework and Action Plan

From Vision to Action

Wednesday 14 March, 5pm to 8pm

Fletcher Hall, Vicerage Road, Swinton

6.3 	The timetable for the development of the Salford West Strategic Regeneration 	Framework and Action Plan is as follows:

| DATE | ACTION |
| --- | --- |
| Jan / Feb 2007 | Draft the Futures Report |
| March 2007 | Consultation on the Futures Report |
| April 2007 | Draft Final Documents |
| May 2007 | Adopt Strategic Framework & Action Plan |
| May 2007 onwards | Implement the Action Plan |