# Report to the Swinton Community Committee

# 14th August  2007

Title:	Salford West Strategic Regeneration Framework and Action Plan; final consultation.

Background Documents (available for public inspection):

Regenerating a Great City:  Salford’s Neighbourhood Renewal Strategy

Central Salford Vision and Regeneration Framework

Contact Officers:

Maura Carey, Group Leader, Regeneration Strategy and Co-ordination, 0161 793 2903

Lynne Braid, Graduate Trainee, 0161 793 3444

Ward(s) to which the Report Relates:

All Salford West wards:  Little Hulton, Walkden North, Walkden South, Worsley, Boothstown & Ellenbrook, Pendlebury, Swinton North, Swinton South, Eccles, Winton, Barton, Irlam, Cadishead.

1.	Background

1.1	As you will be aware Salford City Council is in the process of developing a Strategic Regeneration Framework and Action Plan for Salford West.  It is a key document for the future of the area, linking  opportunities for investment across a variety of sectors.  The Framework and Action Plan will identify, co-ordinate and prioritise opportunities for major development and investment.

2.	Consultation to date

2.1 	Following a baseline analysis a series of consultation workshops with Councillors, statutory and private sectors was held in December 2006.  Stakeholders examined the key issues and opportunities in Salford West, as well as the future role of the area.  This resulted in a 20 year vision for that area being drafted.

2.2 	A further round of consultation in March 2007 included a second series of workshops as well as exhibitions across the area.  This was followed up in April by a number of Directorate meetings and a dinner for the private sector hosted by the Leader of the Council.  This resulted in a set of priorities being drafted for the area.

3	Final stage consultation – methods

3.1	The full draft framework will be available on the Council’s web pages for a minimum of six weeks during the summer.  This will include an on-line feedback form.

3.2 	A summary booklet will outline the draft framework in a more accessible format.  It will be accompanied by a questionnaire asking people for their views on the draft.    Both the booklet and questionnaire will be available electronically and in printed format.  The booklet will be distributed to public areas such as libraries, public buildings, community centres, leisure centres, dentists and doctors.  It will also be e-mailed and/or posted to a range of community groups across the areas.  In addition it will be sent to residents who have been involved in previous consultations and stated that they wished to stay involved.

3.3 	Community Committees will be consulted over the summer period.  Where possible this will be as a dedicated agenda item on existing Community Committee meetings.   A range of events and festivals will be taking place over the summer period.  Where possible there will be a Salford West stall at one event in each Community Committee area.

4.	Final stage consultation – timetable

  - Timetable

| Consultation method | Timing |
| --- | --- |
| Full document on the internet | From 09/07/07 to 28/08/07 |
| Summary booklet | From w/c 09/07/07 to 28/08/07 |
| Community Committee consultations | Summer 2007 |
| Attend 1 event in each area | Summer 2007 |

5. 	Adopting the framework

5.1	The summer consultation round will shape the final Salford West Strategic Regeneration Framework and Action Plan.  The revised document will be reported through the city council structures.  It is anticipated that it will be adopted by Salford City Council in late 2007.