## £0.5-£5.0 million
Partnered Projects £0.5 Million - £5 Million
PM | QS | [6 empty] | A | B | C | D | G (B-D) |  | b1
|  | Job No | Date of QS Report |  | Contract Name | Start on Site Date | Finish On Site Date | Contract Target Cost. (including KPI bonus) | Revised/ Predicted Contract Target Cost £(including KPI bonus) | Predicted Target Cost £ (including KPI bonus) | Forecast Final Actual Cost £ (including KPI bonus) | Actual Cost Variation £ | % Saving (Neg've is Over spend) | Contractor Bonus From Shared Saving (G) | KPI Bonus included in total | Total Cost to client (estimate in italics) D+b1 | Cot per property | Notes
Partner Cruden
PD | JR | H2677 H10021 H10022 |  | 1 | Arrowhead Block improvement Phase I-3 | 2005-01-24 | 23/09/05 eot 27/01/06 | 2142110 | 2375965 | 2375965 | 2104543 | 271422 | 11.4237 | 135711 | 37821 | 2240254 | 14352 | Instruction of additional works, 7 extra shops, external refurb. Closedown meeting held
PD | MB | H10056 |  | 2 | Littleton Road Block improvement Phase III&IV | 2005-05-23 | 17/03/2006-- eot 19/0506 | 1330406 | 1399854 | 1399754 | 1167805 | 232049 | 16.5767 | 116024.5 |  | 1283829.5 | 10528 | Addition of rear yard walls . Closedown meeting held
DT | SA | E2605 | 2006-12-15 | 3 | Westwood Park Primary School Extension | 2005-03-21 | 2005-12-23 | 1310491 | 1390670 | 1266847 | 1266847 | 123823 | 8.9038 | 61911.5 |  | 1328758.5
MH | MK | E10669 | 2007-01-16 | 4 | Surestart Fiddlers Lane | 2006-02-13 | 2006-09-04 | 517250 | 546427 | 546427 | 522197 | 24230 | 4.4343 | 12115 |  | 534312
AS | SA | E2622 | 2007-01-25 | 5 | Ordsall P S and Children’s Centre | 2006-04-03 | 2007-07-27 | 5083103 | 5083103 | 5078540.46 | 5078540.46 | 4562.54 | 0.089759 | 2281.27 |  | 5080821.73
AS | MK | E2709 | 2006-12-08 | 6 | Worsley Fit City | 2006-04-10 | 2007-03-21 | 2975160 | 3060964 | 2974230 | 2974230 | 86734 | 2.8336 | 43367 |  | 3017597
PD | MB | H10058 | 2007-01-17 | 7 | Littleton Rd Improvement Ph V | 2006-09-22 | 2007-01-24 | 525648 | 833653 | 833653 | 833653 | 0 | 0 | 0 |  | 833653 | 12373 | rear walls re-instated into contract.
KM | SR | H2618 | 2006-12-08 | 8 | Langworthy Shops Ph II | 2006-07-24 | 2007-05-07 | 799676 | 752949.25 | 771974 | 771974 | -19024.75 | -2.5267 | -9512.375 |  | 762461.625
PD | MB | C2663 | 2007-01-15 | 9 | Littleton Rd Shops | 2006-08-29 | 2006-11-27 | 216311 | 324394 | 252638 | 252638 | 71756 | 22.12 | 35878 |  | 288516 |  | Additional Work, to shops.
PM | QS | [6 empty] | A | B | C | D | G (B-D) |  | b1
|  | Job No |  |  | Contract Name | Start on Site Date | Finish On Site Date | Contract Target Cost. (including KPI bonus) | Revised/ Predicted Contract Target Cost £(including KPI bonus) | Predicted Target Cost t £ (including KPI bonus) | Forecast Final Actual Cost £ (including KPI bonus) | Actual Cost Variation £ | % Saving (Neg've is Over spend) | Contractor Bonus From Shared Saving (G) | KPI Bonus included in total | Total Cost to client (estimate in italics) D+b1 | Cot per property | Notes
Partner G & J Seddon
KM | SR | H10024 |  | 1 | Weast Block improvement Phase III | 2005-01-10 | 26/08/05 eot 28/10/2005 | 657995 | 715570 | 715570 | 617562 | 98008 | 13.6965 | 49004 |  | 666566 |  | Extra property added, enforcement work to property added. Closedown meeting held
TN | SR | D2601 |  | 2 | Salford Sports Village | 2005-01-10 | 2006-02-03 | 3809361 | 3992844 | 3992844 | 3749728 | 243116 | 6.0888 | 121558 |  | 3871286 |  | Extra work to bund wall, car park.
BG | SR | E2607 |  | 3 | Grosvenor Rd CPS Remodelling | 2005-04-25 | 2006-03-03 | 1005880 | 1005880 | 1151104 | 914000 | 91880 | 9.1343 | 45940 |  | 959940 |  | Numerous adds and omits to the contract. Closedown meeting held
AS |  | E2606 |  | 4 | Wharton CPS Remodelling | 2005-04-25 | 09/09/05 eot 23/09/05 | 320551 | 370587 | 370587 | 256686 | 113901 | 30.7353 | 56950.5 |  | 313636.5 |  | Omitted canopies, Extra works to car park and ramp. Closedown meeting held
AS | MB | E2603 |  | 5 | Boothstown Methodists Primary School Remodelling | 11//7/05 | 2005-10-07 | 229804 | 198329 | 198329 | 117777 | 80552 | 13.6965 | 40276 |  | 158053 |  | Nothing omitted, contract target high. Closedown meeting held
KM | MB | H10610 | 2006-10-26 | 6 | West of Seedley Park III/IV | 2005-10-17 | 2006-08-21 | 1003215 | 1003215 | 854214 | 563401 | 439814 | 43.8405 | 219907 |  | 783308 | 5027
KM | MB | H10550 | 2006-10-24 | 7 | Seedley West Phase III- Block Improvement | 2006-01-23 | 2006-11-06 | 603568 | 626587 | 626587 | 353190 | 273397 | 43.6327 | 136698.5 |  | 489888.5 | 13489
BG | KB | E10726 | 2007-01-17 | 8 | St Charles Swinton (Surestart) | 2006-03-27 | 2006-07-28 | 664469 | 664469 | 688127 | 688127 | -23658 | -3.5604 | -11829 |  | 676298
KM | RDB | H10723 | 2006-12-05 | 9 | Co-operative Street Home swaps | 2006-03-13 | 2007-02-02 | 691416 | 862385 | 862385 | 805000 | 57385 | 6.6542 | 28692.5 |  | 833692.5 | 86239
KM | RDB | H11333 |  | 10 | Weast Block Improvements Phase V | 2007-01-08 | 2007-08-08 | 693560 | [5 empty] | 0 |  | 0
|  | S2579 | 2006-12-15 | 11 | Barton Moss SU | 2006-10-30 | 2007-05-21 | 777911 | 888195 | 888195 | 888195 |  |  | 0 |  | 888195

## KPI's £0.5-£5.0 M
Partner Cruden
[7 empty] | KPI 1. Customer satisfaction 25% |  |  |  | KPI 2. Time predictability 25% | KPI 3 Safety 10% | KPI 4 Defects at Handover 40% | Comments
[7 empty] | Target 80% |  |  |  | Target Completion on time | AIR 15% better than national average | Zero Defects |  | AIR = No of reportable accidentsx100,000/ Average no of persons on site
|  | Job No | Date of QS Report |  | Contract Name |  | End User 50% | Commissioning Officer 25% | Social inclusion 25% | Combined KPI 1 |  |  |  |  | Sector average 897.00 source HSE Work related injuries and ill health in construction. 2005/6
PM | QS | Job No |  |  | Contract Name | Completed | Percentage |  |  | Percentage
PD | JR | H2677 H10021 H10022 |  | 1 | Arrowhead Block improvement Phase I-3 | 23/09/05 eot 27/01/06 | 83.3 | 73.75 | 80 | 80.0875 | Achieved on the extended contract date | Zero Accidents | Zero defects | Contract extended to Take further work. Favourable comments received from Client Officer, Colin Goodall re the contribution of the Tenant Liaison officer to the smooth running of the contract and the speedy resolution of householders problems. ALL KPI's SATISFIED
PD | MB | H10056 |  | 2 | Littleton Road Block improvement Phase III&IV | 17/03/2006-- eot 19/0506 | 69.69 | 85.71 | 100 | 81.2725 | Achieved on the extended contract date | 1 reportable accident. KPI not achieved. | Zero defects | 1 ONLT KPI's,2 & 4 SATISFIED
DT | SA | E2605 | 2006-12-15 | 3 | Westwood Park Primary School Extension | 2005-12-23 |  |  |  | 0 |  |  |  | Further work carried out post contract by the same contractor.
MH | MK | E10669 |  | 4 | Surestart Fiddlers Lane | 2006-09-04 | 83 | 83 |  | 62.25
AS | SA | E2622 | 2006-12-13 | 5 | Ordsall P S and Children’s Centre | 2007-07-27 |  |  |  | 0
AS | MK | E2709 | 2006-11-08 | 6 | Worsley Fit City | 2007-03-21 |  |  |  | 0
PD | MB | H10058 | 2006-10-25 | 7 | Littleton Rd Improvement Ph V | 2007-01-24 |  |  |  | 0
KM | SR | H2618 | 2006-12-08 | 8 | Langworthy Shops Ph II | 2007-05-07 |  |  |  | 0
PD | MB | C2663 | 2006-11-20 | 9 | Littleton Rd Shops | 2006-11-27 |  |  |  | 0
Partner G & J Seddon
[7 empty] | KPI 1. Customer satisfaction 25% |  |  |  | KPI 2. Time predictability 25% | KPI 3 Safety 10% | KPI 4 Defects at Handover 40% | Comments
[7 empty] | Target 80% |  |  |  | Target Completion on time | AIR 15% better than national average | Zero Defects
|  | Job No | Date of QS Report |  | Contract Name |  | End User 50% | Commissioning Officer 25% | Social inclusion 25% | Combined KPI 1
PM | QS |  |  |  | Contract Name | Completed | Percentage |  |  | Percentage
KM | SR | H10024 |  | 1 | Weast Block improvement Phase III | 26/08/05 eot 28/10/2005 | 94 | 77.7 |  | 66.425 | Completed two weeks before extended contract date | Zero Accidents | Zero defects | Contract extended to Take further work. Favourable comments received from Client Officer, T Smith re the contribution of the Tenant Liaison officer to the smooth running of the contract and the speedy resolution of householders problems. Social inclusion still to be resolved
TN | SR | D2601 |  | 2 | Salford Sports Village | 2006-02-03 |  |  |  | 0
BG | SR | E2607 |  | 3 | Grosvenor Rd CPS Remodelling | 2006-03-03 | 94.4 | 94.4 |  | 70.8 | Achieved on the extended contract date | Zero Accidents | Zero defects
AS |  | E2606 |  | 4 | Wharton CPS Remodelling | 09/09/05 eot 23/09/05 | 49.4 | 49.4 |  | 37.05 | Completed 2.5 weeks late | Zero Accidents | Zero defects | NB start on site was 11/07/05
AS | MB | E2603 |  | 5 | Boothstown Methodists PS Remodelling | 2005-10-07 | 94 | 94 |  | 70.5 | Achieved on the extended contract date | Zero Accidents | Zero defects
KM | MB | H10610 | 2006-10-26 | 6 | West of Seedley Park III/IV | 2006-08-21 |  |  |  | 0
KM | MB | H10550 | 2006-10-24 | 7 | Seedley West Phase III- Block Improvement | 2006-11-06 |  |  |  | 0
BG | KB | E10726 |  | 8 | St Charles Swinton (Surestart) | 2006-07-28 | 90 | 90 |  | 67.5
KM | RDB | H10723 | 2006-12-05 | 9 | Co-operative Street Home swaps | 2007-02-02 |  |  |  | 0
KM | RDB | H11333 |  | 10 | Weast Block Improvements Phase V |  |  |  |  | 0
|  | S2579 | 2006-12-15 | 11 | Barton Moss SU | 2007-05-21 |  |  |  | 0