SALFORD CITY COUNCIL

CABINET WORK PLAN 2009/10

Helping People through the Recession

Salford City Council

Cabinet Work Plan 2009/10

Helping People through the Recession

Introduction

This year's Cabinet Work Plan focuses tightly on what the Council will do in 2009/10 to help people in Salford to respond to the recession. It identifies activities that directly help people and businesses to reduce damage and hardship from the recession, while not forgetting continuing opportunities.

Our focus on action that we will take this year complements the strategic approach in the Salford Agreement 2008-11. In particular, the Child Poverty Strategy that we will launch in September will capture the activity in this Work Plan and much else besides to ensure that all of our young people can get a decent start in life.

The Work Plan shows the Council doing what it can to ease the impact of the recession on people and businesses in Salford so that when it lifts they are well-placed to take advantage of opportunities for success.

Themes

The Council can help people through the recession in many ways. To make this range of activities easier to understand we have clustered them around the following themes:

- Getting and keeping a job

- Supporting new and existing local businesses

- Maintaining income and managing debt

- Getting and keeping a home

- Knowing where to turn – publicity about sources of help

- Making the most of public resources

The action plans and activities in the following pages relate to these themes, and how we will translate them into action. We have also listed the indicators from the Salford Agreement that relate most directly to each theme (page 15).

Getting and keeping a job

As unemployment rises and the number of vacancies falls, many people will find getting a job difficult. Those who are still in a job will be even keener to hold on to it. Those who have always found it hardest to get and keep a job will find it even harder. So, the council will do what it can to help those who have just lost their jobs, or face doing so, while still developing working neighbourhood teams with its partners for those who have been workless for a long time.

| Action plans | Activities | End date | Lead member & officer |
| --- | --- | --- | --- |
| Deliver local support to reduce impact of economic downturn | Design services for people affected by the recession including – skills and work support, housing, debt and financial advice, business support and health support | June 2009 | Cllr John Merry/ Chris Marsh |
|  | Agree information sharing protocol between key agencies (Jobcentre Plus, Learning and Skills Council, Local Authorities, etc), to measure the impact of the recession and the performance of support interventions | June 2009 |  |
|  | Undertake monthly performance of support interventions and deliver action plans put in place to address issues | August 2009 |  |
| Develop and deliver working neighbourhood teams | Launch working neighbourhood teams in Eccles, the New Deal for Communities area and Ordsall and Langworthy | May 2009 |  |
|  | First monthly working neighbourhood team performance reports produced | June 2009 |  |
|  | Local implementation teams in place for phase 2 areas (Higher/ Lower Broughton and Walkden and Little Hulton) | July 2009 |  |
|  | Develop delivery mechanism for cross-boundary working neighbourhood team across Higher Broughton/ Cheetham Hill | Sept 2009 |  |
|  | Launch working neighbourhood teams in Walkden and Little Hulton, and Higher/ Lower Broughton | Sept 2009 |  |
|  | Local implementation teams in place for phase 3 areas (Swinton, Irlam and Cadishead, and Weaste) | Sept 2009 |  |

| Action plans | Activities | End date | Lead member & officer |
| --- | --- | --- | --- |
| Integrate worklessness/ 14-19 agendas | Launch integrated Think Skills and Work Board to address worklessness/ 14-19 agendas | June 2009 |  |
|  | Joint co-commissioning group in place to co-ordinate worklessness/ 14-19 commissioning | July 2009 |  |
|  | Develop delivery mechanism to integrate Connexions/ Skills and Work processes | Sept 2009 |  |
| Reduce re-offending and assist the rehabilitation of offenders through assistance in finding work | Assist the development of the changing directions mentoring project, and support the back to work team and the together women’s project to enable offenders or those at risk of offending to find employment | March 2010 | Cllr David Lancaster/ Don Brown |
|  | Use early interventions and restorative justice approaches to reduce the number of first time entrants into the criminal justice system by seeking out education and training opportunities to facilitate employment | March 2010 |  |
| Improve job opportunities for care leavers | Mentoring schemes utilised across the Council via the young ambassadors scheme to support care leavers in the transition into the workplace | July 2009 | Cllr Bill Hinds/ Debbie Brown |
|  | Provide work experience opportunities to care leavers | Sept 2009 |  |
|  | Ring-fence apprenticeship and other suitable opportunities for care leavers | Sept 2009 |  |
|  | Connexions advise and support care leavers to be best prepared for the workplace, through job clubs and direct work, alongside the leaving care team and other agencies | Sept 2009 |  |
| Maximise the take-up of educational maintenance allowance | Connexions Salford send a ‘calendar of events’ letter to all parents/ carers of year 11 pupils outlining activities through out the academic year they need to be aware of, including the application process for educational maintenance allowance | Sept 2009 | Cllr John Warmisham/ Lesley Craven (interim) |
|  | Share best practice to ensure advisers of young people know what financial support is available and how it is delivered effectively to pupils, students and their parents and carers | Sept 2009. |  |
|  | Promote educational maintenance allowance in community newsletters and other local publications, e.g. LIFE magazine, Salford Advertiser, etc | Jan 2010 |  |
|  | Distribute information on financial support available to further education students | Feb 2010 |  |
|  | Connexions personal advisers liaise with the designated careers/ connexions coordinator within each school during March 2010 to ensure sufficient numbers of educational maintenance allowance packs are ordered and distributed to pupils | March 2010 |  |
| Expand pathways to employment programme into other Council front-line services | First phase delivery of citywide catering employment programme and assessment of success/ programme development needs following first ‘cohort’ | May 2009 | Cllr Joe Murphy/ Mark Reeves |
|  | Placement of first phase programme trainees within citywide | May 2009 |  |
|  | Launch second phase of citywide catering and cleaning pathways to employment programme | August 2009 |  |
|  | Placement of second phase programme trainees | Sept 2009 |  |
|  | 6 month programme review undertaken and action plan to address issues delivered thereafter | Sept 2009 |  |

Supporting new and existing businesses

People’s success in getting and keeping jobs depends a lot on demand for their skills from successful businesses. The council recognises the difficulties that local businesses are facing, and the increased difficulty of starting new ones.

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Pay suppliers promptly to help cash flow, particularly small and medium sized employers. | Review the number and impact of re-setting suppliers’ records with short or immediate payment terms when they ask for it to help with their cash-flow difficulties | Sept 2009 | Cllr Bill Hinds/ Geoff Topping |
|  | Review take-up of purchase cards by suppliers to settle payments | Sept 2009 |  |
|  | Launch web portal facility for suppliers to submit their invoices with payment terms of 10 days | Sept 2009 |  |
| Deliver business start up support for people who are facing redundancy | Integrate business start up advice with ‘rapid response team’ and gain approval from Jobcentre Plus to contact firms who have submitted HR1 forms | June 2009 | Cllr John Merry/ Rob Pickering |
|  | Commission intensive support package for people wanting to start businesses April – June 2009 - £28,000 so that there is support for them until the North West Development Agency contract is finalised in July 2009 | July 2009 |  |
|  | Co-commission with North West Development Agency ‘intensive start-up support’ contract (£288,000) to insure people facing redundancy are a target group for the provision | July 2009 |  |
|  | Integrated promotional campaign through Business Liaison North West, Neighbourhood newsletters, Business IN Salford magazine, LIFE IN Salford, website, etc to ensure take up of mainstream provision | July 2009 |  |
| Deliver support for existing businesses that are facing operational difficulties | Identify suitable funding streams to provide face-to-face support for businesses rather than remote support (which businesses constantly tell us is ineffective) | July 2009 | Cllr John Merry/ Rob Pickering |
|  | Host a special business summit in conjunction with the Greater Manchester Chamber of Commerce on finance for business | Aug 2009 |  |
|  | Identify suitable funding to provide financial assistance as a short term measure to struggling businesses e.g. through reduction/ freeze on business rates, establish an emergency fund | Sept 2009 |  |
| Encourage local economic benefit | Hold a workshop with Bovis Lend Lease to ensure local companies can gain access to major public sector supply chain/ sub contract work | May 2009 |  |
|  | Hold procurement workshops to encourage local suppliers to tender for public sector contracts | July 2009 |  |
|  | Secure funding to develop and deliver a buy local campaign that can run city wide and be adapted to focus on individual town centres | Aug 2009 |  |
| Promote commercial premises (short term), and influence their development of commercial stock to maximise inward and foreign direct investment (longer term) | Contact Salford’s property agents to encourage them to refresh/ promote their current stock | June 2009 | Cllr David Lancaster/ Rob Pickering |
|  | Deliver with Manchester Inward Investment Agency a ‘locate Salford’ campaign, promoting the benefits of Salford as an investment location particularly emphasising the competitive rental levels, including: mail shots to all active enquires locality/ familiarisation tours publicity opportunities – web and publications | Sept 2009 |  |
|  | In partnership with Manchester Inward Investment Agency provide intensive account management to 10 Foreign Owned Companies located in Salford, to help retain them within the city and encourage additional investment long-term. | March 2010 |  |
|  | Work with developers/ site owners to improve their commercial offer to meet current and forecasted demand | March 2010 |  |
| Tackle businesses dealing in counterfeit products and/ or failing to meet regulatory standards | Review impact of intelligence led approach in combating counterfeiting and rogue traders | Sept 2009 | Cllr Joe Murphy/ Ron Pennington |
|  | Undertake 4,000 business inspections | March 2010 |  |
|  | Help businesses to comply with law, for instance through programmes of test purchasing | On-going/ March 2010 |  |
| Develop tourism in Salford to support local businesses | Fully integrate into our tourism marketing offer ‘beat the credit crunch’ measures | July 2009 | Cllr John Merry/ Susan Wildman |
|  | Review take-up of work with local businesses to sell the city, offer packages, promotional offers and opportunities to sell and promote at key events (including on-site concessions and cross promotions) | Sept 2009 |  |
|  | Respond to the closure of Ordsall Hall with public relations activities and on-line marketing to serve virtual visitors and ensure an engaged and informed audience in place when the hall re-opens in 2011 | Sept 2009 |  |
|  | Evaluate numbers and spend of overseas visitors in response to international and in-bound marketing campaigns, e.g. continued coverage with US heritage magazine and projects of international interest such as music map and Ordsall Hall ghost cam | Dec 2009 |  |
|  | Exploit potential 2012 opportunities including the Cultural Olympiad and opportunities to bring 2012 visitors to the Northwest, and showcase the city and local businesses | Dec 2009 |  |
|  | Develop major events for local residents such as ice rink, proms in the park and other events in parks and urban spaces | Dec 2009 |  |
|  | Tailor marketing messages to encourage people to holiday in Salford and Manchester and ensure representative quality and consistent information about Salford is being communicated externally | March 2010 |  |
|  | Work closely with The Lowry on their ‘I love Salford’ campaign offering incentives and discounts to all Salford residents | March 2010 |  |

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Support businesses by tackling crimes that impact on them in an economic downturn | Deter and prevent commercial robbery | March 2010 | Cllr David Lancaster/ Don Brown |
|  | Disrupt the market for stolen goods | March 2010 |  |
|  | Deliver advice and business grants to improve business security (70-80) | March 2010 |  |
|  | Encourage the adoption of ‘secured by design’ status for all new commercial developments | March 2010 |  |
|  | Promote the services of Quaywatch to commercial premises citywide | March 2010 |  |
|  | Address crime that indirectly affects businesses, e.g. vehicle crimes affecting staff and customers | March 2010 |  |
|  | Co-ordinate the deployment of mobile CCTV | March 2010 |  |
|  | Combat robberies in commercial premises with Greater Manchester Police and partners as part of the violence at work initiative | March 2010 | Cllr Joe Murphy/ Mark Reeves |
|  | Frustrate the stolen goods markets in conjunction with Greater Manchester Police | March 2010 |  |

Maximising income and managing debt

Whether in work or not, maintaining a reasonable income and managing debt is a concern for many people at any time, and the services which the council offers recognises this. During a recession, that concern grows and affects more people, with the danger that its effects will reduce people’s abilities to enjoy a decent quality of life now, and to take opportunities in the future.

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Deliver fast-track benefit claims service | Implementation of e-benefits to allow claims to be completed over the telephone or via a Gateway Centre | Sept 2009 | Cllr Bill Hinds/ John Tanner |
| Design flexible debt recovery procedures for residents affected by the recession | Make arrangements for payments that are appropriate to the means of the customer or business, being sympathetic to the difficulties they might be experiencing | Sept 2009 |  |
|  | Take appropriate recovery action as early as possible to avoid customers falling too far into arrears | On-going/ March 2010 |  |
| Promote affordable credit and combat illegal money lending | Run Anti-Loan Shark Campaign on 6 April in partnership with the Department for Business, Enterprise and Regulatory Reform illegal money lending team and the City Council’s Financial Inclusion Group | Sept 2009 | Cllr Keith Mann/ Keith Darragh |
|  | 6 community events to be held for clients | Sept 2009 |  |
|  | Display pop-up banners in council premises and other venues (8 venues to start) promoting advice services | On-going/ March 2010 |  |
| Develop the financial inclusion agenda | Contribute and develop the activity of the Financial Inclusion Working Group in using money for two years from the Department of Work and Pensions ‘Growth Fund’ (Financial Inclusion Fund) to develop financial inclusion infrastructure across the Salford and Manchester and East Lancashire | Sept 2009 | Cllr Keith Mann/ Keith Darragh |
|  | The Greater Manchester and Lancashire financial inclusion champions to co-ordinate relevant services and provide access points for further funding | Sept 2009 |  |
| Promote affordable warmth | Continue to employ data matching to identify potential entitlement to affordable warmth grants and assistance amongst service clients with referrals to the Affordable Warmth Access Referral Mechanism and the affordable warmth team (estimated number of referrals is 350) | Dec 2009 |  |
|  | Secure resources to extend data matching to include low income families as well as those aged 60+ | March 2010 |  |
|  | Work together with the UK Public Health Association Greater Manchester Fuel Poverty Initiative to tackle the link between ill-health, poorly heated homes and low income by promoting the concept of prescribing ‘income maximisation’ amongst general practitioners and health professionals | On-going/ March 2010 |  |
| Develop and implement Child Poverty Strategy | Launch a child poverty strategy for the city that focuses a partner’s resources and activities on reducing child poverty. | Sept 2009 | Cllr John Merry/ Chris Marsh |
| Deliver quality income/ debt advice to employees | Run financial awareness programme by ”internal marketing and promotion” of “self-help” groups across the Council | Sept 2009 | Cllr Bill Hinds/ Debbie Brown |
|  | Invite River Valley credit union into the workplace to provide awareness sessions | Oct 2009 |  |
|  | Offer financial and family counselling for affected employees by specialist advisors from outside of the directorate/ authority (where appropriate), i.e. family support | Nov 2009 |  |

Getting and keeping a home

The recession and the credit crunch in particular have created difficulties for people in buying a home to suit them, and for some staying in the one they already have. This is creating greater demand for advice services and for social housing across the city.

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Deliver Salford Housing Options Point – SHOP | Restructure housing options service and relocate teams into Salford housing options point – SHOP | June 2009 | Cllr Peter Connor/ Mike Wright |
|  | Deliver housing advice surgeries at external locations, including Gateway Centres and partner housing offices, to a minimum of 1 day per week | Sept 2009 |  |
|  | Redesign procedures to focus on homelessness prevention and holistic assessment, including money and work/education/ training advice | Jan 2010 |  |
|  | Deliver Year 1 of 2 year trailblazer action plan with Government funding for enhanced housing options, including work-related training, community outreach officers, social exclusion and home ownership co-ordinators, co-location of staff into ‘SHOP’ and research into modular building to reduce overcrowding | March 2010 (Year 1) |  |
|  | Extend housing options assessments to include wider assessment of money, debt and worklessness as they impact on the housing options available | March 2010 |  |
| Tackle increasing homelessness within the city | Continue to develop homelessness prevention options, and increase homelessness prevention to a minimum of 4 per thousand households | March 2010 |  |
| Deliver effective housing applications process | Housing allocations policy to become more responsive to current market conditions through monitoring and review, enabling changes to bandings and priorities to ensure efficient allocations are made, based on need | Sept 2009 |  |

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Develop plans for delivery of a Council managed mortgage scheme | Identify target development schemes for the provision of Council mortgages | May 2009 |  |
|  | Develop and implement a mechanism for the delivery of the mortgage proposal to enable Salford City Council to provide mortgage assistance to citizens in order to purchase properties in the city | June 2009 |  |
| Protect people’s homes | Implement central government mortgage rescue schemes in partnership with money advice agencies, registered social landlords and Salford Money Line | Sept 2009 | Cllr Peter Connor/ Mike Wright |
|  | Ensure that money and debt advice is joined-up with implementation of mortgage rescue schemes through joint protocols and co-location of staff where appropriate | Dec 2009 |  |
|  | Produce homeowner profile of the city and potential ‘fracture points’, e.g. ex-‘right-to-buy’ tenants who have ‘sub-prime’ mortgages they can no longer afford to enable targeted advice and support | July 2009 | Cllr Peter Connor/ Keith Darragh |
|  | Assess emergency mortgage advice sessions held 1-2 days per month on County Court possession hearing days in partnership with Citizens Advice Bureau and others | Sept 2009 |  |
|  | Work with Housing Connections Partnership to ensure the government’s national mortgage rescue scheme is brought to effective use within the city | March 2010 |  |
|  | Monitor mortgage re-possession and arrears data via the Council of Mortgage Lenders, Ministry of Justice and the Financial Services Authority (it is estimated that at least 25% of clients will be owner occupiers) | March 2010 |  |
| Disrupt and prevent acquisitive crime that affects peoples homes | Implement an early warning system for landlords on emerging crime trends | July 2009 | Cllr David Lancaster/ Don Brown |
|  | Marketing campaign to raise public awareness (targeting schools, colleges and universities) of the consequences of buying stolen goods | Sept 2009 |  |
|  | Promote the accredited landlord scheme and incorporate minimum requirements for home security | Sept 2009 |  |
|  | Deliver DNA property marking scheme in 3 domestic burglary hotspot areas | Dec 2009 |  |
|  | Work with partners to reduce the upturn trend for domestic burglary | March 2010 |  |
|  | Provide positive interventions to homeowners who fall victim to domestic burglary, e.g. free target hardening (500) | On-going/ March 2010 |  |

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Address the increased risk of domestic abuse, associated homelessness and economic impact on families | Launch violence against women strategy | Sept 2009 |  |
|  | Commission appropriate services to support victims and witnesses and to reduce offending behaviour | Sept 2009 |  |
|  | Support the multi-agency risk assessment conference process and the specialist domestic violence court | March 2010 |  |
|  | Provide target hardening support to keep people safe in their homes (50) | March 2010 |  |
|  | Support families whose tenancy is at risk due to anti-social behaviour through the Salford assisted families project | On-going/ March 2010 |  |

Knowing where to turn – publicity about resources of help

The council knows that many people are not aware of the help and advice that is available to them, and that for others the sheer volume of it is off-putting. So, a major part of its help for residents is to help them to find their way around what is on offer so that they can make the most of it.

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Launch tackling recession website and helpline | Review use and impact of recession helpline | July 2009 | Cllr Bill Hinds/ John Tanner |
|  | Review use and impact of drop-in advice sessions in Gateway Centres with partners | July 2009 |  |
|  | Review use and impact of the mobile advice centre’s advice and guidance in the areas of the city that are hit the hardest by the recession | July 2009 |  |
| Promote sources of recession help available to local residents | Publicity included in LIFE IN Salford publication | Monthly | Cllr John Merry/ Susan Wildman |
|  | Ensure all sources of help available are published on the Council’s website | March 2010 |  |
|  | Consider whether specific publicity/ marketing on the provision of advice and support is necessary, including media activity | March 2010 |  |
| Target financial support/ advice to affected residents through customer profiling | Produce recession customer profile for all customer facing teams | Sept 2009 | Cllr Bill Hinds/ John Tanner |
|  | Signposting customers to the services that are able to help them | March 2010 |  |
| Enhance access to benefits advice and income maximisation | Advertise the Welfare Rights Services through ‘Loan Shark’ Campaign (see above), ‘Life in Salford, press releases, leaflets, promotional material in general practitioners practices/ health centres, etc – estimated number of clients who should receive advise is 4,000 with £7 million in benefits generated | April 2009/ on-going | Cllr Keith Mann/ Keith Darragh |
|  | Continue to target and promote benefit take-up amongst people aged 60+ - data matching (housing benefit/ council tax benefit), users of home/ day care services, patients in health centres particularly developing pro-active contacts through primary health care staff | On-going/ March 2010 |  |
| Enhance access to debt advice | Referrals from Housing Connections Partnership - particularly those seeking assistance under the ‘Mortgage Rescue Scheme’ (approximately 20-40 referrals) | March 2010 | Cllr Keith Mann/ Keith Darragh |
|  | Identify extra resources to increase debt advice awareness, e.g. postcards advertising debt advice service sent out with council tax bills funded by the Department of Business, Enterprise and Regulatory Reform, Information pack on debt relief orders, investigating funding from residential social landlords, etc. | March 2010 |  |
|  | Debt advisers from April 2009 will be accredited to process the new debt relief orders on-line (bankruptcy for people with debts under £15,000 and limited, disposable income/ assets involving a much reduced fee) – should benefit 60 clients | On-going/ March 2010 |  |
|  | Promote briefings on debt awareness and practical debt solutions to up to 60 front-line workers, designed to increase access points for basic advice around cheaper fuel, basic bank accounts, charitable trusts, etc | On-going/ March 2010 |  |

Making the most of public resources

The council and other public services spend a lot of money in the city providing services and the jobs that go with them. The council, for instance, is the biggest employer in the city. Alongside the services specifically targeted on helping people through the recession the council will apply its staff and financial resources to best help people through the recession as well as to maintain the other services which they use.

| Action plans | Activities | End date | Lead |
| --- | --- | --- | --- |
| Deliver the Council as an exemplar employer and promote employability agenda with partners | Develop work replacement programme for workless residents and young people | June 2009 | Cllr John Merry/ Chris Marsh |
|  | Apprenticeships programme developed for appropriate Council staff and new recruits | June 2009 |  |
|  | Academy programme adopted as council policy as preferred method of recruitment for entry level vacancies | Aug 2009 |  |
|  | Launch work placement programme | Sept 2009 |  |
|  | Launch the Council’s apprenticeship programme | Sept 2009 |  |
|  | Collate information in current employability initiatives and opportunities | Sept 2009 |  |
|  | Identify and utilise partner and partnership events and processes offering scope for promotion of employability agenda, including roll out of academy model, work placements and apprenticeships | Nov 2009 |  |
| Develop the local employment benefit of Mediacity:UK | Mediacity:UK public sector partners group in place to co-ordinate strategy and delivery | May 2009 | Cllr John Merry/ Chris Marsh |
|  | Mediacity:UK supply chain mapping work completed | June 2009 |  |
|  | Strategy for use of Mediacity:UK open centre space for community benefit launched | July 2009 |  |
|  | Develop Mediacity:UK on tour programmes to raise awareness for local communities of the opportunities of the development | Aug 2009 |  |
|  | Recruit pathways to employment co-ordinator to manage local employment and training opportunities | Aug 2009 |  |
| Integrate community safety with other activity in areas that recession has hit hardest | Target sustainable neighbourhood action projects in recession hotspots and develop actions to address worklessness | Sept 2009 | Cllr David Lancaster/ Don Brown |
| Promote take-up of free school meals | Survey of school satisfaction with current system | Sept 2009 | Cllr Bill Hinds/ John Tanner |
|  | Alert schools to application process including information for parents/ carers and training for schools who are not currently inputting on to the system | Sept 2009 |  |
| Develop the horticultural academy | Salford City Council’s grounds maintenance service to lead and co-ordinate the programme lead apprenticeship scheme on behalf of 7 Association of Greater Manchester Authorities – 7 unemployed young adults from across Greater Manchester will be provided with the basic horticultural skills | March 2010 | Cllr Joe Murphy/ David Seager |

Salford Agreement 2008-11 (refreshed version)

Indicators relating directly to Salford City Council Cabinet Workplan 2009-10

| Key |
| --- |
| Bold = Designated indicators Not Bold = Supporting indicator | Italics = Statutory indicators # = Working Neighbourhood Fund (WNF) indicators <> = Place Survey (PS) Indicator |

| Getting and keeping a job |
| --- |
| Salford Agreement 2008-11 (as refreshed ) – indicators relating to Salford City Council Cabinet Workplan 2009-10 |
| Indicator number and description | Baseline | Targets | SSP Delivery Partners *Lead partner |
|  |  | 2008/9 | 2009/10 | 2010/11 |  |
| NI 117 | 16 to 18 year olds who are not in education, employment or training (NEET) (#) WNF | 7.6% (Jan 2008) | 7.2% | 6.7% | 6.2% | Salford City Council* Learning and Skills Council Pendleton College Salford College Eccles College |
| NI 146 | Adults with learning difficulties in employment | 13.5% (2007/8) numerator | 18.0% | 22.4% | 26.9% | Salford City Council* (Learning Difficulties Service)/ IAS)* Jobcentre Plus |
| NI 150 | Adults receiving secondary mental health services in employment | 5.6% (2007/8) | 5.9% | 6.3% | 6.8% | Salford City Council* GM West mental health Service NHS Foundation Trust Jobcentre Plus Salford PCT |
| NI 151 | Overall employment rate (working age) | 71.0% (2007) | 71.83% | 72.67% | 73.5% | Jobcentre Plus* Salford City Council* Salford PCT Salford CVS GM Chamber of commerce Pendleton College Salford College Eccles College |
| NI 153 | Working age people claiming out of work benefits in the worst performing neighbourhoods (#) WNF | 34.8% (Feb 2007) | 32.56% | 30.28% | 28% | Jobcentre Plus* Salford City Council* Learning and Skills Council Salford Primary Care Trust Salford Council for Voluntary Services GM Chamber of commerce Pendleton College Salford College Eccles College |
| NI 164 | Proportion of working age population qualified to at least Level 3 or higher | 43.2% (2006) | 44.2% | 46.2% | 50% | Learning and Skills Council* Salford City Council Pendleton College Salford College Eccles College |
| NI 161 | Number of Level 1 qualifications in literacy (including ESOL) Achieved | 1038 | 1059 Provisional | 1080 Provisional | 1103 Provisional | Learning and Skills Council* Salford City Council Pendleton College Salford College Eccles College |
|  |  | New Baseline1383 Sources used FE, TTG, UFI, WBL, ACL, ESF Aim level analysis using syntax (2006/7) | 1389 (2007/8) New target 1395 (2008/9) | New Target 1402 | New Target 1408 (4205 3 year cumulative total) |  |
| NI 162 | Number of Entry Level qualifications in numeracy achieved | 90 169 (2006/7) Actual | 100 Provisional New targets established 182 actual (2007/8) 194 | 110 Provisional New targets established 207 | 120 Provisional New targets established 220 (621 3 year cumulative total) | Learning and Skills Council* Salford City Council Pendleton College Salford College Eccles College |
|  |  |  | 30% increase over 4 years from 2006/7 to 2010/11(7.5% from 06/07 baseline each year |  |  |  |
| NI 163 | Proportion of working age population qualified to at least Level 2 or higher (#) WNF | 63.5% (2006) | 65.5% | 68.5% | 72.8% | Learning and Skills Council* Salford City Council Pendleton College Salford College Eccles College |
| LPI 74 | Self employment - % of those employed that are self employed, working age | 8.1% (2006) | 8.3% | 8.5% | 8.7% | Salford City Council* North West Development Agency Greater M/C Chamber of Commerce/ Business Support Solutions Jobcentre Plus & MIDAS |

| Supporting new and existing businesses |
| --- |
| Salford Agreement 2008-11 (as refreshed ) – indicators relating to Salford City Council Cabinet Workplan 2009-10 |
| Indicator number and description | Baseline | Targets | SSP Delivery Partners *Lead partner |
|  |  | 2008/9 | 2009/10 | 2010/11 |  |
| NI 166 | Median earnings of employees in the area | 421.6 (2007) | 431.6 | 441.6 | 451.6 | Salford City Council* NW Development Agency Greater M/C Chamber of Commerce/Business Support Solutions Jobcentre Plus Learning & Skills Council Central Salford URC & MIDAS |
|  |  | 437.7 (2008) | N/A | New target 437.9 | New target 459.1 |  |
| NI 171 | New business registration rate | Awaiting Vat registration dataset (Sept 08) | To be set | To be set | To be set | Salford City Council* North West Development Agency Greater M/C Chamber of Commerce/Business Support Solutions & MIDAS |
|  |  | New baseline 95.8% (2007) | New target 96.13% | New target 96.46% | New target 96.8% |  |

| Maximising income and managing debt |
| --- |
| Salford Agreement 2008-11 (as refreshed ) – indicators relating to Salford City Council Cabinet Workplan 2009-10 |
| Indicator number and description | Baseline | Targets | SSP Delivery Partners *Lead partner |
|  |  | 2008/9 | 2009/10 | 2010/11 |  |
| NI116 | Proportion of children in poverty | 27.8% (2007) | 26.07% | 24.33% | 22.60% | Salford City Council* Jobcentre plus* |
|  | New definition (unconfirmed) The number of children living in households whose income is below 60% of the national median | New baseline to be agreed at the end of 2009/10 | New target to be agreed at the end of 2009/10 | New target to be agreed at the end of 2009/10 | New target to be agreed at the end of 2009/10 |  |

| Getting and keeping a home |
| --- |
| Salford Agreement 2008-11 (as refreshed ) – indicators relating to Salford City Council Cabinet Workplan 2009-10 |
| Indicator number and description | Baseline | Targets | SSP Delivery Partners *Lead partner |
|  |  | 2008/9 | 2009/10 | 2010/11 |  |
| NI 154 | Net additional homes provided | 1718 (2006/7) | 1600 | 1600 | 1600 | Salford City Council* |
| NI 155 | Number of affordable homes delivered (gross) | 115 (2007/8) | 200 | 250 | 300 | Salford City Council* |
| NI 156 | Number of households living in temporary accommodation | 46 House-holds (2007/8) | 38 | 24 | 15 | Salford City Council* |
| NI 32 | Repeat incidents of (MARAC referred) domestic violence | To be developed April 09 | To be developed April 09 | To be developed April 09 | To be developed April 09 | Salford City Council* Greater Manchester Police |
|  |  | New baseline Salford MARAC 31% (Oct 2007 – Nov 2008) | New target N/A | New target 28% (March 2010) | New target 27% (March 2011) |  |
| NI 19 | Rate of proven re-offending by young offenders | New baseline 1.55 per 100 (1.55 Jan – March 2005) | 1.512 per 100 (tbc by Community Safety) | 1.49 per 100 (tbc by Community Safety) | 1.46 per 100 (tbc by Community Safety) | Youth Offending Team* (and relevant statutory responsible partners) |
| NI 16 | Serious acquisitive crime | 35.01 rate per 1,000 7,633 (number) (2007/8) | 32.21 7,022 Reduce by 15% over 3 years 7% this year 7,264 | 30.81 6,717 Reduce by 5% | 29.76 6,488 Reduce by 3% | Greater Manchester Police* Salford City Council |

Knowing where to turn – publicity about resources of help

| Making the most of public resources |
| --- |
| Salford Agreement 2008-11 (as refreshed ) – indicators relating to Salford City Council Cabinet Workplan 2009-10 |
| Indicator number and description | Baseline | Targets | SSP Delivery Partners *Lead partner |
|  |  | 2008/9 | 2009/10 | 2010/11 |  |
| LPI 73 | Developing Mediacity:UK | To be set | To be set | To be set | To be set | Central Salford URC* Salford City Council North West Development Agency |
|  | New definition:- maintain a minimum of 10% of Salford residents working on construction and related trades on Phase 1 of Mediacity:UK | N/A | N/A | 10% of Salford residents employed on Phase 1 | 10% of Salford residents employed on Phase 1 |  |
| LPI 87 | Access to employment by public transport (and other specified modes) – households access to Mediacity:UK within 30 minutes | 24.7% (2006/7) | 24.7% | 30% | 40% | Salford City Council* |
| NI 1 | % of people who believe people from different backgrounds get on well together in their local area | 685 (06 BVP proxy) baseline to be reviewed on Place Survey results finalised (Jan 09) | 69% target to be reviewed when Place Survey results finalised | 70% target to be reviewed when Place Survey results finalised | 71% target to be reviewed when Place Survey results finalised | Salford City Council* Salford CVS Greater Manchester Police Salford PCT Greater M/C Chamber of Commerce University of Salford Greater M/C Fire and Rescue Salford City College Learning and Skills Council Jobcentre Plus |
|  |  | New baseline 64.9% Place Survey (2008/9) | New target N/A | New target 66.6% | New target 68.3% |  |

# Text boxes

Supporting new and existing businesses

- Deliver prompt payment to suppliers

- Deliver business start up support

- Deliver support for existing businesses

- Encourage local economic benefit

- Promote Salford’s commercial premises

- Tackle businesses dealing in counterfeit products

- Develop tourism in Salford to support local businesses

- Support businesses by tackling crimes that impact on them

Knowing where to turn – publicity about resources of help

- Launch tackling recession website and helpline

- Promote sources of recession help

- Target financial support/ advice

- Enhance access to benefits advice and income maximisation

- Enhance access to debt advice

Getting and keeping a job

Making the most of public resources

- Deliver the Council as an exemplar employer

- Develop the local employment benefit of Mediacity:UK

- Integrate community safety with other activity in areas that recession has hit hardest

- Promote take-up of free school meals

- Develop the horticultural academy

Maintaining income and managing debt

- Deliver fast-track benefit claims service

- Design flexible debt recovery procedures

- Promote affordable credit and combat illegal money lending

- Develop the financial inclusion agenda

- Promote affordable warmth

- Develop and implement child poverty strategy

- Deliver quality income/ debt advice to employees

- Deliver local support to reduce impact of economic downturn

- Develop and deliver working neighbourhood teams

- Integrate worklessness/ 14-19 agendas

- Reduce re-offending and assist the rehabilitation of offenders

- Improve job opportunities for care leavers

- Maximise the take-up of educational maintenance allowance

- Expand pathways to employment programme to support worklessness

Getting and keeping a home

23. Deliver Salford Housing Options Point   – SHOP

- Tackle increasing homelessness

- Deliver effective housing applications process

- Develop plans for delivery of a Council managed mortgage scheme

- Protect people’s homes

- Disrupt and prevent acquisitive crime that affects people’s homes.

- Address the increased risk of domestic abuse, associated homelessness and economic impact on families