Appendix 3

STRATEGIC REVIEW OF GOVERNANCE:

PROPOSALS TO REALIGN ORGANISATIONAL ARRANGEMENTS

TIMETABLE OF EVENTS/NEXT STEPS

|  | Cabinet endorsement of the outline proposals | - | Completed, 16/7/04 |
| --- | --- | --- | --- |
|  | Circulation of Cabinets proposals to all Elected Members; selected partners – i.e: LSP; staff and trade unions | - | Completed, 20/7/04 |
|  | - Closing date for Members responses/views | - | Completed, 20/8/04 |
|  | Cabinet consideration of |  |  |
|  | (i) Members’ views submitted for final approval | - | 1/9/04 |
|  | (ii) Report to full Council on 15th September 2004 | - | Completed via Council Agenda Group 6/9/04 |
|  | Appointment of (i) Lead Members to new Cabinet Portfolios; (ii) Executive Support members | - | 13/9/04 |
|  | Cabinet consideration of |  |  |
|  | (i) Cabinet Sub-Groups (ii) Senior Management Structure | - | ) ) 15/9/04 ) ) |
|  | (iii) Arrangements for appointment of Strategic Directors |  |  |
|  | Appointment of Strategic Directors | - | 1st October onwards |
|  | Cabinet consideration of proposals from Strategic Directors for Senior Management structure via Heads of Service | - | October |
|  | Reports to Cabinet on: - Members’ development needs re: new roles and responsibilities - New Constitution/Scheme of delegation - Progress with implementation of detailed arrangements | - | October/November |
|  | Top Team Development Programme – Cabinet Away Day | - | 3/11/2004 |
|  | Cabinet Protocols New ways of working: |  |  |
|  | Cabinets’ Strategic Agenda Cabinet Sub Groups re: key initiatives/cross-cutting issues/priorities Proposed Strategic Work Programme Arrangements for Cabinet to monitor/evaluate progress |  |  |
|  | - Prof. S. Leach’s Scrutiny Report: Action Plan |  |  |
|  | Proposals for Implementation |  |  |

c:\timetable of events