## Appendix 1
|  | Capital Programme 2005/06 | [18 empty] | Resources 2005/06
| SAP |  | 2005/06 Estimate | Contract |  | Actual spend | Profiled spend | [11 empty] | Profiled spend | profiled spend received | Single capital pot | RING FENCED | Unsupported Borrowing |  | CAPITAL RECEIPTS
| REF |  |  | Start | Finish | Dec | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Dec |  | SCE (R) | SCE (R) |  | RCCO |  | GRANT | OTHER | TOTAL |  | TSG | EP | NDS | Surestart | STANDARDS FUND | DFC | SEED | DFG | SRB | ERDF | NDC | Lottery | NWDA | HMRF | Home Office | Other | TOTAL | Notes
|  |  | £m |  |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m |  | £m | £m |  | £m | £m | £m | £m | £m |  | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
PRIVATE SECTOR HOUSING
| summary | Langwothy / Seedley | 5.519 |  |  | 2.747 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 0.45992 | 3.6793
| summary | NEW DEAL/ NORTH IRWELL | 6.348 |  |  | 4.328 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 0.529 | 4.232 | [26 empty] | 0
| summary | Higher Broughton | 10.15 |  |  | 7.624 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 0.84583 | 6.7667 | [26 empty] | 0
| summary | CLAREMONT / WEASTE | 2 |  |  | 1.37 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 1.3333 | [26 empty] | 0
| summary | ENTERPRISE PARK | 1.251 |  |  | 0.261 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.10425 | 0.834 | [26 empty] | 0
| summary | ORDSALL | 0.64 |  |  | 0.125 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.053333 | 0.42667 | [26 empty] | 0
| summary | NON AREA BASED | 4.125 |  |  | 1.357 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 0.34375 | 2.75 | [26 empty] | 0
| summary | OUTER AREA / CITYWIDE | 4.354 |  |  | 1.938 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 0.36283 | 2.9027 | [26 empty] | 0
| summary | Underprogramming ** | -1.059 |  |  |  | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.08825 | -0.706 |  | 3.481 |  |  |  | 7.129 | 22.706 | 0.012 | 33.328 |  |  | 0 | [5 empty] | 0.784 | 1.573 | 0.579 | 1.55 |  |  | 18.22 |  |  | 22.706 | .012 section 106 lima public house return for trinity park from 04/05 outturn
| 14.434 | PRIVATE SECTOR HOUSING -TOTAL | 33.328 |  |  | 19.75 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 2.7773 | 22.2187 |  | 3.481 | 0 | 0 | 0 | 7.129 | 22.706 | 0.012 | 33.328 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.784 | 1.573 | 0.579 | 1.55 | 0 | 0 | 18.22 | 0 | 0 | 22.706
PUBLIC SECTOR HOUSING
Page 2 | summary | 2005/06 New Starts - Partners | 10.355 |  |  | 7.832 | 0 | 0 | 0.624 | 1.962 | 1.241 | 1.05 | 1.204 | 0.997 | 1.045 | 0.624 | 0.647 | 0.41 | 6.081
Page 3 | summary | 2005/06 New Starts Citywide | 0.452 |  |  | 0.07 | 0.023 | 0 | 0.007 | 0 | 0.04 | 0 | 0 | 0.025 | 0.06 | 0.017 | 0.074 | 0.165 | 0.07
Page 4 | summary | 2004/05 New Starts | 4.009 |  |  | 2.627 | 0.691 |  | 0.311 | 0.557 | 0.238 | 0.228 | 0.335 | 0.369 | 0.312 | 0.3 | 0.496 | 0.287 | 2.36
Page 5 | summary | 2004/05 Insulation Schemes | 0.049 |  |  | 0.048 | 0 | 0 | 0.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.005 | 0.048
Page 6 | summary | 2003/04 New Starts | 0.033 |  |  | 0.023 | 0.037 | 0 | -0.035 | 0 | 0.008 | 0 | 0.013 | 0 | 0 | 0 | 0 | 0.009 | 0.023
Page 7 | summary | ROLLING PROGRAMMES | 2.903 |  |  | 1.327 | 0.142 | 0 | 0.098 | 0.123 | 0.226 | 0.226 | 0.399 | 0.34 | 0.285 | 0.266 | 0.278 | 0.39 | 1.214
Page 8 | summary | New Deal - Kersal/Charlestown | 0.161 |  |  | 0.017 | 0.003 |  | 0.002 | 0.002 | 0.002 | 0.003 | 0.022 | 0.007 | 0.007 | 0.007 | 0.036 | 0.038 | 0.034
Page 9 | summary | SRB/Estate Action/ CC Schemes 1 | 1.176 |  |  | 0.803 | 0.168 | 0 | 0.025 | 0.148 | 0.205 | 0.082 | 0.039 | 0.096 | 0.081 | 0.076 | 0.087 | 0.167 | 0.667
Page 10 | summary | PPR Programme | 0.194 |  |  | 0.125 | 0.004 |  | 0.003 | 0.106 | 0.005 | 0.001 | 0.035 | 0.003 | 0 | 0 | 0 | 0.065 | 0.154
Page 11 | summary | Demolitions | 0.67 |  |  | 0.125 | 0.067 | 0 | 0.029 | 0.112 | -0.039 | 0.021 | 0.042 | 0.07 | 0.077 | 0.12 | 0.15 | 0.143 | 0.232
Page 12 | summary | Retentions/Balances | 0.156 |  |  | 0.043 | 0.007 | 0 | 0.003 | 0.027 | -0.001 | 0 | 0.002 | 0 | 0.003 | 0.01 | 0 | 0.101 | 0.038
Page 13 | summary | Resources and underprogramming | -0.271 | [14 empty] | 0.231 | 0 |  | 2 |  |  | 1 |  | 16.887 |  | 19.887 | [11 empty] | 0.04 |  |  |  |  | 16.847 | 16.887 | 16m MRA, 0.300m extra care housing slipped at outturn
|  | PUBLIC SECTOR HOUSING - TOTAL | 19.887 |  |  | 13.04 | 1.142 | 0 | 1.115 | 3.037 | 1.925 | 1.611 | 2.091 | 1.907 | 1.87 | 1.42 | 1.768 | 2.001 | 10.921 |  | 2 | 0 | 0 | 1 | 0 | 16.887 | 0 | 19.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0 | 0 | 0 | 16.847 | 16.887
|  | HOUSING TOTAL | 53.215 |  |  | 32.79 | 3.9193 | 2.7773 | 3.8923 | 5.8143 | 4.7023 | 4.3883 | 4.8683 | 4.6843 | 4.6473 | 4.1973 | 4.5453 | 4.7783 | 33.1397 |  | 5.481 | 0 | 0 | 1 | 7.129 | 39.593 | 0.012 | 53.215 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.784 | 1.573 | 0.579 | 1.59 | 0 | 0 | 18.22 | 0 | 16.847 | 39.593
CHILDREN'S SERVICES
|  | NDS 4 | 0.022 | Apr 05 | Mar 06 |  | 0.004 | 0.004 | 0.005 | 0.005 | 0.004 | [7 empty] | 0.022 | [6 empty] | 0.022 |  | 0.022 |  |  |  | 0.022 | [13 empty] | 0.022
| e02005 | Capitalised salaries | 0.181 | Apr 05 | Mar 06 | [12 empty] | 0.181 | 0 | [5 empty] | 0.181 | 0 |  | 0.181 | [17 empty] | 0
| e04611 | Devolved Formual Capital | 2.128 | Apr 05 | Mar 06 | 1.608 | 0.177 | 0.178 | 0.177 | 0.178 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.178 | 0.178 | 1.418 | [6 empty] | 2.128 |  | 2.128 | [6 empty] | 2.128 | [10 empty] | 2.128
| e03134 | NDS Condition/Modernisation | 2.288 | Apr 05 | Aug 06 | 1.547 | 0.02 | 0.02 | 0.02 | 0.023 | 1.008 | 0.381 | 0.381 |  | 0.381 |  |  | 0.054 | 1.853 | [5 empty] | 0.695 | 1.593 |  | 2.288 |  |  |  | 1.593 | [13 empty] | 1.593
| e04006 | Class size reduction | 0.001 | Apr 05 | Mar 06 | [12 empty] | 0.001 | 0 | [5 empty] | 0.001 | 0 |  | 0.001 | [17 empty] | 0
| e00515 | PFI 2 | 0.023 |  |  | 0.021 |  |  |  |  | 0.02 |  |  | 0.003 |  |  |  |  | 0.023 | [5 empty] | 0.018 | 0.005 |  | 0.023 | [6 empty] | 0.005 | [10 empty] | 0.005
| e00018 | Primary Review | 3.209 | Feb 04 | Dec 05 | 2.487 | 0.02 | 0.02 | 0.02 | 0.02 | 0.023 | 0.527 | 0.527 | 0.432 | 0.201 | 0.484 | 0.452 | 0.483 | 1.589 |  | 0.499 |  |  |  | 1.728 | 0.982 |  | 3.209 |  |  |  | 0.406 |  |  | 0.473 | 0.103 | [9 empty] | 0.982 | 0.023 citywide contribution
| e02004 E02032 | Schools Access Initiative | 0.435 | Apr 05 | Mar 06 | 0.189 | 0.014 | 0.014 | 0.014 | 0.014 | 0.015 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.227 |  | 0.323 |  |  |  | 0.041 | 0.071 |  | 0.435 |  |  |  | 0.071 | [13 empty] | 0.071
| E00017 | Surplus Place Removal Radclyffe/St Clements | 0.195 | Feb 04 | Aug 07 | 0.217 | 0.014 | 0.014 | 0.014 | 0.014 | 0.012 | 0.013 | 0.013 | 0.02 | 0.021 | 0.02 | 0.021 | 0.019 | 0.114 | [6 empty] | 0.195 |  | 0.195 | [16 empty] | 0.195 | 0.195
| e00510 | The Albion | 0.206 | Apr 01 | Mar 06 | 0.059 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.026 | 0.026 |  |  |  |  | 0.029 | 0.177 | [5 empty] | 0.206 | 0 |  | 0.206 | [17 empty] | 0
| e04851 | Beacon Resource Centre | 0.282 | May 04 | Aug 05 | 0.222 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.027 | 0.027 | 0.007 | 0.007 | 0.007 | 0.007 | 0.07 | 0.191 |  | 0.001 |  |  |  | 0.281 | 0 |  | 0.282 | [17 empty] | 0
| E00514 | Wentworth High School | 0.036 | Apr 05 | Mar 06 | 0.011 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.024 | [5 empty] | 0.036 | 0 |  | 0.036 | [17 empty] | 0
|  | ACG minor works | 0.009 | Apr 05 | Mar 06 | 0.002 | [11 empty] | 0.009 | 0 | [5 empty] | 0.009 | 0 |  | 0.009 | [17 empty] | 0
| e01008 | VA minor works | 0.004 | Apr 05 | Mar 06 | 0.001 | [11 empty] | 0.004 | 0 | [5 empty] | 0.004 | 0 |  | 0.004 | [17 empty] | 0
| e04756 | Little Hulton Childrens Centres | 1 | Apr 05 | Mar 06 | 0.403 | 0.01 | 0.01 | 0.02 | 0.1 | 0.1 | 0.25 | 0.25 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.792 | [6 empty] | 1 |  | 1 |  |  |  |  | 1 | [12 empty] | 1
| e04758 | Larkhill Childrens Centres | 0.269 | Apr 05 | Mar 06 | 0.203 | [6 empty] | 0.072 | 0.103 | 0.072 | 0.007 | 0.007 | 0.008 | 0.175 | 2005-08-15 | [5 empty] | 0.269 |  | 0.269 |  |  |  |  | 0.269 | [12 empty] | 0.269
| e04750 | Winton Nursery | 0.188 | Apr 05 | Mar 06 | 0.167 | [11 empty] | 0.188 | 0 | x | [5 empty] | 0.188 |  | 0.188 |  |  |  |  | 0.188 | [12 empty] | 0.188
| e04751 | Barton Moss Neighbourhood Nursery | 0.095 | Apr 05 | Mar 06 | 0.014 | [7 empty] | 0.022 | 0.009 |  |  | 0.064 | 0.022 | [6 empty] | 0.095 |  | 0.095 |  |  |  |  | 0.095 | [12 empty] | 0.095
| e04757 | Belvedere | 0.386 | Apr 05 | Mar 06 | 0.172 | [6 empty] | 0.056 | 0.032 | 0.077 | 0.052 | 0.101 | 0.068 | 0.088 | [6 empty] | 0.386 |  | 0.386 |  |  |  |  | 0.386 | [12 empty] | 0.386
| e04760 | North Swinton Childrens Centres | 0.12 | Apr 05 | Mar 06 | 0.006 | [6 empty] | 0.004 |  |  |  |  | 0.116 | 0.004 | [6 empty] | 0.12 |  | 0.12 |  |  |  |  | 0.12 | [12 empty] | 0.12
| e04761 | Irlam Childrens Centres | 0.273 | Apr 05 | Mar 06 | 0.045 | [6 empty] | 0.028 |  | 0.004 | 0.04 | 0.06 | 0.141 | 0.028 | [6 empty] | 0.273 |  | 0.273 |  |  |  |  | 0.273 | [12 empty] | 0.273
|  | Barton Moss Childrens Centre |  |  |  | 0.007
|  | Bradshaw st | 0.176 |  |  | 0.002 | [7 empty] | 0.027 | 0.037 | 0.037 | 0.037 | 0.038 | 0.027 | [6 empty] | 0.176 |  | 0.176 |  |  |  |  | 0.176 | [12 empty] | 0.176
| E04852-3 | Specialist colleges | 0.129 | Apr 05 | Aug 05 | 0.134 | 0.025 | 0.025 | 0.025 | 0.025 | 0.029 | [7 empty] | 0.129 | [6 empty] | 0.129 |  | 0.129 | [16 empty] | 0.129 | 0.129
| e02027 | adult education grant | 0.01 | Apr 05 | June 05 | 0.029 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | [7 empty] | 0.01 | [6 empty] | 0.01 |  | 0.01 | [16 empty] | 0.01 | 0.01
| e00037 | Charlestown primary | 0.002 | [14 empty] | 0.002 | 0 |  |  |  |  | 0.002 |  | 0 |  | 0.002 | [17 empty] | 0
| e04696-e04705 | School Travel Plans | 0.086 | Apr 05 | Mar 08 | 0.042 | [6 empty] | 0.016 |  |  |  |  | 0.07 | 0.016 | [6 empty] | 0.086 |  | 0.086 | [5 empty] | 0.086 | [11 empty] | 0.086
|  | Neighbourhod learning in deprived communities | 0.061 | [14 empty] | 0.061 | 0 | [6 empty] | 0.061 |  | 0.061 | [16 empty] | 0.061 | 0.061 | LSC grant neighbourhod learning in deprived communities
| e02031 | ICT in Schools | 0.004 |  |  | 0.004 | [6 empty] | 0.004 | [12 empty] | 0.004 |  | 0.004 | [16 empty] | 0.004 | 0.004
|  | CHILDREN'S SERVICES - TOTAL | 11.818 |  |  | 7.592 | 0.34 | 0.341 | 0.351 | 0.435 | 1.444 | 1.456 | 1.636 | 0.93 | 1.093 | 0.931 | 0.97 | 1.891 | 6.929 |  | 0.823 | 0 | 0 | 0.002 | 3.2 | 7.793 | 0 | 11.818 |  | 0 | 0 | 2.092 | 2.507 | 0.086 | 2.606 | 0.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.399 | 7.793
|  | HIGHWAYS | [43 empty] | 0
| D00003 | Cadishead Way Stage 1 | 0 | 1991-01-01 | 1992-03-01 | 0 | [12 empty] | 0 | [8 empty] | 0 | [17 empty] | 0
| D00004 | Cadishead Way Stage 2 | 6.966 | 2004-02-01 | 2005-09-01 | 3.578 | 0.7 |  | 0.711 | 0.711 | 0.711 | 0.711 | 0.711 | 0.711 |  |  |  | 2 | 4.966 |  | 0 | 1.732 |  |  |  | 6.482 |  | 8.214 |  | 6.482 | [15 empty] | 6.482
| D00005 | Manchester/Salford Inner Relief Route | 3.719 | 2001-02-01 | 2004-11-01 | 2.902 | [5 empty] | 2.901 |  | 0.272 | 0.272 | 0.274 |  |  | 3.173 | [6 empty] | 2.527 |  | 2.527 |  | 2.527 | [15 empty] | 2.527
|  | Local Safety schemes | 0.754 | 2004-04-01 | 2005-03-01 | 0.506 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.062833 | 0.50267 | [8 empty] | 0
|  | Bridge Assessment and Strengthening Schemes | 0.558 | 2004-04-01 | 2005-03-01 | 0.201 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.0465 | 0.372 | [8 empty] | 0
|  | Principal Roads Structural Maintenance | 1.723 | 2004-04-01 | 2005-03-01 | 1.088 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 0.14358 | 1.1487 | [8 empty] | 0
|  | Public Transport Schemes | 0.118 |  |  | 0.04 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.0098333 | 0.078667 | [8 empty] | 0
|  | Schemes to Assist Cycling | 0.603 | 2004-04-01 | 2005-03-01 | 0.453 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.05025 | 0.402 | [8 empty] | 0
|  | Other Minor Schemes | 0.479 | 2004-04-01 | 2005-03-01 | 0.277 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.039917 | 0.31933 | [8 empty] | 0
|  | Highway Services Depot Overhead | 0.24 |  |  | 0.18 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.16 | [8 empty] | 0
| 0.028 | Block 3 overprogramming less cfwd receipts | -0.25 | [14 empty] | -0.25 | 0 | [8 empty] | 0
| 0.019 | carryforward cont to salford central | 0.019 | [14 empty] | 0.019 | 0 | [8 empty] | 0
|  | Major schemes anticipated overspend | 0.055 | [14 empty] | 0.055 | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D07230-d07259 | [24 empty] | 0 |  | 0 | [17 empty] | 0
|  | Improvements to the highway network | 0.25 |  |  |  | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.019 | 0.168 | [8 empty] | 0
D99999 7015 contains , 0.250 highways improvement less overprogramming of 0.115 | [20 empty] | 4.126 |  |  |  | 0.297 | 0 | 0.07 | 4.493 | [17 empty] | 0 | 30k contribution from Tesco as part of Section 278 agreement D00939 other half of scheme funded from block 3, 40k sustrans contribution D00808
|  | HIGHWAYS - TOTAL | 15.234 |  |  | 9.225 | 1.0939 | 0.39392 | 1.1049 | 1.1049 | 1.1049 | 4.0059 | 1.1049 | 1.3769 | 0.66592 | 0.66792 | 0.39392 | 2.2159 | 11.2903 |  | 4.126 | 1.732 | 0 | 0 | 0.297 | 9.009 | 0.07 | 15.234 |  | 9.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.009
COMMUNITY, HEALTH AND SOCIAL CARE
| S05106 | The Limes - Fire Safety | 0.026 | [9 empty] | 0.007 | 0.007 | 0.007 | 0.005 |  |  | 0.014 | [5 empty] | 0.026 | 0 |  | 0.026 | [17 empty] | 0
| S05052 | Barton Moss Expansion | 0.13 |  |  | 0.005 | [7 empty] | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 |  |  |  |  | 0.12 |  | 0.01 |  | 0.13 | [16 empty] | 0.01 | 0.01 | barton moss rcco, DFES secure accomodation
| S05107 | White Meadows - Fire Safety | 0.025 |  |  | 0.005 |  |  | 0.005 |  |  | 0.005 | 0.005 | 0.005 | 0.005 |  |  |  | 0.02 | [5 empty] | 0.025 | 0 |  | 0.025 | [17 empty] | 0
| S09008 | Day Services Modernisation Unallocated | 0.002 | [14 empty] | 0.002 | 0 |  | 0.002 |  |  |  |  | 0 |  | 0.002 | [17 empty] | 0
| S05109 | The Limes - Bathroom/laundry/anc space impr | 0.05 |  |  | 0.002 | [6 empty] | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.01 | 0.016 | [5 empty] | 0.05 | 0 |  | 0.05 | [17 empty] | 0
| S02501 | Emerson House |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| S05151 | Modernising Intermediate Care | 0.009 |  |  | 0.005 |  |  |  |  | 0.003 | 0.003 | 0.003 | [5 empty] | 0.009 |  | 0.005 |  |  |  | 0.004 | 0 |  | 0.009 | [17 empty] | 0
| S05112 | Day Services Modernisation | 0.024 |  |  | 0.017 |  |  |  |  | 0.008 | 0.008 | 0.008 | [5 empty] | 0.024 | [5 empty] | 0.024 | 0 |  | 0.024 | [17 empty] | 0
| S05113 | Homes to Trust | 3.308 |  |  | 1.935 | [5 empty] | 0.925 | 0.397 | 0.397 | 0.397 | 0.397 | 0.397 | 0.398 | 1.719 |  |  |  | 3.308 |  |  | 0 |  | 3.308 | [17 empty] | 0
| S06054 | Alexandra House - Bathroom & Toilets | 0.003 |  |  | 0.002 | [5 empty] | 0.003 | [6 empty] | 0.003 | [5 empty] | 0.003 | 0 |  | 0.003 | [17 empty] | 0
| S06152 | Craig Hall Re-roofing | 0.003 |  |  | 0.003 | 0.003 | [11 empty] | 0.003 |  | 0.003 |  |  |  |  | 0 |  | 0.003 | [17 empty] | 0
| S06155 | Waterside - Replacement boiler | 0.016 | [8 empty] | 0.016 | [6 empty] | 0.016 | [5 empty] | 0.016 | 0 |  | 0.016 | [17 empty] | 0
| S06157 | Waterside 05/06 car parking |  |  |  | 0.001 | [19 empty] | 0 | [19 empty] | 0
| S08061 | Crompton House - remodelling of garage | 0.1 | [9 empty] | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0.015 | 0.034 |  | 0.1 |  |  |  |  | 0 |  | 0.1 | [17 empty] | 0
| S09010 | Brierley CC - Demolition stables/gym | 0.008 |  |  | 0.01 |  |  |  |  | 0.003 | 0.003 | 0.002 | [5 empty] | 0.008 | [5 empty] | 0.008 | 0 |  | 0.008 | [17 empty] | 0
| S09011 | Wardley CC - Car park/paved areas resurface | 0.008 | [8 empty] | 0.004 | 0.004 | [5 empty] | 0.008 |  | 0.008 |  |  |  |  | 0 |  | 0.008 | [17 empty] | 0
| S09012 | Wardley CC - Replacement boiler | 0.02 | [9 empty] | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.005 | 0.006 | [5 empty] | 0.02 | 0 |  | 0.02 | [17 empty] | 0
| S09013 | Boothstown CC - Replacement boiler | 0.033 | [9 empty] | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.003 | 0.012 |  | 0.033 |  |  |  |  | 0 |  | 0.033 | [17 empty] | 0
| S08056 | Improving Information Management 2004/2005 | 0.137 |  |  | 0.016 |  |  | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.011 | 0.084 | [5 empty] | 0.1 | 0.037 |  | 0.137 | [16 empty] | 0.037 | 0.037
| S08057 | Integrated Children's Services 2004/5 | 0.057 |  |  | 0 |  |  |  |  | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.008 | 0.028 | [6 empty] | 0.057 |  | 0.057 | [16 empty] | 0.057 | 0.057 | child service grant
| S08058 | Improving Information Management 2005/2006 | 0.248 |  |  | 0.022 |  |  |  |  | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.124 | [5 empty] | 0.1 | 0.148 |  | 0.248 | [16 empty] | 0.148 | 0.148
| S08059 | Integrated Children's Services 2005/6 | 0.086 |  |  | 0 |  |  |  |  | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.009 | 0.044 | [6 empty] | 0.086 |  | 0.086 | [16 empty] | 0.086 | 0.086
| S04004 | Mental Health - S C E (2002/2004) |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| S04005 | Mental Health - S C E (2003) |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| S04006 | Mental Health - S C E (2004/2005) | 0.126 |  |  | 0.101 |  |  |  | 0.005 |  | 0.03 | 0.025 | 0.021 | 0.029 | 0.016 |  |  | 0.081 |  |  | 0.106 |  |  |  | 0 | 0.02 | 0.126 | [17 empty] | 0 | .020 mental health contribution
| S04007 | Mental Health - S C E (2005/2006) | 0.128 |  |  | 0.001 | [7 empty] | 0.025 | 0.025 | 0.025 | 0.025 | 0.028 |  |  |  | 0.128 |  |  |  | 0 |  | 0.128 | [17 empty] | 0
| S09003 | Boothstown / Worsley C C Refurb - Retention | 0.002 | [6 empty] | 0.002 | [8 empty] | 0.002 | [6 empty] | 0 | 0.002 | 0.002 | [17 empty] | 0 | .002 community contribution
| S09005 | Wardley Community Centre - Retention | 0.002 | [6 empty] | 0.002 | [8 empty] | 0.002 | [6 empty] | 0 | 0.002 | 0.002 | [17 empty] | 0 | .002 community contribution
| S09007 | Womens Centre | 0.006 | [5 empty] | 0.003 | 0.003 | [8 empty] | 0.006 | [6 empty] | 0 | 0.006 | 0.006 | [17 empty] | 0 | .006 community contribution
| S00001 | Alterations to Properties - Foster Carers | 0.036 |  |  | 0.02 |  |  |  | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.02 |  |  |  |  | 0.036 |  | 0 |  | 0.036 | [17 empty] | 0
| S06051 | Humphrey Booth L B - Booth's Charity Funded | 0.019 |  |  | 0.027 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.004 | [6 empty] | 0.019 | [6 empty] | 0 | 0.019 | 0.019 | [17 empty] | 0 | .019 humphrey booth
| S06052 | Humphrey Booth Ordsall - Booth's Charity Funded | 0.031 |  |  | 0.019 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.006 | [6 empty] | 0.031 | [6 empty] | 0 | 0.031 | 0.031 | [17 empty] | 0 | .031 humphrey booth
| S09101 | STASH Day Centre | 0.165 |  |  | 0.168 |  |  |  | 0.033 | 0.033 | 0.033 | 0.033 | 0.033 |  |  |  |  | 0.165 | [6 empty] | 0.05 | 0.115 | 0.165 | [16 empty] | 0.05 | 0.05
| S01003 | Sutherland House Refurbishment | 0.079 |  |  | 0.076 |  |  |  |  | 0.015 | 0.04 | 0.022 |  |  |  |  | 0.002 | 0.077 | 2005-07-04 | [5 empty] | 0 | 0.079 | 0.079 | [17 empty] | 0
| S05006 | The Grange - Playroom |  |  |  | 0.001 | [19 empty] | 0 |  | 0 | [17 empty] | 0
| S05007 | Station Road |  |  |  | 0.008 | [19 empty] | 0 |  | 0 | [17 empty] | 0
| S06102 | St Georges - Kitchen |  |  |  | 0.036 | [19 empty] | 0 |  | 0 | [17 empty] | 0
| S06151 | Waterside Resource Centre | [16 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
|  | COMMUNITY, HEALTH AND SOCIAL CARE -TOTAL | 4.887 |  |  | 2.488 | 0.011 | 0.008 | 0.03 | 0.071 | 0.137 | 1.147 | 0.607 | 0.615 | 0.59 | 0.57 | 0.549 | 0.552 | 2.524 |  | 0.151 | 0.234 | 3.308 | 0.156 | 0.376 | 0.388 | 0.274 | 4.887 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.388 | 0.388
ENVIRONMENTAL SERVICES
| F00022 | Parks Infrastructure Improvements | 0.111 |  |  | 0.002 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.00925 | 0.074 | [5 empty] | 0.097 | 0 | 0.014 | 0.111 | [17 empty] | 0 | 0.014 boundary road irlam s106 use as capital receipts this year,
| F00032 | Lightoaks Park | 0.026 |  |  | 0.012 | [11 empty] | 0.026 | 0 | 2005-05-09 |  |  |  |  | 0.02 | 0.006 |  | 0.026 | [16 empty] | 0.006 | 0.006 | greening greater manchester
| F00033 | Princes Park Tennis Court | 0.017 |  |  | 0.014 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.011333 | [5 empty] | 0.017 | 0 |  | 0.017 | [17 empty] | 0
| F10001 | Parr Fold Pavillion | 0.272 |  |  | 0.166 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.022667 | 0.18133 | [5 empty] | 0.134 | 0 | 0.138 | 0.272 | [17 empty] | 0 | 0.138 insurance money
| F00010 | Mandley Park | 0.101 |  |  | 0.073 | [11 empty] | 0.101 | 0 | 2005-01-27 |  |  |  | 0.003 |  | 0.098 |  | 0.101 | [12 empty] | 0.098 |  |  |  |  | 0.098
| F00011 | Lightoaks Park NOF | 0.066 |  |  | 0.265 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.0055 | 0.044 | [6 empty] | 0.066 |  | 0.066 | [12 empty] | 0.066 |  |  |  |  | 0.066
| F00011 | Eccles Recreation Grd/ Albert Park MUGA | 0.08 |  |  |  | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.0066667 | 0.053333 | [6 empty] | 0.08 |  | 0.08 | [12 empty] | 0.08 |  |  |  |  | 0.08
| F00011 | Albert Park | 0.047 |  |  |  | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.0039167 | 0.031333 | [6 empty] | 0.047 |  | 0.047 | [12 empty] | 0.047 |  |  |  |  | 0.047
| F00011 | Winton park | 0.129 |  |  |  | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.01075 | 0.086 | [6 empty] | 0.129 |  | 0.129 |  |  |  |  | 0.085 | [7 empty] | 0.044 |  |  |  |  | 0.129
| F00030 | Eccles Recreation Grd | 0.017 |  |  |  | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.011333 | [6 empty] | 0 | 0.017 | 0.017 | [17 empty] | 0 | 0.017 eccles rec section 106
| F00013 | Beechfarm Lottery | 0.104 |  |  | 0.094 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.0086667 | 0.069333 | [6 empty] | 0.104 |  | 0.104 | [12 empty] | 0.104 |  |  |  |  | 0.104
| F00014 | Princes Park | 0.093 |  |  | 0.076 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.062 | [6 empty] | 0.077 | 0.016 | 0.093 | [12 empty] | 0.077 |  |  |  |  | 0.077 | 0.016 bmx bandits community contribution
| F00017 | Croal Irwell Access/Fencing section 106 | 0.028 |  |  | 0.024 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.0023333 | 0.018667 |  |  |  |  | 0.004 |  | 0 | 0.024 | 0.028 | [17 empty] | 0 | 0.024 section 106, 0.004 parks grounds maintenance budget
| F00018 | Sharp Street, Walkden section 106 | 0.04 |  |  | 0.04 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.026667 | [6 empty] | 0 | 0.04 | 0.04 | [17 empty] | 0 | section 106
| F00025 | Peel Park section 106 | 0.024 |  |  | 0.024 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.016 | [6 empty] | 0 | 0.024 | 0.024 | [17 empty] | 0 | section 106
| F00004 | Cemetery Roadways | 0.059 |  |  |  | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.0049167 | 0.039333 | [5 empty] | 0.059 | 0 |  | 0.059 | [17 empty] | 0
| F00007 | Buille Hill Park Restoration | 0.184 |  |  | 0.008 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.12267 | [5 empty] | 0.184 | 0 |  | 0.184 | [17 empty] | 0
| F00008 | Cemetery Headstones | 0.055 |  |  | 0.003 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.0045833 | 0.036667 | [5 empty] | 0.055 | 0 |  | 0.055 | [17 empty] | 0
| F00023 | Recycling Bring Sites | 0.025 |  |  | 0.027 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.0020833 | 0.016667 | [5 empty] | 0.025 | 0 |  | 0.025 | [17 empty] | 0
| F00024 | SCE Crofters Heights | 0.005 |  |  | 0.005 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.0033333 |  |  | 0.005 |  |  |  | 0 |  | 0.005 | [17 empty] | 0
| F000 | Waste Performance Efficiency Grant | 0.095 |  |  |  | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.0079167 | 0.063333 | [6 empty] | 0.095 |  | 0.095 | [16 empty] | 0.095 | 0.095
| F00021 | Chesnut Ave Depot |  |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| f00034 | Hancocks Tip Site Investigation | 0.071 |  |  | 0.021 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.0059167 | 0.047333 |  |  | 0.071 |  |  |  | 0 |  | 0.071 | [17 empty] | 0
| f20001 | Robin Hood sidings | 0.016 |  |  |  | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.0013333 | 0.010667 |  |  | 0.016 |  |  |  | 0 |  | 0.016
| F00035 | Wheeled Bins | 0.03 |  |  |  | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.02 |  |  |  | 0.03 |  |  | 0 |  | 0.03 | [17 empty] | 0
| F00031 | St Marys Park Playground | 0.113 | [14 empty] | 0.113 | 0 | [6 empty] | 0 | 0.113 | 0.113 | 2005-10-24 | [17 empty] | 0.113 section 106 George Wimpey, restawhile at oakham trading estate
| F00037 | Beechfarm playing fields drainage | 0.161 |  |  | 0.021 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.013417 | 0.10733 |  |  |  |  | 0.03 |  | 0.122 | 0.009 | 0.161 | 2005-12-05 | [15 empty] | 0.122 | 0.122 | 0.122 football foundation
[26 empty] | 0 |  | 0 | [17 empty] | 0
|  | ENVIRONMENTAL SERVICES - TOTAL | 1.969 |  |  | 0.877 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.14408 | 0.38408 | 1.1527 |  | 0 | 0.092 | 0.03 | 0.037 | 0.591 | 0.824 | 0.395 | 1.969 |  | 0 | 0 | 0 | 0.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.516 | 0 | 0 | 0 | 0.223 | 0.824
ARTS & LEISURE
partially adjusted via control 04/05 | w00001 | City wide investment | 0.218 |  |  | 0.149 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.14533 |  |  |  | 0.218 |  |  | 0 |  | 0.218 | [17 empty] | 0
| E05703 | Winton Community Library | 0.004 |  |  |  | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.00033333 | 0.0026667 | [5 empty] | 0.004 | 0 |  | 0.004 | [17 empty] | 0
| e05030 | Cleavley Athletic Track | 0.093 |  |  | 0.05 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.00775 | 0.062 | [5 empty] | 0.091 | 0.002 |  | 0.093 | [12 empty] | 0.002 |  |  |  |  | 0.002
| e05031 | DDA arts and leisure | 0.044 |  |  | 0.012 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.029333 | [5 empty] | 0.044 | 0 |  | 0.044 | [17 empty] | 0
| E05032 | Efficiency Improvements | 0.003 |  |  |  | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.002 | [5 empty] | 0.003 | 0 |  | 0.003 | [17 empty] | 0
| e05033 | Sports Village | 1.733 |  |  | 1.715 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 0.14442 | 1.1553 | [5 empty] | 0.197 | 1.536 | 0 | 1.733 | [11 empty] | 0.639 |  |  |  |  | 0.897 | 1.536
| e05037 | Ordsall Recreation Centre | 0.017 |  |  | 0.008 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.011333 |  |  |  |  | 0.017 |  | 0 |  | 0.017 | [17 empty] | 0
| E05041 | Roller Hockey Relocation | 0.026 |  |  | 0.016 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.0021667 | 0.017333 |  |  |  |  | 0.013 |  | 0 | 0.013 | 0.026 | [17 empty] | 0 | 0.013 scl contribution,
| E05042 | Leisure CCTV |  |  |  | 0.013 | [19 empty] | 0 |  | 0 | [17 empty] | 0
| E05038 | Arts and Leisure - Broughton Pool additional scheme | 0.017 |  |  | 0.026 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.0014167 | 0.011333 | [6 empty] | 0 | 0.017 | 0.017 | [17 empty] | 0 | 0.017 cont from SCL
|  | Arts and Leisure - Irlam Pool additional scheme | 0.03 |  |  |  | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.02 | [6 empty] | 0 | 0.03 | 0.03 | [17 empty] | 0 | 0.030 cont from SCL
|  | Eccles Youth Centre | 0.01 |  |  |  | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.0066667 | [5 empty] | 0.01 | 0 |  | 0.01 | [17 empty] | 0
|  | Hope Library | 0.005 |  |  |  | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.00041667 | 0.0033333 | [6 empty] | 0 | 0.005 | 0.005 | [17 empty] | 0 | NHS contribution
|  | Library service computerisation | 0.014 |  |  |  | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0011667 | 0.0093333 | [5 empty] | 0.014 | 0 |  | 0.014 | [17 empty] | 0
|  | SPACE | 0.04 |  |  | 0.055 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.026667 | [6 empty] | 0.04 |  | 0.04 | [12 empty] | 0.04 |  |  |  |  | 0.04
| E05036 | Orthodox Jewish school | 0.127 |  |  | 0.006 | [8 empty] | 0.06 | 0.067 |  |  | 0 | 2005-10-17 | [5 empty] | 0.115 | 0.012 | 0.127 | [12 empty] | 0.115 |  |  |  |  | 0.115 | 0.012 school contribution
| E05015 | Clarendon | 0.289 |  |  | 0.245 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.024083 | 0.19267 |  |  |  |  | 0.05 |  | 0.186 | 0.053 | 0.289 | [12 empty] | 0.186 |  |  |  |  | 0.186
| E05013 | Irlam | 0.12 |  |  | 0.009 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | [6 empty] | 0.12 |  | 0.12 | [12 empty] | 0.12 |  |  |  |  | 0.12
| E05011 | Lledr Hall and additional building works | 0.88 |  |  | 0.797 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.58667 |  |  |  | 0.095 | 0.123 |  | 0.639 | 0.023 | 0.88 | [12 empty] | 0.639 |  |  |  |  | 0.639
| E05027 | Fit City Worsley | 0.153 |  |  | 0.137 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.01275 | 0.102 | [5 empty] | 0.153 | 0 |  | 0.153 | [17 empty] | 0
| E05019 | St Ambrose Barlow | 0.015 |  |  | 0.015 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.01 | [6 empty] | 0.015 |  | 0.015 | [12 empty] | 0.015 |  |  |  |  | 0.015
| E05021 | St Patricks | 0.063 |  |  | 0.063 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.00525 | 0.042 | [6 empty] | 0.063 |  | 0.063 | [12 empty] | 0.063 |  |  |  |  | 0.063
| E05043 | Bridgewater FC faclity | 0.464 |  |  | 0.1 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.038667 | 0.30933 | [6 empty] | 0 | 0.464 | 0.464 | [17 empty] | 0 | Greenbank trust .092, peel investments 0.098, bridgewater fc 0.019, football foundation 0.266
| E05034 | Talmud Torah | 0.015 |  |  | 0.001 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.00125 | 0.01 | [6 empty] | 0.015 |  | 0.015 | [12 empty] | 0.015 |  |  |  |  | 0.015
|  | Porfolio manager | 0.018 |  |  |  | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.012 | [6 empty] | 0.018 |  | 0.018 | [12 empty] | 0.018 |  |  |  |  | 0.018
|  | CSD Officers | 0.114 | [14 empty] | 0.114 | 0 | [6 empty] | 0.114 |  | 0.114 | [12 empty] | 0.114 |  |  |  |  | 0.114
|  | Eccles Recreation centre fitness equipment | 0.07 | [12 empty] | 0.03 | 0.03 | 0.01 | 0 |  |  |  | 0.07 |  |  | 0 |  | 0.07
| E05040 | Clarendon Fitness centre | 0.02 |  |  | 0.017 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.0016667 | 0.013333 | [6 empty] | 0.014 | 0.006 | 0.02 | [16 empty] | 0.014 | 0.014 | 0.006 scl contribution
[26 empty] | 0 |  | 0
|  | ARTS & LEISURE - TOTAL | 4.602 |  |  | 3.434 | 0.35758 | 0.35758 | 0.35758 | 0.35758 | 0.35758 | 0.35758 | 0.35758 | 0.35758 | 0.41758 | 0.45458 | 0.38758 | 0.48158 | 2.8607 |  | 0 | 0 | 0.383 | 0.203 | 0.516 | 2.877 | 0.623 | 4.602 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.639 | 1.327 | 0 | 0 | 0 | 0.911 | 2.877
CUSTOMER AND SUPPORT SERVICES
| C00059 7027 | Software Development | 2.225 | [14 empty] | 2.225 | 0 | [5 empty] | 2.225 | 0 |  | 2.225 | [17 empty] | 0
adjusted via control 04/05 | c00063 7015 | Data Centre | 0.164 |  |  |  | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.013667 | 0.10933 |  |  |  | 0.164 |  |  | 0 | 0 | 0.164 | [17 empty] | 0
| C00063 7025 | Data centre ancillaries | 0.145 |  |  | 0.143 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.012083 | 0.096667 |  |  |  | 0.145 |  |  | 0 |  | 0.145 | [17 empty] | 0
adjusted via control 04/05 | C00064 | Replacement Council Tax system | 0.123 |  |  | 0.123 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.01025 | 0.082 |  |  |  | 0.123 |  |  | 0 |  | 0.123 | [17 empty] | 0
| C00069 | Upgrading IT training rooms | 0.012 |  |  | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.008 | [5 empty] | 0.012 | 0 |  | 0.012 | [17 empty] | 0
on revenue journalled at year end | C00062 | Highways depot | 0.039 | [14 empty] | 0.039 | 0 | [5 empty] | 0.039 | 0 |  | 0.039 | [17 empty] | 0
| C00054 | Schools networking lease |  |  |  | 0.007 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
|  | Members IT equipment | 0.059 | [11 empty] | 0.059 |  |  |  | 0 |  |  |  | 0.059 |  |  | 0 |  | 0.059 | [17 empty] | 0
| C00067 | Implementing e government | 0.15 |  |  | 0.046 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.1 | [6 empty] | 0.15 |  | 0.15 | [16 empty] | 0.15 | 0.15 | e governmnent grant 05/06
|  | CUSTOMER AND SUPPORT SERVICES - TOTAL | 2.917 |  |  | 0.32 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | 0.1085 | 0.0495 | 0.0495 | 2.3135 | 0.396 |  | 0 | 0 | 0.491 | 0 | 2.276 | 0.15 | 0 | 2.917 | [16 empty] | 0.15 | 0.15
CHIEF EXECUTIVE
|  | NDC | 1.267 |  |  | 0.052 | [11 empty] | 1.267 | 0 | [6 empty] | 1.267 |  | 1.267 | [10 empty] | 0.163 | 1.104 | [5 empty] | 1.267
| A30003 | Salford Innovation Park | 0.157 |  |  | 0.06 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.013083 | 0.10467 |  |  |  | 0 |  |  | 0.157 |  | 0.157 | [10 empty] | 0.147 | 0.01 | [5 empty] | 0.157
|  | Crescent Police Station |  |  |  | 0.014 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
|  | Central Salford | 0.05 |  |  | 0.048 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.033333 | [5 empty] | 0.05 | 0 |  | 0.05 | [17 empty] | 0 | chapel st receipts slipped from 0405
| A00009 | Expanding Boundaries |  |  |  | 0.118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
|  | Gateway | 0.64 | [13 empty] | 0 | 0.64 | 0 | [6 empty] | 0.64 |  | 0.64 | [11 empty] | 0.61 |  |  |  |  | 0.03 | 0.64
|  | Environmental/Shop Parade Improvements | 0.1 |  |  |  | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.066667 | [6 empty] | 0.05 | 0.05 | 0.1 | [11 empty] | 0.05 | [5 empty] | 0.05
|  | Chapel st receipts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  | Economic Development | 0.15 |  |  |  | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.1 | [5 empty] | 0.15 | 0 |  | 0.15 | [17 empty] | 0
|  | Cultural Quarter | 0.07 |  |  |  | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.0058333 | 0.046667 | [5 empty] | 0.07 | 0 |  | 0.07 | [17 empty] | 0
|  | Public Realm Improvements | 0.05 |  |  |  | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.0041667 | 0.033333 | [5 empty] | 0.05 | 0 |  | 0.05 | [17 empty] | 0
|  | Chapel Street Walking Plan | 0.061 |  |  |  | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.0050833 | 0.040667 | [5 empty] | 0.05 | 0 | 0.011 | 0.061 | [17 empty] | 0 | chapel st receipts section 106
|  | Contribution to URC Business Plan | 0.218 |  |  |  | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.018167 | 0.14533 | [5 empty] | 0.218 | 0 |  | 0.218 | [17 empty] | 0
| A40112 | BBC Consultants |  |  |  | 0.004 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| A20050 | A6 works for URC |  |  |  | 0.011 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D01425&D01450 | Chapel Street/URC (04/05 Slippage) | 0.179 |  |  |  | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.014917 | 0.11933 | [5 empty] | 0.179 | 0 |  | 0.179 | [17 empty] | 0
|  | Riverside Bowling and Leisure Activity Centre | 0.165 |  |  |  | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.01375 | 0.11 | [6 empty] | 0.165 |  | 0.165 | [11 empty] | 0.165 | [5 empty] | 0.165
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0
|  | CHIEF EXECUTIVE - TOTAL | 3.107 |  |  | 0.307 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2.007 | 0.8 |  | 0 | 0 | 0 | 0 | 0.767 | 2.279 | 0.061 | 3.107 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31 | 1.939 | 0 | 0 | 0 | 0 | 0.03 | 2.279
PLANNING SERVICES
| D07016 | Manchester Bolton Bury Canal | 0.705 |  |  | 0.062 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.05875 | 0.47 |  |  |  | 0.667 |  | 0.038 | 0 |  | 0.705 | [17 empty] | 0
| D01901 A30001 | Liverpool Road Eccles | 0.124 |  |  | 0.017 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.010333 | 0.082667 | [5 empty] | 0 | 0.124 |  | 0.124 | [9 empty] | 0.024 | [6 empty] | 0.1 | 0.124 | 0.064 srb, 0.1 NRF,
|  | Purchase of Meadow Road Campus | 2.8 |  |  | 0.021 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 0.23333 | 1.8667 | 2005-07-04 |  |  |  |  | 2.8 | 0 |  | 2.8 | [18 empty] | 2.8m purchase and receipt not shown on programme or receipts forecast
|  | Purchase of Hulme St Nursery | 0.3 |  |  |  | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.2 | [5 empty] | 0.3 | 0 |  | 0.3
|  | Purchase of Church St Eccles | 0.36 | [14 empty] | 0.36 | 0 | [5 empty] | 0.36 | 0 |  | 0.36 | [17 empty] | 0
| D02151 | Detroit Bridge | 0.58 |  |  | 0.532 |  |  | 0.074 | 0.074 | 0.075 | 0.113 | 0.113 | 0.113 |  |  |  | 0.018 | 0.562 | 2005-04-18 |  |  |  |  | 0.345 | 0 | 0.235 | 0.58 | [17 empty] | 0
| D07024 and D08064 | City Academy Access Road | 0.04 |  |  | 0.012 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.0033333 | 0.026667 | [5 empty] | 0.04 | 0 |  | 0.04 | [17 empty] | 0
| D00050 | Investment in the Highways | 5 |  |  | 2.323 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 3.3333 |  |  |  | 5 |  |  | 0 |  | 5 | [17 empty] | 0
|  | Eccles Town Centre Slipped from 04/05 | 0.01 |  |  | 0.007 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.0066667 | [5 empty] | 0.01 | 0 |  | 0.01 | [17 empty] | 0
|  | Red City Developments | 0.03 | [7 empty] | 0.03 | [7 empty] | 0.03 | 2005-06-27 |  |  |  |  | 0.03 | 0 |  | 0.03
|  | NHS LIFT - Walkden | 0.237 |  |  |  | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.01975 | 0.158 | [6 empty] | 0.237 |  | 0.237 | [16 empty] | 0.237 | 0.237
|  | Swinton Library temporary relocation | 0.186 |  |  |  | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.0155 | 0.124 | [6 empty] | 0 | 0.186 | 0.186 | [17 empty] | 0 | lift enabling fund
| C00060 and D07008 | Ordsall Neighbourhood office | 0.395 |  |  | 0.377 | 0.023 | 0.065 | 0.085 | 0.085 | 0.08 | 0.032 | 0.012 | 0.005 | 0.008 |  |  |  | 0.387 |  |  |  |  | 0.034 | 0.172 | 0.174 | 0.015 | 0.395 |  |  |  |  | 0.174 | [12 empty] | 0.174 | .118 office moves budget
| D06071 | LIVIA Community Engagement Programme | 0.103 |  |  | 0.052 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.0085833 | 0.068667 | [6 empty] | 0.103 |  | 0.103 | [13 empty] | 0.1 |  |  | 0.003 | 0.103 | CEP grant
| D01958 | Newlands (LIVIA) | 0.1 |  |  | 0.001 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.066667 | [5 empty] | 0.1 | 0 |  | 0.1 | [13 empty] | 0 |  |  |  | 0
| D07200-d07229 | Disabled Access Improvements | 0.239 |  |  | 0.075 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.019917 | 0.15933 | [5 empty] | 0.239 | 0 |  | 0.239 | [17 empty] | 0
| D07401 | Frederick Road/Camp Street | 0.052 | 2005-08-01 | 2005-12-01 | [7 empty] | 0.02 | 0.025 | 0.007 |  |  |  | 0.045 | 2005-08-08 | [5 empty] | 0.052 |  | 0.052 | [16 empty] | 0.052 | 0.052 | Dealing with the Disadvantaged DoT Neighbourhood Road Safety Initiative grant
| D07400 | Langworthy Area - Traffic Calming Scheme | 0.217 | 2005-08-01 | 2005-12-01 | 0.137 | [5 empty] | 0.037 | 0.05 | 0.05 | 0.05 | 0.03 |  |  | 0.137 | 2005-08-08 |  |  |  |  | 0 | 0.217 |  | 0.217 | [16 empty] | 0.217 | 0.217 | Dealing with the Disadvantaged DoT Neighbourhood Road Safety Initiative grant
| d08000 | [17 empty] | 0 | [6 empty] | 0 |  | 0
| D08006 |  |  |  |  | 0.001
| d08024 | Adelphi Project stretch |  |  |  | 0.009 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08026 | Higher Broughton Regeneration |  |  |  | 0.07 | [12 empty] | 0 | [6 empty] | 0 | 0 | 0
| d08030 |  |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08034 | Swinton Design plans |  |  |  | 0.007 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08035 | Oakwood section 106 |  |  |  | 0.003 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08036 | LIFT project |  |  |  | 0.066 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08040 |  |  |  |  | 0 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08041 | [17 empty] | 0 | [5 empty] | 0 | 0 |  | 0
| D08044 | Seedley School |  |  |  | 0.002
| d08045 | Ordsall Primary School |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08046 | Higher Broughton Schools |  |  |  | 0.001
| d08048 | [17 empty] | 0 | [6 empty] | 0 |  | 0
| d08051 | Newlands initiative |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08052 | Walkden pool refurbishment |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08055 | Primary School Review |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08059 | Lower Broughton Regeneration |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08060 | Chapel St Pedestrianisation |  |  |  | 0.011 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08064 | City Academy - Verdant Lane Survey |  |  |  | 0.016 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08066 | Ordsall Development Framework |  |  |  | 0.029 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08067 | Higher Broughton Communtiy Hub |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| d08069 | Land Exchange SCC +UoS Ground Investigation |  |  |  | 0.027 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0
on sap d99999 7027 |  | Advance Fees | 0.1 |  |  | 0.26 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.066667 | [5 empty] | 0.1 | 0 |  | 0.1 | [17 empty] | 0
| D07013 | Relocation of Soc servs to Emerson House | 0.1 |  |  | 0.018 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.066667 | [5 empty] | 0.02 | 0.08 |  | 0.1 | [16 empty] | 0.08 | 0.08 | lift enabling fund
|  | disp starts here | [16 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06108 | Demolition Windsor School |  |  |  | 0.009 | [12 empty] | 0
| D06110 | Disposal Buille Hill |  |  |  | 0.003 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06115 | Lowry High School Salford 7 |  |  |  | 0.004
| D06116 | Disposal PCL/Chapel Street |  |  |  | 0.004 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06117 | Salford Shopping City |  |  |  | 0.006 | [12 empty] | 0
| D06118 | Demolition New Croft |  |  |  | 0.057 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06121 | Land at Sovereign Street |  |  |  | 0.002 | [12 empty] | 0
| D06122 | Demolition Ordsall District Centre |  |  |  | 0.065 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06123 | Disposal Chapel Wharf |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0
| D06126 | Land Adjacent to Duchy Inn |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06127 | Adelphi St and Meadow Road |  |  |  | 0.009 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D06129 | Demolition of police station stanwell road |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0
0 | [18 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0
on sap d99999 7027 |  | Disposal Costs | 0.166 |  |  | 0.166 | 0.166 | [11 empty] | 0.166 | [5 empty] | 0.166 | 0 |  | 0.166 | [17 empty] | 0
| D07020 | Former Police Station, Stanwell Road ** | 0.735 |  |  | 0.699 |  |  |  | 0.685 |  | 0.05 | [6 empty] | 0.735 | 2005-06-06 |  |  |  |  | 0.735 | 0 |  | 0.735
|  | Higher Broughton Community Hub ** | 0.1 |  |  | 0.007 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.0083333 | 0.066667 | [5 empty] | 0.1 | 0 |  | 0.1
|  | Demolition Newcroft High School | 0.058 |  |  | 0.057 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.0048333 | 0.038667 | [5 empty] | 0.058 | 0 |  | 0.058
| d06053-d06071 | NWDA Headroom projects |  |  |  | 0.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0
|  | LIVIA | 0.069 | [14 empty] | 0.069 | 0 | [5 empty] | 0.006 | 0.063 |  | 0.069 | [16 empty] | 0.063 | 0.063
|  | NWDA Tatton Park | 0.026 | [14 empty] | 0.026 | 0 | [5 empty] | 0 | 0.026 |  | 0.026 | [13 empty] | 0.026 |  |  |  | 0.026
|  | Oakwood Section 106 | 0.009 | [14 empty] | 0.009 | 0 | [5 empty] | 0 | 0 | 0.009 | 0.009 | [17 empty] | 0 | section 106
|  | Eccles Town hall auditorium | 0.004 | [14 empty] | 0.004 | 0 | [5 empty] | 0.004 | 0 |  | 0.004 | [17 empty] | 0
|  | Countryside Programme | 0.01 | [14 empty] | 0.01 | 0 | [5 empty] | 0.01 | 0 |  | 0.01 | [17 empty] | 0
|  | Barton SES | 0.075 | [14 empty] | 0.075 | 0 | [5 empty] | 0.075 | 0 |  | 0.075 | [17 empty] | 0
| D03600 | conserving and developing Ordsall Hall | 0.148 |  |  | 0.058 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.012333 | 0.098667 |  |  |  |  | 0.009 | 0.139 | 0 |  | 0.148 | [17 empty] | 0 | .005 e&L rcco, 0.004 arts and leisure RCCO, see sept mon depts
|  | SRB | 0.001 |  |  | 0.001 | [11 empty] | 0.001 | 0 | [5 empty] | 0.001 | 0 |  | 0.001 | [17 empty] | 0
D07018 | Summary | Corporate Office Moves Plan | 1.484 |  |  | 0.002 | [7 empty] | 0.185 | 0.185 | 0.371 | 0.371 | 0.372 | 0.185 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D07018 | Wimpey Building | [22 empty] | 0.489 | 0 |  | 0.489 | [17 empty] | 0
| D07018 | Desktop implementation team A Partington | [22 empty] | 0.019 | 0 |  | 0.019 | [17 empty] | 0
|  | Turpike house | [22 empty] | 0.055 |  |  | 0.055
|  | Desktop implementation team 3 posts | [22 empty] | 0.046 |  |  | 0.046
| c00068 | Relocation of customer services contact centre |  |  |  | 0.113 | [18 empty] | 0.208 |  |  | 0.208
| D07018 | Minerva |  |  |  | 0.009 | [18 empty] | 0.034 | 0 |  | 0.034 | [17 empty] | 0
|  | Crompton | [22 empty] | 0.095 |  |  | 0.095
|  | Unity House | [22 empty] | 0.14 |  |  | 0.14
|  | Other Moves | [22 empty] | 0.121 |  |  | 0.121
|  | Civic Centre phases 1 &2 | [22 empty] | 0.277 |  |  | 0.277
| D07026 | Auditorium Turnpike House | 0.191 |  |  |  | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.015917 | 0.12733 | [5 empty] | 0.191 | 0 |  | 0.191 | [17 empty] | 0
| c00068 | Call Centre Relocation- building works | 0.044 |  |  | 0.023 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.029333 | [5 empty] | 0.044 | 0 |  | 0.044 | [17 empty] | 0
| D07027 | Civic Centre Reception Refurbishment | 0.045 |  |  | 0.049 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.00375 | 0.03 | [5 empty] | 0.045 | 0 |  | 0.045 | [17 empty] | 0
| D07028 | Trinity Park |  |  |  | 0.007 | [19 empty] | 0 |  | 0 | [17 empty] | 0
| D07014 | Quays Maintenance Office Move | 0.003 |  |  | 0.003 | [11 empty] | 0.003 | 0 | [5 empty] | 0.003 | 0 |  | 0.003 | [17 empty] | 0
| D07260-D07299 | Footpath works | 0.184 |  |  | 0.006 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.015333 | 0.12267 | [5 empty] | 0.184 | 0 |  | 0.184 | [17 empty] | 0
|  | relocation Tourist Inofrmation Centre | 0.001 | [14 empty] | 0.001 | 0 | [5 empty] | 0.001 | 0 |  | 0.001 | [17 empty] | 0
| D03501 | Pendleton Church Area Study |  |  |  | 0.125 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D03502 | Highway and Community Safety | 0.03 |  |  | 0.004 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.02 | [6 empty] | 0.03 |  | 0.03 | [11 empty] | 0.03 | [5 empty] | 0.03
| D03503 | Minor Works Fund | 0.01 |  |  | 0.003 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.00083333 | 0.0066667 | [6 empty] | 0.01 |  | 0.01 | [11 empty] | 0.01 | [5 empty] | 0.01
| D03505 | Physical Design Strategy |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [17 empty] | 0
| D03506 | Mini Bus | 0.006 |  |  | 0.002 | [6 empty] | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.002 | [6 empty] | 0.006 |  | 0.006 | [11 empty] | 0.006 | [5 empty] | 0.006
|  | River Irwell Walkway | 0.07 | [10 empty] | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | [6 empty] | 0 | 0.07 | 0.07 | [17 empty] | 0 | section 106
| D08018 D08053 | Salford Shopping Food Retail Development | 0.054 |  |  | 0.193 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.0045 | 0.036 | [5 empty] | 0.014 | 0 | 0.04 | 0.054 | [17 empty] | 0 | .016 salford shopping city, 0.016 tescos, 0.008 GMPTE
empty c00060 | [23 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | [12 empty] | 0
|  | PLANNING SERVICES - TOTAL | 15.201 |  |  | 5.431 | 1.098 | 0.974 | 1.068 | 1.753 | 1.094 | 1.141 | 1.105 | 1.302 | 1.174 | 1.325 | 1.295 | 1.872 | 9.535 |  | 0 | 0 | 5.667 | 0.043 | 7.814 | 1.122 | 0.555 | 15.201 |  | 0 | 0 | 0 | 0.174 | 0 | 0 | 0 | 0 | 0.024 | 0 | 0.046 | 0 | 0.126 | 0 | 0 | 0.752 | 1.122
|  | 05/06 PROGRAMME TOTAL | 112.95 |  |  | 62.464 | 7.1134 | 5.1454 | 7.0974 | 9.8294 | 9.1334 | 12.7894 | 9.9724 | 9.5594 | 8.9404 | 8.4394 | 8.4344 | 16.4954 | 68.6273 |  | 10.581 | 2.058 | 9.879 | 1.441 | 22.966 | 64.035 | 1.99 | 112.95 |  | 9.009 | 0 | 2.092 | 2.766 | 0.086 | 2.606 | 0.103 | 0.784 | 1.597 | 0.889 | 4.214 | 1.843 | 0.126 | 18.22 | 0 | 19.7 | 64.035
|  | Education contribution to cap'n of revenue | [18 empty] | 0.2 |  |  |  | -0.2 |  |  | 0
|  | Education SB adjustment | [18 empty] | 6.8 |  |  |  | -6.8 |  |  | 0
|  | EFFECT OF 04/05 OUTTURN | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROGRAMME TOTAL | 112.95 |  |  | 62.464 | 7.1134 | 5.1454 | 7.0974 | 9.8294 | 9.1334 | 12.7894 | 9.9724 | 9.5594 | 8.9404 | 8.4394 | 8.4344 | 16.4954 | 68.6273 |  | 17.581 | 2.058 | 9.879 | 1.441 | 15.966 | 64.035 | 1.99 | 112.95 |  | 9.009 | 0 | 2.092 | 2.766 | 0.086 | 2.606 | 0.103 | 0.784 | 1.597 | 0.889 | 4.214 | 1.843 | 0.126 | 18.22 | 0 | 19.7 | 64.035
** Shown as funded by capital receipts, if receipts are unavailable unsupported borrowing will be used
Private sector housing loan to partnership £0.466m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Private sector housing land at elton st £0.690m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Private sector housing premises at Great Clowes St £0.300m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Timing adjustments
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
[26 empty] | 0 |  | 0 | [17 empty] | 0
|  | Red Rose Scheme | [23 empty] | 0 |  | 0 | [17 empty] | 0
|  | Total | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resources total (includes receipts required) | 112.95 | [17 empty] | 10.581 | 2.058 | 9.879 | 1.441 | 22.966 | 64.035 | 1.99 | 112.95 |  | 9.009 | 0 | 2.092 | 2.766 | 0.086 | 2.606 | 0.103 | 0.784 | 1.597 | 0.889 | 4.214 | 1.843 | 0.126 | 18.22 | 0 | 19.7 | 64.035
|  | adjust for actual reciepts | #REF! | [21 empty] | #REF!
|  | Resources adjusted for forecast receipts | #REF! | [17 empty] | 10.581 | 2.058 | 9.879 | 1.441 | #REF! | 64.035 | 1.99 | #REF!
|  | programme including unfunded from 03/04 | 112.95
|  | Sufplus/(shortfall) in resources over programme | #REF!
Finacc 04 timing differences
[9 empty] | 0506 | 04/05 | 03/04 | 02/03
HMRF
NWDA
|  | surestart | [8 empty] | 19785
ERDF
|  | School Contributions | [9 empty] | 175989
|  | Insurance Clifton Primary / Broadwalk | [9 empty] | 261581
Dept of Health Barton Moss Expansion
Sure Start (Winton linrary)
|  | Beesley Green NOF |  |  |  | shaded area is 534 timing difference in
|  | NOF/PE Sports |  |  |  | resources due
SPACE
Central salford
|  | Chapel Wharf | [9 empty] | 146000
|  | Fire insurance Moorside CP fire damage claim not finalised | [6 empty] | 126071.52
|  | RCCO due E00037, from budget on D(or E??)6110 agreed with Dave mac to correct in new year | [6 empty] | 1500
|  | Winton Community Library RCCO from dev services | [6 empty] | 8000
-5.934
-5.934
Note on C15: Loan to the Higher Broughton Partnership £0.466m capital receipts of unsupported borrowing if no receipts available
Note on C248: City of Salford: slipped from 04/05
Note on D53: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D79: block 3 forecast 5716 need to include overhead and c/way stage 1 less resources 4126. Then adjust for brought forward receipts, central salford cont and other contributions
Note on D163: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D169: City of Salford:
Note on D170: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D193: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D195: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D196: City of Salford: 04/05 office moves budget unallocated at end of year, reduces carry forward of office moves spend
Note on D200: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D254: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D305: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D350: City of Salford: £0.030m 04/05 office moves budget unallocated at end of year, reduces carry forward of office moves spend
Note on H15: this line represents HMRF monthly cash flow estimate it is used to cash flow all private sector programme pro rata
Note on W2: City of Salford: single capital pot 9001
Note on X2: City of Salford: ringfenced 9003
Note on Y2: City of Salford: 9001 unsupported borrowing
Note on Z2: City of Salford: 9011
Note on Z116: Barton moss contribution 0.036 goes through at year end as an appropriation, not as a contribution
Note on AA2: City of Salford: 9007 COLUMN SHOWS CAP RECEIPTS REQUIRED NOT THOSE AVAILABLE
Note on AA248: 90k cap receipts from windfall footpath repairs pot
Note on AA354: 90k to detroit bridge
Note on AE2: City of Salford: 9035 other govt grants 9037 other grants 9039 privat sector cont 9041 other cont
Note on AF2: City of Salford: 9035
Note on AG2: City of Salford: 9037
Note on AH2: City of Salford: 9027
Note on AI2: City of Salford: 9055
Note on AK2: City of Salford: 9045
Note on AL2: City of Salford: 9043
Note on AM2: City of Salford: 9035
Note on AN2: City of Salford: 9037
Note on AO2: City of Salford: 9037
Note on AP2: City of Salford: 9057
Note on AQ2: City of Salford: 9029
Note on AR2: City of Salford: 9037
Note on AS2: City of Salford: 9035
Note on AU2: City of Salford: 9037

## Appendix 2
2005/06 ESTIMATED CAPITAL RECEIPTS
| CAPITAL |  | USABLE
| RECEIPT | Prop'n | Amount
| £000s | % | £000s
COMPLETED DISPOSALS
Housing Right-to-Buy | 15276 | 25 | 3819
Housing Land
Land at Lane End | 60 | 50 | 30
General Fund - Properties and Land
Moorfield House | 100 | 100 | 100
Land adjacent to Hope Hospital | 14 | 100 | 14
Community Centre Kenyon Way | 85 | 100 | 85
St Johns playing field, Walkden | 206 | 100 | 206
Sale of Shares Modesole | 715 | 100 | 715
7 Ashley Drive | 134 | 100 | 134
Land at Ravenscraig Road | 50 | 100 | 50
TOTAL COMPLETED | 16640 |  | 5153
APPROVED DISPOSALS
Housing Right-to-Buy | 3724 | 25 | 931
Housing Land & Property | 169 | 50 | 84.5
General Fund - Properties and Land* | 5191 | 100 | 5191
TOTAL ESTIMATED DISPOSALS | 9084 |  | 6206.5
TOTAL ESTIMATED RECEIPTS | 25724 |  | 11359.5
Less - Costs to be set against capital receipts |  |  | 500
NET ESTIMATED RECEIPTS 05/06 |  |  | 10859.5
RECEIPTS BROUGHT FORWARD |  |  | 14082
ESTIMATED RECEIPTS FOR 2005/06 |  |  | 24941.5
RECEIPTS REQUIRED FOR 2005/06 CAPITAL PROGRAMME |  |  | 15966
SURPLUS/(SHORTFALL) IN CAPITAL RECEIPTS |  |  | 8975.5
*includes £2.8m (gross) receipt for land swop with the university
Note on C13: City of Salford: CAPITAL RECEIPTS Line 1
Note on C27: City of Salford: SHOULD EQUAL LINE 2
Note on C31: City of Salford: CAPITAL RECEIPTS LINE 3
Note on C33: City of Salford: CAPITAL RECEIPTS LINE 4
Note on C35: City of Salford: CAPITAL RECEIPTS LINE 5
Note on C39: City of Salford: SHOULD EQUAL LINE 6
Note on F27: City of Salford: SHOULD EQUAL LINE 2

## Appendix 3
CAPITAL RECEIPTS 2005/06
TIMESCALES-RECEIPTS IN EXCESS OF £100,000
Disposal | Estimated Receipt | Preliminaries/Marketing | Legal/Planning | Completion
£m
St Simon St | 0.3 | deposit received October |  | March
Willowbank/Mere drive Site, Clifton. | 0.5 | - |  | 29th March
Guide St Salford | 0.1 |  | November | February
Legendary Properties | 0.12 |  |  | March

## Appendix 4
Lead Member Corporate Services - 2005/06 Tender Approvals
Scheme Details |  | Costs |  | Source of
| 2005/06 | 2006/07 | Total | Funding
Onwards
| £m | £m | £m
Barton Lane, Eccles | 0.054 | 0 | 0.054 | LTP Block 3
Liverpool Road Bus Stop improvements | 0.104 | 0.007 | 0.111 | LTP Block 3
| 0.158 | 0.007 | 0.165