| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO.6 |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |  |  |
| TO THE BUDGET SCRUTINY COMMITTEE ON FRIDAY 23rd January 2009 |  |  |
| ###### TITLE: CAPITAL MONITORING 2008/09 |  |  |
| RECOMMENDATION : Members are requested to review the current position regarding the 2008/09 capital programme and recommend to Cabinet that the current position continues to be monitored. |  |  |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2008/09 capital programme and expenditure to date. |  |  |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Wednesday 3 December 2008 2. Various working papers within the Finance Division |  |  |
| CONTACT OFFICER : Marion Rigg 793-2685 E-mail: marion.rigg@salford.gov.uk |  |  |
| ASSESSMENT OF RISK : ###### Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2008/09 remains fully funded. |  |  |
| SOURCE OF FUNDING : ###### This report identifies the sources of funding for the 2008/09 Capital Programme. |  |  |
| LEGAL ADVICE OBTAINED : Not Applicable |  |  |
| FINANCIAL ADVICE OBTAINED : ###### This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |  |  |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |  |  |
| KEY COUNCIL POLICIES : Budget Strategy |  |  |

Report Details

- Introduction

At the meeting of the Budget Scrutiny Committee on the 3 December 2008 members were informed that the current capital programme for 2008/09 was £115.092m with capital funding amounting to £111.200m, comprising assumed internal funding of £37.8165m and estimated external funding of £73.384m, giving a shortfall in resources of £3.892m.

This report now advises members of recent developments regarding the 2008/09 capital programme.

2.  	2008/09 Capital Programme

Review of Capital Programme

Members are asked to note the following adjustments to the capital programme and resources in December 2008:-

Programme

|  | November 2008 | This Month | Variation | ### Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Private Sector Housing | 31.121 | 31.121 | 0.000 |  |
| Public Sector Housing | 14.054 | 14.054 | 0.000 |  |
| Children's Services | 20.518 | 20.939 | 0.421 | Refurbishment of Clifton Youth Centre |
| Highways | 6.111 | 6.111 | 0.000 |  |
| Community, Health And Social Care | 4.896 | 5.039 | 0.143 | See note 1 |
| Environmental services | 3.474 | 3.652 | 0.178 | Refurbishment of Cadishead Park and Patricroft Recreation Ground |
| Customer and Support Services | 2.970 | 3.019 | 0.049 |  |
| Chief Executives | 23.664 | 18.453 | (5.211) | See note 2 |
| Sustainable Regeneration | 8.284 | 7.884 | (0.400) |  |
| Total Programme | 115.092 | 110.272 | (4.820) |  |

###### Resources

|  | November 2008 | This Month | Variation | ### Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 5.584 | 6.496 | 0.912 |  |
| Unsupported Borrowing | 33.083 | 33.083 | 0.000 |  |
| Revenue contribution to capital outlay | 0.751 | 0.785 | 0.034 |  |
| Capital receipts | (1.602) | (5.821) | (4.219) | See note 3 |
| Subtotal - Internal resources | 37.816 | 34.543 | (3.273) |  |
| Grants | 72.519 | 67.823 | (4.696) | See note 4 |
| Other Contributions | 0.865 | 1.003 | 0.138 |  |
| Subtotal - External resources | 73.384 | 68.826 | (4.558) |  |
| Total Resources | 111.200 | 103.369 | (7.831) |  |
| Surplus/(Shortfall) | (3.892) | (6.903) | (3.011) |  |

Comments on Programme adjustments

There have been the following adjustments to the capital programme

Note 1 – Community Health & Social Care

- Funding for the renewal of the fire alarm and electrical wiring, at Granville House, has been received from the PCT.

- The transfer of capital receipts and grant income received from the PCT, has been used to complete the refurbishment of St George’s House

Note 2 - Chief Executive

- Irwell City Park – In previous reports the purchase of the Vanguard site had been duplicated in the tables above.  It was included in the Chief Executive’s programme both within the URC Business Plan and as a separate item. This has now been corrected.  There is no effect on the bottom line deficits as grant funding matched budget.

- £812,000 grant funded spend on the Metro link project has been brought forward from 2009/10

Comments on Resources adjustments

Note 3 – Capital Receipts

- Capital receipts for the Tesco site in Salford and the Boysnope Wharf site in Eccles are now expected in 2009/10.

Note 4 - Grants

- The grant funding for the Irwell City Park was already included in the URC business plan.

- Grant funding for Metro link project has been brought forward from the expected spend in 2009/10.

- A grant £452,000 has been received from the Youth Capital Fund Plus for the refurbishment of Clifton Youth Club.

3	Expenditure to Date

Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of December.

###### Actual Spend Against Profile to 31 December 2008

|  |  |  | Expected spend to date |  |  | Variance against |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Programme | 2007/08 Spend Profile | Monthly profile | Actual Spend to date | 2007/08 Spend Profile | Monthly profile |
|  | Private sector housing | 31.121 | 16.806 | 23.341 | 16.777 | -0.029 | -6.564 |
|  | Public sector housing | 14.054 | 7.589 | 10.541 | 8.002 | 0.413 | -2.539 |
|  | Children's Services | 20.939 | 14.239 | 15.704 | 13.527 | -0.712 | -2.177 |
|  | Highways | 6.111 | 3.300 | 4.583 | 4.386 | 1.086 | -0.197 |
|  | Community, Health And Social Care | 5.039 | 2.705 | 3.779 | 1.205 | -1.500 | -2.574 |
|  | Environmental Services | 3.652 | 1.972 | 2.739 | 1.174 | -0.798 | -1.565 |
|  | Customer and Support Services | 3.019 | 0.548 | 2.264 | 0.979 | 0.431 | -1.285 |
|  | Chief Executives | 18.453 | 13.123 | 13.840 | 9.480 | -3.643 | -4.360 |
|  | Planning Services | 7.884 | 4.257 | 5.913 | 6.120 | 1.863 | 0.207 |
|  | 07/08 Programme Total | 110.272 | 64.538 | 82.704 | 61.650 | -2.888 | -21.054 |

- Recommendation

Members are requested to review the current position regarding the 2008/09 capital programme and confirm recommendations to Cabinet that the current position continues to be monitored.

JOHN SPINK

###### CITY TREASURER