| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. 7 |
| --- | --- |

REPORT OF THE CITY TREASURER

TO BUDGET SCRUTINY COMMITTEE ON WEDNESDAY 4 NOVEMBER 2009

TITLE:  REVENUE BUDGET 2009/10: BUDGET MONITORING

RECOMMENDATION:  Members are invited to consider and comment on the contents of the report.

EXECUTIVE SUMMARY: This report outlines the current position of expenditure against the 2009/10 revenue budget.

BACKGROUND DOCUMENTS: Service budget monitoring reports to lead members. (Available for public inspection)

CONTACT OFFICERS:

Tony Thompstone, tel. 793 3245 tony.thompstone@salford.gov.uk

ASSESSMENT OF RISK: Key budgetary control risks are identified in this report.

SOURCE OF FUNDING: Revenue Resources

LEGAL ADVICE OBTAINED: Not applicable

FINANCIAL ADVICE OBTAINED: This report concerns key aspects of the Council’s revenue finances and has been produced by the Finance Division of Customer and Support Services.

WARD(S) TO WHICH REPORT RELATE(S):      None specifically

KEY COUNCIL POLICIES: 2009/10 Revenue Budget

Report Detail

1	Summary

1.1	Overall, the council budget for 2009/10 is £218.3m and the forecast expenditure for the year is £218.6m.

1.2	This report sets out in more detail the current position of expenditure against budgets, highlights any risks/sensitivities, and forecasts the year end position.

2	Current position

2.1	The current position is set out in the table below, overall there is an adverse variance to date of £1.765m on the General Fund and £1.277m on Dedicated Schools Grant.

| Net expenditure against budgets up to 30/09/09 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Division of service | Profiled budget to date | Expenditure to date | Variance | (F)av/ Adv |
|  | £000 | £000 | £000 |  |
| Chief Executive’s | 7,032 | 7,104 | 72 | A (amber) |
| Children’s Services –General Fund | 30,835 | 31,470 | 635 | A (red) |
| Community Health and Social Care | 35,861 | 35,715 | -146 | F (green) |
| Customer and Support Services | 15,510 | 15,747 | 237 | A (amber) |
| Environmental Services | 7,081 | 7,196 | 115 | A (amber) |
| Sustainable Regeneration | 9,043 | 9,848 | 805 | A (red) |
| Precepts and Charges | 13,072 | 13,102 | 30 | A (amber) |
| Capital Financing | 12,250 | 12,267 | 17 | A (amber) |
| Total General Fund | 130,684 | 132,449 | 1,765 | A (red) |
| Children’s Services -DSG | 11,937 | 13,214 | 1,277 | A (red) |

This reflects salaries and wages and other expenditure up to 30/09/2009.

● (AMBER) Chief Executive’s

The directorate is expected to be within budget at year end.  However, work is on-going on the budget virements connected with Organisational Development, Strategy, Policy and Performance and Project and Performance Management think efficiency workstreams which have been transferred into Chief Executive’s as part of the Think Efficiency programme.

● (RED) Children’s Services

The total variance for Children’s Services is £1.912m, of which £1.277m relates to the Dedicated Schools Grant and £0.635m relates to the General Fund.

Within the DSG the main area of overspending is non-maintained special school placements, which is currently overspent by £0.807m, whilst the forecast overspend for the full year remains unchanged at £1.614m.

Whilst an overspend on the Dedicated Schools Grant may not have an adverse effect on the City Council’s budget it will impact on the resources available to schools.  Plans are in place to reduce the overspend and any overspending at year end will need to be topsliced from the 2010-11 DSG budget.

The forecast overspend at outturn for the General Fund has improved to £0.303m, after additional work on the budget to identify savings following on from the report to Scrutiny members last month.

● (GREEN) Community Health and Social Care

There is a slight favourable variation on the Community, Health and Social Care budget which is expected to continue to year-end and is due to casual vacancies.

● (AMBER) Customer and Support Services

The directorate overspend to date is due to the loss of income from the provision of services to external sources, i.e. the Housing Revenue Account, City West and Greater Manchester Police Authority.  However, income and expenditure continue to be monitored closely to keep overall expenditure within budget by year-end.

● (AMBER) Environment

The current variance of £115k is mainly a result of delays in the roll out of the co-mingled recycling service, AGMA Vehicle Management Services collaboration working to establish best practice and legal fees in relation to a Trading Standards prosecution.

The Environment Directorate is currently projecting an overspend of £282k due to the delay in the roll out of the co-mingled recycling service and an AGMA charge early in the year for the VMS study, along with legal fees still being incurred in a Trading Standards prosecution.  Income and expenditure continue to be closely monitored and action taken with the intention of operating within the 2009/10 budget over the financial year.

● (RED) Sustainable Regeneration

The forecast outturn has improved to an overspend of £1.120m, with £0.500m of highways maintenance expenditure to be charged to the capital programme.

● (AMBER) Precepts and Charges

The favourable variation on the Precepts and Charges budget is based on a waste disposal tonnage forecast for 2009/10 that gives an anticipated saving of £200k on the waste disposal levy for the year.

● (AMBER) Capital Financing

The capital financing budget will be within budget at the year end.

Prudential indicators for treasury management can be seen at Appendix 2, to date they have not been exceeded.

3	Forecast position

3.1	Extrapolating the current position outlined in section 2 above and taking into account the pressures outlined, the position set out below is projected for the year end.

| Forecast net year-end position |  |  |  |  |
| --- | --- | --- | --- | --- |
| Division of service | Annual budget | Forecast outturn Expenditure | Variance | (F) favourable/ (A) adverse |
|  | £000 | £000 | £000 |  |
| Chief Executives | 15,192 | 15,192 | 0 | F (green) |
| Children’s Services –General Fund | 52,894 | 53,197 | 303 | A (red) |
| Community Health and Social Care | 73,932 | 73,856 | -76 | F (green) |
| Customer and Support Services | 7,934 | 7,934 | 0 | F (amber) |
| Environmental | 15,569 | 15,569 | 0 | F (amber) |
| Sustainable Regeneration | 28,272 | 29,392 | 1,120 | A (red) |
| Precepts and Charges | 26,184 | 25,984 | -200 | F (green) |
| Capital financing | 24,503 | 24,203 | -300 | F (green) |
| Inflation/Contingency | -26,169 | -26,769 | -600 | F (green) |
| Total | 218,311 | 218,558 | 247 | A (red) |
| Children’s Services -DSG | 17,067 | 19,238 | 2,171 | A (red) |

Inflation/Contingency

Manchester Airport Group has declared a reduced dividend payable in 2009 in view of current trading conditions and this will reduce income to the Council by £300k, but this has been partially offset by reduced NNDR bills on a corporate properties that have had reduced rateable values agreed.

In addition, there is a saving of £600k on pay this year, due to the settlement of the pay award at 1%.

- Reserves

  - The forecast position with reserves as a result of the 2008/09 outturn and the current monitoring position for 2009/10 is as follows:-

|  | 2009/10 Budget | 2008/09 Outturn | 2009/10 Monitoring |
| --- | --- | --- | --- |
|  | £m | £m | £m |
| B/fwd 1st April 2009 | 9.8 | 9.7 | 9.7 |
| Budgeted Contribution from Reserves | (2.9) | (2.9) | (2.9) |
| Forecast Year-end Variation | Nil | Nil | (0.3) |
| C/fwd 31st March 2010 | 6.9 | 6.8 | 6.5 |

4.2	Forecast reserves at year end are £6.5m which would be above the minimum level considered prudent of £6.0m.

5	Housing Revenue Account

5.1	The HRA is forecast to be within budget at year end.

6	Service Efficiencies and Income Proposals

6.1	Appendix 1 provides details of the approved savings included in the 2009-2010 revenue budget.

6.2	Based on the savings to the end of September of £10.136m, there are a further £2.634m still to be achieved.  There will be an additional call on reserves if the savings are not achieved, although directorates are anticipating any shortfalls in their projections reported above.

7	Recommendations

7.1	Members are invited to consider and comment on the contents of this report.

John Spink

City Treasurer

Appendix 1

| SUMMARY OF SERVICE EFFICIENCIES AND INCOME PROPOSALS AND THINK EFFICIENCY 2009/10 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Ref | Proposal |  | 2009-10 | Actioned | In progress | Outstanding |
|  |  |  | £000 | £000 | £000 | £000 |
| Chief Executives |  |  |  |  |  |  |
|  | ABG funding to support partners |  | 60 | 60 |  |  |
|  | General housekeeping |  | 10 | 10 |  |  |
|  |  |  | 70 | 70 | 0 | 0 |
| Children’s Services |  |  |  |  |  |  |
| CS1 |  | Salford Skills Centre | 100 | 100 |  |  |
| CS3 |  | Salford People | 10 | 10 |  |  |
| CS6 |  | Youth Service | 25 | 25 |  |  |
| CS7 |  | Barton Moss earmarked reserve | 250 | 250 |  |  |
| CS8 |  | Increased charges | 35 | 35 |  |  |
|  |  |  | 420 | 420 | 0 | 0 |
| Community Health and Social Care |  |  |  |  |  |  |
| CHSC1 |  | Utilise Transforming Social Care Grant to fund review function to take forward personalisation | 181 | 181 |  |  |
| CHSC2 |  | Utilise Transforming Social Care Grant to part fund the direct payments contract | 68 | 68 |  |  |
| CHSC3 |  | Increase casual vacancy factor on Adult Social Care mainstream funded employee budgets | 200 | 200 |  |  |
| CHSC4 |  | Reconfiguration of day service placements for Older People | 90 | 90 |  |  |
| CHSC5 |  | Renegotiation of supported living service for Physical Disability Services | 45 | 45 |  |  |
| CHSC6 |  | Charging Policy Income | 105 | 105 |  |  |
| CHSC7 |  | Increased income from review of S117 cases | 33 | 33 |  |  |
| CHSC9 |  | Assumed increase in client contributions and other income to fund Adult Social Care Services - reduction in centrally held price provision | 342 | 342 |  |  |
| CHSC10 |  | Purchase of Burrows House net revenue saving | 9 |  | 9 |  |
| CHSC11 |  | Culture & Leisure reduction in salary enhancements to represent operational establishment | 39 | 39 |  |  |
| CHSC12 |  | Painting and decorating programme - one years slippage of part of the programme | 30 | 30 |  |  |
| SCL1 |  | One off reduction in Management fee - contra capital project | 600 | 600 |  |  |
|  |  |  | 1,742 | 1,733 | 9 | 0 |
| Customer and Support Services |  |  |  |  |  |  |
| C&SS2 |  | Delayed payback unsupported borrowing - Core Comms Infrastructure | 138 | 138 |  |  |
| C&SS3 |  | Delayed payback unsupported borrowing - Data Section | 20 | 20 |  |  |
| C&SS4 |  | Content Management Pool lease | 24 | 24 |  |  |
| C&SS5 |  | Oracle licence termination | 85 | 85 |  |  |
| C&SS6 |  | Delayed payback unsupported borrowing - Council Tax System replacement | 51 | 51 |  |  |
| C&SS7 |  | Academy recruitment - focus clerical entry leading to advertising saving and use of ABG | 190 |  |  | 190 |
| C&SS8 |  | Graduate recruitment delete remaining placement | 28 | 28 |  |  |
| C&SS9 |  | Health and safety - delete 1 post | 25 | 25 |  |  |
| C&SS10 |  | Accountancy reduce posts to reflect Environment restructure and reduced HRA | 80 | 80 |  |  |
| C&SS11 |  | Payroll - improve cash flow on external reimbursements | 20 | 20 |  |  |
| C&SS12 |  | Land Charges - lose 0.5 FTE post | 11 | 11 |  |  |
| C&SS13 |  | Terminate / buy out Norwel System Lease | 25 | 25 |  |  |
| Ref |  | Proposal | 2009-10 | Actioned | In progress | Outstanding |
|  |  |  | £0 | £0 | £0 | £0 |
| C&SS14 |  | Registrars - fee increases and additional income | 5 | 5 |  |  |
| C&SS15 |  | Elections - budget not required for expenses, rent of polling stations and casual staff | 75 | 75 |  |  |
| C&SS16 |  | Location of out of hours service - potential to merge telephony equipment with contact ctre. | 100 |  |  | 20 |
| C&SS17 |  | New Gateway Centres - scope to generate income from external users |  |  |  | 20 |
| C&SS18 |  | Merge Benefits Fraud and Internal Audit investigation teams |  |  | 20 |  |
| C&SS19 |  | ICT in the Community - scope to re-deploy staff |  |  |  |  |
| C&SS20 |  | Review/reorganise existing print services |  |  |  | 20 |
| C&SS21 |  | NNDR - deletion of 2 posts | 40 | 0 |  | 20 |
|  |  |  | 917 | 587 | 20 | 310 |
| Environmental Services |  |  |  |  |  |  |
| ES1 |  | Parks & Open Spaces - Tarmacing of footpaths and roadways | 100 | 100 |  |  |
| ES2 |  | Parks & Open Spaces - Playground painting programme | 20 | 20 |  |  |
| ES3 |  | Environmental Strategy - Senior Project Development Officer | 34 | 34 |  |  |
| ES4 |  | Environmental Strategy - Other professional fees | 4 | 4 |  |  |
| ES5 |  | Business & Operational Support - Facilities & Operational Support | 20 | 20 |  |  |
| ES6 |  | Regulatory Services - Environmental Health | 35 | 35 |  |  |
| ES7 |  | Regulatory Services - Environmental Protection | 35 | 35 |  |  |
| ES8 |  | Playground inspection scheme | 20 | 20 |  |  |
| ES9 |  | Parks & Ground Maintenance - Bulb Planting Scheme | 40 | 40 |  |  |
| ES10 |  | Refuse Collection/street cleaning - retain JWS disposal | 150 | 150 |  |  |
| ES11 |  | VMM structure proposals | 20 | 20 |  |  |
| ES12 |  | DSO reliance on DSO surplus | 250 | 250 |  |  |
| ES13 |  | Fees & Charges 5% uplift | 165 | 165 |  |  |
|  |  |  | 893 | 893 | 0 | 0 |
| Sustainable Regeneration |  |  |  |  |  |  |
| HP1 |  | Recharge Choice Based Letting service to additional users | 15 | 15 |  |  |
| HP2 |  | Charge for landlord licensing / landlord accreditation | 15 | 15 |  |  |
| HP3 |  | Rationalisation and greater control of stationary | 10 | 10 |  |  |
| HP4 |  | Cancellation of catering with the exception of Planning Panel | 15 | 15 |  |  |
| HP5 |  | Housekeeping - 5% reduction in appropriate controlable costs | 50 | 50 |  |  |
| HP6 |  | Charge for immigration certificates | 8 | 8 |  |  |
| HP7 |  | Accommodation rationalisation | 30 | 30 |  |  |
| HP8 |  | Enhanced Options Trailblazer Project | 30 | 30 |  |  |
| HP9 |  | New contract Care on Call service | 10 | 10 |  |  |
|  |  | Urban Vision | 200 | 200 |  |  |
|  |  | Hoarding advertising | 40 | 40 |  |  |
|  |  | Miscellaneous income | 3 | 3 |  |  |
|  |  |  | 426 | 426 | 0 | 0 |
| Corporate |  |  |  |  |  |  |
|  |  | Carbon Management Reduction Programme | 100 |  | 100 |  |
|  |  | Essential User car allowances | 300 |  |  | 300 |
|  |  | Think Efficiency Workstreams |  |  |  |  |
|  |  | Administration | 542 | 192 | 350 |  |
|  |  | Customer Services | 1,092 | 83 | 1,009 |  |
|  |  | Democratic Process | 104 | 6 | 98 |  |
|  |  | Management Structures | 617 | 678 |  |  |
|  |  | Marketing and Communication | 181 | 159 | 22 |  |
|  |  | Procurement | 4,021 | 3,986 | 35 |  |
| Ref |  | Proposal | 2009-10 | Actioned | In progress | Outstanding |
|  |  |  | £0 | £0 | £0 | £0 |
|  |  | Programme and Project Management | 145 | 44 | 101 |  |
|  |  | Strategy, Policy and Performance | 842 | 463 | 379 |  |
|  |  | Transactional Finance | 151 | 152 |  |  |
|  |  | Transactional HR | 57 | 245 |  |  |
|  |  | Workforce Management | 511 | 0 | 511 |  |
|  |  | Total | 8,663 | 6,008 | 2,605 | 300 |
|  |  | Cumulative Total | 13,131 | 10,137 | 2,634 | 610 |

Prudential Indicators	Appendix 2

| a) Authorised Limit for External Debt, Forward Estimates | 2009/10 | 2010/11 | 2011/12 |
| --- | --- | --- | --- |
|  | £m | £m | £m |
| Total Authorised Limit for External Debt | 684 | 744 | 809 |
| Actual Gross External Debt as at 30/09/09 | 508 |  |  |

This limit represents the total level of external debt (and other long term liabilities, such as finance leases) the council is likely to need in each year to meet all possible eventualities that may arise in its treasury management activities.

| b) Operational Boundary for External Debt | 2009/10 | 2010/11 | 2011/12 |
| --- | --- | --- | --- |
|  | £m | £m | £m |
| Total Operational Boundary for External debt | 584 | 644 | 709 |
| Actual Gross External Debt as at 31/09/09 | 508 |  |  |

This limit reflects the estimate of the most likely, prudent, but not worse case, scenario without the additional headroom included within the authorised limit.  The operational boundary represents a key benchmark against which detailed monitoring is undertaken by treasury officers.

C) Net Borrowing

In order to ensure that, over the medium term, net borrowing will only be for a capital purpose, the Council should ensure that the net external borrowing does not, except in the short term, exceed the total of the capital financing requirement in the preceding year plus the estimates of any additional capital financing requirement for the current and the next two financial years.  This forms an acid test of the adequacy of the capital financing requirement and an early warning system of whether any of the above limits could be breached.

To date this indicator has been met.  The current capital financing requirement is £421m and the net borrowing requirement £386m.  During September the headroom on this indicator varied between £25m and £38m.