|  | PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |  | ITEM NO |
| --- | --- | --- | --- | --- |
| REPORT OF THE DIRECTOR OF CORPORATE SERVICES |  |  |  |  |
| TO THE BUDGET COMMITTEE ON WEDNESDAY, 7th FEBRUARY 2001 |  |  |  |  |
| TITLE : CAPITAL PROGRAMME MONITORING 2000/2001 |  |  |  |  |
| RECOMMENDATIONS : Members are requested to note the contents of this report and the proposed adjustments to the 2000/2001 Capital Programme. |  |  |  |  |
| EXECUTIVE SUMMARY : The report provides details of the current position of the 2000/2001 Capital Programme |  |  |  |  |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Committee 10th January 2001 2. Various working papers within the Finance Division |  |  |  |  |
| CONTACT OFFICER : Chris Mee 793-2685 |  |  |  |  |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |  |  |  |  |
| KEY COUNCIL POLICIES : Capital Programme 2000/01 |  |  |  |  |

REPORT DETAILS

1.    INTRODUCTION

1.1  At the meeting of Budget Committee on the 10th January 2001, members approved a revised

capital programme for 2000/01 of £66.008m funded by estimated resources of £68.211m.

  - This report advises members of the current position regarding the 2000/01 capital programme.

2.    2000/2001 CAPITAL PROGRAMME

2.1  It was reported to Budget Committee on the 10th January 2001 that the revised capital

programme for 2000/01 was £66.008m funded by estimated resources of £68.211m

resulting in net available resources of £2.203m, of which £1.547m was required to fund

expenditure in 2001/02 for Eccles Town Centre.

  - Members are now requested to note the following adjustments to the capital programme and resources.

Programme        Resources

£m                    £m

Approved programme/resources at                                          66.008               68.211

10th January 2001

| - Development Services NWRDA Headroom Schemes :- i) Chapel St Regeneration : - - Bexley Square - Chapel St Refurbishment - Salford Station / New Bailey St (approved by Lead Member Dev. Services 27/11/00) ii) Broughton Village - Environmental & Security Improvements (approved by Lead Members for Dev. Services, Corp. Services 2/10/00) iii) Walter Greenwood Court - Demolition (approved Lead Member Housing - 6/10/00) iv) Seedley & Langworthy - Environmental Improvements (approved by Lead Members for Dev. Services, Housing & Education - 4/9/00) Canalside Walkway Phase 6 (approved by Lead Member Dev. Services - 23/10/00) Harold Riley Archive - ERDF contribution (approved by Cabinet 28/11/00) Trafford Rd / Quays Junction - Brought Forward From 2001/02 a) Development Services (Cont.) Lower Broughton Regeneration Strategy (approved by Cabinet - 26/9/00) - Arts & Leisure SRB 2 - Broughton Pool Leisure Trust - Consultancy (Slippage to 2001/02) - Capital Receipts Revised estimate of Usable Capital Receipts (Slippage of receipt to 2001/02) - Corporate Services Project E-merge - Consultancy Costs Payroll Module brought forward from 2001/02 | 0.212 0.444 0.548 0.750 0.484 0.213 0.174 0.025 0.208 Programme £m 0.023 0.100 (0.150) 0.147 | 0.212 0.444 0.548 0.750 0.484 0.213 0.174 0.025 Resources £m 0.023 0.100 (0.100) |
| --- | --- | --- |
|  | 69.186 | 71.084 |

  - A summary of the revised capital programme is attached at Appendix 1.

  - Appendix 2 analyses the estimated resources and Appendix 3 the latest capital receipts.

  - Actual expenditure at 29th January is £36.537m which represents 53% of the programme.

3.    COMMENTS

  - There has been a net reduction in available resources during the month of £0.305m leaving a balance of £1.898m, of which £1.697m is now required to fund expenditure in 2001/02 for Eccles Town Centre (£1.547m) and Leisure Trust consultancy costs (£0.150m) leaving £0.201m available.

  - The above reduction is mainly as a result of the slippage of an expected capital receipt to 2001/02 and expenditure on Trafford Rd / Quays Junction and E-merge payroll, being brought forward from 2001/02.

  - Members are requested to note that the Education programme includes underprogramming of £1.386m as a result of slippage of the new Primary Special School which must be carried forward to meet commitments in 2001/02.

3.4  There is provision within the Highways programme of  £3.189m for the Manchester/Salford

Inner Relief Route.Members are requested to note that part of this expenditure will slip to

2001/02 due to the approximately 2 month delay in commencement on site (now due to be

February 2001).Discussions are ongoing with GONW to ensure resources are allocated in

line with the revised phasing of expenditure once it is known.

4.    RECOMMENDATIONS

  - Members are requested to note the contents of this report and the proposed adjustments to the 2000/2001 capital programme.

J. SPINK                                                A. WESTWOOD

Head of Finance                                   Director of Corporate Services