Contents

| Section | Subject | Page |
| --- | --- | --- |
| 1.0 | Executive Summary | 7 |
| 1.1 | Background to the Project | 7 |
| 1.2 | Strategic Context | 7 |
| 1.3 | Understanding Market Change and Housing Needs | 8 |
| 1.4 | Business Need and Stock Condition | 8 |
| 1.5 | Options Appraisal | 8 |
| 1.6 | Preferred Option | 8 |
| 1.7 | Public Sector Comparator and Value for Money | 9 |
| 1.8 | Affordability | 9 |
| 1.9 | Project Delivery Arrangements | 10 |
| 1.10 | Risk Allocation and Accounting Treatment | 10 |
| 1.11 | Project Management, Governance and Delivery | 10 |
| 1.12 | Statutory Processes | 10 |
| 1.13 | Commitment of Stakeholdersand Sponsors | 11 |
| 2.0 | Background to the Project | 11 |
| 2.1 | About the City of Salford | 11 |
| 2.1.1 | Population | 11 |
| 2.1.2 | Socio-Economic Data | 11 |
| 2.1.3 | Salford City Council | 12 |
| 2.2 | Our Vision | 12 |
| 2.3 | Decent Homes Investment Strategy | 13 |
| 2.4 | Pendleton PFI Objectives | 14 |
| 3.0 | Strategic Context | 14 |
| 3.1 | Scheme Context | 14 |
| 3.2 | National Policy Context | 15 |
| 3.2.1 | Sustainable Development | 15 |
| 3.2.2 | Sustainable Communities | 15 |
| 3.2.3 | Making Homes Decent | 15 |
| 3.2.4 | Housing and Regeneration Bill | 15 |
| 3.3 | Regional Strategies and Policy Framework | 16 |
| 3.3.1 | Northern Way Growth Strategy | 16 |
| 3.3.2 | Regional Spatial Strategy for the North West | 16 |
| 3.4 | Sub-Regional Policy Framework | 16 |
| 3.4.1 | The Housing Market Report 2007 | 16 |
| 3.4.2 | Manchester Salford Housing Market Renewal Pathfinder | 17 |
| 3.4.3 | Greater Manchester Strategic Housing Market Assessment | 17 |
| 3.5 | Local Context | 17 |
| 3.5.1 | Community Plan | 17 |
| 3.5.2 | ‘Shaping our Place’ – Draft Housing Strategy for Salford 2008 -2011 | 18 |
| 3.5.3 | Central Salford Urban Regeneration Company | 18 |
| 4.0 | Understanding Market Change and Housing Needs | 19 |
| 4.1 | Current Housing Provision | 19 |
| 4.2 | Turnover | 21 |
| 4.3 | Demand | 21 |
| 4.3.1 | Current Analysis | 21 |
| 4.3.2 | Housing Questionnaire Survey | 22 |
| 4.3.3 | Future Growth | 23 |
| 4.3.4 | Future Role for Pendleton in the Housing Market | 23 |
| 5.0 | Business Need and Stock Condition | 24 |
| 5.1 | Estate Overview | 24 |
| 5.2 | Stock Analysis and Property Numbers | 24 |
| 5.2.1 | Communal and Estate Facilities | 25 |
| 5.3 | Current Stock Condition and Investment Requirement | 25 |
| 5.3.1 | Stock Condition Survey | 25 |
| 5.3.2 | Multi-Storey Stock Condition | 27 |
| 5.3.3 | Additional Specialist Surveys | 29 |
| 5.4 | Assessment of Capital and Lifecycle Costs | 31 |
| 5.5 | Investment Need | 31 |
| 5.6 | Rationale for Retaining Stock | 32 |
| 6.0 | Options Appraisal | 33 |
| 6.1 | Stage 1 – City-Wide Stock Options Appraisal | 33 |
| 6.1.1 | Evaluation of Delivery Options | 34 |
| 6.2 | Stage 2 – Detailed Assessment | 35 |
| 6.2.1 | Evaluation of Short List of Options | 37 |
| 6.3 | Service Delivery Options | 37 |
| 6.3.1 | Identification of Service Delivery Options | 38 |
| 6.3.2 | Appraisal of Service Delivery Options | 38 |
| 6.3.3 | Preferred Approach | 39 |
| 6.4 | Market Sounding | 39 |
| 6.4.1 | Phase One – Investment Route | 40 |
| 6.4.2 | Phase Two – Scope Development | 40 |
| 6.4.3 | Phase Three – Refinement of Scope | 41 |
| 6.4.4 | Summary of Response to the Market | 43 |
| 7.0 | Preferred Option | 43 |
| 7.1 | Development Opportunities | 44 |
| 7.2 | Pendleton Re-housing Plan | 45 |
| 7.2.1 | Supporting Vulnerable Groups | 46 |
| 8.0 | Public Sector Comparator and Value for Money | 47 |
| 8.1 | Qualitative Assessment | 47 |
| 8.2 | Quantitative Assessment | 48 |
| 8.3 | Risk Analysis and Management | 49 |
| 8.4 | Optimism Bias | 49 |
| 8.4.1 | Capital Expenditure Optimism Bias | 49 |
| 8.4.2 | Lifecycle Expenditure Optimism Bias | 51 |
| 8.4.3 | Operating Expenditure Optimism Bias | 52 |
| 8.4.4 | Optimism Bias Overview | 53 |
| 8.5 | Taxation Adjustment | 53 |
| 8.6 | VfM Sensitivities | 53 |
| 8.5 | Conclusions to VfM Analysis | 53 |
| 9.0 | Affordability | 54 |
| 9.1 | Scheme Affordability | 54 |
| 9.2 | PFI Affordability | 54 |
| 9.3 | New Build Affordability | 55 |
| 9.4 | Sensitivities | 56 |
| 9.5 | Conclusion to Affordability Analysis | 57 |
| 10.0 | Project Delivery Arrangements | 57 |
| 10.1 | Project Agreement | 57 |
| 10.1.1 | Approach to Key Contractual Issues | 58 |
| 10.1.2 | Structure and Length of Contract | 58 |
| 10.1.3 | Service Commencement and Phasing | 59 |
| 10.1.4 | Approach to Stock Surveys | 59 |
| 10.1.5 | Benchmarking of Costs and Income | 59 |
| 10.1.6 | TUPE Arrangements | 59 |
| 10.1.7 | Warranty Issues | 59 |
| 10.1.8 | Contractor and Council Obligations | 60 |
| 10.1.9 | Refinancing | 60 |
| 10.1.10 | Hand-back of Assets at the End of the Contract | 60 |
| 10.1.11 | Changes in Law | 60 |
| 10.1.12 | Monitoring Arrangements | 60 |
| 10.1.13 | Change Mechanism | 60 |
| 10.1.14 | Termination Events | 60 |
| 10.2 | Output Specification Summary | 60 |
| 10.2.1 | Overview of Property Management Standards | 61 |
| 10.2.2 | Overview of Service Performance Standards | 61 |
| 10.2.3 | Value for Money in Service Delivery | 61 |
| 10.2.4 | Interface Arrangements | 61 |
| 10.2.5 | Future Development of the Output Specification | 62 |
| 10.3 | Payment Mechanism | 63 |
| 10.4 | Development Element of the PFI Scheme | 63 |
| 11.0 | Risk Allocation and Accounting Treatment | 63 |
| 11.1 | External Audit Opinion | 64 |
| 11.2 | Project Risk Management | 64 |
| 12.0 | Project Management, Governance and Delivery | 65 |
| 12.1 | Project Delivery Structure | 65 |
| 12.2 | Portfolio Management Board | 65 |
| 12.3 | Housing Investment Options Programme Board | 66 |
| 12.4 | Strategic Client Group | 67 |
| 12.5 | Project Team | 67 |
| 12.6 | External Advisors | 68 |
| 12.7 | Project Budget | 68 |
| 12.8 | Gateway Review | 69 |
| 12.9 | Project Delivery Programme | 69 |
| 13.0 | Statutory Processes | 70 |
| 13.1 | Planning | 70 |
| 13.1.1 | Current Status | 70 |
| 13.1.2 | Pendleton Planning Guidance | 71 |
| 13.1.3 | Planning Approach | 71 |
| 13.2 | Title Arrangements | 72 |
| 13.3 | Notice of Intention to Demolition | 72 |
| 13.4 | Compulsory Purchase and Blight Notices | 72 |
| 13.5 | Highway and Footpath Closures | 73 |
| 13.6 | Leaseholders | 73 |
| 13.7 | Section 25 Notices | 73 |
| 14.0 | Commitment of Stakeholders and Sponsors | 74 |
| 14.1 | Community Consultation | 74 |
| 14.2 | Communications Strategy | 74 |
| 14.3 | Hard to Reach Groups | 74 |
| 14.4 | Commitment to the Project | 75 |

|  | Tables |
| --- | --- |
| 1 | Tenure Diversification Analysis |
| 2 | Breakdown of Property Type |
| 3 | Property Size Analysis of Council Stock (within the PFI area) |
| 4 | Turnover Analysis in Multi-Storey Flats |
| 5 | Bid Per Vacancy Analysis |
| 6 | Current Stock Breakdown |
| 7 | Stock Breakdown Post Demolition |
| 8 | Communal Facilities |
| 9 | Breakdown of Properties Surveyed |
| 10 | Required External Remedial Works to Multi-Storey Blocks |
| 11 | Over-Cladding Systems |
| 12 | Evaluation of Delivery Options – Summary Matrix |
| 13 | Advantages of Each Respective Service Delivery Approach |
| 14 | Disadvantages of Each Respective Service Delivery Approach |
| 15 | Qualitative Assessment |
| 16 | Indicative PFI VfM |
| 17 | Capital Expenditure Optimism Bias |
| 18 | Lifecycle Expenditure Optimism Bias |
| 19 | Operating Expenditure Optimism Bias |
| 20 | Optimism Bias |
| 21 | VfM Indifference Points |
| 22 | Scheme Affordability |
| 23 | Project Key Figures |
| 24 | New Build Units |
| 25 | Key Sensitivities |
| 26 | Affordability Sensitivities |
| 27 | Risk Allocation |
| 28 | Membership of the Portfolio Management Board |
| 29 | Membership of the Housing Investment Options Programme Board |
| 30 | Membership of the Strategic Client Group |
| 31 | Membership of the Project Team |
| 32 | Additional Resource |
| 33 | Project Milestones |

|  | Appendices |
| --- | --- |
| 1 | Location Plan |
| 2 | Pendleton Estate Analysis |
| 3 | Thomason’s Review & Appraisal of Multi-Storey Tower Blocks |
| 4 | Pendleton PFI Development Opportunities Location Plan |
| 5 | Overview of Build Cost Model Inputs |
| 6 | Turner & Townsend Stock Condition Appraisal Report |
| 7 | Cost Breakdown Per Property Type |
| 8 | Draft Output Specification |
| 9 | Issues & Options Report 2006 |
| 10 | Preferred Options Report 2007 |
| 11 | Option Appraisal Evaluation Methodology |
| 12 | Evaluation Team Reports |
| 13 | Evaluation Results Summary |
| 14 | Service Delivery Plan |
| 15 | Market Testing Phase One - Statements of Intent |
| 16 | Pendleton Re-Housing Plan |
| 17 | Data Book |
| 18 | Salford City Council OBC Financial Model |
| 19 | Draft Phasing Plan |
| 20 | Accounting Treatment |
| 21 | Letter from External Auditor (to follow) |
| 22 | Risk Management Plan |
| 23 | Risk Register |
| 24 | Gateway Review Report |
| 25 | Project Delivery Programme |
| 26 | Pendleton Planning Guidance |
| 27 | Communications Strategy |
| 28 | Executive Board Report and Minutes (Cabinet Minutes to follow) |

# 1.0	Executive Summary

## 1.1	Background to the Project

The Pendleton Housing Private Finance Initiative (PFI) scheme is the result of a detailed appraisal of the housing investment options for the delivery of decent homes in Central Salford.  The appraisal process concluded that PFI was the most appropriate route to secure the level of required investment to deliver extensive refurbishment, remodelling and new build in line with the council’s vision for housing:-

‘To create a future where people see Salford as a great place to live.  A place where you can find a choice of popular homes in desirable locations, served by excellent housing services’.

The council and its partners have developed a series of scheme objectives, which will be used as core principles for evaluating and guiding the development of the PFI initiative. They form a local response to national strategy initiatives including sustainable communities, an increase in the availability of affordable homes and the provision of decent homes for all.  The scheme objectives are as follows:-

- To create a better choice of quality housing, by refurbishing the retained social housing to the Decent Homes Standard and providing new build quality homes for social rent and sale by 2015.  All housing will address forthcoming statutory environmental and sustainable guidelines.

- To transform the image and future perceptions of Pendleton by improving the quality of housing design, open space, through good design techniques and guidance to develop future proof homes, which improve community safety and reduce the fear of crime by 2015.

- To ensure that local residents are fully involved in the planning, development, implementation and delivery of the scheme in partnership with other local stakeholders.

- To create mixed income sustainable communities which retain existing communities and attract new residents to the area, by improving housing choice, employment opportunities, retail and recreation facilities by 2025-2030.

- To support the regeneration and future success of the wider Central Salford area, the city and the Manchester city region.

The council and its partners have used the basis of these scheme objectives to undertake a comprehensive assessment of the current stock in terms of its condition and the role the area can play in meeting future needs within the housing market.

## 1.2	Strategic Context

The proposals within this PFI scheme are aligned not only to meeting the Government’s agenda of achieving Decent Homes, but also to the objectives of the Northern Way Growth Strategy.  This aims to reduce the economic disparities between the North of England and the rest of the country, within which the quality and nature of the region’s housing plays a key part.  The PFI scheme offers the opportunity to address this current imbalance through the provision of an appropriate mix of good quality housing to attract and retain sufficient wealth creators and skilled workers to sustain the region’s growth and achievement towards narrowing the gap agenda.

## 1.3	Understanding Market Change & Housing Needs

The Pendleton PFI area is dominated by an excessive level of council owned homes, with over 93% of all properties falling into this category.  The dilution of this mono-tenure through the ability to exercise Right to Buy has been minimal with only 149 completed applications over the last 26 years.  The profile of property type is limited further by the fact that 60% of the council owned stock is within multi-storey blocks, with only 543 houses present.  The overall effect of this lack of choice has been to narrow the socio-economic composition of the area.

In addition, a level of instability exists across the estate, particularly within the multi-storey blocks, with a turnover rate at over 10% per annum in some blocks. In order to provide a degree of stability to this element of the housing market, it is the council’s intention to consolidate the number of available flats by demolishing four blocks.   This will have the effect of both rationalising demand to a reduced number of newly refurbished properties and providing development opportunities for new properties more in line with future housing needs.  A particular requirement that has been identified is the need for more family orientated accommodation.

## 1.4	Business Need & Stock Condition

The OBC sets out in detail how the council has sought to ensure that the stock condition data it holds is of a standard that provides confidence that the preferred option is deliverable and that the associated costs are robust.  Overall, over two phases, 80% of the stock has been surveyed which, supported by a number of specialist surveys, focused upon high risk elements such as asbestos, wall ties and ground condition.

In terms of the multi-storey blocks, the council’s understanding and experience, together with the high level of condition information it has gathered, have enabled it to develop a robust cost assessment of the options it expects to deliver with a high degree of confidence. The council has sought specialist consultant advice to ensure that the proposed solutions are capable of being delivered and offer value for money.

## 1.5	Options Appraisal

The council has undertaken a thorough option appraisal process which originally commenced in 2003 with an evaluation of available investment vehicles against the council’s objectives for the area. This high level assessment concluded that the PFI model offered investment beyond Decent Homes and provided investment for remodelling and new provision essential for the sustainability of the area, ensuring best fit with wider strategic housing market renewal and regeneration interventions.

The second stage of the option appraisal process involved a detailed assessment of the stock within the Pendleton estate to determine the proposed scope of works to be delivered via the PFI model. This required the delivery of a comprehensive community consultation exercise in an effort to gauge clarity on peoples’ issues and concerns, combined with a study of the actual condition of properties. This information, supplemented by a financial analysis of the proposed options, was used to conclude the overall Preferred Option; a process which was finalised in December 2007.

## 1.6	Preferred Option

The overall scope of the PFI scheme and associated development element, under the umbrella of ‘Creating a New Pendleton’, includes:-

- Retention and refurbishment of 1,251 council owned properties to a level above Decency Standard

- Refurbishment of external fabric and communal services to flat complexes

- Demolition of 891 properties, including four multi-storey blocks of flats (inclusive of owner occupied and leasehold properties)

- Provision of a minimum of 460 units for affordable rent

- Provision of c950 units for market sale

- Provision of a minimum of 25 units for intermediate housing opportunities

- Improved access and parking facilities through targeted re-modelling

- Design improvements to reduce opportunities for crime and improve perception of the area

The housing management function within the PFI area will be relinquished by Salix Homes in favour of the PFI contractor upon contract award. Services to be included in the PFI contract include:-

- Repairs & maintenance

- Re-servicing of voids

- Caretaking & cleaning

- Tenancy management

- Income collection & debt recovery

- Lettings

Under the lettings function the council will require the contractor to contract with the Choice Based Lettings system, currently administrated by Housing Connections Partnership, the Common Service Provider of this function across the city.

In developing the re-housing plan for Pendleton it was recognised that independent living in all our communities is vital.  The Supporting People Programme enables the council to develop long term housing options and priorities with partners in care and health.  Housing Connections Partnership and Supporting People are able to offer a range of services including assistance with applying for benefits, support settling into a new home, and support accessing medical and specialist services, amongst others.

## 1.7	Public Sector Comparator (PSC) and Value for Money (VfM)

The preferred PFI procurement route is expected to deliver Value for Money (VfM), in comparison to traditional procurement. The council has used the CLG bid pricing model and complied with the Treasury’s “Value for Money Assessment Guidance”. The council has considered:-

- Quantitative evaluation and

- Qualitative assessment

The initial results of the quantitative evaluation indicate that based on a blended equity IRR of 15%, the indicative PFI VfM is 4.93%.

## 1.8	Affordability

In accordance with guidance, the council has used the CLG financial model to calculate the level of Unitary Charge and additional contributions from the HRA.  The Model has been included as a supporting document to this OBC in Appendix 18.

The Model calculates that a Unitary Charge of £12.515 million at April 2011 prices will be required by the SPV to meet its contractual obligations.  The Unitary Charge will be funded from the following sources:-

- A PFI credit of £120.649 million, to which will be applied a PFI credit interest rate of 5.5%.

- Allocation of repairs and maintenance budget of £1,056 per unit per annum and supervision and management budget of £625 per unit per annum.  Both figures are based on 2008/09 allocations, indexing at RPI.

- Additional HRA revenue resources of £2.018 million per annum in April 2011 prices.

In addition to the above, £5.000 million of demolition costs and £7.000 million of home loss and disturbance costs will be funded outside of the PFI through the council’s capital budgets.

The council can confirm that based on the figures outlined above, the Project represents an affordable scheme.

## 1.9	Project Delivery Arrangements

The council will produce project documentation which is based on and consistent with the 4ps/CLG Housing Procurement Pack 2004 (HPP).  This includes use of the HPP guidance on development of a Payment Mechanism and Output Specification.  To compliment the output specification a Service Delivery Plan has been developed to further consider interface arrangements with key partners, where an overlap in service provision could be perceived.

The proposed length of the PFI contract is 30 years.  The council will utilise HPP and SoPC4 and hence key contractual issues such as termination, refinancing, change in law, indemnities, insurance and changes will follow this guidance.  It is not the council’s intention to have a separate Development Agreement to cover the terms under which the development sites will be disposed of to the private sector, but the council is prepared to be flexible on this issue.

## 1.10	Risk Allocation and Accounting Treatment

Project risks are identified and managed on a monthly basis by the appropriate task group.  Key risks are subsequently reported to the project team by each task group lead and are subsequently escalated to the Strategic Client Group and Housing Investment Options Programme Board as deemed appropriate by the Project Manager and Project Director.  The project risk register is also scrutinised and challenged internally on a bi-monthly basis by senior managers within the council.

The Pendleton PFI scheme will comply with the Accounting Code of Practice, HPP guidance and SoPC4.  The council is committed to achieving a risk balance that receives a positive accounting determination, and considers that an “off balance sheet” position should be achievable based on the proposed risk allocation structure.

## 1.11	Project Management, Governance and Delivery

A project governance structure is in place, which establishes clear roles and responsibilities within the decision making process. A number of task groups have been established to focus on finance, legal, master planning & land, technical & services and communications.  Each task group lead then provides a highlight report to the project team, to agree which items need to be reported to the Strategic Client Group for a decision.  Key project risks and items for approval are subsequently reported to the Housing Investment Options Programme Board and Portfolio Management Board.

## 1.12	Statutory Processes

The council has identified and considered the approach to a range of major statutory processes, which will come into effect as a direct result of the PFI scheme.  These issues cover planning, title arrangements, Notice of Intention to Demolish, compulsory purchase and blight notices, highways and footpath closures, leaseholders and Section 24 and 25 notices.

## 1.13	Commitment of Stakeholders and Sponsors

Extensive consultation has taken place with the local community since 2005 to develop a preferred investment option for the Pendleton area.  To support the work of these groups and provide consistent communications, a comprehensive Communications Strategy has been developed, to take the PFI scheme forward from OBC development and through procurement.

The council recognises that different people are able to commit different amounts of their time, and therefore have developed opportunities to encourage residents to participate at a level that suits them.  By working with appropriate agencies and utilising a wide variety of consultation techniques, the council will also ensure that hard to reach groups are adequately and appropriately consulted.

Members are aware of the level of commitment required to ensure a successful procurement is delivered, and Members across all parties within the council have shown their support for this scheme, including full Cabinet approval of the OBC.

# 2.0	Background to the Project

The council’s Expression of Interest for the proposed scheme in Pendleton was accepted onto the 5th round of the Private Finance Initiative programme on the 21st December 2006.

This Outline Business Case (OBC) describes the detailed strategic and financial assessment for the delivery of the proposed scheme.  The development of this document has been stakeholder focused ensuring that, in particular, the views and requirements of Pendleton’s community are at the centre of the proposals.

## 2.1	About the City of Salford

Salford is a city in transformation, building on its proud heritage and moving into an exciting future as a thriving cultural, economic and residential location.  From urban vibe to greenbelt tranquility, Salford is making the most of the diversity of its waterfront, urban and countryside environments to create places where people want to live, work, invest and visit.

Salford is in close proximity to Manchester city centre with excellent road and public transport links to all parts of the UK.  The city is well placed as a visitor and commercial centre with Manchester International Airport, gateway to over 200 international destinations, just a few miles away.  The city of Salford covers 37 square miles (60% being green space) and is home to approximately 220,000 people, 1,400 offices, 2,200 industrial premises, and 30 miles of rivers and canals.

### 2.1.1	Population

In 2001, Salford had a population of 216,103, consisting of a broad cross-section of people from a wide variety of ethnic and cultural backgrounds.  The city’s population is characterised by a higher than average proportion of single person households (36.7% compared to an average 30.0% for England and Wales), and a relatively low proportion of couples both with and without children (37.7% compared to an average of 44.8% for England and Wales, Census 2001).  The 2001 Census shows that Salford has a relatively young population, as one quarter of the population are below the age of 20 (25.8%).

### 2.1.2	Socio-Economic Data

Since 2001, the city’s employment rate has risen from 70.4% to 73.4% in 2005.  The city’s unemployment rate continues to fall, and in 2006, it stood at 3.7% and is moving towards the national average.

Salford has high levels of deprivation in neighbourhoods across the city, particularly located in Central Salford and certain areas of West Salford.  The 2007 Index of Multiple Deprivation identifies Salford as being the 15th most deprived local authority in England.  At a Super Output Area (SOA) level 29.4% of the city’s population live within neighbourhoods that are amongst the 7% most deprived nationally.

Although average household incomes in the city have risen, they are still around £1,000 below the Greater Manchester average.  In 2006, the mean household income for Salford was £28,400.  This difference with Greater Manchester may be partly explained by the higher than average proportion of people claiming Income Support benefit (6.2% compared to the UK average of 3.6%), the higher unemployment rate and the greater proportion of people aged 16-74 that are permanently sick/disabled (9.5% compared to the national average of 5.3% (Census 2001)).

Significant areas of Salford have been transformed in recent years through high profile regeneration schemes such as Salford Quays, but areas, such as Pendleton remain socially and physically deprived.  The council anticipates that the investment secured through Housing PFI will now offer the opportunity to kick-start comprehensive regeneration in the Pendleton area.

### 2.1.3	Salford City Council

In January 2006 the council’s detailed three year assessment (the corporate assessment) took place. The details of this assessment are available on the Audit Commission's website www.audit-commission.gov.uk.  This assessment recognised that:-

"the council has worked with its partners and the wider community to determine clear and challenging ambitions for the area which are aligned to local need. It is providing strong community leadership to deliver these ambitions which are widely shared, owned and understood by partners and stakeholders. These ambitions are driving the council’s and its partners approach to delivering improvements for local people".

In February 2008, the council received its latest judgement from the Audit Commission in which it was awarded three out of four stars and described as "improving well”. Two years ago the council had two stars.  In their report, the Audit Commission recognised the progress made by the council which has improved the lives of local people. The Commission stated that Salford had improved in most priority areas and overall its improvement compared well with other authorities.

## 2.2	Our Vision

Salford’s Community Plan, ‘Making the Vision Real 2006 – 2016’, outlines how the council and its partners will deliver the vision outlined below:-

‘In 2016, Salford will be a beautiful and welcoming city, driven by energetic and engaged communities of highly skilled, healthy and motivated citizens, who have built a diverse and prosperous culture and economy which encourages and recognises the contribution of everyone, for everyone’

The council wants to help create a city that is:-

- A healthy city

- A safe city

- A learning and creative city

- A city where children and young people are valued

- An inclusive city

- An economically prosperous city

- A city that’s good to live in

The council’s vision for housing is:-

‘To create a future where people see Salford as a great place to live.  A place where you can find a choice of popular homes in desirable locations, served by excellent housing services’

At a local level, ‘Shaping our Place’, the draft housing strategy for Salford for 2008 to 2011, states the council’s intention to ensure that the housing needs and aspirations of people are identified, and resources are spent on meeting local objectives.

The council remains committed to improving housing and housing services within the city for the benefit of customers and all Salford residents as part of the delivery of this vision.  The council will also aim to ensure that the city offers the highest quality housing in respect of:-

- Promoting independence

- Quality homes

- Affordable choice

- Excellent services

- Effective partnerships

This strategy has been drawn up following wide ranging consultation exercises.  The views of as many stakeholders as possible have been included in the strategy – including residents, customers, elected members, service delivery partners and officers of the council.

Establishing a PFI scheme within the Pendleton area will make a significant contribution towards achieving these priorities for the Pendleton community and will support the wider sustainability of the Central Salford area as a whole.

The audit commission has recently (June 08) concluded an inspection of the council’s strategic housing services.  The strategic housing service provided by the council is assessed as being a 'good', two star service with promising prospects for improvement.

The audit commission noted that ‘the council is achieving an impact in a number of areas as it seeks to balance its housing market, address affordability issues, improve private sector housing conditions and deliver services to vulnerable people in the community. Housing is a clear corporate priority and there has been some success at addressing conditions in the private sector and rebalancing housing markets. There is a strong approach to both involving the community and working in partnership at the strategic level. Partnering with the private sector has achieved success both in delivering new housing and value for money. Access to services for vulnerable people is easy and, set within a history of high levels of homelessness this is now starting to be addressed through embracing the prevention agenda. The council has a robust and up to date research base upon which to develop strategies and is focusing its efforts on delivering things which make a positive impact on local people’.

## 2.3	Decent Homes Investment Strategy

The council’s Decent Homes Investment Strategy brings together complex investment plans to form a long term and robust solution for achieving sustainable decent homes for all Salford housing stock.  Commended by the Community Housing Task Force, this investment strategy was developed through a three-phase housing options review process undertaken between December 2003 and May 2005.

This review concluded that a mixed investment strategy was the most appropriate way to obtain the level of funding that was necessary, and proposed that:-

- A Private Finance Initiative be pursued to deliver extensive refurbishment, remodelling and new build homes in the Pendleton area.

- A new Local Housing Company be established, to which homes in West Salford are transferred to deliver strong tenant involvement, increased investment and improved service delivery.

- A new regeneration focused ALMO be created to manage homes in Central Salford, Beechfarm and Rainsough Brow.

- A Common Services Provider be established to deliver a range of services to each of the new organisations to achieve consistent service delivery and efficiencies of scale.

- A strong strategic housing function is retained within the council to provide direction and set the overall housing strategy.

At that time, PFI was selected as the preferred option for the Pendleton area based upon the investment required to refurbish and remodel 1,255 homes and create the circumstances to re-provide a minimum of 232 new affordable homes. It was deemed that insufficient investment was available through both the ALMO and Stock Transfer options to achieve the vision for the area.

## 2.4	Pendleton PFI Objectives

The council and its partners have developed a series of scheme objectives, which will be used as core principles for evaluating and guiding the development of the PFI initiative. These objectives reflect the close relationship between PFI and planning guidance for the Pendleton regeneration area, and the achievement of the strategic objectives set out by the Housing Strategy.  These objectives are:-

- To create a better choice of quality housing, by refurbishing the retained social housing to the Decent Homes Standard and providing new build quality homes for social rent and sale by 2015.  All housing will address forthcoming statutory environmental and sustainability guidelines.

- To transform the image and future perceptions of Pendleton by improving the quality of housing design and open space, through good design techniques and guidance to develop future proof homes, which improve community safety and reduce the fear of crime by 2015.

- To ensure that local residents are fully involved in the planning, development, implementation and delivery of the scheme in partnership with other local stakeholders.

- To create mixed income sustainable communities which retain existing communities and attract new residents to the area, by improving housing choice, employment opportunities, retail and recreation facilities by 2025-2030.

- To support the regeneration and future success of the wider Central Salford area, the city and the Manchester city region.

# 3.0	Strategic Context

## 3.1	Scheme Context

It is vital that full consideration is given to the context within which the PFI and planning guidance for the Pendleton regeneration area is being developed. Both have a key role in supporting a range of other local, regional and national plans and strategies, and can in turn benefit from those other initiatives.  In particular, consideration needs to be given to the challenges and strategic documents outlined in this section.

## 3.2	National Policy Context

### 3.2.1	Sustainable Development

The concept of "sustainable development" is central to the current planning system, and therefore there is a requirement that the planning guidance for the Pendleton regeneration area ensures that new development contributes to the achievement of this principle.  Sustainable development is essentially about achieving the following, in a complimentary manner:-

- High and stable levels of economic growth and employment

- Social progress that meets the needs of everyone

- Effective protection of the built and natural environment

- The prudent use of natural resources

### 3.2.2	Sustainable Communities

Central Government defines “sustainable communities” as:-

‘Places where people want to live and work, now and in the future. They meet the diverse needs of existing and future residents, are sensitive to their environment, and contribute to a high quality of life. They are safe and inclusive, well planned, built and run, and offer equality of opportunity and good services to all.’

The overall aim of the council’s proposal ‘Creating a new Pendleton’ is to develop an inclusive community that meets the needs of all stakeholders for the long term.  A key component in achieving this vision will be the delivery of the PFI scheme, linked closely to the development of specific planning guidance for the Pendleton area and which is in alignment with the objectives of the Central Salford Urban Regeneration Company (URC).

### 3.2.3	Making Homes Decent

The Government believes that everyone should have the opportunity to have a decent home. Decent homes are important for the health and well-being of those living in them and are a key element to thriving, sustainable communities.

All councils and housing associations were challenged, by the Government, to meet the decent homes standard.  For local authorities who could not deliver the Decent Homes target by retaining their stock, three options were available to bring in the required investment (ALMO, stock transfer and PFI).  Following a city-wide stock option appraisal exercise, PFI was identified as the preferred investment route for Pendleton (see section 6.0 – Option Appraisal).  The investment secured through PFI will deliver a standard of improvement to properties that will achieve the Decent Homes standard as a minimum, and in addition will also provide the opportunity to achieve significant improvements to the environment.

### 3.2.4	Housing and Regeneration Bill

The Housing and Regeneration Bill proposes to establish the new Homes and Communities Agency (HCA) which will focus on delivering more affordable homes across all tenures and driving investment into regeneration.  The new agency will pioneer innovative and more efficient ways of working with key partners to support regeneration and provide decent places as well as decent homes.

The Bill also proposes to provide councils with more incentive and freedom to build new homes. Also, it will be mandatory for all new homes to be rated against the Code for Sustainable Homes.  The council intends to explore the opportunities being made available to councils within the Bill to ensure the regeneration of Pendleton is optimised and fulfils the objectives laid down at the commencement of the scheme.

## 3.3	Regional Strategies and Policy Framework

### 3.3.1	Northern Way Growth Strategy

The Northern Way Growth Strategy is seeking to reduce the economic disparities between the North of England and the rest of the country (currently a £29 billion output gap), in order to support the overall economic success of the country with a more balanced pattern of economic growth. The Manchester City Region, focused around Greater Manchester, is the North’s most successful economic area with the greatest economic prospects, particularly in areas such as the Regional Centre (which includes Salford Quays and the Chapel Street area within Salford).  Pendleton is well positioned to take advantage of this, and also to support the City Region’s success by providing the type of residential neighbourhood that will be attractive to both existing and potential new residents.

The current overall quality and nature of the City Region’s housing is acting as a constraint to further improved economic performance, as the quality of choice necessary to attract and retain sufficient numbers of wealth creators and skilled workers, particularly in the key growth sectors, is not present.  This reinforces the need to plan and provide for housing growth as well as support housing-led regeneration.  The Pendleton PFI scheme provides significant opportunities to begin to address this imbalance and meet the objectives of the Northern Way Growth Strategy.

### 3.3.2	Regional Spatial Strategy (RSS) for the North West

The draft RSS for the North West provides a framework for the distribution of regional housing provision over the period 2003 to 2021.  The required housing provision over this period, for Salford, was set at 28,800 new homes, equating to an annual average provision of 1,600 new dwellings, compared with the previous target of 530 dwellings.

Both the current approved and future draft version of the RSS place a strong emphasis on directing development and complimentary investment to the inner city areas of both the Manchester and Liverpool City Regions, such as Pendleton.

## 3.4	Sub-Regional Policy Framework

### 3.4.1	The Housing Market Report (Making Housing Count) 2007

‘Making Housing Count’ was commissioned by the Association of Greater Manchester Authorities (AGMA) in the autumn of 2005.  The aim of the report was to develop a robust and comprehensive evidence base to inform the development of a coherent strategy for housing across the Manchester City Region that would support the long term economic growth of the conurbation.

The final report highlighted that as a result of strong household growth, rising prosperity and prolonged economic growth, housing market conditions across the Manchester City Region have changed dramatically over the last decade.  This has resulted in a number of emerging issues including:-

- A lack of appropriate housing.

- Availability of affordable housing provision.

- Supply of social housing as re-letting of properties has diminished substantially as a result of lower turnover and higher house prices.

- Requirement for more interventionist approaches to neighbourhood management, to mitigate the negative impact of increased levels of private renting and higher turnover.

### 3.4.2	Manchester Salford Housing Market Renewal Pathfinder

The Manchester and Salford Housing Market Renewal Pathfinder (MSP), established in 2003, provides a long term strategy for ensuring transformation of weak housing markets across Manchester and Salford. The recent prospectus submitted to Government for 2008/11 for £163 million will continue the work carried out to date, including significant new development in targeted neighbourhoods and support for improvements to homes and the surrounding environment.

These two sub regional housing initiatives have been developed to support household growth arising from increased economic success, and to address housing issues rising from under investment. The economic plans set out in the City Region Development Plan have now been expanded upon in the draft Multi Area Agreement (MAA) for Greater Manchester in 2007.

The draft MAA includes a set of proposals around skills and employment, enterprise, innovation and sustainable growth, and infrastructure and housing. The two proposals that relate to housing include a number of actions:-

- A transformation in the overall quality and range of the residential offer

- A substantial increase in supply

- Enhanced access to affordable housing

- A more robust sub-regional planning framework

The MAA will add further clarity to the proposals set out in the Manchester City Region Development Programme, which sets out the scale of employment growth expected over the next fifteen years, estimated at over 100,000 additional jobs in the regional centre.

### 3.4.3	Greater  Manchester Strategic Housing Market Assessment

Deloitte and GMA Grimley were commissioned by the Association of Greater Manchester Authorities (AGMA) to carry out a housing market assessment covering the whole of the region.  Their initial findings were presented in April 2008, and included a number of conclusions which are mitigated to a degree by the anticipated outcomes of the PFI scheme, as follows:-

- There has been a significant increase in the working age population since 1997 contributing to the economic growth of the region but the supply of new housing to meet this increased demand has been uneven across the region.

- The high demand for family housing is not being matched by supply.  Areas of good quality family housing are often on the periphery and for many, outside their affordability envelope.

- The region contains significant pockets of young people and students but due to an overall increase in property prices, affordability is an issue and hence the ability to retain this element of the population.

## 3.5	Local Context

### 3.5.1	Community Plan

Salford's Community Plan, ‘Making the Vision Real’, was published in December 2005 and identified a clear vision for the city, as outlined in section 2.2.  The regeneration activity that is underway in Pendleton supports all the core themes within the plan, but  specifically contributes towards creating ‘a city that’s good to live in’.  This has an emphasis on protecting and improving the environment, and providing access to decent, affordable homes that meet the needs of local people.  It also identifies the importance of delivering large-scale physical regeneration and transformation in the city over the next ten years.

### 3.5.2	‘Shaping our Place’ – Draft Housing Strategy for Salford 2008-2011

The council’s draft strategy for housing, ‘Shaping our Place’, demonstrates how the council intends to work further towards achieving the five overarching goals as outlined in section 2.2.

Housing has a key role to play in the creation of neighbourhoods of choice, where good schools and services, high quality urban fabric, and good transport links support vibrant communities. Salford is at the heart of the City Region economy, contributing to and benefiting from the economic growth. This growth presents a new opportunity for the city.

‘Shaping our place’ focuses on all housing types in the city – social and private rented, owner occupied, general and supported housing. By giving an understanding of the current position the strategy sets clear priorities of how housing issues are to be dealt with. Many of these issues are complex and cannot be resolved by just one organisation. Therefore the Housing Strategy is the responsibility of, and will be delivered by a range of partners that make up the Salford Strategic Housing Partnership with the council being accountable for its delivery.

The Affordable Housing Strategy 2006 aimed to ensure that housing across all tenures was as accessible as possible, ensuring that local people could get a foot on the housing ladder.  Affordability is a key housing issue in the city; an updated strategy is currently being developed to respond to changes in Government Policy, the housing market and the city’s information base.

A Housing Needs Assessment was published in October 2007 and this stated a need for 674 affordable dwellings per annum.  The draft Affordable Housing Strategy Update sets out the tenure mix that will be needed to meet this need, and the sizes of properties required, findings on house prices and their relationship to income, affordable housing supply and considers the issue of key worker need.

### 3.5.3	Central Salford Urban Regeneration Company

The Central Salford Urban Regeneration Company (URC), approved by Central Government in January 2005, brings together private and public sector partners with the mission of driving forward the transformation of Central Salford and helping to create a vibrant, modern city. The company uses a mixture of public assets, funding and powers to attract high levels of private sector investment, stimulate quality development, and strategically deliver and co-ordinate the sustainable regeneration of the Central Salford area.

Their vision, outlined within the Regeneration Framework for Central Salford, states:-

‘Central Salford will be transformed. A beautiful, vibrant new urban centre with striking economic opportunity waiting to be born out of its fine heritage and the unveiling of its many natural assets. These include a wonderful meandering river and fantastic open spaces, which will be enhanced to provide a distinctive setting for the area. Where the City is fragmented it will be re-connected. The City's elegant but under-used buildings and its vacant but potent spaces will be filled with places to live, work, shop and enjoy life.’

This framework is consistent with the planning guidance for Pendleton.  Importantly it identifies Pendleton and the Shopping City as one of five Transformation Areas within the Central Salford area. These areas have been identified as places where focused investment will have the greatest potential for stimulating long term regional economic growth.  The URC’s aspiration is that Pendleton will become Central Salford’s shopping and community destination, and the gateway connecting neighbourhoods, Chapel Street/Salford City Centre and the Manchester regional centre. The URC will increasingly play a key role in the development and delivery of the transformation of neighbourhoods across Central Salford and in doing so bring the potential for significant added value to the PFI proposal.

# 4.0	Understanding Market Change and Housing Needs

In 2006 the council commissioned Fordham Research to carry out both an independent Housing Needs Assessment (HNA) in accordance with CLG guidance, and a supplementary   Strategic Housing Market Assessment.  Both studies were completed by October 2007.  The information from these studies, combined with consultation questionnaire results, Census 2001 data and databases from within the council have been used to analyse the current and future demand trends for housing both at a Pendleton and city wide level.

This section summarises the findings and conclusions from that analysis, and discusses the role which the Pendleton PFI scheme will play, in aligning future housing demand with a level of provision and tenure diversification, to secure the long term sustainability of the area.

## 4.1	Current Housing Provision

In 2007, 25% of Salford’s housing stock was council owned with a further 6% owned by Registered Social Landlords (RSL’s).  This represents a level of almost double that of the national average for social housing (18.2%).

The lack of tenure diversification has proven to be on a more significant scale within the PFI area, with 93.4% of all homes owned by the council.  The opportunity to exercise Right to Buy (RTB) has done little to dilute the level of council ownership in the area with only 149 completed applications over the last 26 years, 17% of which have become leaseholders.  This is presented below in greater detail in Table 1 – Tenure Diversification Analysis:-

Table 1 – Tenure Diversification Analysis

Source: Asset Management Database (September 2007), Council Tax Database (December 2007), RSL Database (May 2007), HIP HSSA 2007.

Property Type

Out of the 2,111 properties which make up the 93.4% council ownership, there are only 543 houses compared to the 1,259 properties defined as multi-storey flats.  This oversupply of council owned multi-storey flats, accounting for 60% of council stock, is presented in more detail in Table 2 – Breakdown of Property Type, below:-

Table 2 – Breakdown of Property Type

Source: Salford City Council Asset Management Database, September 2007.

Note: Non-council includes RTB and leaseholder properties but excludes RSL and multi-storey blocks in private ownership.

The high level of council owned multi-storey flats reinforces the narrow socio-economic composition of the area with 61% of Pendleton’s residents being one person households.

The limited variation in property type is compounded by the fact that over 50% of the council’s stock only has two bedrooms, with a further 24% being bedsits or one bedroom properties.  This is presented below in Table 3 – Property Size Analysis of Council Stock (within the PFI area):-

Table 3 – Property Size Analysis of Council Stock (within the PFI area)

Source: Salford City Council Asset Management Database, September 2007.

Although 21.9% of council properties have three or more bedrooms, 20% of those are within low rise flats and are therefore deemed as not preferable for family accommodation.  Unfortunately, given the limited level of suitable family housing in the area, these low rise flats are often taken up as a last resort by families seeking larger accommodation.  The scope of the PFI aims to redress this imbalance of supply.

## 4.2	Turnover

Overall, turnover is reducing across the Pendleton area but there is still substantial ‘churning’ in parts of the estate, especially in the multi-storey flats.  Although a level of demand exists, the source is primarily from transient households who are unconnected to the area and unlikely to stay in the long term. The council believes that this level of instability can be addressed through the PFI scheme by clearing certain elements of the stock, particularly multi-storey flats.  By reducing the supply, whilst retaining and refurbishing more popular homes to a higher standard, the council aims to manage long term demand more efficiently.

The more stable element of the population who live in flats would be consolidated into a smaller number of newly refurbished homes.  This will also reduce turnover rates, which in a significant number of multi-storey flats is at over 10% per annum, as outlined in more detail in Table 4 below:-

Table 4 – Turnover Analysis in Multi-Storey Flats

|  | Total voids 2006/07 | Total voids 2007/08 | Total number of properties | Turnover 2006/07 (%) | Turnover 2007/08 (%) |
| --- | --- | --- | --- | --- | --- |
| Holm Court | 0 | 1 | 76 | 0 | 1.3 |
| Malus Court | 6 | 2 | 83 | 7.2 | 2.4 |
| Hornbeam Court | 3 | 1 | 42 | 7.1 | 2.4 |
| Beech Court | 3 | 0 | 76 | 3.9 | 0.0 |
| Plane Court | 4 | 5 | 84 | 4.8 | 6.0 |
| Spruce Court | 29 | 35 | 176 | 16.5 | 19.9 |
| Salix Court | 3 | 1 | 67 | 4.5 | 1.5 |
| Thorn Court | 10 | 19 | 176 | 5.7 | 10.8 |
| Whitebeam Court | 7 | 6 | 44 | 15.9 | 13.6 |
| Peach Tree Court | 10 | 16 | 100 | 10.0 | 16.0 |
| Pear Tree Court | 9 | 7 | 100 | 9.0 | 7.0 |
| Apple Tree Court | 11 | 11 | 92 | 11.0 | 11.0 |
| Fitzwarren Court | 25 | 20 | 134 | 17.9 | 14.3 |
| Total | 120 | 124 | 1250 | 8.7 | 8.2 |

Through the PFI, four blocks (Fitzwarren Court; Peach, Pear & Apple Tree Courts) will be cleared and demolished, reducing the over supply of council owned multi-storey flats from 1250 to 824.

## 4.3	Demand

### 4.3.1	Current Analysis

As discussed in section 4.2, although turnover is reducing as a whole across the estate, there are pockets of properties where it remains unsustainably high, which supports the assumption that changes are required to both the supply and tenure of properties on offer.  Currently, 50% of residents have lived in their properties for less than 5 years indicating that if a sustainable future is to be secured for the Pendleton area then alongside the retention of the core long-term residents, replacement properties need to be provided which meet current and future need.

Table 5 below provides comparative data of the level of demand per vacancy for Pendleton against the figures at a city-wide level.  These figures are based on data drawn from the inception of the Choice Based Lettings system in August 2007 through to April 2008:-

Table 5 – Bid Per Vacancy Analysis

| Property Type/Size | City Wide Average 2007/08 | Pendleton Average 2007/08 |
| --- | --- | --- |
| 1 Bed High Rise | 34 | 44 |
| 1 Bed Low Rise | 33 | 24 |
| 2 Bed House | 89 | 86 |
| 2 Bed High Rise | 40 | 42 |
| 2 Bed Low Rise | 45 | 56 |
| 3 Bed House | 96 | 91 |
| 3 Bed Low Rise | 36 | 32 |
| 3 Bed Maisonette | 39 | 44 |
| 4 Bed House | 94 | 78 |

The council believes that investment is justified on those properties for retention based on the demand for good quality affordable homes for rent in the Pendleton area.  Demand for one bedroom flats is above the city average but this is partly due to the significant availability of such properties in the area.  This also accounts for the demand for two bedroom flats in both low rise and multi-storey accommodation compared to the city average.  Demand for three bedroom houses is slightly below the city average but still relatively high.  The limited availability of three bedroom houses can account for the willingness of applicants to apply for three bedroom maisonettes in an effort to secure appropriately sized accommodation in the Pendleton area.

Over the last five years, the number of people registering interest for three and four bed properties in Pendleton has increased from 838 applicants on the waiting list in 2003 to 1676 applicants in 2007.  As discussed earlier, the limited supply of suitable family accommodation leads many families to accept larger flats in low rise blocks.  The re-provision proposals within the PFI focus on providing larger traditionally viewed family accommodation to address this need.

### 4.3.2	Housing Questionnaire Survey

As an integral part of the consultation exercise carried out in 2007, described in greater detail in section 6.2, residents were asked for their views on their future housing aspirations.  17.9% of respondents stated that they would like to purchase their home or purchase a percentage of their home.  Of this 17.9%, 65% of respondents indicated that their preference would be to remain within the PFI area.  The inclusion of a mechanism to foster affordable home ownership will be provided through the Project documentation as part of the wider PFI scheme.  A minimum of 25 new properties within this intermediate housing category will be provided to facilitate those on lower incomes who wish to purchase their own homes, achieving the first step onto the property ladder.

The results of the survey also concluded that 60.3% of respondents would prefer to rent their future home from a Registered Social Landlord (RSL).  The opportunity for this increased choice will be delivered as part of the schemes’ proposals which include the provision of a minimum of 460 new homes for rent through an RSL.

### 4.3.3	Future Growth

Salford’s population is predicted to significantly increase over the next ten years, a position which is supported by research undertaken by ECOTEC Consortium.  In their report Modelling Demographics and Housing in Manchester and Salford published in February 2005, they predict an increase of 6000 households in Salford, between 2001 and 2016.

To further supplement the assumptions made in the report, it has recently been confirmed that Salford will be the future location for mediacity:uk.  This incorporates the relocation of a number of departments within the BBC to the north of England, creating further employment opportunities and investment in the area.  It is estimated that a further 15,000 new jobs will be created as a result of this new development.

In order for Pendleton to position itself to play a key role in the housing needs of this increase in population, a rationalisation of the oversupply of multi-storey flats is required combined with a level of replacement which reflects the needs of that growth.  The proposed demolition programme within the PFI scheme creates greater development opportunities through more efficient use of the land, both in terms of higher density levels and use of incidental space, which currently serves no defined purpose, enabling a level of tenure diversification to take place.

Pendleton is also adjacent to the University of Salford, which is currently home to over 2,500 staff members and approximately 18,000 students.  It is hoped that the regeneration of the Pendleton area will encourage graduates from the university to remain in the area and purchase or rent a home once they have completed their studies.

### 4.3.4	Future Role for Pendleton in the Housing Market

Pendleton currently fulfils a minimal role within the housing market, limited by the high propensity of unsuitable family orientated accommodation.   The proposed developments in the area will provide new housing opportunities for both existing and new residents. The close proximity of the Pendleton PFI area to Manchester and the regional centre will offer increased employment opportunities for residents and also for graduates of Salford University, and may attract new skills to the area.

The Pendleton PFI project aims to deliver a sustainable mix of properties inclusive of new one and two bed apartments for young professionals and individuals who wish to live in Pendleton, and three and four bedroom houses allowing families to remain in Pendleton, whilst attracting new households to the area.  The achievement of a shift in tenure diversification will lead to a dilution in the current concentration of economically inactive households.  By providing variety in the combination of property size and tenure type, there will be an increased likelihood of creating a mix of population in terms of age, lifestyle and economic status that will achieve long term sustainability.

The opportunity to realign housing provision to meet current and future market demand coupled with the employment opportunities available in Manchester city centre and Salford Quays provides Pendleton with a sound basis for the future.  The ability of Pendleton to fulfil its potential of attracting those on higher incomes will depend on the appropriate housing and environment being provided.

# 5.0	Business Need and Stock Condition

## 5.1	Estate Overview

Pendleton is an area that has experienced comprehensive redevelopment in the past, initiated by large-scale clearance in the early 1960’s.  The experimental construction techniques and design principles used in the replacement housing, together with the relative speed with which the built form failed, contributed to the deterioration in both the quality of the built environment and social fabric with crime and anti-social behaviour on the increase. Throughout the 1980’s and 1990’s Pendleton was the subject of a number of disconnected interventions which did little to improve the limited housing choice and connectivity with surrounding areas. Appendix 1 provides a location plan and identifies each of the individual estates included within this proposal.  A detailed analysis of each of the seven estates included within this scheme can be found in Appendix 2.

The council recognises that Pendleton needs to be revived under a comprehensive process of transformational change, for the benefit of Central Salford and ultimately for the wider sub-regional economy.  To achieve this, Pendleton requires a level of intervention on a size and scale which will have meaningful and measurable impact.  Piecemeal improvement and interventions in the past have tended to be reactive, and whilst addressing prominent issues they have failed to create genuine transformational change.  The Pendleton Housing PFI scheme will be the catalyst for this step change.

## 5.2	Stock Analysis and Property Numbers

The scheme currently consists of 2136 existing dwellings (including 25 leasehold properties). The majority of dwellings, particularly the multi-storey blocks, were built by the council in the 1970’s and are of mixed construction types and systems. A breakdown of the current property position is summarised in Table 6 below:-

Table 6 – Current Stock Breakdown

| Construction Type | Number of Bedrooms | Lease-holder | Total |
| --- | --- | --- | --- |
|  | 0 | 1 | 2 | 3 | 4 |  |  |
| Multi-Storey |  |  |  |  |  |  |  |
| Fram Gerrard | 3 | 95 | 194 | 0 | 0 | 8 | 300 |
| Bison | 0 | 44 | 89 | 1 | 0 | 1 | 135 |
| Concrete Frame | 14 | 226 | 584 | 0 | 0 | 10 | 834 |
| Total | 17 | 365 | 867 | 1 | 0 | 19 | 1269 |
| Traditional Low Rise |  |  |  |  |  |  |  |
| Flat Low Rise | 0 | 80 | 0 | 5 | 0 | 1 | 86 |
| Flat Medium Rise | 0 | 44 | 96 | 83 | 3 | 5 | 231 |
| Flat Over Shop | 0 | 1 | 0 | 0 | 0 | 0 | 1 |
| Maisonette Over Shop | 0 | 0 | 0 | 6 | 0 | 0 | 6 |
| Houses | 0 | 0 | 145 | 261 | 75 | 0 | 481 |
| Total | 0 | 125 | 241 | 355 | 78 | 6 | 805 |
| Wimpey No Fines (Low Rise) | 0 | 0 | 33 | 24 | 5 | 0 | 62 |
| Overall Total | 17 | 490 | 1141 | 380 | 83 | 25 | 2136 |

Of these 2136 dwellings, it is proposed to demolish 869 units including nine leasehold properties leaving 1267 dwellings (including 16 leaseholders) for refurbishment.  Overall 891 properties will be demolished inclusive of 22 owner occupied houses.  A percentage of the loss of council owned rented properties will be supplemented through a level of new build social housing within the area, provided through an RSL as part of the new development opportunities, which will be part enabled through the proposed demolition.   This revised position is summarised in Table 7 below:-

Table 7 – Stock Breakdown Post Demolition

| Construction Type | Number of Bedrooms | Lease-holder | Total |
| --- | --- | --- | --- |
|  | 0 | 1 | 2 | 3 | 4 |  |  |
| Multi-Storey - Concrete Frame | 14 | 226 | 584 | 0 | 0 | 10 | 834 |
| Traditional Low Rise |  |  |  |  |  |  |  |
| Flat Low Rise | 0 | 80 | 0 | 5 | 0 | 1 | 86 |
| Flat Medium Rise | 0 | 15 | 37 | 0 | 0 | 5 | 57 |
| Flat Over Shop | 0 | 1 | 0 | 0 | 0 | 0 | 1 |
| Maisonette Over Shop | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Houses | 0 | 0 | 140 | 122 | 27 | 0 | 289 |
| Total | 0 | 96 | 177 | 127 | 27 | 6 | 433 |
| Overall Total | 14 | 322 | 761 | 127 | 27 | 16 | 1267 |

### 5.2.1	Communal and Estate Facilities

Table 8 below indicates what communal and estate facilities are present across the PFI area.

Table 8 – Communal Facilities

| Estate | Communal Facilities | Estate Facilities |
| --- | --- | --- |
|  | Lifts | Door Entry Systems* | Common Room | Laundry Room | Garage |
| Broadwalk | 24 | 31 | 9 | 2 | 49 |
| High Street | 8 | 7 | 4 | 1 | 0 |
| Lindinnis/Denbigh | 0 | 0 | 0 | 0 | 0 |
| South Clarendon | 0 | 16 | 0 | 0 | 0 |
| Amersham Street | 0 | 47 | 0 | 0 | 0 |
| Athole Street | 0 | 0 | 0 | 0 | 0 |
| Nursery Street | 0 | 0 | 0 | 0 | 0 |
| Totals | 32 | 101 | 13 | 3 | 49 |

*number given indicates the number of fob/key access points within properties per estate.

## 5.3	Current Stock Condition and Investment Requirement

### 5.3.1	Stock Condition Survey

In 2003, the council commissioned Savills to undertake a condition survey to provide information to feed into the housing investment stock options appraisal process. This work provided a representative 17% condition sample across the city.  The survey estimated that overall 69% of council housing stock in Salford failed the Decent Homes Standard at that time. The figure for Pendleton was 73%.

The report concluded that although the council’s properties had been reasonably well maintained within the available resources, major capital investment had been lacking. Consequently, a significant number of major components had either reached or were near to reaching the end of their economic life and therefore required replacement. This was the key contributing factor leading to the high percentage of properties failing the Decent Homes Standard.

In 2005, following the council’s decision to review its housing investment options, an additional condition survey for the proposed Pendleton PFI area was commissioned on the advice of CLG. Urban Vision & Capita Symonds Ltd were engaged in December 2005 to carryout a full 100% survey to be followed by a series of specialist site investigations across the Pendleton area.

The contract was split over two phases. The first phase, comprising of a 60% sample, was completed in May 2006.  An interim set of condition data, representing a 27% sample was used to support the submission of the Expression of Interest.  To ensure that a representative and statistically accurate sample was achieved, over 170 property types were identified at the start of Phase 1 with each subject to proportionate sampling. The property types were defined by each dwelling’s location (block/street), type (house/flat) and configuration (mid/end terraced, ground/mid/top floor flat).  This approach has enabled the council to achieve a high level of certainty in the condition of the properties included within the PFI scheme.

The second phase of condition survey was commenced following approval from CLG to proceed with developing the Outline Business Case.  This condition survey, which was completed in August 2007, achieved a position where the council had up to date information covering over 80% of the stock in the PFI area.  The numbers of properties surveyed are presented in Table 9: -

Table 9 – Breakdown of Properties Surveyed

| Estate | Number of Properties | Numbers surveyed |
| --- | --- | --- |
| High Street Estate |  |  |
| Multi Storey |  |  |
| Apple Tree Court | 92 | 74 |
| Pear Tree Court | 100 | 81 |
| Peach Tree Court | 100 | 81 |
| Fitzwarren Court | 134 | 108 |
| Low Rise |  |  |
| Holcombe Close | 35 | 28 |
| Rosehill Close | 7 | 5 |
| Sedgefield Close | 16 | 13 |
| Brydon Close | 64 | 51 |
| Chartwell Close | 16 | 12 |
| Edghill Close | 49 | 40 |
| Fitzwarren Close | 5 | 4 |
| Denbigh Estate | 40 | 32 |
| Lindinis Estate | 71 | 57 |
| South Clarendon Estate | 215 | 174 |
| Nursery Street Estate | 73 | 59 |
| Athole Street Estate | 63 | 51 |
| Amersham Street Estate | 182 | 147 |
| Broadwalk Estate (multi storey) |  |  |
| Beech Court | 76 | 61 |
| Holm Court | 76 | 61 |
| Hornbeam Court | 42 | 34 |
| Lombardy Court | 26 | 21 |
| Plane Court | 84 | 68 |
| Salix Court | 67 | 54 |
| Spruce Court | 176 | 142 |
| Sycamore Court | 93 | 75 |
| Thorn Court | 176 | 142 |
| Whitebeam Court | 44 | 35 |

The council discussed the stock condition data it holds, along with bidders’ survey expectations and requirements, in market soundings held in January 2008. The majority of the organisations contacted stated they would require a further survey to be undertaken prior to bid submission.  As per expectation, the short-listed bidders would agree the survey brief and the list of organisations who would be invited to tender.  This level of input was considered essential for bidders and their funders, if they are to accept property condition risks.

Overall the indications are that, however reliable the council’s data, bidders will not be prepared to rely on the existing information, as they have had no input into the brief or any opportunity to select the organisations who have undertaken the inspections. The programme assumes that such a survey will be undertaken at short-listing stage. The outcome will also be warranted to the council and provide a further source of information on which the council can rely to assess the condition of the stock, and to further inform the council about the extent of the Latent Defects risk.

Allowance has been made within the programme for the Bidders’ Surveys to take place prior to finalising the Invitation to Submit Detailed Solutions (ISDS). It is anticipated that the results will be available to the council and bidders by September 2009. Final adjustments can then be made to the ISDS in discussion with bidders, before proposals are submitted in October 2009.

### 5.3.2	Multi-Storey Stock Condition

Whilst a number of the existing multi-storey blocks will be demolished as part of the project, a total of nine blocks will be retained and refurbished.  The council recognises that the refurbishment of the multi-storey blocks represents a risk to bidders and has therefore undertaken a significant amount of investigative work as outlined in this section.

The Building Research Establishment (BRE) was commissioned in 2001 to carry out intrusive structural surveys on the high-rise blocks, which were later reviewed by Curtin’s Consulting Engineers in 2003. Many of the high-rise blocks in the Pendleton PFI area were found to require extensive works in order to meet the Decent Homes Standard and be sustainable for the longer-term.

In 2007, Thomasons Consulting Civil & Structural Engineers were commissioned to review the investigation reports produced by both BRE and Curtins in relation to the nine multi-storey blocks proposed for inclusion within the Pendleton PFI Project. Their report confirmed that all the blocks suffered from similar defects, although the degree to which each suffered varied between blocks. Generally, the defects related to spalling concrete elements; the deterioration of concrete nibs and steelwork shelf angles and in cases, an inadequate number of wall ties, many of which have corroded. The report proposed a remedial works strategy for each block that would extend the life of the blocks for the life of the commission and potentially beyond.  The Thomasons report is attached as Appendix 3 with a summary of the remedial works, which have been used to inform the cost model for the scheme, presented in Table 10 below:-

Table 10 – Required External Remedial Works to Multi-Storey Flats

| Block | Remedial Works |
| --- | --- |
| Malus Court Plane Court | Removal or isolation of the existing wall ties and installation of new remedial stainless steel wall ties. Removal and reinstatement of stainless steel shelf angles. Cathodic protection for external cladding panels |
| Hornbeam Court Whitebeam Court | Removal or isolation of the existing wall ties and installation of new remedial stainless steel wall ties. Remove the concrete nibs and install stainless steel shelf angles to support the masonry at each floor level. Overclad parapet walls with removable weatherproof fascia. |
| Spruce Court Thorn Court | Works to Thorn Court already carried out by Salix Homes. Remedial works to Spruce Court to be delivered through the PFI. |
| Beech Court Holm Court | Removal or isolation of the existing wall ties and installation of new remedial stainless steel wall ties (could be undertaken in two phases). |
| Salix Court | Removal or isolation of the existing wall ties and installation of new remedial stainless steel wall ties (could be undertaken in two phases). |

For those high-rise blocks that are to be retained and refurbished within this proposal, the council has included for the provision of an external over-cladding system, as recommended by the specialist investigations.  Over-cladding provides a number of clear benefits in respect to preserving the structural integrity of the blocks primarily by preventing water ingress.  The proposed over-cladding systems will also have the additional non structural benefit of enhancing thermal performance and aesthetics of the building.  The proposed cladding systems summarised in Table 11 below, as recommended by Thomasons, would not be undertaken until the remedial works outlined in Table 10 had been carried out.

Table 11 – Over-Cladding Systems

| Block | Over-cladding System |
| --- | --- |
| Malus Court Plane Court | Cementitious or polymer-modified cementitious render mechanically fixed to the substrate through a layer of insulation. |
| Hornbeam Court Whitebeam Court | Thin-coat acrylic or polymer (cement-free) render mechanically fixed to the substrate through a layer of insulation. |
| Spruce Court Thorn Court | Pressure-equalised rain screen (cassette) system comprising an outer panel, a ventilated cavity and an inner leaf. Designed to deflect the majority of water off the outside face but allow any penetrating water to be disposed of through drainage. |
| Beech Court Holm Court | Thin-coat acrylic or polymer (cement-free) render mechanically fixed to the substrate through a layer of insulation. |
| Salix Court | Cementitious or polymer-modified cementitious render mechanically fixed to the substrate through a layer of insulation. |

Both the Curtins and Thomasons reports also recommended that as part of any over-cladding works, that the flat roofs of the blocks should be refurbished to prevent ingress of water into the upper storey and structure of the building. Complete replacement or overlaying with a single ply membrane (incorporating additional insulation) would minimise the extent of any ongoing repairs required and could provide a 30 year weather-tight roof.

### 5.3.3	Additional Specialist Surveys

In addition to the condition surveys, a number of specialist surveys/investigations were also commissioned by the council in order to ensure that both a robust cost model could be developed, and that any risk relating to stock condition could be confidently transferred to the contractor.

- Asbestos

Urban Vision were commissioned by the council in 2007 to undertake a fully compliant Type 2 material identification and assessment survey (Sampling Survey).  A 16% representative sample of the housing stock covering all construction types were surveyed inclusive of communal areas.  This data has been cloned to represent a 100% cost profile around asbestos remedial works which have been included within the build cost model. The asbestos visual and sampling works undertaken were not of an intrusive nature given that the properties surveyed were fully occupied.

Urban Vision have produced a fully detailed and comprehensive Asbestos Survey report including recommendations for each of the properties surveyed; the survey reports are compliant, certified and fully detailed as per the council’s briefing document.

- Wall Tie Surveys

Thomasons were commissioned by the council in October 2007 to undertake a preliminary wall tie survey to establish the condition of the cavity wall ties within the low-rise housing stock in a number of the Pendleton estates. A sample of the different types of properties were inspected on the different estates; 5% of the South Clarendon, Denbigh, Lindinis and Nursery Street (houses only) estates which are proposed for retention, and 1.4% of the High Street, Athole and Amersham estates which are considered for demolition.

The cavity wall ties within the properties inspected were generally in good condition with only slight evidence of corrosion and no loss of section. There was also no evidence of horizontal cracking or outwards bulging of the walls which often signify deterioration of the cavity wall ties.

- Ground Investigations

A ‘ward screening’ exercise has been undertaken for the Pendleton area by environmental services.  The study concluded that the area has had a varied history of previous industrial usage with chemical (including bleach and dye works), oil and engineering works noted across the area.

Overall the area was classified as a low/medium risk as the type of contaminants associated with such works are usually straightforward to remediate, with recommendations that sampling is undertaken in all areas where the ground is likely to be disturbed or utilised when undertaking new developments.  A series of ground investigation works have already been undertaken, but it is recognised that further sampling will be required in the future where sites currently require a level of demolition.

Ground investigations assessing geotechnical properties, ground gas and contaminants have been completed for the sites listed below, which have been identified for residential new build (please refer to Appendix 4 for a plan of the development opportunities):-

- Former Windsor High School

- Former Kingsley Court

- Athole & Amersham

- High Street

The level of sampling undertaken across key development sites has provided a level of certainty to costs relating to any required remediation works, thereby reducing the level of unknown contingencies in the future when establishing land valuations with bidders.  This is being further supplemented by studies for the presence of newts and Japanese Knotweed which are currently being undertaken by WSP Environmental, and will be completed by September 2008.

- Mechanical & Electrical (M&E)

In 2006 Urban Vision were commissioned by the council to undertake a fully compliant Mechanical, Electrical and Lifts Survey of selected multi-storey blocks inclusive of a representative sample of the different archetypes. The surveys undertaken were a visual non-intrusive inspection.

The reports include detail of the type of plant, its approximate age and overall condition along with suitability of the plant with an indication to its remaining serviceable life.  In line with the brief, representative and robust replacement costs have also been provided. These costs have subsequently been incorporated within the cost modelling data base.  Detail of the maintenance and servicing history of the plant is also identified within the reports.

- DDA

A fully compliant DDA Access Audit Survey across selected multi-storey and low-rise accommodation has been undertaken by Urban Vision. The survey, completed in 2007, is in accordance with Part III of the Disability Discrimination Act 1995 (Provision of Goods, Facilities and Services) and covers approach and entrance, entrances, car parking, horizontal & vertical circulation/way-finding provisions and means of escape. The purpose of this comprehensive report is to provide a basis for a structured, prioritised and costed programme of building works to be delivered as part of the PFI scheme. The associated costs for these works have again been used within the cost modelling data.

Also, whilst the main emphasis of the Access Audit Reports relate to public access to goods, facilities and services, Urban Vision have also included an element of cross-over relating to employment issues as per Part II of the DDA. This element will be further covered within the council’s bidder’s documentation.

- Fire Safety

In 2007, Urban Vision undertook a fully compliant Fire Survey Report across a representative sample of multi-storey and low-rise accommodation. The findings of this survey have been used to develop a programme of works which have been costed and included within the build cost model.  The works, to be delivered through the PFI scheme, will significantly improve the fire safety of the buildings, and ensure that a long-term fully compliant plan that meets the requirements of the Regulatory Reform (Fire Safety) Order 2005 is maintained.

- Energy Audit

Urban Vision were commissioned by the council in 2007 to undertake an Energy Audit on a representative selection of the stock within the PFI area. The results of the 60% sample survey have been recorded along with several energy audit reports and summaries.

## 5.4	Assessment of Capital and Lifecycle Costs

The survey information described above has been used by the council to determine the estimated refurbishment costs for the project.  This information has been analysed by the council’s advisors, Turner & Townsend, and they have produced the cost estimates shown in Appendix 5. Turner & Townsend have drawn on their knowledge of good industry practice, benchmarking through their own in-house database, and extensive experience of PFI schemes and other bids to inform their approach to pricing the project.  A summary report of the appraisal conducted by Turner & Townsend is attached as Appendix 6.

The low rise stock within the scheme comprises 41% of the dwellings for refurbishment and is of two main construction types.  93% of the low rise properties are of traditional brick cavity wall construction.  These are all construction types where the condition issues are well understood. The council and Turner & Townsend have assessed the works required, based on their experience, and consider the condition issues for these archetypes to represent relatively low risk.  As such, transferring the condition risks to the private sector is expected to be straightforward.  The remaining 7% are of a Wimpey No Fines construction and are all included within the proposals for demolition.

The council has recognised that the refurbishment requirements for the external elements of the multi-storey blocks are more complex to assess and therefore has sought additional guidance from Curtins and from Thomasons Consulting Civil & Structural.  Each company has reviewed, in 2003 and 2007 respectively, the intrusive structural assessments that were carried out on all the multi storey blocks by BRE Consulting in 2001.  The council is confident that a detailed works and associated cost profile have now been developed for the refurbishment of the external elements.   The approach and proposals for dealing with the external elements of the blocks to be retained are set out in more detail in section 5.3.2.

Turner & Townsend have prepared capital and lifecycle programmes and cost estimates for each property in the scheme (Appendix 7), based upon the stock survey information sourced from Urban Vision and Capita.  This has been complemented by the use of their own information sources, including benchmarking against other scheme costs, council data, and their experience of pricing PFI schemes for both the public and private sector.  The cost estimates are based on meeting the requirements set out in the Draft Output Specification, attached as Appendix 8.

## 5.5	Investment Need

An analysis of the significant level of stock condition information gathered by the council over the last 5 years, as outlined in section 5.3.1, has shown that the majority of dwellings proposed for retention within the scheme do not currently meet the Decent Homes Standard.  All the properties will either require comprehensive replacement of their fixtures and fittings in the first five years, or a minimum of once over the life of the contract.  The cost estimates for the scheme have been based on improving the high levels of non-decency in the early years of the contract, with £72.946m capital investment envisaged in years 1-5.

A five year programme is proposed to ensure that properties are refurbished within a relatively short, defined period, having regard to their current condition, but also taking into account the practicalities of working with tenants in-situ.  The minimisation of disruption to tenants will be achieved by effectively setting a limit on the extent of the works taking place within the estate at any one point in time.  The works may include:-

- Kitchen renewal

- Bathroom renewal

- Electrical installation renewal

- Heating and water system renewal

- Window renewal

- External door renewal

- Decoration

- Repairs to roofs

- Repair/replace gutters, rainwater and soil pipes

- General repairs & external painting

- Insulation and energy efficiency improvements

- Structural repairs to the fabric of the multi-storey blocks and the application of over-cladding system to improve energy efficiency and act as a rain screen.

- Refurbishment over the contract period of Communal Services to all flats, including Lifts, Mains Services, CCTV, aerials, door entry systems and redecoration of stair wells.

- Refurbishment of the communal facilities within the supported sheltered housing schemes, including the laundry, community room and kitchen.

The life cycle profile has been based on average component life and an assessment of the approaches to life cycle costing that bidders use.

## 5.6	Rationale for Retaining Stock

One of the key reasons behind the council’s decision to demolish specific multi-storey blocks is centred on construction type.  The four blocks allocated for demolition are all large panel system built properties, a construction type which, without significant investment, are not durable enough to provide the required life expectancy.  The loss of these blocks will also support the project objective of rationalising the level of social rented properties within multi-storey blocks in order to open up development opportunities for increased tenure diversification, as explained in greater detail in section 4.0.  The inclusion of Peach and Apple Tree Court within the demolition proposals further supports this principle as they are adjacent to the former Windsor High School site and can therefore be easily incorporated into the redevelopment of this specific area of the estate.

The four blocks allocated for demolition are all within the High Street estate which is an area with particular inherent design issues.  The low rise properties are inefficiently laid out, locking in isolated pockets of land which serve no clear defined purpose.  The positioning of the multi-storey blocks adjacent to the low rise properties also creates an uncomfortable scale differentiation with no gradual scaling or regard to modern urban design principles.  It is an acknowledgement of these factors, discussed in detail during the Option Appraisal process outlined in greater detail in section 6.0, which has led the council to take the decision that the whole of the High Street estate offers the best opportunity for delivering a significant level of the new build to achieve the desired level of tenure diversification.

The blocks for retention are all of a concrete frame construction for which, with specific remedial work and appropriate application of an external protective layer to reduce the effects of weathering, there is confidence that the life expectancy can surpass the concession period.  Excluding Spruce Court and Thorn Court, the remaining blocks for retention are all clustered around communal gardens and shared secured parking.  Isolating any of these blocks for inclusion within the demolition proposals to support the principle of rationalisation does not provide the redevelopment opportunities or accessible clearance which the other blocks provide.  In addition, the provision of properties refurbished to a high standard combined with a residualisation in the over-supply of multi-storey accommodation will in turn lead to a reduced turnover in some of these blocks where an above average turnover rate currently exists.

In the last five years Thorn Court has received significant investment including external structural repairs and a programme of kitchen and bathroom replacement.  The council is confident that this recent investment will improve confidence with residents which will in turn reduce the level of turnover.  It is hoped that this success can be repeated for Spruce Court once the required investment has been delivered through the PFI.  The reduction in the number of multi-storey flats in the area will also lend itself to improving the sustainability of these two landmark blocks.

In terms of the rationale for the low-rise stock retention, again this has been driven by construction type and consequently the value for money analysis of the required investment, combined with an assessment of the role the properties will play in meeting future housing requirements.

The Amersham Street estate currently consists of what is considered to be inappropriate family accommodation comprising of large three to four bedroom flats.  The sustainability of this stock is uncertain as families will continue to move out as and when more appropriate traditional family housing becomes available.  Where traditional housing exists on the Amersham Street estate, this will be retained. Lindinis, Denbigh and the Nursery Street estate, all offer traditional family housing and hence are very popular areas. These are all of a construction type where the condition issues are well understood and therefore where the council feels that any Latent Defect risk will be minimal, hence the decision to retain all the properties within these areas.

The South Clarendon estate, although inclusive of family houses, is set out in a ‘Radburn’ style which in theory should have provided a safe pedestrian environment.  Unfortunately, in practice it has provided a ‘warren’ of footpaths and areas of isolated space which has created an environment that lends its self to criminal activity and an extensive maintenance liability to the council.  The council’s proposed response to these problems is one of retention with a reform of the physical layout with actual demolition of houses kept to a minimum.  The creation of ‘traditional’ streets with the provision for in-curtillage parking or as a minimum, ability to park on the road-side, combined with a rationalisation of footpaths will design out a significant level of the current social problems.  The introduction of a new road system within this area also facilitates the utilisation of the former Kingsley Court site as a real development opportunity.

# 6.0	Options Appraisal

The council has undertaken a detailed and comprehensive analysis of a range of options for improving the built environment in Pendleton. This section describes the process and results of the assessment which has taken place to determine the best option for delivery of the objectives outlined in section 3.0.

## 6.1	Stage 1 – City-Wide Stock Options Appraisal

In October 2004, what was then the Office of Deputy Prime Minister (ODPM) confirmed to all local housing authorities that there were three options available for securing the additional resources required to meet and maintain the Decent Homes standard.  The options to consider were the creation of an Arms Length Management Organisation (ALMO), Private Finance Initiative (PFI) or stock transfer.

In developing the option appraisal framework, the council chose to divide the City into eight areas. One of the areas, Pendleton, was brought forward for early appraisal so as to maintain the potential for consideration as a PFI area in light of the timescales to develop an Expression of Interest, should a PFI prove to be the preferred choice of investment vehicle.

The options considered for the Pendleton area were:-

- Option 1 - Council retention

- Option 2 – Arms Length Management Organisation (ALMO)

- Option 3 - Private Finance Initiative (PFI)

- Option 4a - Stock transfer to an existing registered social landlord

- Option 4b - Stock transfer to a newly created local housing company

The option to ‘Do Nothing’ was disregarded for consideration as it did not represent a viable option to counteract the decline in the condition of the housing stock or in the quality and effectiveness of services to tenants and stakeholders.

### 6.1.1	Evaluation of Delivery Options

The options were identified and appraised in the ‘Housing Stock Options Appraisal - City Wide’ report (Draft May 2005) prepared by Price Waterhouse Coopers (PWC). Within this report, an evaluation matrix was developed and each option evaluated against an agreed set of criteria for each area.

The evaluation criteria used in the stock options appraisal process were based on the achievement of the council and project objectives.  The first four criteria outlined in Table 12, were deemed as absolutely essential.  Each criterion was assessed as one of:-

| ‘Yes’ | - | would be achievable |
| --- | --- | --- |
| ‘Looks possible’ | - | more likely to be achieved than not |
| ‘Probably not’ | - | less likely to be achieved |
| ‘No’ | - | would not be achievable |

A summary matrix detailing the results of the appraisal of each option for the Pendleton area is presented in Table 12:-

Table 12 – Evaluation of Delivery Options Summary Matrix

| Criteria | Option 1 Council Retention | Option 2 ALMO | Option 3 PFI | Option 4a Transfer RSL | Option 4b Transfer LHC |
| --- | --- | --- | --- | --- | --- |
| a) Meets decent homes and other essential repair expenditure requirements | No | Yes | Yes | Yes | Yes |
| b) Can be delivered | No | Looks possible | Looks possible | Probably not | Probably not |
| c) Is there enough money to deliver all necessary works and management over next 5 years? | No | Looks possible | Looks possible | Looks possible | Looks possible |
| d) Can this solution for your area fit with other local solutions to meet city wide needs? | No | Looks possible | Yes | Looks possible | Looks possible |
| e) Is there enough money to deliver all necessary works and management over next 30 years? | No | Probably not | Looks possible | Looks possible | Looks possible |
| f) Potential to exceed Decent Homes Standard | No | No | Yes | Looks possible | Looks possible |
| g) Popularity amongst tenants and residents | No | Looks possible | Yes | No | No |
| h) Will help give homes and estates a long term future | No | Probably not | Yes | Looks possible | Looks possible |
| i) Can help to achieve better performance and standards of service | No | Yes | Yes | Yes | Yes |
| j) Could offer a practical solution for the whole of the council’s stock | No | Probably not | No | No | No |
| k) Does it increase resident involvement and accountability? | No | Yes | Yes | Yes | Yes |
| l) Provides new governance opportunities for tenants and other stakeholders | No | Yes | Probably not | Yes | Yes |
| m) Maintains affordable rents/service charges | Yes | Yes | Yes | Yes | Yes |
| n) Tenancy rights protected | Yes | Yes | Yes | Looks possible | Looks possible |
| o) Provides money for new homes | No | No | Yes | Looks possible | Looks possible |
| p) Staff rights protected | Yes | Yes | Yes | Looks possible | Looks possible |

The analysis for Pendleton indicated that:-

- Council retention was not an option.  The report concluded that failure to adopt a sound investment strategy for the council owned homes in this area would counteract any proposed regeneration activity. Retention by the council did not represent a viable option to counteract the decline in the condition of the housing stock or in the quality and effectiveness of services to tenants and stakeholders.

- An ALMO solution was not appropriate for the area given the need to secure both improvements to the physical environment and achieve a required level of mixed tenure to ensure future sustainability.

- An RSL based solution was not feasible in view of the extent of the dowry requirement for the retained homes (estimated at £26,970 per retained home) in addition to the remodelling and redevelopment costs.

- The Option Appraisal Matrix indicated that PFI was preferable to both Transfer and ALMO solutions. The PFI model offered a higher level of investment beyond Decent Homes and provided investment for remodelling and new provision essential for the sustainability of the area, ensuring best fit with wider strategic housing market renewal and regeneration interventions.

- The PFI option also had the overwhelming support of tenants as evidenced through the consultation exercise which indicated that 68% of those consulted were in favour of PFI.

The results of the appraisal exercise concluded that the only viable option to achieve the objectives for Pendleton which had the support of stakeholders was via the PFI route.

## 6.2	Stage 2 – Detailed Assessment

The next stage in the option appraisal process entailed a detailed assessment of the stock within each individual estate, with the resultant Preferred Option to be delivered through PFI.  ‘Do Nothing’ and ‘Do Minimum’ options were considered for all of the estates within the PFI area throughout this second stage of the option appraisal process.

The ‘Do Nothing’ Option - was deemed to reflect a continuation of the current standard with only essential maintenance activity being carried out.

The ‘Do Minimum’ Option - related to the achievement of the Decent Homes Standard by carrying out Asset Management Plan Priority 1-3 repairs as outlined below:-

- Priority 1 - Urgent works that will prevent immediate closure of premises and/or address an immediate high risk to the health and safety of occupants and/or remedy a serious breach of legislation.

- Priority 2 - Essential work required within two years that will prevent serious deterioration of the fabric or services and/or address a medium risk to the health and safety of occupants and/or remedy a less serious breach of legislation.

- Priority 3 - Desirable work required within three to five years that will prevent deterioration of the fabric or services and/or address a low risk to the health and safety of occupants and/or remedy a less serious breach of legislation.

Further options to be considered for each individual estate began their development at the ‘Workshop Pendleton’ which was held from the 22nd to the 24th September 2005.  Approximately 150 stakeholders participated in this opportunity to discuss the ‘Prospects’ (ideas) for the area, facilitated through exhibitions, presentations and workshops.  The ideas and issues discussed at this event formed the basis of a range of development options for the area, which were detailed in an ‘Issues and Options’ Report, attached as Appendix 9.

In March 2006, the ‘Issues and Options’ report received in principle support from the Lead Member for Housing, the Pendleton PFI Group, and the Pendleton Community Forum.

Following this the ‘Issues and Options’ report was subject to a six week public consultation period between the 19th May and the 29th June 2006.  Overall feedback from the consultation was very positive, with support for the vision, strategic objectives and proposed options.  A number of challenges were identified, including the need to:-

- Create a balanced mix of housing provision across the area

- Improve the quality of public transport provision

- Take account of population increase in terms of the impact upon transport infrastructure

- Improve permeability through the area, including better cycling and pedestrian facilities

- Improve and increase the provision of open spaces

- Create high density development around the town centre and public transport facilities

- Improve the mix of employment initiatives and opportunities

- Reduce crime

The large number of broad options considered during the ‘Issues and Options’ consultation were later narrowed down to a range of common elements and three more detailed ‘Preferred Options’ (Appendix 10).  These options included proposals on how PFI investment will be spent in the area.  Residents were asked to indicate if they liked or disliked each of the options, and additional space was provided for general comments.

Consultation on the ‘Preferred Options’ with the local community and key stakeholders took place from the 15th June to the 26th July 2007. Over 30 events and a door knocking exercise were arranged to maximise opportunities for the local community to get involved and be at the heart of setting a framework for the areas regeneration over the next 10 -15 years. In total, approximately 6,500 questionnaires were sent, one to each residential address within the Pendleton regeneration area, which led to a 10.5% response rate.

In light of this consultation, a short-list of individual estate options remained for further appraisal as detailed in section 6.2.1.

### 6.2.1	Evaluation of Short List of Options

The evaluation criteria used in the options appraisal process for the project are based on the achievement of the council and project objectives described above.  The stock options for the project have been rigorously evaluated against three key criteria:-

- Technical and Masterplanning (25%) including Strategic Vision & Design, safety, environmental improvement, transport and connectivity and general land use.

- Finance (40%) including Affordability.

- Consultation (25%) outcomes and acceptability to stakeholders and the community.

Three evaluation teams, with appropriate expertise, assessed each criterion, and their scores and reports were considered by a Main Evaluation Panel, who awarded the final 10% of the marks, based on their assessment of the individual Evaluation Group reports and the overall comprehensiveness of each proposal.

A copy of the methodology and evaluation criteria and a full breakdown of the scores from the evaluation teams are contained in Appendix 11.  Individual reports from each of the three Evaluation Groups are presented in Appendix 12. A summary score profile is provided in Appendix 13.

## 6.3	Service Delivery Options

In July 2007, the council established Salix Homes, a new Arms Length Management Organisation (ALMO) for Central Salford responsible for delivery of the “landlord” services to approx 8,000 homes.  In addition, Salix Homes is also responsible for the management of those properties within the PFI area for an interim period until such time as service commencement by the PFI contractor. Currently, Salix Homes delivers its housing management services through the use of both its own core staff and through the use of sub-contractors.  One of the key organisations to which services are contracted out is Housing Connections Partnership (HCP).

HCP currently operates as a division within the council’s Housing & Planning Directorate, responsible for delivering a wide range of housing support services to residents and RSLs across Salford.  HCP delivers 12 key services which have been divided into four over-arching themes or portfolios which are:-

| Services for Independent Living Specialist Housing Services Salford Care on Call Sheltered Housing Extra Care | Housing Choice & Support Services Salford Home Search (Choice Based Lettings) Housing Advice & Support Services Supported Tenancies Social Housing Furnished Homes |
| --- | --- |
| Safer Homes, Safer Living Anti Social Behaviour Team Housing Crime Reduction | Customer, Business & Partnerships Innovation & Service Development Team |

### 6.3.1	Identification of Service Delivery Options

Within the housing PFI market place there are generally two options for the delivery of services through PFI:-

A.	Standard – which includes all of the services associated with ‘hard’ facilities management (FM) (repairs & maintenance, void property management, grounds & estate maintenance, caretaking and cleaning) and also those services regarded as ‘soft FM’ (lettings, tenancy management, income & debt recovery and tenant & resident involvement).

B.	Non-Standard – which includes the hard FM services only.  The delivery of the soft FM services is retained by the council directly or via the established ALMO.

The difference between the two options is driven by the need to include a RSL partner within the bidding consortium or not. Option A does require a RSL to be part of the consortium, with consortia bidding for schemes that follow Option B generally only consisting of a Funder(s), Builder and FM Service Provider.

In addition to the core housing management functions described above, the council also needed to consider how to deal with more specialist activities such as the management of Right to Buy applications, Sheltered and Supported housing and, specific to this scheme, the delivery of the Re-housing Plan.

### 6.3.2	Appraisal of Service Delivery Options

In summary, the two service delivery options available to the council were appraised with the conclusions drawn presented in Tables 13 and 14:-

Table 13 – Advantages of Each Respective Service Delivery Approach

| Advantages |
| --- |
| Option A - Standard | Option B – Non-Standard |
| Single point of contact through the PFI contractor | Council control over FM services (customer service) |
| Life cycle, maintenance and asset condition risks transferred to private sector | Life cycle, maintenance and asset condition risks transferred to private sector |
| Market is used to this type of PFI package | Retention of allocations function allows the council to control who lives where and prevents PFI operator ‘cherry-picking’. |
| Can draw upon benefits of “One Service”, coordination of activities | Potentially easier to incentivise the consortium to deliver its services. |
| Council does not need to appoint soft FM service provider (in-house or outsource) | Sheltered Accommodation remains council service, i.e. no premium for bringing in specialists. |

Table 14 - Disadvantages of Each Respective Service Delivery Approach

| Disadvantages |
| --- |
| Option A - Standard | Option B – Non-Standard |
| Council loses direct control over ‘soft’ FM services (customer service) | Council would have to appoint suitable resource to deliver ‘soft’ FM services (in-house or outsource) |
| Potential impact to ALMO, to be minimised through exploration of other business opportunities | Potential interface issues between the PFI operator and the ‘soft’ FM provider |
| Potentially have to pay a premium for debt funding/rent collection whilst it is being recovered | No One Stop Shop for Pendleton Housing PFI |
| Poor performance of contractor impacts on whole service. | Difficult to manage cash-flow if debt needs to be recovered – Consortium still needs paying |
| Running of Sheltered Accommodation could require specialist FM service provider | Need to develop a consortium payback mechanism for properties sold under Right-to-Buy. |

### 6.3.3	Preferred Approach

After consideration of all the issues involved it was agreed at both the Housing Investment Options Programme Board and endorsed at Portfolio Management Board to include the Standard Service options package within the PFI Scheme.

In addition to the PFI Contractor providing services, Salix Homes and HCP also play a key role in discharging the council’s social housing responsibilities. Formal and clearly defined interfaces between Salix Homes, HCP and the PFI Contractor will need to be considered to cover those areas where there could be confusion caused by a perceived service overlap, typical areas of consideration are CCTV security, allocations, grounds maintenance and community/tenant involvement.  The proposed division of services is outlined in the Service Delivery Plan attached as Appendix 14.

## 6.4	Market Sounding

Over the last three years the council has hosted a number of open days, undertaken market questionnaires and carried out a range of interviews, to establish an indication as to whether the scheme and proposed procurement approach will be of interest to the market.  The consultation with the market can be summarised as follows:-

| Market Open Day | - | 24th January 2005 |
| --- | --- | --- |
| Market Questionnaire | - | Late January 2005 |
| Market Open Day | - | 25th November 2005 |
| Informal Interviews | - | March 2006 |
| Market Questionnaire | - | June/July 2007 |
| Market Open Day | - | 12th July 2007 |
| Informal Interviews | - | July 2007 |
| Market Questionnaire | - | January 2008 |

### 6.4.1	Phase One – Investment Route

During 2005, the council hosted two Soft Market Testing days. Both events were well attended by a selection of funders, RSLs, developers and contractors, many of whom were experienced in bidding for housing PFI contracts as well as having an awareness of existing regeneration programmes in the Central Salford area.

The first event was held on the 24th January 2005 focusing on:-

- The strategic context in terms of stock options appraisal and the HMR Pathfinder

- Pendleton master planning process

- Key opportunities

- Area profile

- Stock condition

- Initial scope of contract

- A provisional timetable for project development

Key challenges raised by the group included:-

- The alignment of PFI and master planning

- ‘Quick wins’ to maintain momentum and interest within the community

- Output specification requirements need to be reflected in the stock condition survey brief

The second event, held on the 25th November 2005, set the context to the PFI proposals, but focused mainly on the significant progress that had been made since the previous event, in terms of developing the housing options.   As part of the master planning process a workshop was held where two groups discussed the following three questions:-

- What are your views on the Prospects for Pendleton?

- What would encourage you to invest in Pendleton?

- What are the barriers to investing in Pendleton?

Common themes, raised by both workshop groups, related to the importance of phasing the development, in particular plans for Shopping City, the neighbouring areas and improved roads and transport.  The attendees said they would be encouraged to bid for a PFI contract in Pendleton if they could see that work had started that would improve the general Pendleton area.  Price, style, position and branding were also discussed, with health and educational attainment highlighted as essential for the creation of a place where people want to live and work.  Overall the outline proposals were well received with many organisations demonstrating their commitment to the scheme as well as the approach being undertaken, by signing a Statement of Intent, copies of which are attached as Appendix 15.

### 6.4.2	Phase Two – Scope Development

During 2006, informal interviews were held with a number of private sector organisations, who represented a broad spectrum of interests within the housing PFI market in the North West.   The interviews focused on the areas of:-

- Marketability of the project

- The PFI boundary

- Stock retention levels

- Tenure mix

- Stock outside council ownership

- Opportunities for land packages

- Specific proposal feedback divided by estate

The views expressed, demonstrate that the scheme is an attractive investment opportunity to the private sector.  The risk associated with the inclusion, for refurbishment, of a large number of multi-storey blocks was highlighted. Suggestions were made for a more comprehensive programme of demolition. Concurrent with the previous year’s feedback, the redevelopment of land parcels around the periphery of the site would help to raise the perception of the area as a good investment opportunity.

### 6.4.3	Phase Three – Refinement of Scope

Following confirmation of the preferred housing option for the area in December 2007, a market questionnaire was distributed in January 2008.  Each question appears in turn in the following section, followed by a summary of the responses.

- Phased Building & Demolition

Based on the assumption that all of the development will be included as part of a development agreement linked to the PFI contract, would you express a view about how you would potentially phase a project of this nature, particularly given the level of re-housing?

Most respondents suggested that they would commence re-provision works on the current cleared sites, followed by a phased approach of decant and re-provision.  It was recognised that the re-provision would need co-ordinating with the refurbishment programme and would be dependent on sales pace and affordable re-provision requirements.

- Re-housing Programme

The council would not be in a position to provide vacant possession of all the new development opportunities prior to financial close given the level of clearance proposed.  The expectation would be that the successful contractor would take responsibility for the delivery of the re-housing programme.  What are your views on this approach?

The proposed approach was acceptable to the market, subject to an amount of risk sharing.  The ultimate risk for obtaining possession of properties from tenants would remain with the council.  The contractor would be responsible for re-housing into PFI stock (retained and new build), but the council would be responsible for re-housing elsewhere in Salford.  To support the re-housing programme it was suggested that council considers a moratorium on letting and the use of short term tenancies, whilst the RSL provider could look to utilise any of their vacant stock.

- Mixed Tenure Development

How attractive are the residential development opportunities.  Do you consider the proposed outputs for new homes for affordable and market sale realistic and achievable?

The proposed development sites were considered to be an attractive proposition, in particular their close proximity to Salford University, Manchester City Centre, Salford Quays, transport links etc.  The sites were also viewed to be of a sufficient size to change perceptions of the area.

The required outputs for new build and affordable homes were considered realistic and deliverable, but it was recognised that this would be dependent upon prevailing market conditions and the regeneration of the wider Pendleton area.

- Refurbishment Works

The council proposes that the successful contractor should undertake all the refurbishment works (including multi-storey blocks) with tenants in-situ. What are your views on this approach?

This approach is common within the market and one that is achievable based on experience of other schemes. Resident consultation is essential to discuss the level of disruption and timing of works. Disruption to supplies needs to be kept to a minimum, and temporary facilities provided where necessary e.g. respite facilities. Decants would be used as a last resort in exceptional circumstances for vulnerable people or where asbestos had been found. No access was identified as a potential risk; however the authority would be responsible for developing an appropriate protocol.

- Standard PFI Contract

The council proposes to include all housing management functions within the PFI contract except for the referral of prospective new tenants through the Choice Based Lettings System. What are your views on this approach?

The inclusion of housing management functions was considered a good approach and enhanced the attractiveness of the scheme.  Use of the Choice Based Lettings System was viewed as acceptable, but would need to be reflected in the payment mechanism where re-let times are a potential KPI for the contractor.  The alternative approach would be to pass any penalties via a Service Level Agreement to the CBL service.

- Multi-Storey Refurbishment

The council has opted to retain and refurbish a number of multi-storey residential blocks within the scope of the project.  Please can you identify some of the key issues which may concern you and how these may be mitigated by the council prior to the procurement phase?

The main concern raised was around stock condition, asbestos and structural integrity. The council would need to demonstrate that the blocks have more than a 25-year life expectancy and can be improved at a reasonable cost.  This would also include the achievement of a high SAP rating in an economic manner.

Additional areas of potential risk related to the safety and security of the residents both during and after refurbishment and leaseholder support to the refurbishment plan, including the recovery of charges.  The payment mechanism should also consider potential for multiple failures caused by a single event e.g. lift breaking down.  It was suggested that the council considers capping the private sectors exposure in this respect in order to achieve value for money.

- Retail & Community Facilities

In addition to the services offered by the main shopping precinct at Shopping City the council would like to re-provide a more localised centre incorporating a small number of shops and potentially some community facilities. Does the inclusion of this development make the overall package more or less attractive?

There were mixed views from the market when considering the provision of a localised centre.  Whilst a centre would be advantageous to provide a focal point for the area (which is currently skewed by the position and size of Shopping City), it was recognised that it is often difficult to make these developments commercially stack up without some cross subsidy or they need to be incorporated in a development with well used community facilities.  There would also be revenue funding implications for the ongoing maintenance and management of the facilities.

There were some concerns regarding the viability of shops located under the high-rise blocks, in particular their attractiveness to retailers, passing trade, security and anti-social behaviour.  It was however recognised that some of these concerns could be addressed through careful management.

- Planning Guidance

The council is developing planning guidance for Pendleton which is likely to be adopted in December 2008.  Please can you explain any views you may have regarding the council’s preference for a guidance approach rather than obtaining outline permission?

Planning guidance was viewed as being the most preferable approach as this offers greatest flexibility and fosters the delivery of innovative solutions.  It was suggested that a higher quality scheme will be developed if guidelines are set in terms of the exact numbers of properties to be achieved.  This would also enable bids to be compared on a “like for like” basis.

### 6.4.4	Summary of Response to the Market

The proposals for the Pendleton PFI scheme have evolved over time with the views of the private sector informing the refinement of the scope and framework for procurement.  The council is confident that a proposal has been developed which is attractive to the market and deliverable.  Specific responses in light of market advice have included:-

- Removal of unsustainable and system built multi-storey blocks from the scheme.

- Further structural investigations on the multi-storey blocks commissioned.

- Scope of services included within the contract clearly defined.

- Additional ground investigations for redevelopment areas commissioned.

- High level of certainty in relation to stock condition reached, following completion of 80% survey.

- Completion of the Re-housing Plan, in line with key partners from the Strategic Housing Partnership.

- Clarity on new build densities and parameters of design through the development of an area specific planning guidance document.

- Development of a communications framework to ensure that the local community continue to be engaged and support the proposals.

In order to build upon existing market interest and to ensure a successful and competitive procurement, the council intends to hold a bidders’ information day and provide a marketing prospectus outlining a summary of the scheme within the information supplied, during the OJEU and pre-qualification period.

In addition to the above, the council has also provided certainty to the private sector that the regeneration of the Pendleton area will not take place in isolation.  A number of initiatives have already commenced including:-

- Periphery redevelopment in Langworthy by Urban Splash.

- New LIFT centre currently under construction

- Improved green space e.g. redevelopment of Chimney Pot Park.

- Production of Planning guidance to support the PFI process and outline planning applications

- Discussions are on-going with the owner of Shopping City in relation to future investment and expansion, linking into proposals for a new food superstore in the area

- Successful Affordable Housing Programme bids to deliver 38 units.

# 7.0	Preferred Option

Following the option appraisal process, the overall scope of the PFI scheme and associated development element, under the umbrella of ‘Creating a New Pendleton’, includes:-

- Retention and refurbishment of 1,251 council owned properties to a level above Decency Standard.

- Refurbishment of external fabric and communal services to flat complexes.

- Demolition of 891 properties, including four multi-storey blocks of flats (inclusive of owner occupied and leasehold properties).

- Provision of a minimum of 460 units for affordable rent.

- Provision of c950 units for market sale.

- Provision of a minimum of 25 units for intermediate housing opportunities.

- Improved access and parking facilities through targeted re-modelling.

- Design improvements to reduce opportunities for crime and improve perception of the area.

The housing management function within the PFI area will be relinquished by Salix Homes in favour of the PFI contractor upon contract award.  The council will work with Salix Homes to minimise the impact of this change and look for other business opportunities in the housing market for its ALMO.  Services to be included in the PFI contract include:-

- Repairs & maintenance

- Re-servicing of voids

- Caretaking & cleaning

- Tenancy management

- Income collection & debt recovery

- Lettings

Under the lettings function the council will require the contractor to contract with the Choice Based Lettings system, currently administrated by Housing Connections Partnership, the Common Service Provider of this function across the city.

## 7.1	Development Opportunities

The delivery of the new affordable homes and homes for outright sale will be procured as a single contract integrated within the PFI scheme.  The council will therefore be able to ensure that a comprehensive approach is adopted in relation to the physical redevelopment of the area, as bidders will have to provide a holistic master plan within their proposals.

The council has identified several opportunities for new housing developments to complement the refurbishment works to be carried out through the PFI scheme.  A number of the sites have already undergone clearance which will enable the contractor to commence new build early on in the programme to facilitate the delivery of the Pendleton Re-housing Plan.  All sites are in council ownership and are identified on the plan found in Appendix 4.

- Site 1 – Former Windsor High School Site

The site was occupied by the former Windsor High School (now demolished) and is bound by Churchill Way to the north and West High Street to the south.  The site occupies an area of approximately 3.9 hectares of land with mixed cover.  The majority of the site is grassed with some mature trees along the northern boundary.  Tarmac covered areas include the former school car park and former play area.

- Site 2 – Former Kingsley Court Site

The site was occupied by a block of flats (Kingsley Court), which has now been demolished.  The site currently occupies an area of approximately 0.6 hectares of derelict ground with a mixed cover of concrete and tarmac hard-standing, grass, bushes and brick and concrete hardcore.

- Site 3 – Former Wrotham Close Site

The site was occupied by a block of low rise flats (Wrotham Court), which has now been demolished.  The site currently occupies an area of approximately 0.63 hectares of derelict ground with a mixed cover.

The other potential redevelopment sites also identified on the plan in Appendix 4 require a level of clearance.  They are primarily residential in nature and include the following:-

- Site 4 – High Street

This site includes all four of the multi-storey blocks proposed for demolition (Fitzwarren Court, Apple Tree Court, Pear Tree Court and Peach Tree Court).  These four blocks account for 440 of the 641 properties for clearance in the High Street area.  The remaining properties consist of houses and maisonettes, which are laid out in such a way as to create pockets of vacant land interspersed throughout the estate.  This land offers no defined use and is often locked in by surrounding development offering little opportunity to redevelop in isolation.  Once cleared this site offers an area of 10.52 hectares for new homes.

- Site 5 – Amersham Street

Low-rise flats are the predominant property type within this proposed clearance area.  In total 174 flats will be demolished, none of which are leaseholder properties, to create a development opportunity of 3.17 hectares in size.

- Site 6 – Athole Street

This area consists of 76 houses, 14 of which are Right to Buy properties.  The area lies adjacent to Amersham Street and will therefore offer the opportunity to create a significant new development consisting of modern family homes.  This site is 2.48 hectares in size.

## 7.2	Pendleton Re-housing Plan

The council recognises that to deliver this scheme a robust and deliverable re-housing plan is required.  The Pendleton Re-housing Plan, attached as Appendix 16, has been developed in conjunction with the council’s partners, via the Strategic Housing Partnership, in an effort to ensure that all parties responsible for its delivery are signed up to the proposed phasing and timescales.

The aims of the Re-housing Plan are to:-

- Maximise the number of residents in Pendleton who wish to remain in the area

- Make the most effective use of available properties to facilitate the delivery of the scheme during the refurbishment phase

- Minimise the visual impact of empty properties

- Minimise the management and security costs associated with empty properties

- Ensure that health, social, cultural, educational and support networks are taken into account as a key element of the re-housing process

- Ensure that tenants have as great a choice as possible when moving to a new home in terms of location and tenure

- Ensure that specialist support is provided for elderly and vulnerable residents

- Provide those leaseholders and homeowners requiring re-housing with valuations of their properties early on in the delivery of the Re-housing Strategy.

To assist in the development of the plan, a realistic baseline for housing redevelopment across the PFI area was agreed, taking account of the range of densities and housing type which each site could yield.  The proposed densities and property type are in line with the planning guidance and overall objectives for the regeneration of Pendleton.

As detailed above, the scope of works within the PFI scheme entails the clearance of a total of 891 properties, including leaseholders and RTBs.  Further limited demolition may be required as part of the remodelling proposals for the South Clarendon estate but the number, if any, cannot be defined at this stage as it is dependent upon bidder’s proposals.  The council will inform bidders that the level of clearance in South Clarendon should be kept to an absolute minimum when designing their proposals.

The council is confident that, through the adoption of a number of mechanisms to facilitate the clearance programme, the delivery of the Pendleton Re-housing Plan is achievable.  The focus of this plan, on confirmation of the OBC approval, is the council’s intention to adopt a Local Lettings Policy to ensure those residents with a preference to remain in the area are given priority for any void properties within the stock designated for retention.

There are also a number of new developments taking place on the periphery of the PFI area for which the council has secured 100% nomination rights for the affordable social housing element.  Those residents within properties earmarked for demolition will be prioritised for these properties.

The Pendleton Re-housing Plan includes a time-line which highlights the breakdown of annual void rates and new build re-provision set against the phasing plan over the next eight years.  This annual status table, in line with the overall PFI programme, will provide confidence to the private sector that the achievement of vacant possession of all development opportunities within the scheme is deliverable.

### 7.2.1	Supporting Vulnerable Groups

Independent living in all our communities is vital.  The Supporting People Programme was introduced in April 2003 to help vulnerable people to live independently in their own homes.

In 2005, a five year Supporting People strategy was launched. The programme enables the council to develop long term housing options and priorities with partners in care and health.

The Supporting People team is governed by a Core Strategy Group and Commissioning Body which consists of key partners including the Probation Service, the Primary Care Trust, Health and Social Care, service provider representatives, service user representatives and other departments within Salford City Council.

The programme is responsive to individual needs and choices, supporting a wide range of issues including health, disabilities, lifestyles and social circumstances.

Delivery of the re-housing plan will ensure that individual needs, circumstances and choices are adequately assessed during the re-housing process.  Information obtained during one-to-one interviews will be used to develop tailored support packages.

The council will work in partnership with Housing Connections Partnership (HCP) and Supporting People to ensure a range of services are available, to provide advice and support to allow residents to successfully live independently and maintain their tenancy.  The services available to residents engage with a range of client groups including older people, teenage parents and clients aged under 18, women fleeing or at risk of domestic violence, refugees, offenders and clients at risk of re-offending, and clients with drug and alcohol issues.  The council are able to offer a range of services through HCP and Supporting People including assistance with applying for benefits, support with settling into a new home, and support accessing medical and specialist services, amongst others.

# 8.0	Public Sector Comparator (PSC) and Value for Money (VfM)

Treasury guidance states that a PFI funding option must be rigorously tested for VfM when compared to a traditional procurement route, considering both qualitative and quantitative factors.  The results of this exercise, as completed on the Preferred Option, have been set out below.

The Value for Money (VfM) appraisal detailed in this section has been carried out in accordance with the conventions set out in the following guidance:-

- “Appraisal and Evaluation in Central Government” (known as the Treasury’s Green Book); and

- “Value for Money Assessment Guidance”, issued by HM Treasury in November 2003

## 8.1	Qualitative Assessment

A PFI procurement route must be considered in terms of viability, desirability and achievability. The inclusion of soft services within a PFI project should also be considered from a VfM perspective.  The VfM qualitative assessment has been undertaken and has identified the following as relevant:-

Table 15 - Qualitative Assessment

| Element | Comment |
| --- | --- |
| Viability | There are no strategic or policy reasons why building construction, lifecycle and facilities management services should be retained within the public sector. Successful PFI schemes have demonstrated that efficient services can be maintained over the long term by the private sector, with guaranteed levels of performance within a contractual framework that provides accountability. The Section 151 Officer of Salford City Council is satisfied that, when considering PFI, suitable long-term contracts can be constructed and any strategic or regulatory issues (where applicable) can be overcome. |
| Desirability | The involvement of the private sector under a PFI contract will allow the transfer of risks from the public sector where the private sector is the party best able to manage them. A well managed procurement will also align the interests of the private sector and the council as far as possible, in order to allow the utilisation of private sector resources and skills to realise the vision for the Pendleton area. It is considered that a desirable level of risk transfer could be achieved under a PFI for the Preferred Option using the 4P’s standard documentation. The Section 151 officer of Salford City Council is satisfied that PFI would bring sufficient benefits that would outweigh the expected higher costs of capital and any other disadvantages. |
| Achievability | Current indications are that there is sufficient capacity within the market to allow a successful PFI procurement. Over the last three years the council has hosted a number of open days, undertaken market questionnaires and carried out a range of interviews, to establish an indication as to whether the scheme and proposed procurement approach will be of interest to the market. Following confirmation of the preferred housing option for the area in December 2007, a market questionnaire was distributed in January 2008. The details of this and all other market sounding undertaken are discussed in further detail in section 6.4. The council has previously procured a schools PFI project, and has its Building Schools for the Future scheme in procurement. The benefits of this experience will be fed into the project team for the Pendleton PFI Project in order to enhance deliverability. There are currently uncertain conditions within the funding markets. However, soundings undertaken by Ernst & Young, the council’s financial advisors, have indicated that there is still sufficient appetite for projects of this type. The council has also procured technical, financial and legal advisors and an independent tenant advisor, bringing experience in the delivery of housing PFI schemes to support and strengthen the project team. The Section 151 officer of Salford City Council is satisfied that a PFI procurement programme is achievable, given an assessment of the market, the council’s resources and the attractiveness of the proposal to the market. |
| Housing Management | Treasury Guidance requires that the delivery of soft services is considered against a number of factors including whole life costs, effective management, the integration of design, integration of services, and the whole life cost of the asset. The nature of the Pendleton scheme, in particular the emphasis on area regeneration and the impact of this on the effective design, maintenance and upkeep of public and shared spaces, means that it is intended to include housing management services in the PFI contract. The Section 151 officer of Salford City Council is satisfied that the overall benefits of including housing management services in the Pendleton PFI contracts will outweigh any additional costs and constraints from inclusion. |

The qualitative assessment indicates that a PFI procurement route is viable, desirable and achievable for the Preferred Option.

## 8.2	Quantitative Assessment

In order to identify which procurement option offers VfM a quantitative assessment has been carried out, which compares the relative costs of undertaking a PFI versus a traditional procurement. The purpose of the quantitative VfM appraisal is to identify the total costs to the council of traditional procurement and PFI for the Preferred Option, expressed in terms of Net Present Values (NPVs).

The cost of procurement through PFI has been calculated using the CLG HRA and non-HRA Template Model (“the Model”) and accompanying User Guide.  The Model then compares the NPV of the unitary charge with the risk adjusted costs of traditional procurement.

The key costing assumptions made in the quantitative assessment are detailed in the Data Book (see Appendix 17).

The results from the financial model entitled “Salford City Council_Outline Business Case (OBC) Model.xls” (“the Model”), indicate that, based on blended equity IRR of 15%, the indicative PFI VfM is 4.93%.  The model is included as a supporting document to this OBC attached as Appendix 18. A range of IRRs have been considered to determine the impact that this would have on the indicative PFI VfM, and these are set out in Table 16:-

Table 16 – Indicative PFI VfM

| IRR | Indicative PFI VfM |
| --- | --- |
| 13% | 6.21% |
| 15% | 4.93% |
| 18% | 2.95% |

The results therefore demonstrate that a PFI procurement route represents VfM when compared against a traditionally procured option.

A real rate of 3.5% and a nominal discount rate of 6.0875% have been applied within this quantitative analysis.

## 8.3	Risk Analysis and Management

Risk management arrangements are in place and a risk register has been established to document, monitor and control the risks associated with the project.  Due to the early stage of the project, entries on the Risk Register have not yet been fully costed but have been rated as high, medium or low risk to ensure that they are appropriately monitored.  Therefore an optimism bias adjustment has been adopted in the interim to assess the financial risks associated with the project.  As the scheme moves closer to financial close, it is anticipated that the optimism bias will be superseded by a fully costed risk register.  This approach is as envisaged by the Treasury Green Book (“the Green Book”).

## 8.4	Optimism Bias

Optimism bias reflects the tendency for project developers and appraisers to be overly optimistic in their assumptions about future benefits, and to understate the capital and operating costs associated with a project.  To redress this tendency, appraisers need to make explicit adjustments for this bias based on empirical evidence and adjusted for the specifics of the project.  Optimism bias will reduce as the project specifics are worked up in more detail, being replaced by more project specific risks.

The assumptions included in the OBC Model are based on the Green Book.  The OBC Model requires inputs for both Pre-Financial close and Post-Financial close where mitigation factors can be identified.  The tables in this section identify both sets of inputs.  The Pre-Financial Close optimism bias is applied to both the PFI and publicly funded options.  The Post-Financial close optimism bias is applied to only the publicly funded option.

A workshop was held with key members of the project team in order to establish an initial level of optimism bias to be applied in the VfM analysis.  The output from this workshop was then reviewed and updated prior to OBC submission.  This workshop and subsequent review considered the various mitigation factors that potentially could be applied.  At this stage, the following adjustments have been applied to the different costs to allow for optimism bias.

### 8.4.1	Capital Expenditure Optimism Bias

For capital expenditure the factors are as demonstrated in Table 17 below: -

Table 17 - Capital Expenditure Optimism Bias

| Upper Bound Optimism Bias: | 24.0% |  |
| --- | --- | --- |
|  |  | (1) Mitigation factor |
|  | Uplift % | Pre- Financial Close | Post-Financial Close |
| Procurement |  |  |  |
| Late Contractor Involvement in Design | 2.0 |  |  |
| Poor Contractor Capabilities | 9.0 | 0.5 |  |
| Dispute and Claims Occurred | 29.0 |  |  |
| Project Specific |  |  |  |
| Design Complexity | 1.0 | 0.5 |  |
| Degree of Innovation | 4.0 |  |  |
| Client Specific |  |  |  |
| Inadequacy of the Business Case | 33.0 | 0.5 |  |
| Project Management Team | 1.0 | 0.8 |  |
| Poor Project Intelligence | 2.0 | 0.5 |  |
| Other (specify) | 1.0 |  |  |
| Environment |  |  |  |
| Public Relations | 2.0 | 1.0 |  |
| Site characteristics | 2.0 | 0.3 |  |
| External Influences |  |  |  |
| Economic | 11.0 | 0.5 |  |
| Legislation/Regulations | 3.0 |  |  |
| Total | 100 |  |  |

The mitigation factors are applied to the percentage of bias figures stipulated in order to reduce the optimism bias adjustment for the capital expenditure under each of the options by applying the following formula:

Upper Bound 24% x (100- sum(% of Bias x Mitigation Factor))%

The above pre-financial close capital expenditure mitigating factors have been applied on the following basis:

- Poor Contractor Capabilities: There are a number of experienced bidders in the market that have expressed an interest in the scheme.  The selected contractor is therefore likely to have previous experience, and their capabilities will be rigorously tested through the procurement process.

- Design Complexity: The design of the scheme is not considered to be overly complex, and the council has experience of similar schemes.

- Inadequacy of the Business Case: The business case has been prepared in accordance with guidance issued in the Housing PFI Procurement Pack, and the council has experience of successful submission of previous business cases.  A significant level of work has been completed in terms of scope and costings to enhance the robustness of the financial analysis.

- Project Management Team: A dedicated project management team has been established which includes PFI project managers and input from appropriately qualified and experienced technical, legal, and financial advisors.

- Poor Project Intelligence: A significant level of work has been completed on the project to date including a full stock condition survey and numerous specialist surveys (e.g. asbestos, structural etc).  This has significantly increased the level of information available on the housing stock in the project.

- Public Relations: Extensive consultation events have been completed to liaise with and obtain views of a range of stakeholders.  These views have been afforded appropriate consideration in the development of the OBC.

- Site Characteristics: There are no specific site characteristics that are felt to increase the risk to the project in this case.

- Economic: The economic assumptions within this OBC are believed to be robust and have been reviewed by the project team and their financial advisor.  These are discussed in further detail in Section 9 (Affordability) of this OBC.

To date, no mitigating factors have been applied to the post-financial close capital expenditure optimism bias due to the early stage in the procurement process.

### 8.4.2	Lifecycle Expenditure Optimism Bias

A similar approach has then been taken with respect to the optimism bias on lifecycle expenditure.  The following mitigation factors have been applied to the optimism bias:-

Table 18 - Lifecycle Expenditure Optimism Bias

| Upper Bound Optimism Bias: | 24.0% |  |
| --- | --- | --- |
|  | Uplift % | (1) Mitigation factor |
|  |  | Pre- Financial Close | Post-Financial Close |
| Procurement |  |  |  |
| Other (specify) | 7.0 |  |  |
| Client Specific |  |  |  |
| Inadequacy of the Business Case | 52.0 | 0.5 |  |
| Poor Project Intelligence | 32.0 | 0.5 |  |
| Environment |  |  |  |
| External Influences |  |  |  |
| Technology | 9.0 | 0.5 |  |
| Total | 100 |  |  |

The above pre-financial close lifecycle expenditure mitigating factors have been applied on the following basis:-

- Inadequacy of the Business Case: The business case has been prepared in accordance with guidance issued in the Housing PFI Procurement Pack, and the council has experience of successful submission of previous business cases.  A significant level of work has been completed in terms of scope and costings to enhance the robustness of the financial analysis.

- Poor Project Intelligence: A significant level of work has been completed on the project to date including a full stock condition survey and numerous specialist surveys (eg asbestos, structural etc).  This has significantly increased the level of information available on the housing stock in the project.

- Technology: The project scope and delivery is not especially dependent on technology.

To date, no mitigating factors have been applied to the post-financial close lifecycle expenditure optimism bias due to the early stage in the procurement process.

### 8.4.3	Operating Expenditure Optimism Bias

The following mitigation factors have been applied to the optimism bias in relation to operating expenditure under each option:-

Table 19 - Operating Expenditure Optimism Bias

| Upper Bound Optimism Bias: | 41.0% |  |
| --- | --- | --- |
|  | Uplift % | (1) Mitigation factor |
|  |  | Pre- Financial Close | Post-Financial Close |
| Procurement |  |  |  |
| Project Specific |  |  |  |
| Client Specific |  |  |  |
| Inadequacy of the Business Case | 52.0 | 0.5 |  |
| Poor Project Intelligence | 32.0 | 0.5 | 0.5 |
| Environment |  |  |  |
| External Influences |  |  |  |
| Technology | 9.0 | 0.5 |  |
| Total | 100 |  |  |

The mitigation factors are applied to the % of bias figures stipulated in order to reduce the optimism bias adjustment for the operating expenditure under each of the options by applying the following formula:

Upper Bound 41% x (100- sum(% of Bias x Mitigation Factor))%

The above pre-financial close operating expenditure mitigating factors have been applied on the following basis:-

- Inadequacy of the Business Case: The business case has been prepared in accordance with guidance issued in the Housing PFI Procurement Pack, and the council has experience of successful submission of previous business cases.  A significant level of work has been completed in terms of scope and costings to enhance the robustness of the financial analysis.

- Poor Project Intelligence: A significant level of work has been completed on the project to date including a full stock condition survey and numerous specialist surveys (e.g. asbestos, structural etc).  This has significantly increased the level of information available on the housing stock in the project.  The council also has experience of the management of such projects which further mitigates the associated risk.

- Technology: The project scope and delivery is not particularly dependent on technology.

A mitigating factor has been applied to the post-financial close operating expenditure optimism bias:-

- Poor Project Intelligence: Although the council has limited experience of the capital expenditure and lifecycle expenditure elements of such projects, a significant level of information available to inform the level of operating costs that are likely to be incurred on the stock in question.  This information has been used to inform the costings used in the financial modelling.

No other mitigating factors have been applied due to the early stage in the procurement process.

### 8.4.4	Optimism Bias Overview

As a result of the above assessments, the following optimism bias levels have been applied in the model:-

Table 20 – Optimism Bias

|  | Pre-FBC | Post-FBC |
| --- | --- | --- |
| Capital expenditure | 17% | 24% |
| Lifecycle maintenance expenditure | 13% | 24% |
| Facilities management expenditure | 22% | 34% |

Following the completion of the above optimism bias, an assessment has been made of the outputs to confirm that this is consistent with the overall ‘feel’ of the project.  Given the management experience of such schemes that the council has and the factors discussed above, it is felt that the optimism bias is a fair reflection of the overall arrangements that are in place.

## 8.5	Taxation Adjustment

Where publicly financed options are compared to PFI options, an adjustment must be made to the PSC to reflect the differential UK corporation tax liabilities of conventional  procurement compared to the SPV set up to undertake the PFI contract.  In accordance with the Supplementary Green Book Guidance, a taxation adjustment of 5% has been determined.

This reflects the fact that the nominal cost for facilities management is likely to be about the same as the capital value of the project, at least 50% of the lifecycle maintenance the supplier will provide is on new build and improvements, rather than repairs, and the project will be on the revenue account for tax purposes.

## 8.6	VfM Sensitivities

The indifference points on the variable assumptions within the VfM analysis are set out below.  These have been identified using the Treasury VfM Model, as attached to the CLG HRA Model.

Table 21 – VfM Indifference Points

| Variable | Indifference Point |
| --- | --- |
| Capital expenditure (PSC) | Reduce by 10% |
| Non-employment Operating costs (PSC) | Reduce by 6% |
| Transaction costs (PSC) | Reduce by 1212% |
| Unitary charge (PFI) | Increase by 6% |

## 8.7	Conclusions to VfM Analysis

Both the qualitative and quantitative analysis which has been completed as part of this assessment indicates that a PFI procurement route would provide VfM for the Pendleton PFI scheme.  The council believes that as a result of the work which has been conducted, the sensitivity analysis detailed above and in particular the strength of the qualitative assessment, this conclusion is sufficiently robust.  Therefore, it is proposed that the project identified above is procured through a PFI route.

# 9.0	Affordability

The council is committed to project affordability and will only proceed with a project that it is satisfied is affordable in both the short term and the medium to long term.

This affordability section considers both the affordability of the 1,251 units to be included in the PFI contract, and the re-provision of 460 new build social rented units to be provided by an RSL partner in addition to 25 intermediate units. In addition, c950 new build houses for sale will be provided.

## 9.1	Scheme Affordability

The overall affordability of the project has been assessed in Table 22 below:-

Table 22 - Scheme Affordability

|  | Revenue | Capital | Land |
| --- | --- | --- | --- |
| PFI Credits | £120.649m (equating to HRA grant of £8.301m p.a.) |  |  |
| Repairs & Maintenance Allowances at £1,056 per unit per annum for 1251 units (at 2008/09 prices) | £1.321m per annum |  |  |
| Supervision & Management at £625 per unit per annum for 1251 units (at 2008/09 prices) | £0.782m per annum |  |  |
| Additional HRA revenue resource | £2.018m per annum |  |  |
| Demolition costs |  | £5.000m |  |
| Home loss and disturbance |  | £7.000m |  |
| Land Value |  |  | £6.950m |

## 9.2	PFI Affordability

In accordance with CLG guidance the council have submitted a financial model entitled “Salford City Council_Outline Business Case (OBC) Model.xls” to support the financial requirement.  The Model has been included as a supporting document to this OBC in Appendix 18.  The key assumptions underpinning this model are contained in the Data Book also attached as a supporting document as Appendix 17.

The Model calculates that a Unitary Charge of £12.515 million at April 2011 prices will be required by the SPV to meet its contractual obligations.  A proportion of the Unitary Charge will be inflated by RPI on 1 April in each contract year.  The proportion indexed will be set with reference to the underlying cost base of the SPV, and is currently assumed to be c60%.

Table 23 below sets out the key figures in relation to the Pendleton PFI project:-

Table 23 - Project Key Figures

| Financial Close | Construction start date | Construction period | Total capital costs | Unitary charge | NPV of unitary charges at service commence-ment date |
| --- | --- | --- | --- | --- | --- |
| 1 April 2011 | 1 April 2011 | 5 years | £80.479m | £12.515m | £210.491m |

The Unitary Charge will be funded from the following sources:-

- A PFI credit of £120.649 million, to which will be applied a PFI credit interest rate of 5.5%.

- Allocation of repairs and maintenance budget of £1,056 per unit per annum and supervision and management budget of £625 per unit per annum.  Both figures are based on 2008/09 allocations, indexing at RPI.

- Additional HRA revenue resources of £2.018 million per annum in April 2011 prices.

In addition to the above, £5.000 million of demolition costs and £7.000 million of home loss and disturbance costs will be funded outside of the PFI through the council’s capital budgets.

The PFI credit requirement assumed is in accordance with discussions with CLG at the meeting on 24th April 2008 and subsequently as the financial analysis has been finalised.  The PFI credit ceiling calculated by the CLG v1.8 model, in line with funding guidelines, is £121.307 million.  The level of credit required is therefore within this ceiling.

The council can confirm that based on the figures outlined above, the Project represents an affordable scheme.

## 9.3	New Build Affordability

It is proposed to deliver the following new build units as a single contract integrated with the PFI scheme rather than under a separate Development Agreement.  This is explained further in section 10.4.

Table 24 - New Build Units

|  | Units |
| --- | --- |
| New RSL units funded by NAHP | 460 |
| Intermediate units | 25 |
| Private units for sale | Circa 950 |
| Total units | Circa 1,435 |

In order to facilitate this provision, council owned land has been identified for which an upper and lower band valuation has been provided by the council’s valuers Urban Vision in April 2008. Assuming a mid-point of these valuations, it is estimated that a capital receipt of £6.950 million could be realised from the circa 950 new build for sale units. However in order to facilitate the provision of the RSL and Intermediate units the council anticipates that it will have to accept a less than best value for this land, which will require Section 25 consent from the Secretary of State.

The council has also had ongoing discussions with the Housing Corporation and an indication has been given that they would consider, in principle, providing grant of approximately £11.618m through the National Affordable Housing Programme (‘NAHP’) for 276 affordable homes for rent.

The current expectation is that through provision of land at a less than best consideration, drawdown of anticipated Housing Corporation grant along with resources available to the RSL or other provider, will allow these units to be delivered without any additional resourcing requirement from the council. However, depending on how the development market responds to the current financial climate, the council is aware there may be a need for additional financial support on the affordable units development.

## 9.4	Sensitivities

Analysis has been undertaken around areas of sensitivity that could impact on the overall affordability of the project.  The key areas of sensitivity have been assessed as changes to the PFI funding margin and movements in the value of land that will be used to cross subsidise the RSL new build, and these are summarised as follows:-

Table 25 - Key Sensitivities

| Sensitivity | Additional Resourcing Requirement | Actions Taken |
| --- | --- | --- |
| PFI - Increase in funding margin by 0.5% | £167k per annum (£133 per unit) | The current funding terms include a swap rate of 5.50% and margins of 100 bps. Whilst this is 50 bps in excess of the current market position of 5.00%, an increase in funding costs of a further 50 bps would cause the unitary charge to increase by £232,000. Given the existing buffer an increase is not considered likely at this stage, but the funding situation will be kept under review throughout the procurement process. |
| Proceeds from sale of land – failure to achieve midpoint land valuation | £3,545k | An assessment of the upper and lower land value thresholds has been undertaken, providing a range of £7.090 million as identified above based upon upper and lower land values of £10.496 million and £3.406 million respectively. The midpoint of this range has been used as the base valuation within this OBC. In order to negate any net funding requirement for the RSL new builds, a valuation of £8.347 million would need to be achieved. |

The council has completed its stock condition survey as well as a number of specialist surveys and used these to inform the costs included in the Model.  The affordability cash flows are therefore deemed to be robust.  However, a number of scenarios have been considered that could adversely effect the affordability position of the Project.  The financial impact of such scenarios and the actions that would be taken to address them have been considered below.  This approach is presented in Table 26:-

Table 26 – Affordability Sensitivities

| Sensitivity | Additional Revenue Requirement per Annum | Actions Taken |
| --- | --- | --- |
| Six month delay to procurement | £150k | The timetable that has been set by the council is believed to be robust, and indexation on build costs has been assumed to the mid point of construction. The council would also request in the ISDS documentation that bidders maintain their fixed price for six months post financial close. In the event of a delay and a cost increase, the council would consider the options available to mitigate such an increase, such as a reduction in cost, or the identification of any additional resources in the HRA or capital budgets. |
| 50% Increase in insurance costs | £254k | The insurance market has seen significant increases in premiums in the past. Insurance cost increases are revenue in nature, and as such any increase would not be expected to be funded by the PFI subsidy. Instead, the council would look to release additional funds from the HRA. |
| Increase in housing maintenance and management costs of 10% | £256k | The council is confident in its costings for housing management and maintenance and, as such, would not expect to see an increase in these costs. However, if these costs were to increase, the council would consider any available revenue resources from the HRA, or reducing the scope of services to be delivered through the PFI. |
| Capital costs increase by 10% | £575k | The council is confident in its costings for capital works and, as such, would not expect to see an increase in these costs. However, if these costs were to increase, the council would consider any available capital resources, or reducing the scope of the capital plan to be delivered through the PFI. |

Under each of the sensitivities set out above, the council is confident that the impact can be mitigated by actions that do not involve significantly re-scoping the Project.

## 9.5	Conclusion to Affordability Analysis

Both the affordability and sensitivity analysis undertaken as part of this assessment indicates that a PFI procurement route would provide affordability for the Pendleton PFI scheme.  The council believes that, as a result of the work which has been conducted, this conclusion is sufficiently robust.

# 10.0	Project Delivery Arrangements

The council will produce project documentation which is based on and consistent with the 4Ps/CLG Housing Procurement Pack 2004 (HPP). This includes use of the HPP guidance on development of a Payment Mechanism and Output Specification.

## 10.1	Project Agreement

The Project Agreement will be based on the Model 13A Project Agreement set out in the HPP as updated in November 2007 to incorporate Standardisation of PFI Contracts Version 4 (SoPC4) published in March 2007.  All bidders will be evaluated on their willingness and ability to adhere to the Model 13A Project Agreement and in particular to those elements of it which are required drafting in SoPC4.

The Project Agreement will be certified for the purposes of the Local Government Contracts Act 1997.

### 10.1.1	Approach to Key Contractual Issues

As stated above, the council will utilise HPP and SoPC4 and hence key contractual issues such as termination, refinancing, changes in law, indemnities, insurance and changes will follow HPP and SoPC4.

The council only envisages derogations from HPP/SoPC4 being required for project specific reasons including the following:-

- ground condition and property risk (including asbestos) to tie into the survey information to be provided by the council to bidders (and to be further developed with bidders if necessary);

- changes to accommodate the different types of property included in the project e.g. social rented owned by the council, social rented owned by an RSL and private for sale properties.  This will involve changes to the definitions and to clauses such as the maintenance clause as not all of these properties will be maintained under the Project Agreement in the Unitary Charge;

- property provisions to deal with the different types of property (e.g. leasehold or freehold transfer of the private for sale properties and licence arrangements for the social rented properties owned by the council); and

- changes to the Schedules and Appendices to reflect the detail of the project.

### 10.1.2	Structure & Length of Contract

With regard to the contractual framework of the project, the council:-

- will be flexible and listen to the requirements and concerns of the market with regards to the detail of the contractual structure of the Project; and

- recognises that the solutions adopted by bidders (driven by the make up of their consortia, where the development risk is to lie within the consortia and tax considerations) will dictate the detail of the contractual structure for the project.

Accordingly the detail of the contractual structure will be worked up with bidders during the Competitive Dialogue process.

The council does, however, envisage the contractual structure to be adopted to be based on the following model:-

- a single Project Agreement comprising both the provision of the council owned social houses and the development properties (private for sale, shared ownership and the RSL provided social rented properties).  This is likely to be between the council and a Special Purpose Vehicle (SPV).

- the SPV will have an exclusive right to design, build or refurbish, finance and operate the houses that form the project.  In addition to the Project Agreement there will be a Funder's Direct Agreement between the council, the SPV and Funders with step in rights in the event of default by the SPV.

- obligations with regard to the development properties are likely to be passed down from the SPV via a subcontracting arrangement to a developer/RSL.

- the SPV will have step in obligations in any subcontract with a developer should the developer fail to perform its obligations.  Should this prove unsatisfactory the council will have step in rights – to be determined in conjunction with Funder's rights contained in the Funder's Direct Agreement.

The model envisaged by the council is considered most appropriate to deliver the political aspirations of the council to:-

- procure the wholesale regeneration of the Pendleton area.

- ensure the council owned social rented properties are developed contemporaneously with the private for sale properties given a common termination regime thus ensuring land banking does not take place.

- achieve the redevelopment of the Pendleton area such that the mixed tenure is pepper potted, there are no distinct areas of socially rented dwellings and all housing is tenure blind.

The proposed length of the contract is 30 years.

### 10.1.3	Service Commencement and Phasing

The council envisages there being a short mobilisation period following contract signature, given the number of properties being transferred for management and the requirements this will place on the Contractor to mobilise.  Following the end of the mobilisation period the Contractor will take on board all the social rented properties and manage them to an interim availability standard (bringing any properties which do not meet this, up to standard).  The proposed refurbishment works will be undertaken in phases.  The exact phasing of the works will depend upon the bidders construction proposals but it is envisaged that the works will be carried out over a period of five years.  A Draft Phasing Plan is attached as Appendix 19.

### 10.1.4	Approach to Stock Surveys

The council has procured the carrying out of a stock condition survey of 80% of the council owned stock forming the project.  This has been carried out by Urban Vision and a warranty has been provided by them in respect of the survey.  In addition, a number of specialist surveys, outlined in greater detail in section 5.3.3, have been carried out.  Again, a warranty in respect of this specialist survey information will be available to bidders.

### 10.1.5	Benchmarking of Costs and Income

The council will, in accordance with Treasury guidelines, only be utilising market testing  and not benchmarking as part of the Project.  The council will be flexible with bidders as to which exact services are market tested but envisages the soft services which are capable of being provided separately to be the subject of market testing.

### 10.1.6	TUPE Arrangements

Housing Management Services are included in the Project and as a result it is likely that there will be a TUPE transfer of around 51 staff currently employed by the council's ALMO, Salix Homes.  The council will comply with all requirements set out in TUPE regarding consultation with staff who are to be the subject of a proposed TUPE transfer.

### 10.1.7	Warranty Issues

As mentioned above, warranties will be available to bidders in relation to the stock condition survey and the specialist surveys.  The council does not propose to provide any warranties to the Contractor other than those provided for in the HPP (both the main body of the Project Agreement and Schedule 9).

### 10.1.8		Contractor and Council Obligations

The obligations on the Contractor and the council as part of the Project will be clearly demarcated and set out in the Project Agreement.

### 10.1.9		Refinancing

The council will adopt SoPC4 required drafting in relation to any refinancing of the Project following financial close.

### 10.1.10	Hand-back of Assets at the end of the Contract

The council owned social rented properties will only be provided to the private sector on licence which will terminate at the end of the contract.  SoPC4 provisions on hand-back will apply.  The council will not be seeking hand-back of any of the development properties.

### 10.1.11	Changes in Law

The council will adopt SoPC4 required drafting in relation to Changes in Law.

### 10.1.12	Monitoring Arrangements

The Project Agreement and the performance of the Contractor will be self monitored by the Contractor. Monthly reports will be submitted on performance under the Payment Mechanism.  In accordance with the HPP, the council will have rights of audit and access to undertake its own review and audit of the Contractor's monitoring arrangements and performance under the contract.

The responsibility for monitoring the contract will remain a core strategic housing management function under the Strategic Director of Sustainable Regeneration, with day to day responsibility delegated to the Head of Partnerships & Business Support.

### 10.1.13	Change Mechanism

The council will adopt the 4Ps Model Change Protocol in relation to council and Contractor Changes to the works and services during the life of the project.

### 10.1.14	Termination Events

The council will adopt SoPC4 required drafting in relation to termination of the Project Agreement.

### 10.2		Output Specification Summary

The Output Specification will be based on the CLG model 10 documentation. A summary of the specification and detail on how the document will be developed further is outlined below.

The Output Specification will set out the standards against which service delivery will be measured. The specification identifies the service standards for the contractor and can broadly be split into two distinct areas:-

  - Standards for the physical condition of the dwellings

  - Standards for the delivery of services

a) Conditional Standards

These standards are used to define in measurable terms the condition each dwelling, as a minimum, has to comply with.  Initially these standards will be used to determine the level of capital expenditure required. During the “operational phase” of the contract these standards will generally drive improvement, replacement and maintenance activities. Conditional standards are linked to availability criteria under the payment mechanism.

b) Service Standards

These standards are used to define to what level the PFI Contractor should deliver the services they are contracted to deliver under the agreement. The service standards are generally split into Property Management and Performance Standards, although some might also be classed as Availability Standards under the payment mechanism.

- Property Management Standards

These are the standards relating to the “landlord” tasks and activities, and are likely to be provided by the RSL partner of the consortium.

- Performance Standards

These are the standards relating to the Facilities Management (FM) services, tasks and activities. These will be delivered by the FM partner of the Consortium.

- Availability Standards

These are the standards that allow the council and Contractor to objectively measure  whether a dwelling is “available” to rent, i.e. physically meets the necessary requirements to allow occupation. These standards  will, during the construction phase, guide the Construction partner of the Consortium. During the operational phase compliance with these standards will be the responsibility of the FM partner of the Consortium.

### 10.2.1	Overview of Property Management Standards

An overview of the “landlord” related services are outlined in more detail in Appendix 8, but broadly consist of:-

- Tenancy Management

- Lettings

- Voids (administration)

- Income & Debt Recovery

- Tenant & Community Involvement

The standards that the contractor will be required to comply with will be based on the model 10 documents.

### 10.2.2	Overview of Service Performance Standards

These standards relate to the FM services, tasks and activities and broadly consist of:-

- Repairs & Maintenance

- Voids (redecoration)

- Security

- External Area Maintenance

- Caretaking & Cleaning

As with the Property Management Standards, the contractor will be required to comply with the model 10 documents.  In specific relation to the Reactive Repair Policy, the key principles will be as follows:-

- All reactive repairs shall be executed by the contractor

- Reactive repairs shall be prioritised based on urgency and impact

- Where a reactive repair is required and is demonstrably a direct result of wilful damage of a tenant or other council related party the contractor shall be able to reclaim the costs

- All costs for reactive repairs shall be on an open-book and agreed labour rates basis where such are to be reclaimed

- Reactive repair due to fair wear and tear shall be delivered by the PFI contractor at no additional cost to the council or tenant

- Reactive repairs shall be conducted as soon as practically possible within the temporary and permanent rectification periods assigned to a repair request and should retain or improve the quality or condition of the dwellings

### 10.2.3	Value for Money in Service Delivery

The following principles will be adopted and incorporated into the relevant documents to deliver VfM in Service delivery:-

- Quality and Cost Evaluation of contractor proposals

- Agreed rates and open book accounting principles

- Risk transfer to the party best able to manage the risk

- During the concession term, periodic benchmarking and market testing of the services

- Introduction of a performance related payment mechanism

- Establishment of robust council policies and procedures for contract management of the PFI agreement

### 10.2.4	Interface Arrangements

Due to the number of stakeholders involved in service delivery in the Pendleton PFI area there will be a need for formal interface agreements between the following parties:-

- PFI contractor and Salix Homes

- PFI contractor and HCP

- PFI contractor and Urban Vision

- HCP and Salix Homes

In addition to these potential interface agreements, as a minimum, it will be required to develop clear definitions and segregation of the service provided by Salix Homes, HCP and the PFI contractor.

### 10.2.5	Future Development of Output Specification

Through consultation the model 10 documentation will be made bespoke to the Pendleton scheme. A “final draft” will be issued to the bidders as part of their Invitation to Participate in Dialogue (ITPD) documents. During the dialogue phases the Output Specification will be refined through discussion with the bidders and a final version will be part of the Invitation for Final Tender documents.

A consultation timetable has also been agreed with the PFI Steering Group for developing the Output Specification to ensure they are fully informed as the document evolves. The milestones for consultation are as follows:-

| w/c 19/05/08 | - | Commence consultation on Model 10 |
| --- | --- | --- |
| w/c 16/06/08 | - | Issue v1 of output specification |
| w/c 04/08/08 | - | Commence consultation on v1 |
| w/c 25/08/08 | - | Issue v2 of output specification |
| w/c 15/09/08 | - | Commence consultation on v2 |
| w/c 13/10/08 | - | Issue v3 of output specification |
| w/c 17/11/08 | - | Commence consultation on v3 – to reach “in principal” approval |
| w/c 15/12/08 | - | Issue v4 for formal approval |
| w/c 12/01/09 | - | v4 approved – final draft for ITPD |

## 10.3	Payment Mechanism

The council is currently intending to use the standard form Payment Mechanism taken from the 4P’s Procurement Pack.  This document will be amended for project specifics in order to ensure that the level of deductions obtained provide sufficient incentive on the Contractor to perform without being overly punitive.

The KPIs underpinning the Performance Deductions will be developed with reference to the Output Specification.   This will help to ensure that performance is correctly monitored and the required standards are maintained.  In particular, the Contractor’s performance on Best Value assistance and reporting and their compliance with statutory and legislative requirements will be explicitly covered through the KPIs within the Payment Mechanism.

It is currently envisaged that a Payment Mechanism principles paper will be developed prior to release of the Invitation to Submit Outline Solutions (ISOS) documentation, with a full legal draft being available for release with the Invitation to Submit Detailed Solutions (ISDS) documents.  The final form will be negotiated through the dialogue process.

## 10.4	Development Element of the PFI Scheme

The development element of the Project comprises of the provision of new homes for social rent and private sale, on identified sites, together with any associated environmental improvements and community facilities.

It is not the council's preferred approach to have a separate Development Agreement to cover the terms under which the development sites will be disposed of to the private sector. The council considers that its political aspirations to secure the regeneration of the whole of Pendleton on a tenure blind and pepper potted basis, will be best achieved by the development element of the PFI scheme being incorporated into the Project Agreement.

However, the council is prepared to be flexible on this issue and will consider use of a separate Development Agreement if this is the market's preference or if there are value for money reasons to use a separate Development Agreement. Also the council is aware that the structure of bidder's consortia, and how they deal with the development risk within their consortia, can have a key influence on how the development element of a PFI project is structured contractually. Suitable safeguards will, however, be included within any separate Development Agreement to ensure that the council's political aspirations for the redevelopment of the whole of Pendleton are met and land banking is avoided. The council envisages discussing the contractual structure of the project further with bidders at the prequalification and ISOS stages of the project before formalising its view on the contractual structure for the project.

The PFI Contractor will be required to underwrite the development element of the PFI scheme for an agreed Guaranteed Minimum Price which it will guarantee to pay the council for the development sites. Overage arrangements for the sharing of any increase in value above the Guaranteed Minimum Price will be incorporated.

# 11.0	Risk Allocation and Accounting Treatment

The council is committed to achieving a risk balance that receives a positive accounting determination and also complies with Housing Pack Guidance and SoPC4. The council intends to structure the risk profile as per Table 27. The council’s financial advisors, Ernst & Young LLP (“Ernst & Young”), have assisted the council in its assessment of the OBC, based upon the current documentation in place, and consider that an ‘off balance sheet’ position should be achievable, based on the risk allocation structure proposed, which is summarised in Table 27 below and currently applicable accounting standards and guidance including FRS5 and Treasury Technical Note Number 1: How to Account for PFI Transactions.  A description of the indicative view of the accounting treatment can be found attached as Appendix 20.

Table 27 – Risk Allocation

| Risk | Risk Borne by the Council | Risk Borne by Operator | Significance of Risk |
| --- | --- | --- | --- |
| Demand | ( |  | Low |
| Third party revenue | ( |  | Low |
| Design Risk |  | ( | Medium |
| Penalty regime |  | ( | Medium |
| Changes in relevant cost |  | ( | Medium |
| Obsolescence/Legislative change | (1 | (1 | Low |
| Residual value | ( |  | Low |

1Qualifying Changes in Law affecting general capital expenditure will be shared according to an agreed apportionment of costs (Schedule 3).  Discriminatory and Specific Changes in Law will be paid for through a change to the unitary charge in accordance with the Project Agreement, section 5.2 (SoPC4).

## 11.1	External Audit Opinion

The initial view of the external auditor, the Audit Commission, on the accounting treatment of the scheme is that they are not minded to change the view of the council’s financial advisors, Ernst & Young. See Appendix 21 for a copy of the confirmation letter.

## 11.2	Project Risk Management

Project risk challenge sessions are held on a bi-monthly basis with senior council officers to ensure that all key risks within the project have been identified and classed appropriately.  Potential new risks are initially discussed as a standing agenda item within each Task Group meeting, which are held on a monthly basis.  Task Groups have been established to oversee the specific areas of technical and services, masterplanning and land, communications, and finance and legal.  The process of risk management specific to this scheme is provided in greater detail in the Pendleton Housing PFI Risk Management Plan attached as Appendix 22.

Once identified, the respective Task Group Chair, as an integral element of their highlight report, presents risks linked to each Task Group at Project Team meetings.  Once the incorporation of the risk has been agreed and the respective Risk Owner and Risk Action Owner have been identified, they are added to the Risk Register. This contains details of all risks, their assessment, owners and status. The Risk Register is a control tool for the Project Manager, providing a quick reference to key risks facing the project, what monitoring activities should be taking place and by whom.  A summary of the Risk Register is attached as Appendix 23.

Risk Identification and management will be an on-going task throughout the life of the project. A full review of the Risk Register will be formally undertaken at strategic stages in the project.

# 12.0	Project Management, Governance and Delivery

## 12.1	Project Delivery Structure

In terms of delivering large projects the council has an excellent track record.  Salford has delivered successive large-scale and comprehensive regeneration programmes such as Single Regeneration Budget (SRB), New Deal for Communities (NDC), European Regional Development Fund (ERDF), Salford Quays redevelopment, Housing Market Renewal through the Manchester Salford Pathfinder (MSP) and mediacity:uk.

The council has previous PFI experience through Salford Schools PFI (three secondary special schools and two mainstream secondary schools) and the development of its Building Schools for the Future (BSF) scheme.  Through these schemes a wealth of experience is available within the council’s finance and legal teams, in addition to PFI project management skills.

The council has corporate governance arrangements for its PFI and PPP programme.  This ensures the successful and efficient management and delivery of schemes through the establishment of clear roles and responsibilities within the decision-making process. The corporate governance arrangements will be used for this project, under which the council’s Cabinet approves the Outline Business Case and Final Business Case.  The governance structure is presented in more detail in the diagram below: -

##### Corporate Governance Structure Diagram

## 12.2	Portfolio Management Board

The corporate Portfolio Management Board is chaired by Barbara Spicer, Chief Executive Officer (CEO) of the council.  This Board ensures resources are in place to deliver the portfolio of strategic projects and co-ordinates the council’s approach across projects.

The membership of the Portfolio Management Board is outlined in Table 28.  Senior managers and external advisors are invited to attend the Board as required.

Table 28 – Membership of the Portfolio Management Board

| Board Member | Title/Designation |
| --- | --- |
| Barbara Spicer (Chair) | Chief Executive |
| Kevin Brady | Assistant Chief Executive |
| Alan Westwood | Director of Customer & Support Services |
| Martin Vickers | Director of Change |
| John Spink | City Treasurer |
| David McIlroy | Assistant Director (Corporate Programme & Project Services) |
| Steve Hampson | Corporate Programme & Project Services Manager |

## 12.3	Housing Investment Options Programme Board

The Housing Investment Options Programme (HIOP) Board has been established specifically to ensure the deliverability of each of the housing investment options.  The Board has the delegated authority to take decisions relating to the procurement of the PFI project and to ensure its timely delivery within the parameters approved at Outline Business Case stage.

The Board meets monthly and receives reports from the Project Manager/Project Director on project progress and issues requiring decisions or action from the Board. The report includes an update on project risks, and their management. Where appropriate, it would be the responsibility of the Chair of the Board to recommend a report be referred to the Corporate Portfolio Board or to Cabinet where there are proposed or actual significant changes in project scope (including content, cost, quality or programme).

The membership of the HIOP Board is outlined in Table 29.   Senior managers and external advisors are invited to attend the Board as required.

###### Table 29 – Membership of the Housing Investment Options Programme Board

| Board Member | Title/Designation |
| --- | --- |
| Alan Westwood (Chair) | Strategic Director of Customer & Support Services |
| Bob Osborne | Deputy Director of Housing & Planning |
| Tim Doyle | Chief Executive – City West Housing Trust |
| Kevin Scarlett | Chief Executive – Salix Homes |
| Dave Galvin | Managing Director – Housing Connections Partnership |
| John Spink | City Treasurer |
| Rob Pickering | Head of Partnerships & Business Support |

Specific responsibilities of the Programme Board include:-

- Manage the risks associated with the project

- Manage the quality assurance for the project

- Authorise any major deviations from the agreed milestones and resolve these deviations or escalate as necessary

- Ensure that the required resources are available

- Receive written monthly updates from the Project Manager/Project Director

- Resolve any conflicts escalated by the Strategic Client Group

- Ensure that a post implementation review (or post project review) is scheduled and takes place.

The delegated powers are to the Chair of the Board or in his absence to a nominated member of the Programme Board, in each case subject to the concurrence of at least two other members of the Board.  The Board’s delegated powers are to approve all project specific issues relating to the procurement, construction and facilities management mobilisation of the project, not reserved to Cabinet or delegated to the corporate Portfolio Management Board, including:-

- The publication of the OJEU notice, following corporate Portfolio Management Board approval to commence procurement

- The criteria for the selection of bidders

- The issue of the Pre Qualification Questionnaire and Memorandum of Information

- The initial and any further selection of bidders

- The contract award criteria

- Matters relating to negotiations with bidders

- The issue of documentation during Competitive Dialogue

- The appointment of a preferred bidder and the issue of the Preferred Bidder letter

## 12.4	Strategic Client Group

The Strategic Client Group meets on a monthly basis, prior to the HIOP Board. This group is responsible for monitoring scheme progression, minimising project risk and escalating key decisions as and when required.

The membership of the Strategic Client Group is outlined in Table 30 below.   In addition, officers from other service areas and external advisors are invited to attend the meeting as required.

Table 30 – Membership of the Strategic Client Group

| Group Member | Title/Designation |
| --- | --- |
| Rob Pickering (Chair) | Head of Partnerships and Business Support |
| Paul Longshaw | PFI Project Director |
| Jane Barlow | PFI Project Manager |
| Nigel Dickens | Principal Group Accountant |
| Joe Willis | Director of Investment & Regeneration, Salix Homes |

## 12.5	Project Team

The Project Manager is assisted by the PFI Strategy Officer and specialists from other service areas from within the council. There are also five key Task Group areas (finance, legal, masterplanning & land, technical & services, and communications) each of which has designated areas of responsibility and core team members. The Project Manager and the PFI Strategy Officer along with the Task Group chairs form the Project Team, which meets on a monthly basis to ensure effective co-ordination and forward planning of the procurement process.

The membership of the Project Team is outlined in Table 31.   In addition, officers from other service areas and external advisors are invited to attend the meeting as required.

Table 31 - Membership of the Project Team

| Officer | Designation |
| --- | --- |
| Paul Longshaw | PFI Project Director |
| Jane Barlow | PFI Project Manager and Chair of Technical & Services |
| Vicky Coakley | PFI Strategy Officer – Project Management Support |
| Chris Mee | PFI Accountant – Finance Task Group |
| Pauline Lewis | Senior Business Manger – Legal Task Group |
| Michael Phillips | Principal Consultant - Masterplanning & Land Task Group |
| Chris Gibbins | Director of Neighbourhood Services (Salix Homes) - Communications |
| Kevin Farrell | Independent Tenants’ Advisor |
| Sophie Boswell | Project Support Officer - Administration |

In addition to the core members of the Project Team, allocated resources from other service areas also support the project, as outlined in Table 32 below:-

Table 32 – Additional Resource

| Officer | Designation |
| --- | --- |
| Malcolm Phillips | Associate Planning Consultant – Urban Vision |
| Graham Gentry | Assistant Director – Planning & Development |
| Simon Ashworth | PFI Accountant – Finance Team |
| Sarah Winder | Principal Marketing Officer – Corporate Marketing Team |
| Samantha Tindale | Investment & Regeneration – Salix Homes |
| Matt Roberts | Head of Asset Management – Salix Homes |
| Angela Martens | Assistant Principal Development Surveyor – Urban Vision |
| Nik Puttnam | Senior Development Manager – Central Salford URC |
| Deborah MacDonald | Project Manager (Pendleton) – Salix Homes |
| Chris Whitfield | Housing Market Renewal Officer – Salix Homes |
| Joanne Finnerty | Strategic HR Manager – Human Resources |
| Norman Perry | Team Leader, Legal Services – Land & Property |

## 12.6	External Advisors

The council has appointed Addleshaw Goddard and Ernst & Young to act as the council’s Legal and Financial Advisers respectively for this PFI project.   The council has also appointed Turner & Townsend as its Technical Advisor and also to provide additional project management support.  AoN will advise the council on matters relating to insurance.

An Independent Tenant Advisor (ITA) has also been appointed from Compass@TPAS to encourage and develop stakeholder engagement throughout the procurement of this project.

## 12.7	Project Budget

The council recognises, through the experience of delivering the schools’ PFI schemes and the on-going development of the BSF, the resource requirements necessary to deliver projects of this size and complexity.  The external advisors have been appointed through to Financial Close which has been accounted for in the Directorate’s budget going forward.  The council is committed to the delivery of this project on programme and will respond to any additional resource requirements to achieve this.

## 12.8	Gateway Review

The council has chosen to work with the 4P’s to deliver an independent project assurance assessment through participation in the Gateway Review process.  A Gateway 0 - Strategic Assessment Review was undertaken in May 2008.  The Review Team was impressed with the enthusiasm and dedication of the Project Team.  The actions identified in the Review Report are being implemented in accordance with the Review Team’s recommendations.  A copy of the report is attached as Appendix 24.

## 12.9	Project Delivery Programme

Table 33 below summarises the anticipated key milestones in the project using the Competitive Dialogue process.  A more detailed programme can be found in Appendix 25.

Table 33 – Project Milestones

| Milestone | Date |
| --- | --- |
| OJEU Notice Published | October 2008 |
| Issue Information Pack and PQQ | October - December 2008 |
| Bidders’ Information Day | November 2008 |
| Return of PQQ submissions | December 2008 |
| Long List Confirmed | January 2009 |
| Issue Invitation to Participate in Dialogue | February 2009 |
| Evaluation of Outline solutions | March/April 2009 |
| Confirm shortlist of bidders | May 2009 |
| Invitation to submit detailed solutions | May 2009 |
| Short-listed bidders stock condition survey | July – September 2009 |
| Bidders submit detailed solutions | October 2009 |
| Evaluation and dialogue on detailed solutions | October – February 2010 |
| Selection of two bidders | February 2010 |
| Parallel dialogue with two bidders | February - April 2010 |
| Call for Final tenders | May 2010 |
| Final tenders submitted | June 2010 |
| Competitive dialogue closes | June 2010 |
| Evaluation of final tenders | June – August 2010 |
| Appointment of Preferred Bidder | September 2010 |
| Final negotiations and planning approval | September – December 2010 |
| Contract Award | March 2011 |
| Work commences on site | April 2011 |
| Full service commencement | April 2016 |
| Contract ends | March 2041 |

The council recognises that at this stage the milestone dates within the procurement period are indicative.  A further review of the programme will be undertaken by the council as the project enters procurement.

# 13.0	Statutory Processes

The council has identified and considered the approach to a range of major statutory processes, which will come into effect as a direct result of the PFI scheme. These issues are highlighted in greater detail in this section.

## 13.1	Planning

The council understands that current guidance indicates that outline planning consent should usually be sought prior to OBC approval. The council has considered the application of that guidance to this project, and has concluded, taking account of soundings from the private sector, that an alternative approach be adopted.  The detail of this alternative approach is set out below.

As this is primarily a refurbishment project, the matters requiring planning consent under the PFI contract are expected to be confined to external cladding treatments, predominantly to the multi-storey blocks; the re-modelling works to the South Clarendon estate and potentially for any environmental improvements works. The development element of the Project will also require consent, which would need to be in place prior to onward disposal of the sites to developers.

### 13.1.1	Current Status

The principle of housing within the PFI area has already been established within the Salford Unitary Development Plan (UDP), adopted in June 2006, which sets the planning framework for the city. It identifies Central Salford, including Pendleton, as the major focus for regeneration and investment within the city, with the goal of developing Central Salford as one of the most popular and attractive places to live within the inner areas of Greater Manchester.  The UDP contains no proposals for other uses within the housing parts of the PFI area.

There is a former secondary school site, now vacant, included within the new development opportunities offered within the PFI scheme which, under the UDP, has also been allocated for housing.  Other allocations, not affecting housing land, are for a major retail expansion of the existing town centre and a new health centre, both of which have a significant role to play in aiding the area’s regeneration.

To further mitigate the risk of not achieving future planning approvals, the development sites included in the project are in council ownership; the majority of which are vested within the Directorate of Housing & Planning. There is, therefore, a high degree of certainty that sites are available for sale on condition of the delivery of the new build affordable housing units.

The council is therefore of the opinion that achieving outline planning consent at this stage is unnecessary. An outline planning consent is designed to establish the principle of development on a site for a particular land use, which in this case, has already been confirmed through the UDP and mitigated further through the land ownership.   In addition, given the level of detail available to the council at this stage any outline planning consent is likely to be heavily conditioned, to enable the local planning authority to safeguard its position with respect to any subsequent reserved matters. This may be regarded as unduly constraining for prospective bidders (indeed market soundings support this), who will price upwards accordingly.

In addition, as there is no private sector partner at this stage, there would be problems securing S106 planning obligations, since legally local planning authorities cannot negotiate planning obligations in relation to reserved matters. Potential bidders have indicated that, were the council to consider applying for outline consent, they would not wish to see this happen any earlier than at short listing stage and would want an opportunity to comment on any application, in an attempt to avoid the constraints and potential difficulties described above. Outline consent is also of little benefit to bidders when what is required by funders prior to contract close is full detailed consent.

The council has therefore concluded that there is little or no benefit in seeking outline planning consent, as it does not add certainty in this respect. In fact, it is the opinion of both the council and the private sector that seeking outline consent may increase risks rather than decrease them.

### 13.1.2	Pendleton Planning Guidance

The council’s preference therefore, to assist in the implementation of the PFI scheme, has been to develop specific planning guidance for the Pendleton area.  The Pendleton Planning Guidance, a copy of which is attached as Appendix 26, is due to be adopted in December 2008, once the document has been the subject of planning consultation at its various stages.  The proposals within the guidance are clear but provide a degree of flexibility for bidders.  The guidance sets out:-

- Sub areas within the PFI area on an Ordinance Survey base, identifying the housing for  improvement and redevelopment

- Levels of required affordable housing.

- Indicative layouts of the two principle redevelopment areas including acceptable levels of density, scale and property type.

The council has been conscious for some time of the need to provide an adequate planning background to the PFI bid.  To these ends work began on the local planning guidance for the area in April 2005 when widespread consultation and evidence gathering took place.

In May 2006 an Issues and Options Report was published for consultation setting out a number of broad options for tackling the area’s problems.  These options were then carefully examined in the light of consultation responses and the views of tenants on how to deliver the Decent Homes Standard, undertaken in a separate consultation in mid 2005.

In June 2007 the Preferred Options report was published for consultation.  This narrowed down the proposals to three more detailed ‘preferred’ options.  They were based on consideration of the Issues and Options Report and the continued development of the Housing PFI proposals, together with additional information collected, such as stock condition surveys.  At the end of 2007 a report on this consultation exercise highlighted key responses and areas of consensus and disagreement on the Preferred Options.  This information was then fed into the scheme option appraisal process outlined in section 6.2.1.

The steer to bidders provided through the Pendleton Planning Guidance will be further supplemented through the council’s Supplementary Planning Document on Planning Obligations (adopted March 2006) and the Housing Planning Guidance (adopted December 2006).  Both of these provide guidance on the achievement of a range of types of affordable housing, including intermediate housing.

### 13.1.3	Planning Approach

Bidders will be required to prepare a ‘high level’ plan for the estate which encompasses all of the key outputs expected under the PFI contract as part of their intention to submit detailed solutions. The council’s experience on area based regeneration schemes is that it is advantageous for bidders, rather than the council, to prepare this for the following reasons:-

- New build and refurbishment proposals are more readily integrated if they are prepared as one integrated plan

- There is an increased chance of mixed tenure developments being achieved, as the council will require this to be the approach

- There is an increased chance of innovation and competition, with the council then able to select the bid that offers the most advantageous package of proposals overall, taking into account the ‘outcomes’ being offered (response to the council’s minimum requirements, plus any proposals over and above that which benefit the community) and the commercial proposal (guaranteed minimum price, minimum development criteria and overage)

- There is an opportunity for community consultation on more than one proposal

Market soundings indicated that potential bidders support this approach, as long as the council provides clear strategic guidance on its requirements and on any planning constraints, and would prefer to work with the local authority to produce and agree a plan for the whole area as part of the competitive process and then seek any necessary planning permissions accordingly.  The council has addressed this concern through the development of planning guidance specific to the Pendleton area.

Bidders’ proposals will be assessed, taking account of views expressed during the consultation, on the achievement of the council’s objectives.  The outcome of this process will input into the preparation of Call for Final Tender instructions.  A further round of consultation will then be undertaken on the bidders’ final proposals. Once again, taking account of the views of the community and key stakeholders, the bid which best meets the council’s requirements will be taken forward as Preferred Bidder.

At this stage, the Preferred Bidders’ high level plan will be taken through the necessary statutory planning approval process.  The bidder will also need to secure full planning approvals for those elements requiring consent within the PFI contract. The risk of objections will have been mitigated by the consultation process undertaken during the Competitive Dialogue process.  Planning applications relating to those sites on which the development element of the project will be delivered will be the responsibility of the specific developer concerned, but again, the risk of objection will have been mitigated through the consultation undertaken on the bidders’ high level plan.

## 13.2	Title Arrangements

The council’s legal department has established the extent of the council’s land ownership in the Pendleton PFI area. The council’s land covers a large proportion of the land area and is registered with title absolute.  The information is held in a single file and those parts of the land which are not already used for residential houses/flats are not subject to restrictive covenants which may be used to restrict future residential development.

## 13.3	Notice of Intention to Demolish

The council has the power under the provisions of the Housing Act 2004 to serve Initial and Final Demolition Notices which suspend the Right to Buy in relation to regeneration initiatives and development opportunities.

Following approval of the OBC, it is proposed to seek approval from the Lead Member to issue an Initial Notice of Intention to Demolish on those properties identified for demolition within the early part of the phasing plan to assist with achieving vacant possession.  The proposed phasing plan can be found within the Pendleton Re-housing Plan in Appendix 16.

## 13.4	Compulsory Purchase and Blight Notices

- Compulsory Purchase Orders (CPO)

Wherever possible the council will strive to acquire by agreement, before acquiring by compulsion.  To mitigate the risk of entering into the CPO process the council has been consulting with the local community for a number of years on the future regeneration of the Pendleton area.  The community was consulted on proposals for demolition during the summer of 2007.  During this period the council issued a statement of commitment for people who may be displaced as a result of the regeneration activity.  Further information on compensation and re-housing choices will be made available to those affected by the regeneration proposals once Government approval has been received for the scheme to be procured.

- Blight Notices

Where the value of a property has been reduced by certain categories of planning or other development proposals, owner occupiers (within a specified rateable value limit), may be entitled to serve a ‘blight notice’ on the body responsible for this, requiring them to buy the property at its untainted value.

It is recognised that inclusion within a CPO is only one of many circumstances in which a blight notice may be served and that the acquiring authority has two months to accept or reject the notice.

## 13.5	Highway and Footpath Closures

The PFI contractor will ensure that any proposed highway closures are carried out in accordance with either section 116 of the Highways Act 1980 or section 278 of the Town & Country Planning Act 1990.

Footpaths that require ‘stopping up’ would be dealt with under Section 118 of the Highways Act 1980.  Any footpaths that require only diversion would be dealt with under Section 119 of the Highways Act 1980.

The ISDS requirements will make it clear that any applications for closure or diversion are the contractor’s responsibility.

## 13.6	Leaseholders

The council will seek to recover costs from leaseholders in accordance with the terms of their lease, and will give consideration to the development of financial assistance products, such as equity loans, in order to assist any leaseholders who may be suffering from financial hardship.

In terms of leaseholder debt for major repairs, the maximum amount a landlord can recover from a lessee over any five year period is £10,000.  The council will ensure that Section 20 procedures under the Landlord and Tenant Act 1985 have been implemented.

The council recognises that any costs for capital works on leasehold properties are not covered by PFI credit, and therefore the share of the cost of the works will be recovered by the following means:-

- Full cash payment

- Part cash payment/part by instalments

- Service charge loan, payable by instalments

- A charge taken against the property

## 13.7	Section 25 Notices

It is envisaged that Section 25 consent will be required from the Secretary of State for the disposal of land forming the Project.  This will be requested at the time the Final Business Case is submitted.

# 14.0	Commitment of Stakeholders and Sponsors

## 14.1	Community Consultation

Following the consultation which took place in 2005, as part of the housing investment option appraisal process (outlined in greater detail in section 6.2), the project team has ensured that regular updates on progress are delivered to the community.

The dissemination of information across the estate is facilitated by the comprehensive network of tenants and resident associations which exist.  The Pendleton estate includes 19 individual tenant and resident associations, all of which have representatives on the Network Group, a Tenants Federation Group representing all associations in the area.

In addition, a specific focus group for PFI, the Pendleton PFI Group, was formed in January 2005.  This group consists of five tenant and resident representatives, the three ward councillors for the area, two Salix Homes representatives (specifically from the Housing Management and Pendleton Regeneration Team), the Independent Tenants’ Advisor and members from the PFI Project Team.  Specific issues and proposed appropriate actions relating to the PFI are discussed within this group, covering such areas as the options appraisal, content of the OBC and service performance standards.

Over the last two years, leaseholders have been kept up to date on the stock options process through the Leaseholder Forum.  Since the establishment of Salix Homes in July 2007, the way in which the council consults with leaseholders is under review and a leaseholder charter is currently being developed. The forum provides an excellent opportunity to share information with leaseholders, for leaseholders to exchange issues with each other and to act as a sounding board for new proposals.

To ensure that the PFI scheme does not take place in isolation, the Pendleton Steering Group was established in November 2004.  This group consists of the main stakeholders in the area e.g. the council, Salford University, Community Forum representatives, Greater Manchester Police and the Urban Regeneration Company.  Its purpose is to direct and guide the wider regeneration of Pendleton with surrounding areas; and to ensure that the PFI scheme aligns with the objectives of other initiatives in the vicinity.

## 14.2	Communications Strategy

A comprehensive Communications Strategy, attached as Appendix 27, has been developed to take the scheme forward from OBC development and through procurement.

The strategy follows the principles set out in the “Opening Doors” document, the council’s guide to involvement in housing services.  This guide introduces a new vision for working together to achieve the highest possible standards for involvement and communication between residents and providers of housing services in Salford.  There are a number of ways that residents can get involved and have their say about the housing services they receive.  Residents don’t always need to attend meetings or belong to a group to have their say, although those opportunities are always available.

The council recognises that different people are able to commit different amounts of their time depending on what is currently happening in their lives.  The council’s approach is therefore to encourage residents to participate at a level that suits them, an approach that the successful bidder will be encouraged to adopt.

## 14.3	Hard to Reach Groups

In addition to the above approach, the council recognises that some groups are harder to reach than others e.g. elderly, disabled, youth, BME communities and asylum seekers.  By working with appropriate agencies and utilising a wide variety of consultation techniques, the council will ensure that these groups are adequately and appropriately consulted.

The council has completed an equalities impact assessment as a tool to identify if the proposed scheme affects different groups of people in different ways.  A key outcome from this assessment was that the council needs to improve data collection techniques during consultation events to have a greater understanding of who the different interest and minority groups are in the area.  As a result of this assessment, the project team ensure that relevant data is recorded, allowing the council to measure the effectiveness of future consultation activities more accurately, and to develop intelligence on whom the information is reaching or failing to reach.

## 14.4	Commitment to the Project

Members across all parties within the council have shown their support for this scheme. Full Cabinet have approved the submission of this Outline Business Case (OBC). A copy of the report and minutes can be found in Appendix 28.

Members are very aware of the level of commitment required to ensure successful procurement is delivered and have further demonstrated wider council support for the project through the commitment to fund part of the affordability requirement set out in the OBC.

Local members are also very supportive of the project and have been actively involved in local stakeholder meetings and working with officers and members of the community to ensure that much needed investment is brought to the area.

The local MP Hazel Blears has also taken a particular interest in the project and has been kept informed of progress, through regular briefings, as the project has progressed.

# Text boxes

Leadership / Cabinet

Portfolio Management

Board

Strategic Client Group

External Advisors

Overview & Scrutiny

PFI Steering Group

PFI Project Team

Task Groups

Housing Investment Options Programme Board