14-19 in Salford

A strategy for 14-19 developments in Salford

Produced on behalf of Salford Lifelong Learning Partnership

14-19 in Salford

A strategy for 14-19 developments in Salford

Produced on behalf of Salford Lifelong Learning Partnership

Developing a 14-19 curriculum that meets the needs of all young people and prepares them for adult and working life

# Introduction

This strategy has been produced as a result of development work over the last few years. Following the Area Wide Inspection in 2000, a number of collaborative groups were established, including the 14-19 Participation Group, which commissioned this report. This has overseen a great deal of collaborative activity, designed particularly to develop the vocational curriculum at Key Stage 4 and to encourage participation in learning at 16. In Autumn 2002, a headteacher was seconded to the LEA to develop information and strategy on 14-19 issues. Ideas from his report have been incorporated into this strategy. A mid term review of the inspection produced information and suggestions for future development. Subsequently the Area Wide Inspection Action Plan has been revised to provide a clearer way forward. A 14-19 Away-day in March 2003 and a 14-19 conference in October 2003, involving all partners, have provided a platform for future development. Underlying this there has been a strong push from government to develop the 14-19 phase of learning. Locally there has been a strong desire to establish a clear picture of current achievements and future development – in essence a 14-19 strategy. The development of the 14-19 curriculum, especially the vocational curriculum, is also central to LIG (Leadership Incentive Grant).

# National Context

Early in 2003, the government published “14-19: Opportunity and Excellence”, which proposed greater flexibility in the curriculum at Key Stage 4 and increased vocational options. This was embodied in QCA guidance, issued in September 2003. The government also establishes a Working Group on 14-19 Reform led by Mike Tomlinson to look at longer term issues:

- The need for a stronger vocational offer

- Assessment which is fit for purpose

- A unified framework of qualifications across the ability range and across the whole of the 14-19 phase

The working group is due to report in July 2004, but its interim report proposes Diplomas at 4 levels:

- Entry

- Foundation (roughly equivalent to GCSE grades D-G, NVQ Level 1)

- Intermediate (roughly equivalent to GCSE grades A*-C, NVQ Level 2)

- Advanced (roughly equivalent to A level, AVCE, NVQ Level 3)

Diplomas will share a common core, involving mathematical skills, communication, ICT, an extended project, wider activities, personal planning, review and guidance. Main learning forms the bulk of the young person’s diploma programmes and is selected by the learner. In many cases, it will build on existing academic and vocational qualifications.

# Living in Salford

Situated in the heart of Greater Manchester, the City of Salford covers an area of 37 square miles and has a population of around 216,100. It ranges from a dense urban core at the heart of the Greater Manchester conurbation to the east through established suburban housing areas to areas of high value housing and greenbelt to the west. The City boasts a thriving University, Hope Hospital as a major teaching facility and Salford Reds – a Super League rugby club.  Home to the artist LS Lowry for much of his life, the multi-million pound arts and theatre complex – The Lowry - named in his memory, houses the world’s largest collection of his works.

The City has transformed itself in recent years. The redevelopment of Salford Quays has created a world-class business and cultural area of great national and regional significance. The Commonwealth Games in 2002 offered a wealth of opportunities in terms of job creation and raised the profile of the City. The City is continuing to drive forward regeneration through its Community Plan and Neighbourhood Renewal Strategy. This will ensure that the major change needed in the Central Salford area, to the east of the City, and the stabilisation of neighbourhoods in Salford west is achieved. However, amidst these exciting developments there still exist severe pockets of deprivation, and overall Salford is one of the most deprived areas in the country, and the 4th most deprived area in the North West, with almost 40% of its population living in the 10% most deprived wards in the country (Source: 2000 Indices of Deprivation). The City ranks 31st worst of 354 authorities for employment, and 29th worst of 354 authorities for income. However, beneath this overall picture the authority exhibits a wide range of variation between geographical areas, for example Ordsall is ranked as the 16th worst ward (out of 8415) on the Education Ranking of the 2000 Index of Deprivation whereas Worsley and Boothstown is ranked 7,947, Ordsall is also ranked 12th in the Child Poverty Index and Worsley and Boothstown ranks 6,966.

The Community Plan, developed by the Salford Partnership (Salford’s multi-agency Local Strategic Partnership - LSP), sets out the overarching vision for the City:

“Our vision for Salford is to create a City where people choose to live and work. We aim to improve the quality of life of all our citizens by creating an economically prosperous City with a buoyant and competitive economy; creating and maintaining strong, safe, healthy and sustainable communities where all citizens can participate to the fullest extent in decisions which affect their communities; providing better education for all, to enable children and young people to thrive and fulfil their potential; creating a City that is good to live in by providing quality homes and a clean and healthy environment.”

The Community Plan has seven themes including “A Creative and Learning City” which is driven by the Lifelong Learning Partnership (LLP). The overarching aim of this theme is to support and stimulate lifelong learning and cultural activity to ensure people, particularly children and young people, maximise their potential and pursue personal development and fulfilment. There are three priorities for action in the Community Plan which the LLP are acting on, these are to:

- Improve overall school performance to the national average and ensure that GCSE results improve faster than the rest of the country

- Ensure that all young people leaving education have a recognised qualification

- Achieve a dramatic increase in the participation in post 16 education and training by school leavers

Learning in Salford

The area has one general further education college (FE) college, two sixth form colleges and 14 secondary schools, all of which are 11-16. There are three secondary special schools, one of which has post-16 provision.  The local education authority (LEA) also maintains the Royal Manchester Children’s Hospital School, which provides a post-16 programme for patients.  There are approximately 2,500 young people in the year 11 cohort in 2003/04.

Salford College is the largest provider of vocational courses for 16-19 year olds within Salford and provides a range of courses from level 1 to level 3, both vocational and academic. It has recently established The Salford Academy, specifically for 16-19 year olds and reintroduced A levels. In Eccles College, the majority of 16-19 learners are following predominantly A level courses (academic and vocational), but there is a range of intermediate GNVQ, GCSE, and NVQ level 1 courses and four entry level courses for learners with learning difficulties and/or disabilities. Pendleton College, although designated as a sixth form college has a student profile typical of a tertiary college and offers a wide range of academic and vocational courses at all levels.  All colleges have increased achievement and retention rates considerably over a two/three year period.

Work-based learning is provided by 11 local providers, with numbers of trainees ranging from 30 to 400. Between them they offer almost all occupational areas at AMA (Advanced Modern Apprenticeship) and FMA (Foundation Modern Apprenticeship) level. E2E (Entry to Employment) is offered by YMCA Training, Age Concern, ERP (Employment Regeneration Partnership) and Salford Consortium.

In 1999, just over 34% of 16 year olds in Salford achieved five or more higher grade GCSEs, compared with the then national average of 48%. By 2003, the 5+ GCSE A*-C pass rate had risen to 36.1%. There are significant gender differences in performance at GCSE.  In 2003, girls attained a 42.4% pass rate while boys achieved a 29.9% pass rate at the higher grades.

- In 1999, 55% of 16 year olds stayed on in education (up from 48% in 1998).  By 2003 the percentage continuing in full-time education had increased to 61.5%.  The gap between the participation rate in full-time post-16 education in Salford (61.5%) and that nationally (71.5%) has narrowed from 13% in 1999 to 10% in 2002. However in 2003, this remained static at 60.72% and is now the third lowest figure in the country.

In 2002, 11% of the cohort entered work-based learning, some 3% above the national average. However, this had fallen from 14% in 2001. Latest figures reveal that this has started to recover in 2003, with 13.24% of young people going into work based learning. This has been helped by the introduction of E2E. There is still a substantial proportion of young people in Salford who enter employment, 8.92% in 2003 (this is in addition to those on Modern Apprenticeship), the vast majority of these going into employment with training.

Through Aim Higher Salford schools and colleges are working in partnership with five local higher education institutions – Manchester University, UMIST (University of Manchester Institute of Science and Technology), Manchester Metropolitan University, Salford University and Bolton Institute of Higher Education.

- Positives

- Salford has many positive achievements to be proud of:

- schools and other partners in Salford are committed to 14-19 strategies and understand and appreciate their value

- achievement at Key Stage 3 is improving

- well established collaborative networks, involving all partners, and now being further developed through LIG collaborative

- over the last few years work based learning providers have been increasingly involved in collaboration with each other and with colleges, particularly around leadership and management, joint development activity and E2E

- a wide range of collaborative activity to support progression to post 16 learning, such as taster days, careers fair, summer schools, transition initiatives, through Aim Higher, Excellence in Cities, and Area Wide Inspection activities

- well established provision to meet the needs of the gifted and talented cohort in secondary schools

- the number of students achieving 3+ A/A* at GCSE increased in 2003

- increased participation in learning at 16 (from 70% in 1999 to 74% in 2003). Participation in further education has shown an even more dramatic increase, from 48% in 1998 to 61% in 2003

- reducing NEETs (not in education, employment or training), from 17% in 2001 to 14% in 2002 and 10.74% in 2003

- learning mentors established in all secondary schools, supporting retention and achievement

- involvement in the national Behaviour Improvement Programme

- the establishment of successful collaborative vocational provision at Key Stage 4. All but one secondary school now offer vocational qualifications at Key Stage 4; nine schools offering GCSEs in vocational subjects covering all curriculum areas except engineering; and eight schools offering GNVQ, mainly ICT (information and communication technology). In 2002 32% of Key Stage 4 students were involved in vocational provision, either internal or external. This has increased substantially in 2003; the numbers of year 10 students starting vocational courses in September 2003 included those taking vocational GCSEs 1005 (38.6% of cohort); GNVQ 627 (24%); on college placements 192 (7.3%); at vocational centres 143 (5.5%); with MPower 103 (4%).

- an increased range of curriculum at all three colleges, both academic and vocational, especially at Entry and Foundation levels

- increased achievement and retention at all three colleges

- in the last three years all work based learning providers have been inspected and graded as satisfactory or better

- E2E is now well established with four work based learning providers in Salford and is already making an impact.

- the funding threshold for EMAs (Education Maintenance Allowance) has now been increased allowing more young people to benefit; increasing publicity should bring this to the attention of more families in Salford.

- Areas of work where development work is ongoing or where issues need to be addressed:

- young people need increased support and guidance if they are to make the most of the 14-19 phase

- young people, and particularly their parents/carers, are still not sufficiently aware of the vocational route; progression routes need to be clearer

- achievement at Key Stage 4 is not increasing at a fast enough rate and there are big differences in achievement between boys and girls

- development work is needed to coordinate the various agencies which promote positive attitudes to education

- the participation rate of young people at 16 is still well below the national average and there are wide differences between schools; there are cultural issues in an area where going on to further or higher education is not the norm

- although many students are moving on to college and work based learning they are not necessarily all being retained (there may be a geographic factor here)

- although reducing, there are still too many young people who are NEET (not in education, employment or training)

- schools need support in managing a more flexible Key Stage 4 curriculum, ensuring delivery of core and entitlement subjects, as well as developing the vocational curriculum; there are still some schools that have no vocational curriculum and most schools do not have sufficient provision to offer an entitlement to vocational curriculum

- external vocational placements are not sufficiently secure for schools to have confidence in their continuation; there is a lack of an overarching funding steer from government and a lack of funding specifically for 14-19 developments

- the vocational curriculum at Key Stage 4 is still insufficiently inclusive and doesn’t meet all young peoples’ needs

- schools, colleges, work based learning providers and other providers need to be assured of quality issues – including guidelines for staff, support for students

- while relations between schools and colleges in Salford are good, many young people from catholic schools move on to catholic colleges in Manchester at 16, which are not part of the collaborative network

- development work is needed if schools are to satisfy statutory requirements to introduce work-related learning from Sept 2004

- there has always been a relatively high proportion of young people in Salford in work based learning. This fell in 2002. Although numbers have started to increase in 2003, this improvement needs to be sustained; work based learning providers are involved in a range of activity with schools, but not all schools and not all providers are involved

- schools are finding it difficult to recruit and retain high quality staff

# Mission

- In Salford, we will establish a curriculum, support and progression routes to enable all young people to be involved in learning opportunities that meet their needs, raise aspirations and allow them to achieve their full potential and prepares them for adult and working life

# Vision/objectives

We will: -

- work together collaboratively and sensitively through the Salford Lifelong Learning Partnership and the 14 – 19 Participation Group, involving Salford Education and Leisure Directorate, the Learning and Skills Council Greater Manchester, High Schools (including Special High Schools), Sixth Form and Further Education Colleges, Higher Education Institutions, Employers, Work Based Learning providers, Connexions Salford, and Salford Business Education Partnership, to establish a range of pre and post 16 provision that meets young peoples’ needs

- establish a range of high quality provision at Key Stage 4, both vocational and academic, to ensure that all young people can have a personalised curriculum that meets their needs, making full use of increased flexibilities enabling Salford pupils to equal and exceed the standards of the country’s best

- establish a range of external vocational placements at Key Stage 4 that makes use of all appropriate providers (colleges, work based learning providers, employers)

- ensure that Salford partners are fully cognisant with “14-19 Opportunity and Excellence” and the outcomes of the Tomlinson report in order to plan appropriate developments for the future

- ensure that there is a range of post 16 provision that offers a full range of qualifications, at all levels and in all occupational areas

- ensure that provision pre and post 16 is inclusive and meets the needs of all young people, regardless of ability, special needs, ethnic background or gender

- ensure that there is a clear plan for the contribution to be made to 14-19 developments by different projects and different funding streams

- plan and monitor the success of this initiative through consultation with students and their parents/carers in addition to those listed above

- be prepared to take risks and innovate in order to keep Salford at the forefront of developments

### Action plan

In order to address the issues and take forward the developments identified in this plan, the following action plan is proposed (baselines will be established and activity/impact monitored on an annual basis):

##### Establishing an entitlement at Key Stage 4

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| A1 | Schools will ensure that all Key Stage 4 students, whatever their circumstances, will have access to a personalised curriculum that prepares them for adult and working life, meets their developmental needs and allows them to achieve their full potential | Schools | 2004-2006 | Schools’ mainstream funding |
| A2 | Schools will ensure that students will have the opportunity to develop an Individual Learning Plan, have access to a Connexions Personal Adviser at crucial stages of decision making, and be supported by learning mentors where appropriate (also see B2) | Schools supported by Connexions | 2004-2005 | Schools’ mainstream funding Connexions funding |
| A3 | Schools will ensure that there will be a core entitlement for students on external placements, reflecting recent QCA Guidance on Key Stage 4; tuition in Key Skills – Communication, Application of Number and Information Technology, should be seen as a minimum entitlement | Schools | 2004-2005 | Schools’ mainstream funding |
| A4 | Schools should provide the opportunity to develop personal, social and vocational skills through a range of programmes or experiences, taking account of QCA’s work on personal development | Schools supported by School Improvement Service | 2004-05 | Schools’ mainstream funding |
| A5 | Schools/providers should ensure that all accreditation is based on Section 96 of the Learning& Skills Act 2000 | Schools/All providers | On-going | Increased flexibility/LSDA funding for new courses |
| A6 | Schools will retain responsibility for all students on work, vocational centre, or college placement | Schools | On-going | Schools’ mainstream funding |
| A7 | Schools will ensure that there will be a differentiated curriculum provision at Key Stage 4 to enable non age related accreditation where appropriate, including access to early accreditation or specialised provision, including gifted and talented and other elements of SEN | Schools | On-going | Schools’ mainstream funding |
| A8 | Schools will ensure that all young people at Key Stage 4 will have access to a work-related curriculum, in line with QCA’s recently established guidance; there will be enhanced work experience opportunities with careers advice guidance to ensure progression / continuity Post 16 | Schools supported by 14-19 Coordinator and Salford BEP | From September 2004 | Some AWI funding for training and development Potentially Enterprise Pathfinder funding |
| A9 | Schools/providers should establish strategies to ensure that young peoples’ and their parents’/carers’ views are taken into account in the development of the Key Stage 4 curriculum | Schools/colleges/wbl providers | On-going | Schools’/providers’ mainstream funding |
| A10 | Once the outcomes of the Tomlinson report become clearer, work will be done on establishing an entitlement that spans the whole of the 14-19 age group | 14-19 Participation Group | Autumn 2004 | None required |

Preparing young people at Key Stage 3 for the 14-19 phase

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| B1 | Schools will establish a structured year 9 guidance programme, with access to a Connexions personal adviser where appropriate | Schools supported by Connexions | September 2004 on | Schools/Connexions |
| B2 | Progress File will become a key document in recording and reviewing progress across the whole of the 14-19 phase, building on the substantial experience of the National Record of Achievement; schools, the Connexions Service, post 16 providers and others will work together to support young people in developing an Individual Learning Plan for the whole of the 14-19 phase | Connexions working with schools | Progress File – ongoing ILP – development work 2004/05 | Some AWI funding for developments |
| B3 | A good range of marketing material will be developed for young people and parents/carers, that explains options available at Key Stage 4 and progression routes | Increased Flexibility steering group | Spring 2004 onwards | Increased flexibility funding |
| B4 | Parity of esteem between academic and vocational routes will be promoted with teachers/young people/carers and guardians through development of marketing and information materials, inclusion of partners in parents/carers information evenings etc. etc. | Schools/Connexions/providers | On-going | Schools/Connexions/providers |
| B5 | A broad and balanced curriculum will be maintained at Key Stage 3 to enable all young people to have access to an appropriate 14-19 pathway | Schools | ongoing | Schools’ mainstream funding |

##### Raising achievement at Key Stage 4

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| C1 | All schools, and other partners involved with KS4 students, should be committed to using the increased flexibilities set out in “14-19: Opportunity and Excellence” and the revised national curriculum framework in order to develop a curriculum appropriate to young peoples’ interests and learning styles; where appropriate flexibility will be extended to Key Stage 3; developments will take account of the emerging themes from the 14-19 Working Group | Schools supported by 14-19 Coordinator and providers | 2004-2006 | Mainstream schools funding |
| C2 | Training will be offered to school timetablers to ensure that they are aware of the requirements of flexibility at Key Stage 4 | 14-19 Coordinator/SIO | 2004/05 | AWI Training and development fund |
| C3 | The lessons of Key Stage 3 will be extended to Key Stage 4, especially in teaching and learning | Key Stage 3 strategy manager | 2004 on | DfES Strategy funding |
| C4 | Learning mentors will be used to support students’ achievement and raise expectations at Key Stage 4 | Schools | On-going | EiC funding/LPSA/NRF |
| C5 | Excellence in Cities and Aim Higher will be used to support the raising of achievement at Key Stage 4, including increasing achievement of 5+ A*-C (target of 42%), 5+ A*-G (target 92% by 2004) | EiC Director/schools/SIOs | On-going | EiC/Aim Higher budgets |
| C6 | Programmes will be provided to supported gifted and talented young people. Through the gifted and talented programme and Aim Higher, the proportion of young people achieving the highest grades at GCSE will be increased | Aim Higher Coordinator working with schools | On-going | Aim Higher budget |
| C7 | School improvement officers will support schools in developing their Key Stage 4 curriculum and setting targets to raise achievement at Key Stage 4 | SIOs | On-going | LEA budget |
| C8 | Where appropriate research and innovative projects will be developed to understand and promote the achievement and learning styles of boys at Key Stage 4, building on the Aim Higher pilot | Aim Higher coordinator | 2004/05 | Aim Higher |
| C9 | Full use will be made of developing technologies to enhance achievement, motivation and attainment | CLC Director/School improvement service/ICT services | ongoing | Schools mainstream + ICT budgets |

Ensuring that all young people have access to a vocational curriculum

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| D1 | The range of vocational qualifications at Key Stage 4 will be expanded to meet the needs of all students; all schools should offer at least one vocational qualification | Schools with support of 14-19 Coordinator, IF steering group, providers | On-going | Mainstream school funding supported by IF/LSDA/AWI |
| D2 | External vocational placements will be established on a secure, collaborative basis, on a distributed model i.e. placements in colleges, work-based learning providers, vocational centre, with employers, with common days for external placements | 14-19 Coordinator with colleges/wbl providers | September 2004 onwards | Mainstream school funding supported by IF/LSDA/AWI |
| D3 | Collaborative arrangements between schools, and between schools and colleges (and possibly work based learning providers/employers) will be extended for the delivery of in-school vocational curriculum (GNVQ, GCSEs in vocational subjects), in order to extend the range of vocational qualifications available to individual young people | Schools working with 14-19 Coordinator/LIG manager | On-going | IF/AWI funding, possibly supported by LIG collaborative |
| D4 | Schools will be supported in the introduction of new vocational qualifications, particularly those intended to replace GNVQ | 14-19 coordinator, training and development group | On-going | IF/LSDA/AWI |
| D5 | Information and training for school staff will be offered on the range of new and existing vocational qualifications available at Key Stage 4 | 14-19 coordinator/training and development group | On-going | IF/LSDA/AWI |
| D6 | Rights and responsibilities will be set out formally in a student, parent/carer, school/provider agreement where the vocational provision includes significant time on vocational centre, college, work based learning provider or employer premises | Increased flexibility steering group | Summer 2004 | Increased flexibility |
| D7 | Each student with significant off site provision will have an identified adult mentor, if funding is available, within school who will regularly monitor progress against the Individual Learning Plan | Schools | On-going | Schools mainstream/EiC budget |

Ensuring that the vocational curriculum at Key Stage 4 is inclusive

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| E1 | A range of vocational curriculum and support for students in Key Stage 4 will be developed in special schools, through the LSC funded special needs project | New Croft High School | 2003/05 | LSC AWI |
| E2 | A range of vocational tasters and other support for pupils in PRUs and Learning Support Units and pupils at risk of exclusion in mainstream schools will be developed through PAYP XTRA | Lifelong Learning Directorate PAYP Manager | Jan 2004-Dec 2005 | ESF Co-financing |
| E3 | Schools will maximise the use of existing and future vocational qualifications to meet the needs of pupils of all abilities | Schools with support of IF steering group/14-19 Coordinator | Sept 2004 on | IF/schools’ mainstream funding/AWI |
| E4 | New qualifications, particularly Entry level qualifications will be explored and introduced where appropriate | 14-19 Coordinator with schools/colleges | Sept 2004 onwards | IF/AWI |
| E5 | All partners will monitor provision and developments to ensure that it is sufficiently inclusive | All partners | On-going |  |

Ensure the quality of vocational provision, whether delivered by schools or by external partners

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| F1 | A quality monitoring framework will be established for all Key Stage vocational provision, involving all partners | 14-19 Coordinator | Summer 2004-Spring 2005 | ? |
| F2 | The existing LSDA (Learning and Skills Development Agency) network will be enhanced to ensure training of school and college staff for the vocational curriculum | Eccles College/LSDA Network, but link to LIG collaborative | On-going | LSDA |
| F3 | Training and development of all partners on 14-19 issues will be provided; where possible teachers/tutors delivering vocational qualifications will be recruited from relevant occupational areas or will be offered substantial time for placements in industry | 14-19 Coordinator/Training and Development Group | On-going | LSDA/AWI training and development fund |
| F4 | A 14-19 training and development group will be established to oversee training and development on 14-19 issues | Eccles College – chair, supported by 14-19 Coordinator | On-going | LSDA/LSC AWI training and development fund |

###### Build on existing collaborative arrangements

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| G1 | We will develop an action plan that shows the clear contribution of each project and funding stream that impacts on 14-19 developments | 14-19 Coordinator | Summer 2004 | None required |
| G2 | We will ensure that there is sufficient communication between existing collaborative groups – 14-19 Participation Group, Lifelong Learning Partnership, Salford PLAIT, headteachers and principals group, Aim Higher partnership, LIG collaborative, work based learning providers network – ensuring that the remit of each is clarified and communicated to all | Lifelong Learning Partnership | On-going | None required |
| G3 | The 14–19 Participation Group will monitor, revise and evaluate developments and disseminate good practice | 14-19 Participation group | On-going | None required |
| G4 | Curriculum deputies (with colleges, LEA and other partners) will be empowered to tackle issues of curriculum planning and collaboration | LIG/schools? | 2003/2005 | LIG collaborative/Increased Flexibility |
| G5 | A 14-19 practitioners group will be established across Salford and a practitioners group in each school; a curriculum development group will be established across Salford, to ensure good curriculum progression from Key Stage 4 to post 16 options | 14-19 Coordinator/SIO/schools | From Summer 2004 | AWI Training and Development Fund |
| G6 | Protocols/Service Level Agreements and guidance for all school/college/provider staff will be developed in relation to external vocational placements | Increased Flexibility steering group | Summer 2004 | Increased flexibility |

Increase participation in learning of young people at 16

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| H1 | Careers education from year 7 will be developed in each school, in line with the non statutory framework | Connexions with schools | Sept 2004 onwards | Connexions/schools mainstream |
| H2 | Awareness raising on post 16 options will be developed for all teachers involved in Key Stage 4 | Training and development group/14-19 coordinator | Summer 04 ongoing | AWI training and development fund |
| H3 | Awareness raising with young people on post 16 options will be delivered through |  |  |  |
|  | - Salford careers fair and involvement in Skillcity | Careers fair – Salford PLAIT Skillcity – 14-19 coordinator | annually | AWI funding None needed |
|  | - Tasters for year 10 students in colleges | Salford PLAIT | annually | AWI funding |
|  | - Tasters for year 10 students with work based learning providers | LSC | Summer 2004 | AWI funding |
|  | - Providing full information on all post 16 options, available to all young people and their parents/carers, using national campaigns, web-sites and local information | Connexions/ Aim Higher | ongoing | Connexions LSC/Aim Higher |
|  | - Transition initiatives/events | Aim Higher coordinator | ongoing | Aim Higher |
|  | - Summer schools e.g. M5 4WT | LEA Study support coordinator | annual | NOF/Aim Higher/PAYP/SRB |
|  | - Provision of financial advice, including EMAs | Connexions/EMA Coordinator | ongoing | Connexions |
|  | - Involvement of providers in school careers events, options evenings, parents evenings | Schools and colleges/providers | On-going | None needed |
| H4 | Young peoples’ skills will be developed, including encouraging young people to become independent learners and make full use of e.learning | Schools | ongoing | Schools’ mainstream funding |
| H5 | The Connexions Service will work with partners to decrease the number of young people who are not in education, employment or training | Connexions | On-going | Connexions |
| H6 | School improvement officers will work with schools to set targets to increase participation in learning post 16 | School improvement officers | Form September 2004 | LEA |
| H7 | There will be development work on involvement of work-based learning providers in schools | LSC/14-19 Coordinator | From September 2004 on | LSC AWI |
| H8 | The LEA will work with all its partners, in particular the Connexions Service and Learning and Skills Council, to endeavour to achieve the extremely demanding LPSA (Local Public Service Agreement) participation target of 91% of young people going into education or work based learning at 16 | 14-19 Coordinator | Summer 2004-December 2005 | LPSA pump-priming funding |

Progression routes

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| J1 | Development work will be undertaken to ensure secure progression routes from Key Stage 4 (including vocational qualifications) to post 16 options, including for those young people who are not able to access formal full-time learning | Increased Flexibility steering group | On-going | Increased Flexibility |
| J2 | Methods will be developed to raise the profile of vocational learning with employers and higher education | Increased flexibility steering group | 2004/05 | Increased Flexibility/AWI training and development fund |

#### Post 16 provision

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| K1 | All partners in Salford will collaborate with the Learning and Skills Council Greater Manchester in the implementation and outcomes of the Strategic Area Review, in order to ensure that therange of provision is sufficient for all 14-19 year olds | LSC | Summer/Autumn 2004 | LSC |
| K2 | All providers will work with the Learning and Skills Council to ensure that all provision for all learners is of high quality, whatever their chosen pathway | LSC/providers | On-going | LSC |
| K3 | Providers will work with the Learning and Skills Council to develop their facilities, to ensure that they are appropriate to meet young peoples’ needs and to provide discrete provision for 16-19 year olds | LSC/providers | On-going | LSC |
| K4 | All providers will measure and aim to improve achievement, retention and added value | LSC/providers | On-going | LSC |
| K5 | All providers will work with other partners to support students’ Individual Learning Plan and Progress File, and monitor students’ progress and progression | Colleges/wbl providers | On-going | Mainstream college/provider funding |
| K6 | All colleges will continue to make special arrangements for the cohort of students identified as “gifted and talented” and those identified as being in the widening participation/Aim Higher cohort | LEA Aim Higher coordinator/colleges | On-going | Aim Higher funding |
| K7 | Training will be developed for all provider staff on 14-19 issues, such as new qualifications, post 16 opportunities, progression pathways, preferred learning styles, work with gifted and talented and widening participation group, use of Individual Learning Plan and Progress File, higher education and PPS | Training and development group | On-going | AWI training and development fund |
| K8 | All providers will work with the Connexions Service to support the tracking of students at 16,17,18,19 and Connexions will share the information with partners | Connexions | On-going | Connexions |
| K9 | The LSC will work with all its partners, in particular work-based learning providers to develop the quality and range of provision offered through modern apprenticeship | LSC/wbl providers | ongoing | LSC |
| K10 | A full range of E2E provision will be developed, in partnership with a range of local organisations | LSC/wbl providers | ongoing | LSC |
| K11 | Benchmarking data will be developed to enhance the performance of work-based learning providers | LSC/wbl providers | ongoing | LSC |

16-19 Entitlement

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| L1 | All learners will be entitled to the following, whatever their institution, mode or level of study: | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Free tuition | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Free choice of institution | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Clear entry to courses/training and levels | LSC/Colleges/wbl providers | On-going | LSC |
|  | - A range of provision from entry level to level 3 | LSC/Colleges/wbl providers | On-going | LSC |
|  | - High quality teaching and learning | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Access to basic skills/key skills support | LSC/Colleges/wbl providers | On-going | LSC |
| L2 | All learners on full-time college courses and work based learning will be entitled to: | LSC/Colleges/wbl providers | On-going | LSC |
|  | - An induction programme and assessment on entry | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Pastoral support | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Access to advice on financial support | LSC/Colleges/wbl providers | On-going | LSC |
|  | - careers information, advice and guidance | LSC/Colleges/wbl providers | On-going | LSC |
|  | - access to work related learning | LSC/Colleges/wbl providers | On-going | LSC/AWI |
|  | - enrichment activities | LSC/Colleges/wbl providers | On-going | LSC |
|  | - specialist tuition and facilities | LSC/Colleges/wbl providers | On-going | LSC |
|  | - Support for their Individual Learning Plan and Progress File | LSC/Colleges/wbl providers | On-going | LSC |
| L3 | Once the outcomes of the Tomlinson report become clearer, work will be done on establishing an entitlement that spans the whole of the 14-19 age group | 14-19 participation group | 2004/05 | None required |

Data sharing

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| M1 | The LEA will lead a project to develop a database to support the transfer of school information to meet the needs of colleges | LEA Partnership Information Officer | Spring 2004-2005 | AWI funding |
| M2 | Information on tracking of students will be shared | Connexions/Aim Higher/ Education and Leisure information unit/Partnership Information Officer | On-going | Connexions/Aim Higher/AWI |
| M3 | The Learning and Skills Council Greater Manchester will share information on work-based provider performance, making it publicly available in the same way that data on school and college performance is provided | LSC | ongoing | LSC |

Progression to HE

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| N1 | Through Aim Higher, involving schools, colleges, LEA and universities, to motivate and encourage young people to aim for university through: | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - Summer schools, tasters, HE visits, student conferences | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - Study support programme, masterclasses, HE lecturers, differentiated provision | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - Curriculum projects | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - Aim Higher Roadshow and other marketing activities raising HE profile with students, parents/carers and families | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - HE mentoring | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
|  | - Vocational links between schools, colleges and higher education institutions | LEA Aim Higher Coordinator | ongoing | Aim Higher funding |
| N2 | To support Greater Manchester’s Partnerships for Progression programme, through membership of sub-groups and other activities | P4P/Aim Higher | ongoing | P4P/Aim Higher |
| N3 | To work in collaboration with the University of Salford, to support the University’s Summer School M5 4WT | LEA/University of Salford | annually | ? |

Information and communication

|  | Activity | Lead responsibility | Timescale | Funding stream |
| --- | --- | --- | --- | --- |
| O1 | A termly newsletter will be produced on 14-19 issues | 14-19 Coordinator | termly | AWI training and development fund |
| O2 | In the short term a contacts database will be established on colleges’ web-sites | Eccles College | Summer 2004 | LSDA |
| O3 | In the longer term a dedicated Salford 14-19 web-site will be established | LEA/14-19 Coordinator | 2004/05 | ? |
| O4 | In order to facilitate understanding, cross sector placements will be developed | 14-19 Coordinator | 2004/05 | ? |

Organisations in Salford committed to this strategy

Salford City Council/Education and Leisure Directorate

Learning and Skills Council Greater Manchester

Salford Lifelong Learning Partnership

14-19 Participation Group

Salford PLAIT

Salford Connexions

Salford Foundation/Business Education Partnership

Schools

All Hallows RC High School

Canon Williamson CE High School

Buile Hill High School

Irlam and Cadishead Community High School

Harrop Fold High School

Hope High School

Irwell Park High School

Moorside High School

New Croft High School

Oakwood High School

Royal Manchester Hospital School

St. Ambrose Barlow RC High School

St. George’s High School

St Patrick’s High School

The Albion High School

The Swinton High School

Walkden High School

Wentworth High School

Barton Moss Secure Unit

Broadwalk PRU

Eccles and Irlam PRU

Grosvenor Centre PRU

The Bridges Broadwalk Centre

Colleges

Eccles College

Pendleton College

Salford College

Work based learning providers

Age Concern

Carillion

GDN Training

HCTC

Salford Consortium

SITEC

Skills Solution
START

STEGTA

Training and Manpower

YMCA Training

The Vocational College

### Glossary

14-19: Opportunity and Excellence – sets out the government’s proposals for 14-19. published in early 2003

14-19 Participation Group – responsible to Lifelong Learning Partnership, involving wide range of partners in Salford, responsible for overseeing developments and strategy in 14-19

A level – GCE Advanced Level, in 2000 became AS and A2

Aim Higher – previously Excellence Challenge, part of Excellence in Cities, aimed at widening participation in learning and increasing entry to higher education

AMA/FMA – Advanced Modern Apprenticeship/Foundation Modern Apprenticeship – work based qualifications offered through training providers/employers, including NVQs at levels 2-4, key skills and technical certificates

AVCE – Advanced Vocational Certificate of Education, previously Advanced GNVQ, will be called A level from September 2005

AWI – Area Wide Inspection; when Salford was inspected in 2000 this covered the 16-19 age range, but current inspections cover 14-19

Core/entitlement subjects -  from September 2004, the curriculum at Key stage 4 will become more flexible, with:

Core (compulsory) subjects – English, maths, science, ICT plus work related learning, citizenship, RE, PE, careers education, sex education

Entitlement (options for students) – modern foreign languages, design and technology, arts and humanities

CLC – City Learning Centre

EiC/Excellence in Cities – funding from DfES through LEAs to raise achievement in inner city schools, both primary and secondary

EMA – Education Maintenance Allowance – funding of up to £30 per week, if family income is less than £30,000, for young people who continue in education post 16, as long as they meet certain targets

Entry Level Qualifications –part of the National Qualifications Framework, available at 3 levels for students not ready for Level 1

Foundation level – qualifications offered at level 1 of the National Curriculum Framework

GCSE – General Certificate of Secondary Education, normally taken at age 16; graded A*-G; 5 A*-C equivalent to level 2 of the National Qualifications Framework

GCSEs in vocational subjects – introduced in September 2002 to replace GNVQ Part 1, offered at the same grades as GCSE

IF/Increased Flexibility – DfES funded programme for introduction of GCSEs in vocational subjects and other vocational qualifications at Key stage 4, in Salford steering group chaired by Salford College

Individual learning plans – part of the government’s 14-19 strategy, students will have an individual learning plan for the whole of the 14-19 phase

Key Stage 4 – years 10 and 11 in secondary schools, ages 14-16

Key Stage 3 – years 7-9 in secondary schools, ages 11-14

LEA – Local Education Authority, in Salford Directorate of Education and Leisure

LIG – Leadership Incentive Grant – funding for secondary schools to support collaboration, leadership and management

LPSA – Local Public Service Agreement – agreement between Local Authorities and Government to achieve targets in a wide range of areas

LSC – Learning and Skills Council – responsible for funding and planning all post 16 education and training, except HE

LSDA – Learning and Skills Development Agency – funding to support networks to support training and development for GCSEs in vocational subjects. In Salford, based at Eccles College

M5 4WT – Salford young peoples’ university – summer schools for year 5 - year 10 students

MPower – a unique local programme, providing one day a week placements with employers for Key Stage 4 students, leading to NVQ

NOF – New Opportunities Fund

NVQ – National Vocational Qualification, available at Levels 1-4 and normally taken in a work setting, part of the national Qualifications Framework

P4P/Partners for Progression –HEFCE (Higher Education Funding Council) – funded programme for widening participation and entry to higher education

PAYP – Positive Actions for Young People – funding through Government Office North West and Greater Manchester Connexions – to provide diversionary activities for young people and increase engagement in learning for young people aged 8-24

PAYP XTRA – linked to PAYP, ESF funded project to increase participation and achievement for disaffected 14-19 year olds

Progress File – the successor to national Records of Achievement; materials available for year 9, years 10/11, post 16 learners and adults

PRUs – Pupil referral units – responsible for the education of pupils excluded from school

QCA – Qualifications and Curriculum Authority, responsible for curriculum framework and qualifications in England and Wales

QCA Guidance – Statutory Guidance on Key Stage 4 curriculum, published September 2003

Section 96 – a database of QCA accredited qualifications available for use at Key Stage 4 or 16-19 (accessed via DfES web-site)

SEN – special educational needs

SIO – school improvement officer, part of Education and Leisure Directorate, working with individual schools to help raise achievement

SkillCity – originally a national skills/careers event, available for all ages, but particularly 14-19 year olds, now available annually on a Greater Manchester basis

SRB – Single Regeneration Budget

Strategic Area Review – LSC led review of 14-19 learning in an area

Work related learning – becomes compulsory at Key Stage 4 from September 2004 – learning through work, about work, for work