| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF THE DIRECTOR OF DEVELOPMENT SERVICES

TO THE LEAD MEMBER OF DEVELOPMENT SERVICES

ON THE 9th AUGUST 2004

TITLE : A56 BURY NEW ROAD QUALITY BUS CORRIDOR – PHASE 2.

RECOMMENDATIONS : That approval is given to accept the quotations from City Highways;

i)          For the re-lighting of the A56 Bury New Road.

- For the construction of bus boarding platforms and improvements to traffic signs and lines on the A56 Bury New Road and the A665 Bury Old Road

EXECUTIVE SUMMARY:  The purpose of the report is gain approval to carry out further works to the A56 Bury New Road as part of the Quality Bus Corridor improvement programme and to carry out improvements to the bus facilities on the A665 Bury Old Road.

BACKGROUND DOCUMENTS :	Report to Lead Members for Development Services and Corporate Services – Approval of Capital Programmes - 12th May 2003 and 5th May 2004.

Report to Lead Member Development Services – Alterations to traffic Signals - 6th October 2003

Report to Lead Member Development Services – A56 QBC resurfacing  - 26th January 2004

ASSESSMENT OF RISK: LOW

THE SOURCE OF FUNDING IS; Transport Capital Programme (Block 3)

LEGAL ADVICE OBTAINED; Not Received

FINANCIAL ADVICE OBTAINED; D. McAllister

CONTACT OFFICER; D A Dean x3866

WARD(S) TO WHICH REPORT RELATE(S); Kersal, Broughton

KEY COUNCIL POLICIES; Safer Salford / Stronger Communities, Local Transport Plan

  - BACKGROUND

  - At the meeting on the 26th January 2004, Lead Member was advised of the following schedule of works required to Bury New Road (A56) in order to upgrade the route to the status of a Quality Bus Corridor;

- Resurfacing of the carriageway at the junctions with Moor Lane / Singleton Road and Northumberland Street / Knoll Street.

- Refurbishment of the footways at the junctions with Moor Lane / Singleton Road and Northumberland Street / Knoll Street.

- Construction of bus boarding platforms and stops appropriate to a Quality Bus Corridor.

- Refurbishment of the traffic signals at the junction with Northumberland Street/Knoll Street.

- Refurbishment and introduction of pedestrian facilities to the traffic signals at the junction with Moor Lane/Singleton Road.

- Replacement of existing Pelican Crossings at Devonshire Street, Broom Lane, and Cavendish Road with Puffin Crossings.

- Replacement street lighting equipment is to be installed along the majority of the route.

  - Approval was given at the meeting of the 26th January 2004 to award a contract to Aggregate Industries Ltd for a significant part of the works listed in Paragraph 1.1. Items e) and f) were approved under a separate report to Lead Member on 6th October 2003 and were carried out directly by Greater Manchester Urban Traffic Control (GMUTC).

  - Items a), b) d), e), f) and a proportion of items c) and g) at the junctions with Moor Lane / Singleton Road and Northumberland Street / Knoll St have now been completed by Aggregate Industries and GMUTC.

  - The new street lighting columns erected around the junctions of Moor Lane / Singleton Road and Northumberland Street / Knoll St are still awaiting electrical service connections from United Utilities. As this will involve limited excavation in the footway, the surface course to the footways has been omitted. It is anticipated that this work will be completed by the middle of September.

  - It is also proposed to carry out paving improvement works to 6 bus stops on the A665 Bury Old Road between Singleton Road and Leicester Road as part of the works for which approval is sought in this report.

  - Quotations for remaining work are anticipated from City Highways on 2nd August 2004 and they will be assessed prior to reporting the values verbally at the meeting. The works are as follows:

- Procurement and installation of street lighting equipment for the remaining length of the A56 Bury New Road.

ii) 	Paving works and improvements to 8 bus stops on Bury New Road with associated improvements to traffic signs and lines for the entire length of the route. Localised improvements to 6 bus stops on Bury Old Road.

2.0 FINANCIAL IMPLICATIONS

2.1	There is an allocation of £230,000 in the Transport Capital Programme for 2004/05 (Block 3) for these works to street lighting and bus boarding platforms on the A56 and A665

- CONCLUSIONS

3.1 The introduction of the Quality Bus Corridor measures will particularly assist users of public transport, cyclists and pedestrians.

# Malcolm Sykes

Director of Development Services