C I T Y   O F   S A L F O R D

Development Services Directorate

ENGINEERING AND HIGHWAYS DIVISION

DRAFT BLOCK 3 TRANSPORT CAPITAL PROGRAMME 2001/2

LISTED BY COMMUNITY COMMITTEE

| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| --- | --- | --- | --- | --- |
| Broughton & Blackfriars: Manchester/ Salford Inner Relief Route, Stage 3 Bury New Road Speed Cameras A57 Regent Road/ Ordsall Lane A576/ A56 Gt Cheetham St/ Bury New Road Palatine Bridge Waterloo Bridge Adelphi Footbridge A6 Chapel Street A576 Gt Cheetham St(Gt Clowes St - Bury New Rd) A56 Bury New Road Quality Bus Corridor Pedestrian Route Improvements | Major Highway Local Safety Local Safety Local Safety Bridge Strengthening Bridge Strengthening Bridge Strengthening Structural Maintenance Structural Maintenance Public Transport Other Minor Works | 23087 60 38 30 35 125 30 740 342 476 30 | 9606 60 29 * 30 35 125 30 110 31 150 * 30 | Jointly funded with Manchester City Council Also Ordsall & Langworthy scheme Linked with A56 QBC scheme General maintenance Parapet Strengthening Refurbishment Also Kersal, Pendleton & Charlestown scheme Part of Chapel Street Regeneration Initiative |
| Broughton & Blackfriars Sub-total |  |  | 10236 | £179k shared with other areas |

| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| --- | --- | --- | --- | --- |
| Claremont, Weaste & Seedley: Bolton Road Traffic Calming A5185 Lancaster Road/ Swinton Park Road A576 Eccles Old Road/ Lancaster Road/ Stott Lane A576 Eccles Old Road Underpass Irlams O'th Height Roundabout A576 Eccles Old Rd (Half Edge Lane - Tootal Dr) A576 Eccles Old Road Quality Bus Corridor A576 Eccles Old Road Street Lighting | Local Safety Local Safety Local Safety Bridge Strengtheming Bridge Strengthening Structural Maintenance Public Transport Other Minor Works | 101 23 25 25 25 660 602 40 | 16 22 25 25 * 25 304 50 40 | Carry over from 2000/1 Also Eccles scheme - replace expansion joint Expansion joint sealing Carry over from 2000/1 Carry over from 2000/1 |
| Claremont, Weaste & Seedley Sub-total |  |  | 507 | £25k shared with other areas |
| Eccles: Ellesmere Park Area Traffic Calming Westwood Park Area Scheme A57/ M60 Peel Green Roundabout B5229 Monton Centre A576 Eccles Old Road Underpass Patricroft Garage Retaining Wall Grange Road Bridge Barton Cycling Facilities Contribution to Eccles Redevelopment | Local Safety Local Safety Local Safety Local Safety Bridge Strengthening Bridge Strengthening Bridge Strengthening Cycling Facilities Other Minor Works | 83 162 21 100 25 44 24 150 - | 23 150 21 100 25 * 25 18 20 * 225 | Carry over from 2000/1 Also Claremont, Weaste & Seedley scheme Retaining Wall Strengthening Parapet Strengthening Also Irlam & Cadishead scheme |
| Eccles Sub-total |  |  | 607 | £45k shared with other areas |
| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| Irlam & Cadishead: Cadishead Way, Stage 1 Cadishead Way, Stage 2 20mph Zone - Silver Street Area Cadishead Northwest Area Scheme Carlton Footbridge Irlam Locks Cycle Crossing Barton Cycling Facilities | Major Highway Major Highway Local Safety Local Safety Bridge Strengthening Cycling Facilities Cycling Facilities | 9483 19860 75 100 90 30 150 | 25 100 75 100 90 30 20 * | Scheme complete - land payment only Assessment & design costs Bridge replacement Scheme linked to Trafford MBC proposals Also Eccles scheme £130k carry over to 02/03 |
| Irlam & Cadishead Sub-total |  |  | 440 | £20k shared with other areas |
| Kersal, Pendleton & Charlestown: Broughton Park Area Scheme A6 Broad Street/ A576 Broughton Road Roundabout A576 Cromwell Road/ Littleton Road Littleton Road Pedestrian Safety Scheme Cromwell Bridge A576 Cromwell Rd (Lissadel St - Lwr Bro'ghton Rd) A56 Bury New Road Quality Bus Corridor | Local Safety Local Safety Local Safety Local Safety Bridge Strengthening Structural Maintenance Public Transport | 172 24 14 184 25 500 476 | 170 24 14 180 25 250 150 * | General maintenance £250k carry over to 2002/3 Also Broughton & Blackfriars scheme |
| Kersal, Pendleton & Charlestown Sub-total |  |  | 813 | £150k shared with other areas |

| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| --- | --- | --- | --- | --- |
| Ordsall & Langworthy: Regent Road Improvement Trafford Road, Stage 2 A57 Regent Road/ Ordsall Lane Regent Road Sign Gantry Regent Road/ Oldfield Road Pedestrian Facilities | Major Highway Major Highway Local Safety Bridge Strengthening Other Minor Works | 6637 20042 38 10 46 | 10 1378 29 * 10 45 | Scheme complete - land payment only Scheme complete - land & works payments Also Broughton & Blackfriars scheme General maintenance |
| Ordsall & Langworthy Sub-total |  |  | 1472 | £29k shared with other areas |
| Swinton: A6 Chorley Road/ Station Road Moorside Road/ Wardley Ind' Estate Area Scheme A6 Chorley Road Route Scheme Folly Lane/ Rocky Lane Pedestrian Facilities A572 Dales Brow/ Moorside Rd/ Partington Lane Eccles Road/ East Lancs Road Footbridge Agecroft Railway Bridge Agecroft Road Bridge A666 Manchester Rd/ Bolton Rd Cycling Facilities | Local Safety Local Safety Local Safety Local Safety Local Safety Bridge Strengthening Bridge Strengthening Bridge Strengthening Cycling Facilities | 136 75 90 11 42 10 50 105 100 | 33 75 90 10 42 10 50 58 100 | Carry over from 2000/1 Anti-slip treatment Reconstruction - shared cost with Railtrack Parapet Strengthening |
| Swinton Sub-total |  |  | 468 |  |

| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| --- | --- | --- | --- | --- |
| Walkden & Little Hulton: A575 Walkden Road/ Park Road A6 High Street/ Bolton Road Pedestrian Facilities Hilton Lane Traffic Calming Newearth Road Traffic Calming Westminster Road/ Memorial Road A6 High Street Linnyshaw Bridge A575 Walkden Road/ (Manchester Rd - Park Rd) A6 Manchester Road (Bolton Rd - Smithfold Lane) A5082 Armitage Av (Manchester Rd - Boundary) | Local Safety Local Safety Local Safety Local Safety Local Safety Local Safety Bridge Strengthening Structural Maintenance Structural Maintenance Structural Maintenance | 49 28 41 15 11 100 50 150 600 500 | 5 20 38 15 11 100 50 150 300 0 | Carry over form 2000/1 Carry over from 2000/1 Provision of Puffin Crossing & mini-r'about Parapet Strengthening £300k carry over to 2002/3 Possible late start in 01/02 - likely 02/03 |
| Walkden & Little Hulton Sub-total |  |  | 689 |  |
| Worsley & Boothstown: A572 Worsley Rd (Greenleach Ln - Ringlow P'k Rd) | Structural Maintenance | 172 | 163 | Carry over from 2000/1 |
| Worsley & Boothstown Sub-total |  |  | 163 |  |

| Community Committee / Schemes | Scheme Type | Total Cost (£000s) | Spend in 01/02 (£000s) | Comments |
| --- | --- | --- | --- | --- |
| Citywide/ Other Schemes: Accident Investigation Anti-skid Surfacing Programme Carriageway Markings Signs to Zigzag Markings Bridges General Subways Railtrack Bridge Assessments General carry-over of Principal Road Maintenance Structural Maintenance of Minor Roads City of Salford Travel Plan Demand Management Measures Contribution to Regeneration Initiatives | Local Safety Local Safety Local Safety Local Safety Bridge Strengthening Bridge Strengthening Bridge Strengthening Structural Maintenance Structural Maintenance Other Minor Works Other Minor Works Other Minor Works | - - - 15 - - - - 250 38 200 30 | 40 50 15 15 10 5 90 27 250 27 125 30 | General fund for investigations On-going programme On-going programme Various minor works On-going programme On-going programme Decriminalised Parking set-up costs To assist matching funding |
| Citywide/ Other Schemes Sub-total |  |  | 684 |  |
| GRAND TOTAL |  |  | 16079 Sum of separate sub-totals - 224 less total of Shared schemes 15855 |  |

E/DF/T/8/1

11 April 2001