| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF THE LEAD MEMBER FOR

CHILDREN AND YOUTH & THE LEAD MEMBER FOR EDUCATION

TO THE CHILDREN’S SERVICES SCRUTINY COMMITTEE

ON 13th April 2005

TITLE : Update of post-inspection action plan Barton Moss Secure Care Centre

RECOMMENDATIONS :

That the action plan arising from the Inspection is accepted and that a further report be made to Scrutiny Committee to coincide with the annual monitoring report from Commission for Social Care Inspection.

EXECUTIVE SUMMARY :

Barton Moss is secure accommodation provided under section 25 of the Children Act 1989. The Children (Secure Accommodation) Regulations 1991 require that secure accommodation is approved by the Secretary of State. This requires a triennial inspection leading to the issue of a licence to operate for a further three years.

Barton Moss was inspected for this purpose by the Commission for Social Care Inspection in April 2004. As is customary in such inspections, the Office for Standards in Education was invited to inspect educational provision on the site at the same time.

The Inspection was undertaken against five key standards:

1. Statement of Purpose

2. Resources available to the secure estate

3. Improving life chances

4, Education

5. Quality of Performance

A new licence has been issued by the Secretary of State to authorise the continued operation of the unit for a further three years..

Scrutiny Committee considered the action plan in October 2004. This report presents an update on progress in achieving that action plan.

BACKGROUND DOCUMENTS : 
Report of Inspection of Barton Moss Secure Care Centre CSCI September 2004

Action Plan following inspection.

CONTACT OFFICER : Paul Woltman 793 2243

WARD(S) TO WHICH REPORT RELATE(S)  Not applicable

KEY COUNCIL POLICIES:

##### The report is relevant to the Council’s pledges to

Improving Health in Salford
Reducing crime in Salford
Encouraging learning, leisure and creativity in Salford
Investing in young people in Salford.

DETAILS

The following background information may be of use to Scrutiny Committee members.

Barton Moss was opened in its current form in 1995 as a twenty place secure unit divided into three living areas. This succeeded a seven bed unit which had opened in 1989. The need for high levels of supervision at all times as well as specialist work on offending behaviour and other personal issues mean that there are approximately 100 staff employed at Barton Moss. This includes an administrative support team.

There is educational provision on site for all residents with a dedicated teaching team provided by the Education and Leisure Directorate.

There is also provision in the secure perimeter for sport and leisure activity and for basic health and dental care. The Unit is supported by specialist Child and Adolescent mental Health Services.

Barton Moss is intended to be as self-contained as possible although young men do have to leave for major medical attention. There is also programmed time outside the secure unit for young men as part of their sentence plans. This is highly controlled and supervised.

Barton Moss has always catered primarily for young people who are in trouble. In 1999 the Youth Justice Board took over responsibility from individual local authorities and the Prison Service for placing young people who had been remanded or sentenced to be held in security. In April 2004 it was agreed to contract all twenty beds at Barton Moss to the Youth Justice Board.

# POST INSPECTION ACTION PLAN

| ## STANDARD 1 | Statement of Purpose |
| --- | --- |

| Recommendation | Initial actions | End Date | Lead Responsibility | Resource Implications | Update April 2005 |
| --- | --- | --- | --- | --- | --- |
| 2.1 Senior managers should redraft the section on complaints to emphasise the role of the unit in responding to them and the role of the independent advocacy service. | Completed | Oct 04 |  |  | Achieved This task was reported as fully completed in October 2004. |
| 2.2 As staff access to computers improves, the management team should consider how to create a library of key documents on the server, which staff can access. | All existing templates are now in place on the server. These will be updated and added to as the transition from paper records to electronic format is undertaken. The collation of Local Authority Policies and internal guidance documents is ongoing. | Ongoing Dec 04 | Alison Stephens Mike Lowry | Existing Resources – Admin staff time | Achieved A library of on-line forms has been created. Further task Work is needed to link computers used by teaching staff to the Salford Network and the Barton Moss local network. ###### September 2005 |

# POST INSPECTION ACTION PLAN

| ## STANDARD 2 | Resources Available to the Secure Establishment |
| --- | --- |

| Recommendation | Initial actions | End Date | Lead Responsibility | Resource Implications | Update April 2005 |
| --- | --- | --- | --- | --- | --- |
| 2.3 Senior management, in conjunction with colleagues in personnel, must review all recruitment processes to ensure full compliance with “Choosing with Care” and the “Disqualification for Caring for Children Regulations” | Senior managers and personnel will comprehensively review all recruitment documents, processes and selection methods and produce updated recruitment guidance specifically for Barton Moss | Dec 04 | Paul Woltman Iris Newton | Snr Manager and Principal Personnel officer time | New recruitment processes have been designed for social care staff including competence assessments and psychological tests. To be introduced April 2005. Will then be extended to include teaching staff by September 2005. |
| 2.4 Personnel managers and the unit manager should develop mechanisms to ensure regular communication and provide a forum for resolving difficulties, particularly those related to monitoring sickness, dealing with long term ill health problems and capability issues. | Senior managers will meet quarterly with representatives from personnel to review any staffing issues i.e. related to sickness and health competency issues | Dec 04 | Mike Lowry Joanne Todd | Existing resources – Personnel & Centre Manager time | Achieved In place and ongoing |
| 2.5 Managers should develop an overall strategy to reduce sickness levels | A database is now in place and is maintained by the admin officer and this triggers any member of staff who reaches the trigger points for implementing the Attendance Management procedures. The admin officer relays this information to the individual Head of Home who will then begin the formal process of monitoring sickness. Individual sickness will be a standing item on the quarterly personnel meetings. | Aug 04 | Mike Lowry Joanne Todd Steve Osmond Sharon Howarth | Existing resources – Snr Admin /Centre Manager / Personnel time | Achieved In place and ongoing |
| 2.6 Managers should consider building on the work in open units to recruit bank staff to reduce the demand for overtime from permanent staff. | A quarterly rolling programme of recruitment will be put in place | Jan 05 | Mike Kelly Mike Lowry | Increase in Recruitment Advertising budget and Personnel and Centre Management staff time | Achieved There is now a pool of 6 casual social care staff linked to Barton Moss. |
| 2.7 Personnel staff must urgently provide advice and guidance to managers to ensure compliance with the European Working Time Directive | Personnel will work with senior managers to provide written guidance to ensure compliance. | Dec 04 | Iris Newton Joe Riley Mike Kelly | Snr Principal and Principal Personnel officer time | It is proving difficult to identify confidently the application of this legislation to residential child care workers particularly with regard to “sleeping-in”. Staff who need to sign an “opt-out” have now done so. |
| 2.8 Managers should build on the work already done on NVQs to develop an overall training plan the unit. | A training plan has been developed. | completed | Mike Lowry Steve Osmond Mike Kelly Jacqui Hughes | None | Residential and Education staff have individual Training Plans. These will now be assimilated into a joint plan by July 2005. |
| 2.9 In developing the new contract for advocacy services the unit manager must ensure access to a consistent and skilled service. | The new Advocacy Service has been agreed with Spurgeon’s Child Care (the Provider). This service is complaint with the requirements of the Youth Justice Board. The advocacy co-ordinator is in place and a dedicated part-time advocate and recruits are being recruited and trained. | Dec 04 | Paul Woltman | Will be funded from Barton Moss income. | Recruiting a permanent worker for this task has proved difficult but the Manager of the Advocacy Service has committed to providing it personally until a suitable worker is recruited. |
| 2.10 Managers need to develop a major incident plan, which is agreed with local police and fire authorities. | A meeting will be arranged between Barton Moss, the emergency services and the YJB. | Jan 05 | Mike Kelly Mike Lowry | Management & Emergency services time | There is an evacuation plan in place. This identified high risk young people who may need to be kept in security even in an emergency. This plan now needs formalising with GMP and Fire Authority and discussions are ongoing. |

# POST INSPECTION ACTION PLAN

| ## STANDARD 3 | ## Improving Life Chances |
| --- | --- |

| Recommendation | Initial actions | End Date | Lead Responsibility | Resource Implications | Update April 2005 |
| --- | --- | --- | --- | --- | --- |
| 2.11 The unit manager should commission a review of assessment and care planning arrangements to ensure plans are holistic and sufficiently detailed. | The Strategy Management Group will lead on reviewing assessment and care planning ensuring all aspects of care plans are brought together and recorded in detail and reviewed accordingly. | Nov 04 | Mike Lowry | Centre Management time | Achieved New care planning arrangements have been agreed with the Regulatory Inspector from CSCI. |
| 2.12 The programme team manager with the unit heads should review the way the programme team works to promote the development of the key worker role through training, co-working shared, planning etc. | Key worker package to be co-worked with programme and residential staff with programme leader implementing the process which will include: - Defining roles and responsibilities - Developing criteria / protocol for participating residential social work staff (this to be done in conjunction with heads of homes) - Developing appropriate training - Developing appropriate supervision (with heads of homes and seniors) - Developing a referral system - Developing a data collection system - Developing a monitoring and evaluation system - Developing ongoing support system | Nov 04 | Sue Cook | Centre Management / Strategic Group / Programmes Team time | Achieved All residents, including those on remand, are now included in programmes work on offending behaviour. |
| 2.13 The management team needs to maximise learning opportunities presented through their monitoring of files and record books. | A meeting will be arranged between the three Heads of Homes and Service Manager to investigate the possibility of adopting the performance monitoring data used by the open residential units. | Dec 04 | Linda Graves Tony Quinlan | Centre Management / Children’s Resources Management Time | A process for Performance Monitoring to be fully implemented by September 2005. |
| 2.14 As part of a wider training plan managers should ensure that all staff can access appropriate child protection training. | The Deputy Centre Manager and NVQ Assessor are to access appropriate Child Protection Training in January 2005. They will then prepare a training package for staff within Barton Moss. The Centre will endeavour to purchase CPT from outside agencies. | Cascade training April 05 | Paula Horrocks + Teacher | Cost of training/ Centre Management Time / Staff time to attend | A delay in accessing the initial training – has now resulted in this action being deferred for completion by September 2005. |
| 2.15 Managers need to provide greater guidance on sanctions and single separation which ensures that they are commensurate with the presenting behaviour, not overlong, and that single separation is only used as a sanction of last resort and in accordance with departmental policies and procedures and recognised good practice. | The guidance has been rewritten to incorporate the comments of the inspection please refer to Sec 7 Staff Guidance Manual. Also the Heads of Homes will monitor weekly the use and recordings of single separation and countersign the documentation of single separation. Through supervision and staff meetings the appropriate use and guidance for single separation will be discussed. | Sept 04 | Mike Lowry | Head of Home time | Achieved However, definitive national guidance is still awaited. |
| 2.16 Heads of units must ensure use of restraints is legitimate and recorded appropriately. | It has been re-emphasised through staff meetings and ongoing restraint training courses, the importance of detailing with behaviour prior to the restraint taking place. | Nov 04 | Mike Lowry | None | Achieved Monitoring in place. |
| 2.17 Managers need to provide training for all staff on complaints procedures and ensure that “how to complain” is adequately covered in every admission. | Deputy centre Manager along with Salford’s Complaints Officer will organise a schedule of training for staff on how to deal with a complaint and ensure staff cover this appropriately on admission. | Meeting Jan 05 – April 05 | Paula Horrocks Rae O’Farrell | Training Costs Centre Management & Staff time | Information for young people has been updated and is provided on admission. Training for staff is included in induction. Formal training is still being negotiated. |
| 2.18 Managers need to consider how to manage smoking in the vicinity of Barton Moss. | Arrange initial meetings with staff to produce an interim guidance document to improve the current situation Develop and implement a policy to fully resolve the issue for those staff at Barton Moss who smoke : - staff who can leave the building - staff who cannot leave the building | Dec 04 2005 | Steve Osmond Iris Newton | Possible cost of shelter for smokers £2,000 (To be evaluated) Possible cost of providing staff with breaks inc cover (To be evaluated) | Consideration is still being given to overall management of this issue at Barton Moss. However, the sensitivity of the issue for young people has been discussed with staff and procedures are in place to avoid young people being “reminded” of smoking. |

# POST INSPECTION ACTION PLAN

| ## STANDARD 4 | Education |
| --- | --- |

| Recommendation | Initial actions | End Date | Lead Responsibility | Resource Implications | Update April 2005 |
| --- | --- | --- | --- | --- | --- |
| 2.19 Develop an appropriate careers curriculum with more substantial contributions from the Connexions partnership. | Connexions has now increased to one day a week Barton Moss’ careers curriculum will be based upon the AQA ½ GCSE course Work Related Learning (adapted for non GCSE students). Our Development Plan targeted this for delivery from Sept 204 2 students have been identified for work related experience to start Oct 2004 approx. | Completed Oct 04 Oct 04 | Steve Osmond | Funding and teacher time will come from existing resources | Achieved Careers curriculum is in place. |
| 2.20 Develop a more thorough, well-understood and graduated exclusion policy, with suitable procedures and resources. | Looking into converting toilet area into individual study areas where students could work if removed from the classroom. Mike Lowry to contact Ken Roberts to provide quotes for conversion. Decision taken on whether to go ahead with conversion. | Ongoing Sept 04 Oct 04 | Steve Osmond | SMT and Teacher time Teaching resources from existing budget Staffing from existing resources Possible cost of conversion (approx £9/10,000) – if decision is made to go ahead | The design of a withdrawal area for the Education Unit has been prepared. Design approval and funding are being discussed with DfES. |
| 2.21 Develop and implement agreed policies, procedures through joint discussions and training to support RSW in their roles in classes or in supporting education on the residential units. | A meeting will be arranged between Centre Manager, Head of Education and external managers to develop a formal statement on the role of the RSW in education. | Jan 05 | Mike Kelly Jacqui Hughes | Centre Management / external managers time | A programme of joint management meetings is now in place. An agenda for activities has been established. |

# POST INSPECTION ACTION PLAN

| ## STANDARD 5 | Quality of Performance |
| --- | --- |

| Recommendation | Initial actions | End Date | Lead Responsibility | Resource Implications | Update April 2005 |
| --- | --- | --- | --- | --- | --- |
| 2.22 Managers need to develop a more formal performance management system based on collated data from the developing databases, which need to be expanded to cover other key data. | A meeting will be arranged between Barton Moss Admin Officer, external Senior Admin Officer and external managers | Jan 05 | Mike Kelly Jacqui Hughes | Snr Admin Time External Managers’ Time | This issue has been overtaken by regional developments. Work is under way involving Social Software in the development of YOIS. |
| 2.23 Unit staff and the Information Team must work more closely together to develop a proper information system for the unit | To continue to work with internal and external colleagues to support the redevelopment of the YOIS system by Social Software to meet the needs of the Secure Unit. In the interim period to further develop links with the internal information team to look at developing internal information systems. | Ongoing will be reviewed quarterly | Alison Stephens | Cost of redevelopment and purchase of YOIS software. Internal SLA plus development additional costs | This issue has been overtaken by regional developments. Work is under way involving Social Software in the development of YOIS. Barton Moss is to be used in a pilot scheme for a HR management system as part of the SAP system. |
| 2.24 Managers on the unit need to identify and use the data to help them in their management tasks. | As databases are established the Strategy Management Group to identify what data is to be made available to senior managers. | Jan 05 | Mike Lowry Mike Kelly Steve Osmond Jacqui Hughes | Admin Officer time Strategic Group time | This will need to wait until the new system is in place. |
| 2.25 External managers who are responsible for Regulation 33 visits must ensure compliance with guidance on frequency, purpose and recording. | There is a rota of Councillors and Officers to undertake Regulation 33 visits. The Executive Support Member for Community and Social Services and the Assistant Director (Children’s Services) monitor compliance. Records of visits are considered by a Panel of Councillors. The number of visits completed is reported to Scrutiny Committee. There has been training in July 2004 for Councillors and Officers, which included explanation of the importance of completing visits. | Monitoring is ongoing | Cllr.J.Cullen Paul Woltman | Existing resources – Councillor and Officer time. | In the second half of 2004 4 out of 6 visits were completed. One visit by Councillors and one by an officer were missed. Steps have been taken to remind all concerned of the importance of visits. |
| 2.26 In conjunction with other children’s resources in the authority, the unit manager needs to develop ways of researching the effectiveness of placements and customer satisfaction. | Arrange meeting with Service Manager to develop and monitor a system for the questionnaires distributed following announced rota visits to be shared with units. | Jan 05 | Tony Quinlan Mike Kelly | External Managers’ time | Work is underway on developing a system to ensure that feedback from parents is made available to internal managers. |