- TENDER APPROVAL - PROFORMA

For use in seeking the approval of the Lead Member for Customer and

Support Services to proceed with a capital proposal

| ##### REPORT TO LEAD MEMBER FOR CUSTOMER AND SUPPORT SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Title of Scheme : Lower Kersal Children’s Centre |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommendations (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scheme Details (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender Details (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated - Start Date : May 09 Estimated - End Date : Feb 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FINANCIAL DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommended Tenderer : Crudens Construction Tender Cost : £1,468,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Breakdown of Scheme Cost : |  |  |  |  |  |  |  |  |  |  |  | 09/10 £000‘s |  |  |  | 10/11 £000‘s |  |  |  |  |  | 11/12 £000‘s |  |  | Later £000‘s |  |  | Total £000‘s |  |  |  |  |
| Contract |  |  |  |  |  |  |  |  |  |  |  | 1,468 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,468 |  |  |  |  |
| Fees |  |  |  |  |  |  |  |  |  |  |  | 169 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 169 |  |  |  |  |
| Other (Specify) Furniture and Equipment, Signage |  |  |  |  |  |  |  |  |  |  |  | 45 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 45 |  |  |  |  |
| Total Cost |  |  |  |  |  |  |  |  |  |  |  | 1,682 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,682 |  |  |  |  |
| Phasing of Expenditure (£000‘s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Apr |  | May |  | June |  | July |  | Aug |  |  |  | Sept |  |  |  | Oct |  | Nov |  |  |  | Dec |  |  | Jan |  |  | Feb |  | Mar |  |
| # This Year |  |  |  | # 168 |  | # 168 |  | 168 |  | 168 |  |  |  | 169 |  |  |  | 168 |  | 168 |  |  |  | 168 |  |  | 168 |  |  | 169 |  |  |
| # Next Year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Following Year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note : The monthly cash flow above should be consistent with the contract start and end dates shown above and should allow for normal time lapses which will occur between work being done, claimed for, certified and paid, as well as retentions. Please consult your Capital Accountant if you need assistance with this or any other part of this proforma. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is Scheme In The Current Approved Capital Programme ? Yes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding Identified : |  |  |  |  |  |  |  |  |  |  | 09/10 £000‘s |  |  |  | 10/11 £000‘s |  |  |  |  |  | 11/12 £000‘s |  |  |  | Later £000‘s |  |  | Total £000‘s |  |  |  |  |
| Supported Borrowing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unsupported Borrowing (see note 1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grant (Specify) – Sure Start Children’s Centre Capital Grant |  |  |  |  |  |  |  |  |  |  | 600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Receipts |  |  |  |  |  |  |  |  |  |  | 600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Extended Schools Capital |  |  |  |  |  |  |  |  |  |  | 482 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  | 1,682 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#### REVENUE IMPLICATIONS

Are there any revenue implications of this proposal ? Yes If Yes, please complete the table below ### Are there any other financial implications

| ###### Details | Budget Code | Part Year | Full Year |
| --- | --- | --- | --- |
|  |  | £ | £ |
| Estimated Cost |  |  |  |
| Staffing (please specify) : |  |  |  |
| Teachers x 1 post | E3095 |  | 45000 |
| Centre Manager x 1 post | E3095 |  | 42414 |
| Children Centre Workers x 2.5 posts | E3095 |  | 58088 |
| Family Support x 1 posts | E3095 |  | 26210 |
| Administrative Assts x 1.5 posts | E3095 |  | 30567 |
| Other Running Costs (please specify) : |  |  |  |
| Building Running Costs | E3095 |  | 30000 |
| Capital Financing Costs (see Note 1 below - only to be completed where the use of unsupported borrowing is planned) |  |  |  |
| Total Estimated Cost |  |  | 232,279 |
| To be met from : |  |  |  |
| Surestart & Extended Schools Grant |  |  |  |
| Children’s Centre Revenue Funding |  |  |  |
| Total Funding/Income |  |  | 232,279 |
| Net Revenue Cost/(Saving) |  |  | 0 |

Note 1 : If unsupported borrowing is to be used, capital financing costs can be provided by your Accountant and you should show in the table how revenue savings can be made to fund these costs. Please consult your Accountant if you need assistance with completing this or any other part of this form.

Decision of Lead Member Customer and Support Services Approved/Not Approved