- TENDER APPROVAL - PROFORMA

For use in seeking the approval of the Lead Member for Customer and Support Services to proceed with a capital proposal

| REPORT TO LEAD MEMBER FOR CUSTOMER AND SUPPORT SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Title of Scheme : Re-Roofing Works at Barton Moss C.P. School, Trippier Road, Peel Green, Eccles, M30 7PT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommendations (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scheme Details (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender Details (please append report to your service Lead Member) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated - Start Date : Monday 24th July 2006 Estimated - End Date : Friday 1st Sept 2006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FINANCIAL DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommended Tenderer : Kinder Roofing Ltd Tender Cost : £ 138,040.59 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Breakdown of Scheme Cost : |  |  |  |  |  |  |  |  |  |  |  |  |  | 04/05 £000‘s |  |  |  | 05/06 £000‘s |  |  |  | 06/07 £000‘s |  |  | Later £000‘s |  |  |  |  | Total £000‘s |  |  |
| Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other (Specify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 134 |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |
| Phasing of Expenditure (£000‘s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Apr |  | May |  | June |  | July |  | Aug |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  | Jan |  | Feb |  |  | Mar |  |
| # This Year |  |  |  |  |  |  |  | 17 |  | 117 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Next Year |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Follo-wing Year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note : The monthly cash flow above should be consistent with the contract start and end dates shown above and should allow for normal time lapses which will occur between work being done, claimed for, certified and paid, as well as retentions. Please consult your Capital Accountant if you need assistance with this or any other part of this proforma. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is Scheme In The Current Approved Capital Programme ? Yes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding Identified : |  |  |  |  |  |  |  |  |  |  |  |  | 04/05 £000‘s |  |  |  | 05/06 £000‘s |  |  |  | 06/07 £000‘s |  |  |  | Later £000‘s |  |  |  |  | Total £000‘s |  |  |
| Supported Borrowing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unsupported Borrowing (see note 1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grant (Specify) New Deal for Schools Condition and Modernisation Fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 134 |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |
| Capital Receipts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other (Specify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 134 |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |

#### REVENUE IMPLICATIONS

Are there any revenue implications of this proposal ? No If Yes, please complete the table below ### Are there any other financial implications

| Details | Budget Code | Part Year | Full Year |
| --- | --- | --- | --- |
|  |  | £ | £ |
| Estimated Cost |  |  |  |
| Staffing (please specify) : |  |  |  |
| Other Running Costs (please specify) : |  |  |  |
| Capital Financing Costs (see Note 1 below - only to be completed where the use of unsupported borrowing is planned) |  |  |  |
| Total Estimated Cost |  |  |  |
| To be met from : |  |  |  |
| Total Funding/Income |  |  |  |
| Net Revenue Cost/(Saving) |  |  |  |

Note 1 : If unsupported borrowing is to be used, capital financing costs can be provided by your Accountant and you should show in the table how revenue savings can be made to fund these costs. Please consult your Accountant if you need assistance with completing this or any other part of this form.

Decision of Lead Member Customer and Support Services Approved/Not Approved