REPORT TO THE LEAD MEMBER FORCUSTOMER AND SUPPORT SERVICES

###### 3RD NOVEMBER 2008

###### Budget Monitoring 2008/09

This report is to update the Leadership Team on the position at the 22nd October 2008 relating to the directorate’s revenue budget.

The position in relation to employee costs (including overtime and agency costs) is as follows: -

| Division | Budget | Actual | Variance |
| --- | --- | --- | --- |
|  | April - Oct 2008 | April – Oct 2008 | (-) under/(+) over |
|  | £000 | £000 | £000 |
| Finance | 4201 | 4151 | -50 |
| ICT Services | 2551 | 2525 | -26 |
| Customer Services | 4472 | 4447 | -25 |
| Law & Admin | 2535 | 2532 | -3 |
| HR | 2124 | 2068 | -56 |
| Misc. Finance | 78 | 78 | 0 |
| ##### Total | 15961 | 15804 | -157 |

A projection of salaries to 31st March (based on actual to date and a projection of October salaries) shows an overall under spend of £249k

| Division | Budget | Actual | Projection to 31st March 2009 | Variance |
| --- | --- | --- | --- | --- |
|  | April - March 2008 | April – Oct 2008 |  | (-) under/(+) over |
|  | £000 | £000 | £000 | £000 |
| Finance | 7201 | 4151 | 7136 | -65 |
| ICT Services | 4367 | 2525 | 4310 | -57 |
| Customer Services | 7781 | 4447 | 7722 | -59 |
| Law & Admin | 4346 | 2532 | 4335 | -11 |
| HR | 3631 | 2068 | 3575 | -56 |
| Misc. Finance | 118 | 77 | 117 | -1 |
| ##### Total | 27444 | 15800 | 27195 | -249 |

Summary of the significant issues that have an impact on the budget are:-

| Budget issues | £000 |
| --- | --- |
| ICT in the Community | 70 |
| Home working ongoing costs | 98 |
| Advice team – reduced income | 70 |
| Reduced income from land charge income | 400 |
| Loss of services/ reduction in service to City West - Customer Services – Call Centre - Law & Administration – Procurement - Out of Hours service | 130 8 18 |
| HRA SLA reduction | 250 |
| Total | 1044 |
| Funded by |  |
| Under spend on salaries | 249 |
| Additional income from sale of service to City West - ICT Service - Finance – Audit - SAP | 119 78 62 |
| Additional court cost income | 450 |
| Net effect of Increment budget less strike pay (deducted from budgets) | 118 |
| Total | 1076 |
| Overall surplus | 32 |

The above budget projection assumes that the following savings will be delivered and met from within the directorates budget:-

- Procurement /think Efficiency savings £143k

- Overtime of £48k

- Training/venues budget of £107k

Note

Contribution to TIF referendum of £70k will be charged to directorate but is expected to be funded corporately.

Summary

In order to contain expenditure within budget action needs to be taken to hold all vacancies and not to incur any non-committed expenditure on supplies and services.  At this stage there is  £2.5m of unspent supplies and services budget although there will be significant commitments (e.g. member allowances) against this.  A more detailed exercise is required by managers to identify the value of non-committed expenditure.

Irene Topping

23/10/08