SALFORD’S LOCAL PUBLIC SERVICE AGREEMENT

TARGET ACTION PLAN

| # TARGET 9 Reduce Vehicle Crime by 36.5% by 2005 |  |
| --- | --- |
| # NATIONAL/LOCAL National 17 | # MANDATORY/NON MANDATORY Non Mandatory |
| # LEAD OFFICER Gordon Dickson / Peter Matthews Community Safety Unit Elmstead House 143 Partington Lane Swinton, M27 0SS Tel: 0161 793 3576/3585 Email: gordon.dickson@salford.gov.uk Peter.matthews@salford.gov.uk; | # DEPT/DIRECTORATE Salford Community Safety Unit Chief Executives Directorate |
| # PROJECT SUMMARY As part of the Salford Crime and Disorder Reduction Partnership’s three yearly strategy an implementation plan has been agreed upon which outlines specific and detailed measures for combating vehicle related crime within the city (see attached). Actions include campaigns aimed at promoting safe parking, personal security measures by motorists and park and ride schemes. Diversionary activities are to be provided for young persons at risk of involvement in vehicle crime. Physical measures, such as the provision of CCTV, use of parking restrictions are to be developed in victimised areas reducing the opportunities for offending. Multi agency operations will take place to target prolific offenders and handlers of stolen goods. The Local Public Service Agreement will fund crime prevention publicity, the provision of vehicle security devices for vulnerable persons/vehicles and physical measures in victimised areas including CCTV, fencing and parking restrictions. |  |
| # LINKS TO PLEDGES/COMMUNITY PLAN/OTHER STRATEGIES The LPSA is an important part of the Crime and Disorder Reduction Strategy relating to vehicle Crime, providing funding essential to securing progress This initiative is linked with pledge 4 “A Safer Salford”. In addition, there is also a clear link with Community Plan’s priority for the creation of “A Safe City”. Crime reduction is directly related to a wide range of strategies because of its links with health, young people, safer neighbourhoods, social inclusion, inward investment and provision of a sustainable environment. |  |

# MONITORING ARRANGEMENTS Monitoring will take place using the authorities performance management system. On a quarterly basis the Chief Executive and Leader of the Council will meet with the Lead Member for Community Safety, Director of Strategy and Regeneration and the Community Safety Manager. The data utilised for monitoring purposes is recorded for crime statistics. These are provided to the Community Safety Unit on a quarterly basis, by Greater Manchester Police.

| ## MILESTONES/ACTIONS – 2002/03 |  |  |
| --- | --- | --- |
| ## MILESTONE | ## KEY ACTIONS | ## TARGET DATE |
| SALFORD CRIME AND DISORDER STRATEGY | Develop Audit, undertake consultation and prepare strategy | 26th April 2002 |
| Implementation Plan | Consult partners and develop implementation plan | 31st July 2002 |
| Resources | Identify resources to support | July 2002 (ongoing) |
| Analysis Report | Undertake analysis of “hotspot” area and produce report | 8th August 2002 |
| Report on victimised areas | GMP Crime Reduction Advisors to promote position statement on activities within “hotspot” areas | 23rd August2002 |
| Vehicle Crime Steering Group | Identify membership and assemble group | 9th September 2002 |
| Action Plan | Steering Group to develop partnership implementation plan | 27th September 2002 |
| Implementation | Implement, monitor and evaluate action plans | Ongoing (refer to plan for specific dates) |
| PSA -Marketing Campaign to educate owners re security measures and to promote Park and Ride Initiatives | Crime Reduction Advice in Salford People and Salford Advertiser | November 2002 |
|  | Communications Strategy in place re vehicle crime | December 2002 |
|  | Preparation of up to date literature for circulation in victimised areas | January 2003 |
| PSA- Expansion of Parking Restrictions in Victimised areas | Identification of areas for restrictions within Chapel Street/Trinity area | December 2002 |
| PSA- Improve Level of Security in commercial and Local Authority car parks to Secure Car Parks Award | Costs to be established for improvements at the Salford Shopping Precinct and surrounding areas to Secure Car Parks Standard. | December 2002 |
|  | Work to be completed at Salford Precinct Location | December 2003 |
| PSA- Establishment of krooklock scheme to provide vulnerable persons in victimised areas with security devices at subsidised price | Identification of victimised areas. | December 2002 |
|  | Protocol for scheme in place. | December 2002 |
|  | Purchase of devices | January 2003 |
|  | Scheme in operation in victimised areas | February 2003 |

| ##### FORECAST – PROGRESS AGAINST TARGETS/PERFORMANCE INDICATORS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TARGET/ PERFORMANCE INDICATOR CURRENT POSITION | 2002/03 PROFILE |  |  |  |  | FUTURE YEARS |  | POSITION AT END |
|  | QUARTER 1 APR-JUN | QUARTER 2 JUL-SEP | QUARTER 3 OCT-DEC | QUARTER 4 JAN-MAR | TOTAL 2002/03 | TOTAL 2003/04 | TOTAL 2004/05 |  |
| Reduce Vehicle Crime Number of vehicle crime offences (includes both theft of and from vehicles) per 1000 population Current Performance (1998/99 Baseline – 10,791 offences) 48(per 1,000 population) | 38.51 per 1000 population = 2162 incidents | 37.78 per 1000 population = 2121 incidents | 37.05 per 1000 population = 2100 incidents | 36.32 per 1000 population = 2039 incidents | 36.32 per 1000 population = 8422 incidents | 33.4 per 1000 population = 7503. incidents | 30.5 per 1000 population = 6852 incidents | 30.5 offences per 1000 population (6,852 offences) |

| FORECAST FUNDING AND EXPENDITURE |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FUNDING SOURCE | 2002/03 PROFILE |  |  |  |  | FUTURE YEARS |  | TOTAL ALL YEARS |
|  | QUARTER 1 APR-JUN | QUARTER 2 JUL-SEP | QUARTER 3 OCT-DEC | QUARTER 4 JAN-MAR | TOTAL 2002/03 | TOTAL 2003/04 | TOTAL 2004/05 |  |
| ###### CAPITAL |  |  |  |  |  |  |  |  |
| NRF |  |  |  | 80,000 | 80,000 | 0 | 0 | 80,000 |
| ## PSA Pump Priming |  |  |  |  |  | 43,000 | 0 | 43,000 |
| ## TOTAL CAPITAL |  |  |  | 80,000 | 80,000 | 43,000 | 0 | 123,000 |
| ###### REVENUE |  |  |  |  |  |  |  |  |
| PSA Pump Priming |  |  |  | 30,000 | 30,000 | 7,000 | 0 | 37,000 |
| ## TOTAL REVENUE |  |  |  | 30,000 | 30,000 | 7,000 | 0 | 37,000 |
| #### GRAND TOTAL |  |  |  | 110,000 | 110,000 | 50,000 | 0 | 160,000 |
| ## EXPENDITURE CATEGORY |  |  |  |  |  |  |  |  |
| ###### CAPITAL |  |  |  |  |  |  |  |  |
| Target Hardening Car Parks |  |  |  | 80,000 | 80,000 | 0 | 0 | 80,000 |
| ###### Physical Security Measures |  |  |  | 0 | 0 | 43,000 | 0 | 43,000 |
| ###### TOTAL CAPITAL |  |  |  | 80,000 | 80,000 | 43,000 | 0 | 123,000 |
| ## REVENUE |  |  |  |  |  |  |  |  |
| ## Security Devises |  |  |  | 30,000 | 30,000 | 0 | 0 | 30,000 |
| ## Legal Fees |  |  |  | 0 | 0 | 5,000 | 0 | 5,000 |
| ## Marketing Literature |  |  |  | 0 | 0 | 2,000 | 0 | 2,000 |
| #### TOTAL REVENUE |  |  |  | 30,000 | 30,000 | 7,000 | 0 | 37,000 |
| #### GRAND TOTAL |  |  |  | 110,000 | 110,000 | 50,000 | 0 | 160,000 |

NOTE:  PSA Pump Priming is funding the whole cost of; Physical Security Measures, Security Devises, Legal Fees and Marketing Literature.

Salford Crime and Disorder Reduction Partnership

Crime and Disorder Strategy 2002-2005

Implementation Plan

# Salford Crime and Disorder Partnership

###### VEHICLE CRIME

# Lead Agency – Salford Community Safety Unit, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Carry out further analysis of victimised persons, vehicles, and locations | Salford Community Safety Unit analyst | From existing resources | Publish findings by July 2002 |
| Research potential to expand Park and Ride initiatives | Salford Community Safety Unit | From existing resources | By December 2002 |
| Approach monitoring organisations / insurance companies give out preventative advice and promote safe parking sites | Crime Reduction Advisor / Salford Community Safety Unit | From existing resources | Formation of formal links by December 2002 |
| Research potential to use Name and Shame initiative re car parks with poor security | Salford Community Safety Unit and Communications and Public Relations Team | From existing resources | Report by December 2002 |
| Establish multi-agency group to reduce ability to sell stolen vehicles | Salford Community Safety Unit / Trading Standards Office | From existing resources | Formation of group by December 2002 |
| Use of police mobile CCTV systems in victimised areas | Operational Policing Unit and Salford Community Safety Unit | From existing resources | Six police initiatives x March 2003 |
| Expansion of parking restrictions in victimised areas | Group Engineers – Salford Community Safety Unit analyst | PSA’s | Identification and selection of areas for restrictions by December 2002 |
| Research potential use of warning signs at hot spot locations | Salford Community Safety Unit | From existing resources | December 2002 |

Lead Agency – Communications and Public Relations, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Marketing campaign to educate owners of security measures to be taken and to promote Park and Ride Initiatives | Communications and Public Relations Team | P.S.A’s | Communications Strategy in place by December 2002 Increase persons using Park and Ride scheme x 25% by August 2003 |
| Research potential to use Name and Shame initiative re car parks with poor security | Salford Community Safety Unit and Communications and Public Relations Team | From existing resources | Report by December 2002 |

# Lead Agency – GMP

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Implement Repeat Victimisation Initiative. To contact all victims with advice letter / literature | Operational Policing Unit | From existing resources | All reported victims to receive advice as of April 2002 |
| Provide security devices for vulnerable vehicles in victimised areas | Crime Reduction Advisors | PSA’s | February 2002 |
| Increase accessibility of crime scene surgeries and provide crime prevention advice | Crime Reduction Advisor / Crime Scene Examination Unit | From existing resources | All persons attending surgeries to be offered advice, as of July 2002 |
| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Approach local car dealers to give out preventative advice when selling cars | Crime Reduction Advisor | From existing resources | Six main dealers to participate by December 2002 |
| Approach monitoring organisations / insurance companies give out preventative advice and promote safe parking sites | Crime Reduction Advisor / Salford Community Safety Unit | From existing resources | Formation of formal links by December 2002 |
| Targeted police initiatives within victimised areas | Operational Policing Unit | From existing resources | Four police initiatives by December 2002 |
| More Crime Scene examination of vehicles – establishment of secondary surgery at Swinton Police Station | Operational Policing Unit | From existing resources | 40% of all vehicle subject of crime to be examined and August 2002 |
| Use of Automatic Number Plate recognition equipment | Operational Policing Unit | Safer Communities Initiative | Six operations by March 2003 |
| Pilot rolling road blocks in hot spot areas to identify offenders | Operational Policing Unit/Divisional Traffic Unit | From existing resources | Pilot scheme in place by December 2002 |
| Improve levels of security in commercial car parks towards Secure Car Parks Award | Crime Reduction Advisor | PSA’s | Improvements at six parks to award standard– December 2003 |
| Use of police mobile CCTV systems in victimised areas | Operational Policing Unit and Salford Community Safety Unit | From existing resources | Six police initiatives x March 2003 |

Lead Agency – Trading Standards, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Establish multi-agency group to reduce ability to sell stolen vehicles | Salford Community Safety Unit / Trading Standards Office | From existing resources | Formation of group by December 2002 |

Lead Agency – Youth Service, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Expand diversionary activities such as GEARS etc, including accredited courses | Youth Service | Children’s Fund | Provision of additional activities by December 2002 |

Lead Agency – Probation

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Provide behavioural programmes aimed at offenders involved in vehicle crime | Probation and YOT | From existing resources | Specific programmes in place by December 2002 |

Lead Agency – YOT

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Provide behavioural programmes aimed at offenders involved in vehicle crime | Probation and YOT | From existing resources | Specific programmes in place by December 2002 |

Lead Agency - Development Services, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Improve levels of security in Local Authority car parks towards Secure Car Parks Award | Group Engineers | PSA’s | Improvements at six car parks to award standard by December 2002 |
| Tighter control of planning restrictions to ensure acceptable security levels at car parks | Local Authority planning department | From existing resources | All planning department staff to be provided with additional training by December 2003 |
| Increase longevity of car parks when providing planning permission in order to encourage expenditure on security | Local Authority planning department | From existing resources | All planning department staff to be provided with additional training by December 2003 |
| Expansion of parking restrictions in victimised areas | Group Engineers – Salford Community Safety Unit analyst | Community Safety Budget | Identification and selection of areas for restrictions by September 2002 |

Lead Agency – Housing Services, Salford City Council

| # Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| --- | --- | --- | --- |
| Pilot Homelink initiative whereby vehicles parked outside homes are linked into the home security system | Housing | From existing resources | Evaluation of system x December 2002 |