| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. 5a |
| --- | --- |

REPORT OF THE DIRECTOR OF DEVELOPMENT SERVICES

TO THE ECONOMIC AND COMMUNITY SAFETY SCRUTINY COMMITTEE

3rd November 2003

TITLE :	2001 CENSUS – WORK PROGRAMME

RECOMMENDATIONS :	That this report be noted

EXECUTIVE SUMMARY :

This report appraises Members of delays in the 2001 Census data release schedule, and their impact on the Directorates Census work programme.

BACKGROUND DOCUMENTS :

(Available for public inspection)			None

ASSESSMENT OF RISK				Low

THE SOURCE OF FUNDING IS			N/A

LEGAL ADVICE OBTAINED 			N/A

FINANCIAL ADVICE OBTAINED			N/A

CONTACT OFFICER :				John Reehill (793 3664)

WARD(S) TO WHICH REPORT RELATE(S)	All

KEY COUNCIL POLICIES				N/A

DETAILS (Continued Overleaf)

1.0	ONS Census Data Release Schedule

1.1	The Office of National Statistics (ONS) 2001 Census output schedule involves the phased hierarchical release of Census results – starting with general statistics for large geographical areas and progressing to detailed statistics for small areas, and finishing with migration and travel-to-work origin-destination matrices.

1.2	The output schedule has been subject to a number of delays.  The detailed statistics for Output Areas (OA’s) needed by the Directorate to undertake meaningful analysis of the City’s resident demographic and socio-economic characteristics, have not yet been released in a suitable format.  Release was initially scheduled for May 2003.  The release date has subsequently been put back firstly to July 2003 and then to ‘post 28 August’ for most of the data, with information on migration and travel to work (static tables) being published at an unspecified later date.  It is likely that the detailed OA tables for Salford will be released in September, and the static migration and travel-to-work tables following in October.  Detailed migration and travel-to-work origin / destination matrices will not be released until later in the year.

1.3	The software (SASPAC) that will be used to analyse the OA data is unlikely to be made available by the suppliers until the end of October.  Officers in Development Services will then need to spend approximately 2 weeks installing and testing software, disseminating standard output tables and training census users in other Directorates of the Council.

1.4	This means that, on the basis of current information from ONS, the Directorate will not be in a position to commence detailed analysis of 2001 Census results until mid-November 2003.

1.5	The delays to census output and consequently SASPAC release will impact on the Directorates Census work programme.  Analysis reports scheduled for submission to Cabinet on 30th September, and Economic and Community Safety Scrutiny Committee on 6th October, must now be submitted to latter meetings.  It is suggested that reports be presented to Cabinet and Economic and Community Safety Scrutiny Committee in January 2004.

2.0	Development Services 2001 Census Work Programme

2.1	The Development Planning Section (Information Group) within Development Services will coordinate the corporate census work programme.  The work programme will be administered through the Statistical Information Group (SIG).

2.2	The draft work programme currently includes the following 2001 Census reports.

- Report to Cabinet / Economic & Community Safety Scrutiny Committee on urban regeneration and demographic / household change in Salford.

- Ward Profiles – existing and new boundaries (to be implemented post October 2003),

- SDA Profiles

- Regeneration Area Profiles,

- Topic Papers on:

- Ethnicity / BME Groups,

- Population, demographic and household change,

- Deprivation,

- Housing – conditions, amenities, tenure, type,

- Economic Activity, Employment, Occupations,

- Health, Illness, Carers,

- Qualifications, Students

- Migration

- Travel-to-Work flows / modes

- Census Profile of Salford

3.1	The ONS have compiled basic 2001 Census profiles for all local authority districts.  The profile for Salford is attached.  It contains statistics on population and households, religion, health, economic activity, students / qualifications, housing, and some non-census statistics on house prices and crime.

  - Main points to note are, that relative to the national average, Salford has:

- a similar population age profile – but there are slightly more young people (16-29), fewer in the mid age band (30-59), and a similar proportion aged over 60;

- significantly more single people - never married (see also single person households below);

- significantly fewer people in ethnic non white groups (although the number resident in Salford has increased by about 75% since 1991);

- proportionally fewer persons in all non-Christian religious groups except Jewish;

- significantly more people that are not in good health, affected by limiting long term illness, and permanently sick or disabled;

- significantly fewer residents in employment;

- a similar proportion of persons (aged 16+) in full time education (despite the presence of a large university);

- significantly more people with no educational qualifications;

- a much greater proportion of one person households;

- more lone parents;

- significantly fewer home owners (including mortgagees);

- slightly fewer dwellings lacking central heating and other amenities;

- significantly more households without a car or van; and

- considerably fewer detached dwellings, and more terraced and semi-detached homes.

  - The non-census data indicates that average house prices in Salford are only half of the national average, and that crime rates are much higher.

JR/Census 2001/Report to LM re progress Sept 03.doc

Output Areas – based on unit post codes and containing about 150 households, the smallest 2001 census building blocks.

Demographic and household change in relation to urban regeneration in Salford.