HOUSING SERVICES BEST VALUE PERFORMANCE PLAN (DRAFT 12/12/00)

GIVING ALL THE PEOPLE OF THE CITY THE OPPORTUNITY TO LIVE IN A GOOD QUALITY HOME.

Housing Services

The Housing Services Directorate is organised on both a centralised and area basis and the services are delivered from:

- Two Turnpike H.Q.sites.

- Nine area and three sub-area offices.

- Five building services and external contractor depots.

Achievements in 2000/01 (based on BVPP key performance indicators)

Average re-let time for local authority dwellings let in the financial year.

The target for 2000/01 is 56 days the performance up to the end of November 2000 is  77 days, our performance for 1999/2000 was 105 days. In comparison to last year housing services performance has improved, however performance against the target is not being achieved this is due low demand and an over provision of housing in certain areas. This is a well-documented trend and is currently affecting other local authorities and housing associations in the North of England.

To improve performance we have also introduced a void categorisation, which identifies voids as:

- Those we can let immediately. b) Voids less easy to let requiring an option appraisal. c) Voids where a decision has already been taken to dispose or demolish the property.

We also carry out regular advertising of void properties and have re-organised to provide a greater focus on the lettings process.

The percentage of all repairs requested by tenants completed within target times set by the council.

The target for 2000/01 is 65% the performance up to the end of October 2000 is 66%.

Note:This is based on from when the tenant reports the repair to when it is completed and is therefore measured from notification to completion. Which is the Governments new method of measuring repairs. Historically this indicator has been measured from when it is issued to the contractor to completion our performance up to the end of October using this method is 94%. As this is the first year on reporting performance against the BVPP we need to decide which method we want to adopt for this indicator.

The percentage of all current tenants owing over 13 weeks rent at 31st March, excluding those owing less than £250.

The target for 2000/01 is 6% the performance up to the end of October 2000 is 6.4% our performance for 1999/2000 was 7.27% therefore, in comparison to last year our performance has improved. This is as a result of the introduction of more stringent targets, a review of procedures, prompt legal action and early benefit advice. As a result of these we are on course for achieving the target.

The average weekly cost for each home broken down as follows: Management.

The target for 2000/01 is £11.11 our performance for 1999/2000 was £10.14. The management costs are high as Housing Services provide a fully decentralised service and comprehensive local services e.g. caretakers, security staff, residential and mobile wardens. The information for this performance indicator is only provided annually. However, based on last year’s performance it is envisaged that the target will be achieved.

The number of unfit private sector (excluding Registered Landlords) dwellings dealt with as a proportion of the Councils assessment of need.

The target for 2000/01 is 450, current trends and information available indicates that over 500 properties will have been dealt with by the end of March 2001.

The percentage of private sector stock empty homes brought back into use of all private sector empty stock.

The target for 2000/01 is 3% our projected performance up to the end of March 2001 is 6.8%. To achieve this target Housing Services have introduced an Empty Property Hotline, all properties referred are investigated and entered onto a prioritisation system.

Note: The definition of the above two indicators has changed and these need to be reflected in the new Best Value Performance Plan.

FUTURE PLEDGES-IN 2001/02 WE WILL

Improve the marketing of council property and changing the image of housing in the City in line with the new Marketing Strategies Plan.

Continually reduce the average time to relet empty properties to achieve the Governments upper quartile of 29 days by 2005. Relet time of 48 days to be achieved by 31 March 2002.

Complete 75% of all day to day repairs within target times set by the council from date reported by tenant.

Review the existing empty property strategy and further develop procedures and systems for dealing with empty properties including facilitating enforcement action where appropriate and monitoring and evaluating the effectiveness of our actions.

# PERFORMANCE INDICATOR EXAMPLES

# BEST VALUE REVIEWS

For 2001/02 Housing Services Best Value reviews are:

- Day to Day Repairs

- Voids and Rehousing

- Cash and Rent Arrears

- Nuisance and Estate Management

- Caretaking and Cleaning

A service profile of the above has been completed and the terms of reference for the review have been established the main issues are:

- Set up a Best Value Team

- Improve customer feedback across al services.

- Provide and involve members in a health check on current services in comparison. with other providers and customer requirements.

- Determine the most efficient, effective and equitable method of delivery reflecting service improvements and costs.

- Produce an action plan for implementation.

# LISTENING TO YOU

An annual tenant survey has been commissioned the results of this will be available by March 2001. This information will then be used to assist with the best value review.

# KEY FACTS AND FIGURES

- Stock level at 31/3/00 32095 properties.

- Over 102,000 day to day responsive repairs completed in 1999/2000.

- Over 40,000 gas responsive repairs completed in 1999/2000.

- Gas servicing to over 24,000 properties carried out in 1999/2000.

- The proportion of rent collected in 1999/2000 is 95.6%.