## Sheet1
MONTH:- OCTOBER 2004
PROGRESS MONITORING REPORT (DECENT HOMES SCHEMES - 2004/05 CAPITAL WORKS PROGRAMME)
Area | Work Package | Scheme | Work Type | Survey Progress v Programme | Partner Progress v Programme | COMMENTS
Swinton | PP Wk. Pk. 1 | Wardley | Partial Rewire | Completed as Programme | On site 9/8/04 | 40% Completed
| PP Wk. Pk. 1 | Temple Drive | Elec. Upgrades | Completed as Programme | On site 9/8/04 ahead of Prog | 30% Completed
Eccles | PP Wk. Pk. 1 | Dudley Rd.- Cumberland | Heating | Completed as Programme | On site 9/8/04 | 32% Completed
| PP Wk. Pk. 1 | The Meadows | Heating | Completed as Programme | On site 12/7/04 | 100% Completed
Eccles | PP Wk. Pk. 2 | Baines Ave. | Roofing | Completed as Programme | On site 14/6/04 | 100% Completed
| PP Wk. Pk. 2 | Crossfields | Roofing | Completed as Programme | On site 12/7/04 | 70% Completed
| PP Wk. Pk. 2 | 1-5A Warren St. | Roofing | Completed as Programme | Start Date behind Org. Programme date of the 27/9/04 | Due on site 17/10/04
Eccles | PP Wk. Pk. 3 | Mitchell St. | Rewires | Completed as Programme | Start Date to be as Programme | Due on site 29/11/04
| PP Wk. Pk. 3 | Mitchell St. | Kitchens | 3 weeks Behind Programme, 12 Properties still to be surveyed | Start Date to be as Programme | Due on site 29/11/04
Worsley | Wk. Pk. 1 | Worsley Rd. North | Rewires | Completed as Programme | Start Date to be as Programme | Due on site 17/01/05
Little Hulton | Wk. Pk. 1 | Worsley Rd. North | Bathrooms | Completed | Start Date to be as Programme | Due on site 17/01/05
| Wk. Pk. 1 | Worsley Rd. North | Roofing | Completed as Programme | Start Date to be as Programme | Due on site 4/10/04
| Wk. Pk. 1 | Bridgewater Rd. | Bathrooms | Completed | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | 53 - 67 Manchester Rd. | Kitchens | Completed ahead of Programme | Start Date to be as Programme | Due on site 10/1/05
Eccles | Wk. Pk. 1 | Peel Green (Mees Sq.) | Bathrooms | Completed | Start Date to be as Programme | Due on site 11/10/04
| Wk. Pk. 1 | De Traffords - Moorfield | Bathrooms | Completed | On site 13/9/04 | 0% Completed
| Wk. Pk. 1 | Newlands | Rewires | Completed as Programme | On site 23/8/04 | 0% Completed
| Wk. Pk. 1 | Newlands | Bathrooms | Completed | On site 23/8/04 | 0% Completed
| Wk. Pk. 1 | Newlands | Kitchens | 1 week Behind Programme, 9 Properties still to be surveyed | Start Date to be as Programme | Due on site 18/10/04
Eccles | Wk. Pk. 2 | Lancaster Rd. | Heating | Completed as Programme | On site 16/8/04 | 14% Completed
Eccles | Wk. Pk. 3 | Liverpool Rd. | Kitchens | Surveys Completed | On site 9/8/04 | 55% Completed
| Wk. Pk. 3 | Astley Rd. | Kitchens | Behind Programme, 14 Properties still to be surveyed | On site 6/9/04 | 13% Completed
| Wk. Pk. 3 | Albert St. | Kitchens | Completed | Start Date to be as Programme | Due on site 15/11/04
| Wk. Pk. 3 | Albert St. | Bathrooms | Completed | Start Date to be as Programme | Due on site 15/11/04
| Wk. Pk. 3 | Higson Av. & Peel Green Rd. | Rewires | Completed as Programme | On site 23/8/04 | 0% Completed
| Wk. Pk. 3 | Higson Av. & Peel Green Rd. | Kitchens | Completed | On site 23/8/04 | 0% Completed
| Wk. Pk. 3 | Higson Av. & Peel Green Rd. | Bathrooms | Completed ahead of Programme | On site 23/8/04 | 0% Completed
Eccles | Wk. Pk. 4 | The Avenues | Roofing | Completed as Programme | On site 2/8/04 | 41% Completed
| Wk. Pk. 4 | The Avenues | Repointing & Cavity Ties | Completed as Programme | On site 2/8/04 | 54% Completed
| Wk. Pk. 4 | Peel Green Phase 1 | Repointing & Cavity Ties | Completed as Programme | On site 13/9/04 | 8% Completed
Swinton | Wk. Pk. 1 | The Valley | Heating | Completed as Programme | On site 2/8/04 | 13% Completed
| Wk. Pk. 1 | The Valley | Prior to Paint | Completed ahead of Programme | Revised On site date is 13/9/04 | 0% Completed
Swinton | Wk. Pk. 2 | Manchester Rd. South | Partial Rewire | On Programme | Start Date of the 27/9/04 now revised to a new start date of 18/10/04 | Due on site 18/10/04
| Wk. Pk. 2 | Manchester Rd. South | Kitchens | On Programme | Start Date of the 27/9/04 now revised to a new start date of 3/1/05 | Due on site 3/1/05
Swinton | Wk. Pk. 3 | Parkfield & Moorfield | Bathrooms | Surveys Completed | Start Date of the 11/10/04 now revised to a new start date of 8/11/04 | Due on site 8/11/04
| Wk. Pk. 3 | Worsley Rd. | Partial Rewire | Behind Programme, 10 Properties still to be surveyed | Start Date of the 16/8/04 now revised to a new start date of 4/10/04 | Due on site 4/10/04
| Wk. Pk. 3 | Worsley Rd. | Kitchens | Behind Programme, 10 Properties still to be surveyed | On site 16/8/04 | 25% Completed
| Wk. Pk. 3 | Mossfield | Elec. Upgrades | Completed as Programme | Start Date of the 22/11/04 now revised to a new start date of 3/1/05 | Due on site 3/1/05
| Wk. Pk. 3 | Agecroft | Elec. Upgrades | Completed as Programme | Start Date of the 24/1/05 now revised to a new start date of 22/11/04 | Due on site 22/11/04
| Wk. Pk. 3 | Agecroft | Kitchens | On Programme | Start Date of the 24/1/05 now revised to a new start date of 22/11/04 | Due on site 22/11/04
Salford South | Wk. Pk. 1 | Tootal | Heating | Completed as Programme | On site 6/9/04 | 0% Completed
| Wk. Pk. 1 | Tootal | Elec. Upgrades | Completed as Programme | Start Date of the 16/8/04 now revised to a new start date of 11/10/04 | Due on site 11/10/04
| Wk. Pk. 1 | Tootal | Kitchens | On Programme | Start Date of the 16/8/04 now revised to a new start date of 11/10/04 | Due on site 11/10/04
Salford South | Wk. Pk. 2 | Southgarth | Rewires | Completed as Programme | On site 13/9/04 | 0% Completed
| Wk. Pk. 2 | Southgarth | Bathrooms | Surveys Completed | Start Date of the 23/8/04 now revised to a new start date of 18/10/04 | Due on site 18/10/04
| Wk. Pk. 2 | Southgarth | Kitchens | On Programme | Elemental Scheme cancelled | Awaiting result of Stock Options!!!
| Wk. Pk. 2 | Moss Meadow | Elec. Upgrades | Completed as Programme | On site 23/8/04 | 0% Completed
| Wk. Pk. 2 | Moss Meadow | Bathrooms | Surveys Completed | Start Date of the 23/8/04 now revised to a new start date of 11/10/04 | Due on site 11/10/04
Salford South | Wk. Pk. 3 | Devon Close | Kitchens | On Programme | Start Date Revised to 15/11/04 | Due on site 15/11/04
| Wk. Pk. 3 | Cressington Close | Kitchens | Completed ahead of Programme | Start Date of the 27/9/04 now revised to a new start date of 15/11/04 | Due on site 15/11/04
| Wk. Pk. 3 | Light Oaks Rd | Elec. Upgrades | Completed ahead of Programme | On site 13/9/04 | 0% Completed
| Wk. Pk. 3 | Duchy | Elec. Upgrades | Completed ahead of Programme | Start Date Revised to 20/9/04 | Due on site 20/9/04
| Wk. Pk. 3 | Edgehill Rd | Rewires | Completed as Programme | On site 6/9/04 | 0% Completed
| Wk. Pk. 3 | Edgehill Rd | Roofing | Completed ahead of Programme | Start Date of the 6/9/04 now revised to a new start date of 25/10/04 | Due on site 25/10/04
| Wk. Pk. 3 | Edgehill Rd | Repointing & Cavity Ties | Completed ahead of Programme | Start Date of the 6/9/04 now revised to a new start date of 25/10/04 | Due on site 25/10/04
Salford North | Wk. Pk. 1 | North Clifden Lane | Elec. Upgrades | Completed as Programme | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | North Clifden Lane | Kitchens | On Programme | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | Floral Court | Rewires | Completed as Programme | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | Floral Court | Bathrooms | Surveys Completed | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | Kersall Cell | Heating | Completed as Programme | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | Kersall Cell | Elec. Upgrades | Completed ahead of Programme | Start Date to be as Programme | Due on site 3/1/05
| Wk. Pk. 1 | Lower Broughton 4 | Elec. Upgrades | Completed ahead of Programme | Start Date of the 3/1/05 now revised to a new start date of 11/10/04 | Due on site 11/10/04
Mixed Salford | Wk. Pk. 1 | The Beehive | Prior to Paint | Completed ahead of Programme | On site 19/7/04 | 42% Completed
North & Swinton | Wk. Pk. 1 | Albion Stadium | Prior to Paint | Completed ahead of Programme | Start Date of the 25/10/04 now revised to a new start date of 3/1/05 | Due on site 3/1/05
Prior to Paints |  | Canterbury Gardens | Prior to Paint | On Programme | Start Date of the 25/10/04 now revised to a new start date of 3/1/05 | Due on site 3/1/05