# Area 4 Langworthy

## Crime

The area indicated on the map has suffered 12  burglaries between 16th August 2004 and 7th Jan 2006  2006. This equates to a burglary rate of 36.8 Burglaries

per thousand households. This is almost twice Salford’s average of 23 per thousand households.

In addition to this, in the last 12 months there have been numerous alley gating schemes carried out in the surrounding area. This could result in the burglary rate increasing further with the displacement of crime.

#### Cost

- Total Number of properties = 115

- Cost of scheme £40,000

### A cost of £347 per property

#### Cost Effectiveness

Using Home Office Research Study 217  -The Economic and Social Costs of Crime the average cost of a Burglary on Local Authority Services is  £2300. In order for the gates to be cost effective in 4 years we would need to prevent 17 burglaries in this area. This equates to a 53% reduction in burglaries.

##### Consultation

All consultations have been carried out by the SRB5 Team. Residents Associations have been set up on each alley way to take on the long term maintenance of the schemes. Planning permission and full closures have been attained. Gates are ready to be ordered.

#### Time scales

### Following approval of this report the gates could be erected in 6 – 8 Weeks