OJEC Notice Restrict procedure

Issue memorandum of information and prequalification questionnaire

Issue tender documents

# Re Thinking Construction Flow Chart

Expressions of interest

Bidders responses

Evaluation of prequalification submissions

Long list up to 6 per service category

Bidders responses

Evaluation and selection of preferred partners for interview

Interviews and final selection

Lead Member

Cabinet

Commence New Build / Major Refurbishment

Commence Civil Engineering

Commence Road Surfacing

Commence Mechanical Engineering

Commence Electrical Engineering

Commence Landscape Work

Commence Responsive and Routine Maintenance

Commence One Off Minor Building Works

Key:

Salford Documentation

Bidder Documentation

Development Stage

2nd May 2003

10th June 2003

15th July 2003

29th July 2003

28th August 2003

30th October 2003

1st Dec 2003

22nd Dec 2003

13th Jan 2004

1st Sep 2004

1st Sep 2004

1st June 2004

1st June 2004

1st June 2004

1st April 2004

1st April 2004

1st April 2004

Stage 1

Stage 2

Stage 3

Stage 4

Stage 5

Stage 6

38 Days

5 Days

56 Days

30 Days

14 Days

36 Days

22 Days