Appendix 1                     SALFORD ITA PROJECT COST VARIANCE. FEB 2004 – JANUARY 2005

| Activity | # Indicative # Hours | # Indicative Cost (£) | # Actual Hours | # Actual # Costs | # Variance | # Explanation for Variance |
| --- | --- | --- | --- | --- | --- | --- |
| ### Development of HOSG | 35 | 1,925.00 | 49.5 | 2,475.00 | +14.5 hrs +£550.00 | The HOSG required more development work than anticipated particularly in relation to recruitment interviews. |
| Project planning & monitoring meetings. | 75 | 4,125.00 | 115.6 | 5,685.00 | +40.6 hrs +£1,560.00 | The complicated nature of the financial appraisal and the amount of information emanating from the council required a greater level of inter-team communication than originally anticipated. Phase 3 preparation work accounts for 29.5 hours of this total. |
| HOSG meetings | 60 | 3,300.00 | 109.1 | 5,612.50 | +49.1 hrs +£2,312.50 | The HOSG has needed considerable support in understanding the complexities of the financial appraisal and engagement process. This has exceeded our original estimates. |
| ### HOSG ‘away day’ | 65.5 | 3,800.00 | 85.3 | 3,650.00 | +19.8 hrs -£150.00 | We planned for 1 ‘away-day’ rather than the 2 that were actually held. |
| ### Desk-top review of technical / financial appraisal documentation. | 30 | 1,950.00 | 201 | 13,065.00 | +171 hrs +£11,115.00 | The extent and complexity of the financial data and appraisal has been unprecedented. The input required from our team was underestimated. Phase 3 preparation work accounts for 93.5 hours of this total. |
| Briefing Sessions & Study Visits | 68 | 3,740.00 | 48.5 | 2,590.00 | -19.5 hrs -£1,150.00 | The preparation time required to deliver the briefing sessions and study visits was lower than anticipated. |
| Assessment of Consultation Materials | 35 | 1,925.00 | 79.9 | 3,990.00 | +44.9 hrs +£2,065.00 | Salford CC has produced a considerably greater quantity of consultation materials than expected. Phase 3 preparation work accounts for 29.9 hours of this total. |
| Liaison with Salford CC | 56 | 3,080.00 | 92 | 5,645.15 | +36 hrs +2,565.15 | The size and scope of the appraisal process has required a higher than normal level of liaison. The ITA team has in addition, been required to broker a relationship with senior NPHL officers and has provided training for NPHL staff. |
| Attendance at HOOG meetings | 32 | 1,760.00 | 66.5 | 3,400.00 | +34.5 hrs +£1,640.00 | We anticipated that the HOOG would meet once per month rather than every 2 weeks. |
| Attendance at Business Planning Meetings | 12 | 780.00 | 36.25 | 2,356.25 | +24.25 hrs +£1,576.25 | The Business Planning Meetings have been far more regular than we anticipated. We planned to attend 4 meetings but this was an underestimate. Phase 3 preparation work accounts for 14.25 hours of this total. |
| Attendance at Salford CC Consultation Events | 175 | 9,625.00 | 126 | 6,300.00 | -49 hrs -£3,325.00 | The time spent at each of the events was not as great as anticipated. |
| Special Group Meetings | 24 | 1,560.00 | 15.5 | 1,007.50 | -8.5 hrs -£552.50 | We have been required to support 2 rather than 3 TMOs. |
| Production of various information & consultation materials. | 21 | 27,955.00 | 25 | 13,235.75 | +4 hrs -£14,719.25 | We have produced 1 newsletter rather than the 2 that were originally planned. Second newsletter is planned for Phase 3. |
| Public Meetings & Facilitation of Surgeries/Roadshows | 90 | 5,850.00 | 99.5 | 5,177.50 | +9.5 hrs -£672.50 | We had originally planned for 12 events but this was increased to 14 on advise from the HOSG & NPHL. |
| TARA/SPF Briefing Sessions | 9 | 495.00 | 6.5 | 325.00 | -2.5 hrs -£170.00 | Balance to be accounted for in Phase 3. |
| ### Options Conference/Concluding Away Day | 49 | 2,695.00 | 0 | 0 | -49 hrs -£2,695.00 | Activity planned for Phase 3. |
| ### Attend Salford Peoples Forum Meetings | 24 | 1,320.00 | 29.9 | 1,495.00 | +5.9 hrs +£170.00 | Time spent at each SPF meeting underestimated. |
| ### Provision of Freephone advice line for duration of project. |  | FREE |  |  |  |  |
| Other Community/ Neighbourhood Meetings | 15 | 825.00 | 17 | 850.00 | +2 hrs +£25.00 | Slight underestimate due to additional sheltered scheme meetings attended by ITA team |
| #### Contact / liaison with GO & Media | 16 | 1,040.00 | 37 | 2,713.60 | +21 hrs +£1,673.60 | Greater number of CHTF/HOSG & CHTF/Salford CC meetings held than originally planned for. |
| ### Collation of findings & preparation of report. | 21 | 1,155.00 | 0 | 0 | -21 hrs -£1,400.00 | Activity planned for Phase 3. |
| ### Administration costs including photocopying and postage. | 70 | 1,400.00 | 55.5 | 1,110.00 | -14.5 hrs -£290.00 | Balance to be accounted for in Phase 3. |
| ### Total | 982.5 | 80,305.00 | 1,295.55 | 80,683.25 | +313.05 hrs +£378.25 |  |