SALFORD CITY COUNCIL OPTIONS APPRAISAL

INDEPENDENT TENANTS ADVISOR

PROJECTED PROJECT COSTS

Phase 3 February 2005 – June 2005

| Activity | # Hours | # Cost (£) |
| --- | --- | --- |
| Project planning & monitoring meetings. 5 @ 2.5 hours x 5 team members travel @ 1hour / meeting | 62.5 25 |  |
| Sub Total | 87.5 | 4,812.50 |
| HOSG meetings 6 @ 2.5 hours x 1 team member preparation @ 2 hours / meeting travel @ 1 hour / meeting | 15 12 6 |  |
| Sub Total | 33 | 1,815.00 |
| ### Desk-top review of technical / financial appraisal documentation. Review of final financial appraisal | 35 |  |
| Sub Total | 35 | 2,275.00 |
| Assessment of Consultation Materials | 21 |  |
| Sub Total | 21 | 1,155.00 |
| Liaison with Salford CC @ 14 hours per month x 5 months | 70 |  |
| Sub Total | 70 | 3,850.00 |
| Attendance at HOOG meetings 9 @ 2 hours x 1 team member preparation @ 1 hour / meeting travel @ 1 hour / meeting | 18 9 9 |  |
| Sub Total | 36 | 1,980.00 |
| Attendance at Business Planning Meetings 5 @ 2.5 hours x 1 team member travel @ 1 hour / meeting | 12.5 5 |  |
| Sub Total | 17.5 | 1,137.50 |
| Attendance at Phase 3 Consultation Events 13 Flagship meetings @ 3.5 hours x 1 team member inc. travel 24 drop in/roadshow events @ 3.5 hours x 1 team member inc travel | 45.5 84 |  |
| Sub Total | 129.5 | 7,122.50 |
| TMO Meetings/Briefing Sessions 4 @ 2.5 hours x 1 team member preparation @ 1 hour / meeting travel @ 1 hour / meeting | 10 4 4 |  |
| Sub Total | 18 | 1,170.00 |
| TARA Briefing Sessions 6 @ 2 hours x 1 team member travel @ 1 hour / meeting | 12 6 |  |
| Sub Total | 18 | 990.00 |
| ### Options Conference/Concluding Away Day 1 @ 6 hours x 5 team members preparation @ 14 hours travel @ 1 hour | 30 14 5 |  |
| ### Sub Total | 49 | 2,695.00 |
| ### Attend Salford Peoples Forum Meetings 5 @51hour x 1 team member preparation @ 1 hour / meeting travel @ 1 hour / meeting | 10 5 5 |  |
| ### Sub Total | 20 | 1,100.00 |
| ### Provision of Freephone advice line for duration of project. |  | FREE |
| Other Community/ Neighbourhood Meetings 5 @ 2 hours x 1 team member travel @ 1hour / meeting | 10 5 |  |
| Sub Total | 15 | 825.00 |
| #### Contact / liaison with GO & Media Assume 2 hours / month | 16 |  |
| ### Sub Total | 16 | 1,040.00 |
| ### Collation of findings & preparation of report. | 21 |  |
| Sub Total | 21 | 1,155.00 |
| ### Administration costs including photocopying and postage. | 20 |  |
| ### Sub Total | 20 | 400.00 |
| ### TOTAL excluding newsletter | 606.5 | 33,522.50 |
| Production of final newsletter Newsletter x 1 Printing / Collating Distribution | 7 | 455.00 6,500.00 5,500.00 |
| Sub Total | 7 | 12,455.00 |
| TOTAL including newsletter | 613.5 | 45,977.50 |

All costs are exclusive of VAT