Community and Social Services Directorate

Service Plan

2002/2003

Contents									        Page

Section	1	Introduction,	and						3

Community and Social Services Mission			3

Section	2	Understanding the Environment -

External Environment					4-28

Socio-economic Profile of Salford				4-7

Social Care Needs data					7-12

National Policy Agenda					13

Modernising Local Government			13

Taking this forward Locally				13-17

New Democracy				15-16

Best Value					16

E-government				17

Public Service Agreements			17

Modernising Social Services				18

National Objectives for Adults and 	        Children's Services					18

Quality Protects Initiative for                          Children's Services					18

Children's Services Plans				19

Personal Social Services Performance                        Assessment Framework (PAF)			19

National Priorities Guidance				20

Quality Strategy for Social Care				20

Information for Social Care					21

Adoption Services National Standards			21

National Services Framework for Older People:                                   Integrated Health and Social Care Services		21-22

Learning Disability White Paper: Valuing People		22

Fairer Charging Policies					23

Contents									        Page

Modernising Health						23-24

The NHS Plan					24

Information for Health				25

Primary Care Trusts					25

# Additional Legislative Requirements			25

Lessons form Joint Review and Inspection		26

SSI Chief Inspector Annual Report – Key Messages	27-28

Section	3	Understanding the Environment -

Internal Environment					29-36

Local Policy Agenda						29

Community Plan					29

Community & Social Services Service Plan	30

Health Improvement Programme (HImp)	31

Partnerships at Local level				31-33

Implementing Best Value				33

Performance Assessment Framework (PAF)	34

How Are We Doing?					34-35

Budget						36

Human Resources 					36

Section	4	Key Service Objectives					37-45

Section	5	Community Priorities					46-47

Section	6	Outcome of Best Value Review				48-50

Section	7	Continuous Improvement					51-53

Section	8	Consultation							54

Section	9	Resources							55

Section	10	Delivering Change						56-60

Section	11	Monitoring Arrangements					61-63

Appendices										64-82

Section	1

1.	Introduction.

This Service plan sets out the priorities and key service objectives for achievement in 2002/03. The degree to which these key objectives are met will provide an overall indication of the performance of the Directorate in 2002/03. Key service objectives and targets are designed to measure achievement of the aims contained in the Salford Community Plan, Strategic and Best Value Performance Plan, City Council pledges and Community Action Plans.

2.	Community & Social Services Mission.

To improve the life chances

and

promote independence

of children, young people, adults and communities in Salford.

In delivering our mission to the residents of Salford, we are working to the following high-level imperatives:

- Actively promoting the independence of people who need or are close to needing a service

- Improving the protection of vulnerable children and adults

- Raising standards of care across all service areas and providers

- Developing and enhancing services/partnerships with the health sector, voluntary/community and independent sectors

- Reducing and preventing social exclusion of vulnerable people and groups by cutting levels of inequality and poor health

Section	2

Understanding the Environment.

External Environment.

Socio-economic Profile of Salford.

i)	Population

The Office for National Statistics (ONS) mid 2000 population estimate puts the City's population at 224,300, a decline of 500 from the previous year. This decline comprises a net outward migration of 700, with an increase of 100 in both asylum seekers/ visitor switches and in prisoners. Since 1991, the City's population is estimated to have fallen each year (except 1993/94 when it increased due to boundary changes with Wigan), giving a total estimated decline of 6,600 persons. This is the largest decrease in Greater Manchester. The ONS 1998 based short-term projection suggests that the City's population will decrease by a further 4,100 persons to 220,200 in 2008. This contrasts with a projected increase of 3.8% in the population of England to 1998.

The age structure of the population is similar to the national average, but with slightly more young people aged 15-24 (14.2% compared to 12.0%) and less people of working age 25-44 (45.8% compared to 48.4%).

Around one in three households (31.6%) in the City are occupied by adults who live on their own, compared to a national average of around one in four (26.6%), and this is expected to increase. Similarly, the proportion of lone parents in Salford (5.9%) is greater than the national average (4.1%) (all via 1991 census).

ii)	Deprivation

The City exhibits high levels of poverty and deprivation, being the twenty- sixth most deprived of the 150 Local Authorities with social services responsibilities.  This has serious consequences for the health and social care needs of the population.  There are marked inequalities between the more affluent suburbs and the deprived inner city areas.

| Source Public Health Report | Salford East | Salford West |
| --- | --- | --- |
| Proportion of population claiming income support | 24% | 15% |
| Proportion of working age population unemployed | 6.3% | 4% |
| Excess mortality | 50% | 22% |
| Number of crimes per thousand residents | 189 | 133 |
| Deaths brought forward due to air pollution | 45 | 67 |
| Proportion of older people living alone | 8.2% | 7.1% |
| Percentage of households with no car | 58% | 41% |

iii)	Ethnic Minority Population

Salford has traditionally had a very low ethnic minority population. The 1991 census gives a total non-white population of 2.18%, but within this the proportion aged 0-17 was higher at 3.41%. The main populations identified by the 1991 census suggest that the total population of Salford was made up of: White 97.8%, Black Caribbean/ African/Other 0.5%, Indian/Pakistani/Bangladeshi 0.8% and Chinese/Asian/Other 0.9%.

Black Caribbean		310

Black African			254

Black other			458

Indian		           	910

Pakistani			673

Bangladeshi		          271

Chinese			        653

Other Asian		        275

Other Other                    1006

Total non-white	        4810

White			      215653

# Total Population       220463

This is thought to be a gross under estimate of the ethnic minority population, one reason being that the census was not translated into other languages.

The figures show that the largest ethnic minority populations are in

Broughon/Blackfriars/Kersal - Indian & Pakistani

Pendleton/Langworthy/Ordsall - Chinese

Eccles/Barton/Winton - Bangladeshi & Indian

Salford East has the largest black population

In each area there is also a large number of 'other other'.

Of particular note in Salford is that 'white' includes Jewish, Eastern European and Irish; 'black other' and 'other other' includes Yemeni, Iraqi and other middle Eastern groups. There is a:

Jewish community in Broughton, estimated at 10,000

Asian community in Broughton closer to a much larger Asian community in adjoining wards within Manchester

Yemeni community in Eccles, similar in size to Pakistani and Chinese communities

Chinese community, which is basically evenly spread (except in Irlam)

Asian community in the Irlams O'th Height area

The 2001 census will give a more detailed breakdown and is expected to show an increase in the ethnic minority population. Anecdotal evidence suggests such an increase. Schools have reported an increase in children from ethnic minority backgrounds, for example, a school in Broughton reports a recent influx of children from Nigerian families. The Disabled Children's Register now has 5.8% of children from ethnic minority populations.

# iv)	Health

The DLTR 2000 health rankings show that three quarters of the City's wards are amongst the worst 10% in the country. The ward-ranked worst in this way is Little Hulton, which is ranked 60th out of a total of 8,415 wards.

The standardised mortality ratio for the City for 1997-99 is 135, compared to the national average of 100. Only two wards in the City, out of a total of 20, have an SMR of less than 100. When looking at the nine most common causes of death, only one has an SMR of less than 100 in Salford (female breast cancer: 97), with the highest SMR of 171 relating to cancer of the trachea, bronchus and lung.

The City Council's Strategic Plan has a number of health related targets. One is to reduce the health of the worst off in the City by reducing the SMR in localised areas down to the level of the City overall. Others are to reduce the number of under age pregnancies by at least half (from 14 per 1,000 girls aged 13-15); to reduce death rates from accidents particularly in under 15's by at least a fifth (from 11 per 1000 population); to reduce death rates from coronary heart disease and stroke by at least a third (from 65 for CHD and 21 for stroke); to reduce death rates from all cancers by at least a fifth (from: breast cancer 83.8; lung cancer 64.2).

The local rate of low birth weight babies exceeds the national average: in 1995-1999 8.6% of births in Salford were classified as low weight births (less than 2500g) compared to a national rate of 7.9%. In only 6 of our 20 wards is the rate less than the national average; in one ward (Ordsall) the rate is as high as 12.2%. The rate of births to single mothers in Salford far exceeds the national rate: 24.5% compared to a national figure of 14.8%. In only three wards is the rate less than the national average, with the rate in one ward (Langworthy) being as high as 41.9%. The rate of under 18 conceptions is also high in Salford: the rate per 1000 girls aged 15-17 in 1996-98 was 61.7% in Salford compared to a national rate of 46.4%. In only five wards was the rate less than the national average, the highest rate of 116.1% being in Langworthy. The stillbirth rate in Salford has, for five of the seven years 1993-1999, been greater than the national rate. Similarly, when looking at infant mortality rates in Salford for consecutive three-year periods up to 1997-99, Salford’s rate is greater than the national rate in six of these eight periods.

According to the 1991 census, 17.4% of the population identified themselves as having limiting long-term illness; this was significantly above the national average of 13.1%. Life expectancy in Salford in 1995-97 is less than the national average: for men this is 71.7 (compared to the national figure of 74.4); for women this is 77.5 (compared to the national figure of 79.6).

v)	The Economy/Employment

Unemployment in Salford has hit a 17-year low.  Latest statistics show that the unemployment rate in the City for October 2001 stood at 3.0% compared with 3.9% in December 2000, with 4.3% in June 2000 and 4.9% at the beginning of 2000.  This is the lowest rate of unemployment in the City since figures were first produced in 1983.  The figures also show there has been a particularly sharp fall in the inner-city wards – with Blackfriars, Ordsall, Broughton and Pendleton all experiencing significant falls in unemployment

Social Care Needs data

i)	Older People

The number of people over the age of 65 living in Salford is about 35,500.  This represents 16% of the total population of 220,000.  The number of older people is expected to fall until 2011 and then rise again until 2021.  The number of people over 85 will continue to rise throughout this period.  The projections for the next 20 years are shown in the table below.  Of the total population it is estimated that less than 2% are from ethnic minority.

Measures of poverty also impact on the health and well being of older people.  High levels of unemployment mean that older people in Salford are less likely to have occupational pensions to supplement the basic state pension, leading to further health inequalities.   Poor quality transport and lack of access to a car, together with fear of crime restrict older people’s activities.  These are two of the issues raised most frequently by older people themselves.   Arising from this it is clear that services must be organised as locally as possible to improve access for older people.

| Older People Population Information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### Ages 65 and over |  |  |  |  |  |
| Population | Salford East | Salford West | Salford |  |  |
| Resident | 13,320 | 21,846 | 35,166 |  |  |
| Registered | 14,643 | 20,592 | 35,235 |  |  |

Registered Populations

The registered populations used here are the total number of patients registered with Salford GP Practices.  This figure will include patients who live outside the boundaries of Salford (e.g. approximately 280 patients actually live within the boundaries of Wigan & Bolton but will be included in the registered population figure).

Numbers of older people for who services will be needed

The table below provides an estimate of the number of people who may need services based on national estimates, although this estimate includes those making private arrangements and does not take account of changes in alternatives, which may be developed.

|  | Estimates |  |  |
| --- | --- | --- | --- |
|  | 2000 | 2011 | 2021 |
| Low to moderate dependency | 6030 | 5870 | 6429 |
| Substantial dependency | 3646 | 3561 | 3847 |
| Residential Care | 1171 | 1155 | 1230 |
| Nursing Home | 640 | 632 | 674 |

## ii)	Learning Difficulties

The incidence of people born with severe learning difficulties is currently running at 3:1,000 and people born with mild learning difficulties at 20:1,000 (Health of the Nation Booklet DHSS 1995). This would therefore suggest a prevalence figure of 661 for people with severe learning difficulties living in the Salford area.

During 2000/01 there were:

830 adults with learning difficulties known to the Council

233 adults with learning difficulties receiving community based services 		(as at 31/3/2001)

127 adults with learning disabilities on the books to receive planned 	short-term breaks (as at 31/3/2001)

83 people with learning difficulties in work

2 people with learning difficulties on Direct Payments

2 people with learning difficulties receiving services during 2001/02 who		 were 	from ethnic minority communities

iii)	Mental Health

The approximate number of people experiencing some form of psychological distress in Salford and Trafford was estimated as 112,000, using OPCS Surveys of Psychiatric Morbidity and a General Health Questionnaire survey carried out in 1992.

In the population of Salford and Trafford, two main groups of people experiencing mental health problems can be identified. These groups differ according to the number of people within each group, the severity of symptoms experienced and the complexity of need.

The first group consists of people experiencing the social disability associated with what is usually termed severe mental illness. The number in this group is relatively small, around 4,100 in the whole of Salford and Trafford.

The second group consists of people experiencing a level of psychological distress usually associated with mild to moderate mental illness. Estimates of the size of this group range from 40,000 to 120,000 for the whole of Salford and Trafford.

It is estimated that 25% of people over the age of 85 and that 50% of people in residential and nursing home care suffer some degree of dementia from mild to very severe.  Additionally depression is more common in older people. The problems of people with a long history of mental illness and who are now over    65 must be considered as they represent a small but demanding group of service users.

Most people with mental illness also have a higher lifetime risk of suicide. In    both males and females there is an increasing risk of suicide with age.

Deaths form suicide and undetermined injury (i.e. Coroner’s verdict where     suicide could not be proven with absolute certainty) accounted for 132 deaths in Salford and Trafford for the period 1995-1997

Salford		11.43 deaths per 100,000 population	(80 deaths)

Trafford		7.46 deaths per 100,000 population	(52 deaths)

North West Region	10.56 deaths per 100,000 population	(1769 deaths)

England		9.07 deaths per 100,000 population	(13,921 deaths)

iv)	Children.

There has been a growth in the number of looked after children since 1994 as evidenced by the table below:

| Number of Children Looked After as at 31st March |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 |
| 336 | 365 | 355 | 396 | 447 | 480 | 579 | 607 |

At 31st January 2002 there were 607 looked after children, with the following breakdown:

## Gender					Age

Female	278 				Under 1	   1

Male		329				1 to 4		  99

5 to 8		146

9 to 12	150

13 to 15	120

16 to 17	  77

18 & over	   4

## Ethnicity

White British								551

White Irish								   2

White & Asian							   9

White & Black African						   3

White & Black Caribbean						  11

Other White background						   8

Asian/Asian British – Bangladeshi					   3

Asian/Asian British – Indian					   0

Asian/Asian British – Pakistani					   3

Asian/Asian British – Any other Asian background		   4

Chinese								   2

Other Mixed Background						   6

Any other ethnic group						   1

Declined								   3

Unknown								   1

## Need Category

Absent parenting				  10

Abuse/neglect				483

Disability					  25

Family Dysfunction				  34

Family in acute stress			    9

Low Income					    1

Parental Illness/Disability			  14

Socially unacceptable behaviour		  17

Other						    2

Non-recorded				  12

Child Protection.

| Number of on Child Protection Register as at 31st March |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 |
| 149 | 167 | 144 | 191 | 152 | 139 | 175 | 153 |

| Child Protection Overview | 1997/98 | 1998/99 | 1999/00 | 2000/01 |
| --- | --- | --- | --- | --- |
| Total Number of Registration Conferences | 96 | 87 | 128 | 103 |
| Number of conferences resulting in registration | 61 | 62 | 99 | 85 |
| Percentage of conferences resulting in registration | 64% | 71% | 77% | 83% |
| Total number of new cases added to register | 145 | 142 | 242 | 201 |
| Total number of removals from register | 188 | 155 | 206 | 223 |
| Total on register at end of year | 152 | 139 | 175 | 153 |

| Breakdown of Total on Register by category | 31/3/01 | 30/6/01 | 30/9/01 | 31/12/01 |
| --- | --- | --- | --- | --- |
| Physical injury | 49 | 26 | 39 | 35 |
| Neglect | 66 | 52 | 53 | 50 |
| Emotional abuse | 26 | 27 | 23 | 39 |
| Sexual abuse | 10 | 11 | 11 | 14 |
| Temporary registration | 2 | 4 | 6 | 5 |
| Total on register | 153 | 120 | 132 | 143 |

National Policy Agenda.

Modernising Local Government.

Taking this forward Locally.

Our vision for Salford is to create a City where people choose to live and work.  We aim to improve the quality of life of all our citizens by creating an economically prosperous City with a buoyant and competitive economy; creating and maintaining strong, safe, healthy and sustainable communities where all citizens can participate to the fullest extent in decisions which affect their communities; providing better educational for all, to enable children and young people to thrive and fulfil their potential; creating a City that is good to live in by providing quality homes and a clean and healthy environment.

Community Plan.

The Salford Partnership has taken the Salford Community Plan forward.

Salford has a strong tradition of partnership working as evidenced by our Community Plan, where the Salford Partnership is responsible for taking forward the whole Plan.

The Partnership has been in existence since 1994 and has a core membership, which consists of a range of public, private, voluntary, and community sector representatives. The Salford Partnership is as follows:

##### New Democracy.

i)	The City Council has moved to a Cabinet system of government. Each year it appoints ten members to the cabinet, including both the Leader and Deputy Leader. Eight Lead Members are responsible for the service portfolios listed below:

Education 				Community & Social Services

Arts & Leisure 			Personnel Services

Development Services 		Environmental Services

Housing Services 			Corporate Services

A number of cross cutting portfolios are also allocated as follows:

Community Strategy  	 	Communications

Crime and Disorder			Targets and Pledges

Youth

Authority is delegated to relevant Chief Officers in consultation with respective Lead Members and Deputy Lead Members to take decisions.

ii)	Scrutiny Committees

Five Scrutiny Committees are empowered to hold the Cabinet to account. This overview role has four principal elements: to scrutinise decisions which the Cabinet is planning to take; to scrutinise decisions once taken but not yet implemented; to scrutinise decisions after implementation; and to review performance of the Cabinet in wider terms. The Scrutiny Committees are politically balanced and are shown below:

Economic & Community Safety

Environmental

Health & Social Care

Lifelong Learning & Leisure

Quality & Performance

iii)	Community Committees

In 1992 the City Council developed the Community Strategy to develop models of community participation and consultation. Our Community Strategy is nationally recognised as being at the forefront of community involvement. Our approach is to ensure that local people participate in local decision-making and shape local service delivery.

The City is broken down into 9 Service Delivery Areas (SDAs) with area based Community Committees now well established in each SDA. These Committees develop local Community Action Plans (CAPs) for their area. These CAPs feed directly into the City-wide community planning process and the Community Plan.

The 9 service Delivery Areas are:	Broughton and Blackfriars

Claremont, Weaste and Seedley

Eccles

Irlam and Cadishead

Kersal Pendleton and Charlestown

Little Hulton and Walkden

Ordsall and Langworthy

Swinton

Worsley and Boothstown

Membership comprises local Councillors and representatives of local community and voluntary groups. Each member has full voting rights and members of the general public are encouraged to take part in the debates.

iv)	There are also:

- 2 Regulatory Panels

- 16 non-regulatory panels

- Policy Review Task Groups

Best Value

Best Value is designed to deliver better quality local services and real value for money. The duty of Best Value excepts that our locally provided services are delivered to clear standards of cost and quality by the most economic, efficient and effective means available.

The duty of Best Value requires us to:

- Publish an annual Best Value Performance Plan

- Review all of our services over a 5 year time frame

- Challenge why and how a service is being provided

- Compare our performance with other providers, including organisations in the private and voluntary sectors

- Embrace fair competition as a means of securing efficient and effective services

- Consult with local tax payers, customers and the wider business community

- Demonstrate to local people we are achieving continuous improvements in our service

E-Government.

The modernisation programme (Electronic Modernisation Bill) requires Local Government to develop effective communications so that customers of the Council can communicate electronically. The Council will introduce these changes to make sure that we comply with:

- ensuring front line staff have access to electronic information

- ensuring electronic information is available to the public

- providing electronic links with providers organisations

- providing electronic procurement

- providing electronic communication with Councillors

The City Council received approval for Pathfinder Status in July 2001, in respect  of the development and implementation of e-government targets.  This submission revolves around a programme based on Salford’s approach to    change management.

# Public Service Agreements (PSA).

Public Service Agreements have been in place for some time between Government Departments and the Treasury. Extra funding is available to these Departments on the basis of achieving enhanced levels of performance against specified national priorities.

Local PSA's are negotiated agreements in which the Local Authority aims to achieve demanding improvements in performance across a range of 12 targets over a spending review period. The majority of local targets are drawn from the National PSA targets that depend heavily on Local Authorities for their achievements.

The City Council has entered into a PSA and Community & Social Services has     one PSA target:

related to the: Educational attainment of Looked After Children

Enhanced performance, or delivery of agreed targets ahead of Best value Performance Plan timescales, will lead to access to a performance reward fund.

Modernising Social Services.

The modernisation of Social Services, builds on the expectations outlined in the Modern Local Government "In Touch with People" White Paper (1998). This paved the way for radical improvements in the quality, reliability and cost effectiveness of Social Services.  Promoting a new emphasis on rehabilitation and reducing dependence wherever possible outlines fundamental changes in regulation and provides better protection to vulnerable service users.

The modernisation initiatives include the need to:

- Promote independence for Adults, Older People and 	         Children and Families

- Improve protection of vulnerable children and adults

- Raise standards across all care services

National Objectives for Adults and Children’s Services.

The Department of Health has identified specific national objectives for both Children’s and Adults services.

A total of eleven objectives apply to each area of service.  The objectives may be referred to in Appendix 1.

Quality Protects Initiative for Children’s Services.

Quality Protects is about improving the well being of the children for whom the Local Authority has taken on direct responsibilities:

Quality Protects requires us to be clear about what we want to achieve for the children we are responsible for, whether they are looked after by the Authority or by their families.  The Government believes that Local Authorities should act towards children in their care as any well-meaning natural parents would towards their own children.  This means providing a home, good care, and access to the education and health care, which children need to grow and develop.

To measure these objectives, the Government has introduced a framework for the assessment for children in need and their families.

Current policy is focused on ensuring that children's needs are identified at the earliest possible stage.  The framework has been designed to facilitate a systematic approach to identifying, analysing, understanding and recording a child's needs.

Children's Services Plans.

Arrangements for Children's Services Plans have been reviewed and Plans will be produced on a three yearly cycle and will be reviewed annually.

Responsibility for planning Children’s Services now rests with the Inter Agency Children’s Service Planning Forum, which will produce a triennial overview Children’s Services Plan and will also receive regular Plans covering particular aspects of service i.e. children leaving care, children with disabilities etc

Personal Social Services Performance Assessment Framework (PAF).

Government is measuring Social Services performance using a performance assessment framework, which contains a set of 50 performance indicators, which are designed to be:

- Small enough to be manageable

- Large enough to cover all aspects of performance,     		        all services and all client groups

Structured into five performance areas of Best Value:

- National Priorities and Objectives

- Cost and efficiency

- Effectiveness of service delivery and outcomes

- Quality of services for users and carers

- Fair access

National Priorities Guidance.

# Modernisation Health and Social Services.

Over the past two years, Central Government has laid the foundations for a 10 year programme of modernisation. Government is keen to see the pace of modernisation increase to ensure that the public feel the benefit of services, which are fast, fair, convenient and excellent.  To achieve this aim, both Health and Social Services have a programme of priority areas on which to focus.  These are:

|  |  |  | Priorities |  |
| --- | --- | --- | --- | --- |
| Improving Health |  | Smoking Drugs Teenage Pregnancy |  |  |
| Saving Lives |  | Cancer CHD / Stroke |  |  |
| Fast & Convenient Services |  | Waiting Lists Modern and Times Primary Care |  |  |
| Caring for Vulnerable People |  | Mental Older Peoples Children’s Health Services Services |  |  |
| Modernising Strategies |  | Quality Staff Information Technology |  |  |

The Department of Health has specified objectives and targets, which relates to all elements of the National Priorities Guidance.

Quality Strategy for Social Care.

The Quality Strategy for Social Care places the experience of service users and carers at the centre, it focuses on quality improvement in outcomes for users and carers in social care.

There are three key elements to the Quality Strategy:

- the establishment of a Social Care Institute for Excellence – to ensure that knowledge of what works is translated into practice and disseminated to promote lifelong learning and good practice

- the introduction of a new quality framework to ensure continuous quality improvements, which emphasises local leadership and accountability, the importance of staff development and training, together with higher standards of practice at all levels

- a radical reform of social work training, education and post professional development

# Information for Social Care.

Throughout the early stages of the Government’s ten-year modernisation programme for Health and Social Care, it has been increasingly apparent for the need to improve both management information systems and the management of information to run the business.

“Information for Social Care” a framework for improving quality in Social Care through better use of information technology, has been developed by the Department of Health in collaboration with the ADSS Information management group. It is intended to provide a practical tool kit to help Local Authority Social Services in collaboration with their partner agencies and the DoH to address the Social Care Information Management Agenda and to develop local information strategies.

# Adoption Services National Standards.

Following the Prime Minster’s review of adoption, Government have produced a set of National Adoption Standards in draft form for consultation.

The Adoption standards have been complied to ensure that looked after children, prospective adopters, birth families and the general public understand what they can expect form the Adoption Service and so that all parties receive a fair and equal service wherever they live.

National Service Framework for Older People:

Integrated Health and Social Care Services.

The National Services Framework (NSF) for Older people is an action plan to improve health and social services for older people. It sets new standards and service models of care for all older people whether they live at home, in residential care or are being cared for in hospital. It focuses on:

- Rooting out age discrimination

- Providing person-centred care with older people treated as individuals   with respect and dignity

- Promoting older peoples’ health and independence

It also specifically addresses those conditions, which are particularly significant in older people – stoke, falls, and mental health problems associated with old age.

Council’s with Social Services responsibilities are required to publish a Local Implementation Plan for Older People, detailing local action and progress against national milestones.

Locally we are moving to an integrated service approach, which will see the introduction of a multi-disciplinary, single assessment process for older people.

The key objectives of an integrated service are to ensure:

- that older people can remain at home during illness or following injury unless they need hospital care for clinical reasons

- that people can be discharged from hospital safely as soon as they are fit for discharge

- people achieve their maximum social and physical functioning following illness or injury

- people maintain maximum social and physical functioning after they become frail

- that people with long term disabilities receive the care that gives them maximum independence with safety

- that informal carers are able to provide care for as long as it is agreed appropriate

- equitable and easy access to services across agencies

# Learning Disabilities Service White Paper.

The key message in the White Paper “Valuing People” is the need to improve the life chances of people, with learning difficulties by partnerships especially with people we support, under the logo “nothing about us without us”. There are new national objectives for services for people with Learning Difficulties supported by new targets and performance indicators, to provide clear direction for local agencies.

The objectives focus on the areas:

- better life chances for people with Learning Disabilities

- more choice and control for people with Learning Disabilities

- supporting carers

- improving health for people with Learning Disabilities

- housing, fulfilling lives and employment

- quality services

- partnership working

The Action Plan for delivering Valuing People is written down in the Joint Investment Plan, Section 31 Partnership application and in Better by Design.

# Fairer Charging Policies.

One of the central stands of Government Modernisation policy for Social Care is to promote independence and social inclusion. To date, Government have expressed concern over the service charging mechanisms in place across the country.

The publication of “Fairer Charging Policies”, (guidance November 2001) issued to all Councils with Social Services responsibilities, is designed to create greater consistency and equity in charging regimes throughout England and Wales. Government expects local Councils to review their charging policies, and revise them within the context of new guidance and the sprit of promoting independence and social inclusion.

Community & Social Services charging policy will be reviewed in light of new guidance and will take cognisance of the new “Supporting People Grant” initiative in this regard, in preparation for its introduction in April 2003.

# Modernising Health.

It is widely recognised that the modernisation programmes in the Health and Social Care fields is dependent on both organisations working in close               co-operation and partnership.

The new NHS Modern and Dependable White Paper provides six important principles which underpin the proposed changes and reforms:

- to renew the NHS as a genuinely National service. patients will get fair access to consistently high quality, prompt and accessible services across the country

- to make the delivery of health care against these new National standards a matter of local responsibility. Local doctors and nurses are in the best position to know what patients need and will be in the driving seat in shaping services

- to get the NHS to work in partnerships. By breaking down the organisational barriers and forging stronger links with local Authorities, the needs of the patients will be putt the centre of the care process

- to drive efficiency through a more rigorous approach to performance by cutting bureaucracy, so that every pound in the NHS is spent to maximise care for patients

- to shift the focus onto quality of care so that excellence is guaranteed to all patients, and quality becomes a driving force for decision making at every level of service

- to rebuild public confidence in the NHS as a public service, accountable to patients, open to the public and shaped by their views

These principles will be the backbone of modernisation for Health. The new NHS arrangements will be based on a philosophy, which is built on partnership and driven by performance.

The new NHS performance framework itemises six performance domains by which efficient cost effective performance will be judged:

1.	Health Improvement

2.	Fair Access

3.	Effective delivery of appropriate Health care

- Efficiency

5.	Patient/Carer Experience

6.	Health Outcomes of NHS Care

Assessing the direct contribution of NHS care to improvements in overall health, completing the circle back to the overarching goal of improved health.

The NHS Plan.

The NHS Plan sets out a vision of health services designed around the patient.  The aim of the Plan is to provide a personalised service offering the standards that patients expect and staff want to provide.

The NHS Plan implementation programme sets out a framework within which regional and local plans will fit together.  Health and Local Authorities are required to work in close co-operation to integrate these plans.  This includes:

- Health Improvement Plans

- Joint Investment Plans

- Service and Financial frameworks

- Primary Care Investment Plans

It recognises that this will require investment and reform.  This needs to be achieved in all areas where the NHS and its partners provide services to patients, to users and to the public.  This covers:

- Provision of preventative services

- Support for self care

- Social Care

- Primary Care

- Intermediate Care

- Hospital Care

- Patient and public involvement

# Information for Health.

To support the programme of modernising Health and Social care systems, Government have specified a requirement for Health to take a lead on the development of information management and technology where this crosses agencies boundaries.

# Primary Care Trusts.

Primary Care Trusts have three designated functions:

- to improve the health of the community

- to develop primary and community health services

- to commission secondary care services

It is widely acknowledged that the success of the PCT is dependent upon partnership, co-operation and networking.  The PCT has therefore recognised    the significance of its relationship with the City Council.  The traditional link between the Health Services has been with the local Authority Social Services. With greater emphasis on a holistic approach to addressing the wider determinants of ill health however, the strategic planning of each party will become more entwined. Community & Social Services has representation on     the Board of the Primary Care Trust to facilitate the developments of partnership and joint working.

In addition, a Head of Joint Health and Social Services in Learning Difficulties    has been appointed.

Additional Legislative Requirements.

The additional legislative requirements upon Social Services includes:

- Human Rights Act 1998

- Disability Discrimination Act 1995

- Community Care (Direct Payments) Amendments Regulations 2000

- Carers and Disabled Children's' Act 2000

- Race Relations (Amendment) Act 2000

# Health and Social Care Bill 1999

# Lessons from Joint Review and Inspections.

The Social Services Inspectorate report on the effectiveness of services, helping Government to frame policy, local Authorities to improve services and staff to follow best practice. The Audit Commission promotes the best use of public money by commissioning the District auditor to ensure public money is properly spent and that good value is achieved.

Joint Reviews combine these approaches to look at the overall performance of each Social Services Authority. Reviews aim to improve Social Services by identifying and promoting policies, management and practice, which are achieving better outcomes and Best value.

Reviews start form the experience of people who use Social Services, analyse the practice and management of the Authorities delivering these services and assess whether they represent value for money.

Their foundation is the understanding that local people will get a good deal from their services only when Authorities fit services to people rather than slot people into services; when Councils learn what works well now and reshape their services to meet needs better; and when every pound spent is directed at a specific purpose and costs are kept under constant scrutiny.

The fundamental aim of Joint Review inspections is to:

- improve services for individuals

- enable Authorities to shape better services

- promote better standards and improve the management of practice

- secure better value for money

The Salford Joint Review is programmed to commence in October 2002.

# SSI Chief Inspectors Annual Report - Key Messages.

The Chief Inspectors tenth annual report highlights the following key messages:

- People using services expectations to become involved in the planning of their care and support are much more active, and not just to participate, but to be empowered. Caring for people is still important, but promoting their independence and enhancing their chances in life have become equally important.

- Last year it was reported that councils responsible for social services were working in constructive partnership with health services and other services.  However, performance monitoring shows that progress is slow in many areas of service delivery. A step change is necessary if service users are to experience tangible changes in service choice and quality overall.  There are some significant obstacles to improvement: recruitment and retention of appropriately qualified staff being the most serious.

- Choices for service users are, however, still limited by the shape of existing service models. This is evident in both children’s and older people’s services. In children’s services traditional approaches to both foster and residential care need to be challenged to ensure better quality responses to children in need. For older people, whilst there is an encouraging increase in intensive home care services, intermediate care services have still to make an impact. There is slow improvement in unnecessary hospital admissions.

- For many service users ease of access to services is still very variable. Eligibility criteria are complex and not always transparent. Service users influence in decision-making and the planning of services could also be improved.

- All services are still insensitive to the needs of many black and ethnic minority service users. Whereas many strong policies exist, implementation is weak. Urgent attention needs to be given to improving performance in these areas.

Integrated Services.

- Across the board, aspects of good inter-agency working – in strategic planning and shared vision, effective joint funding and commissioning, and good working relationships – appear as the most frequent basis for success. While progress in this respect is happening, with examples across the country of excellent and imaginative joint services, it is still patchy.

Culture.

- Inspection and review continually demonstrate that employers who have a good record in staff management are also those who deliver the best outcome for people who use the services. Inspections show that retention strategies, good supervision, professional development and appraisal all contribute to helping staff to feel confident and supported.

- Current performance quality is widely variable, but the capacity for improvement is growing. Councils find the scale of the change agenda very stretching but improvements are beginning to show through. Most councils see the development of better performance management as a priority. However, quality assurance practices are still weak.

Section	3

Understanding the Environment

Internal Environment.

Local Policy Agenda.

# Salford Community Plan Priorities.

Salford published its first Community Plan in April 2000.  It represents a community strategy for the future of Salford, setting out the main actions that the City needs to take to meet the challenges of the next five years. It has been produced by the Salford Partnership on behalf of the people living and working in our City and is a tool for partners delivering services across the City.

The Community & Social Services Directorate has a key role to play in delivering the Council's Community Plan and its 6 pledges.  It does this by improving the life chances and promoting the independence of children, young people, adults and communities in Salford.  It also delivers locally the Government's objectives for personal social services.

In undertaking this work, the Directorate employs 1942 people, has a gross budget of £90 million and over 300 contracts with independent providers.

Community Plan Themes

- A Healthy City

- A Safe City

- A Learning and Creative City

- A City where Children and Young People are valued

- An inclusive City with Stronger Communities

- An Economically Prosperous City

- A City that is Good to Live in

6 Pledges

- Better Education for All

- Quality Homes for All

- A Clean and Healthy City

- A Safer Salford

- Stronger Communities

- Supporting Young People

Government Objectives

- Actively promoting the independence of adults and children.

- Improving the protection of vulnerable children and adults.

- Raising standards of care across all service areas and providers.

- Developing and enhancing services/partnerships with Health partners, the voluntary, community and independent sectors.

- Reducing and preventing social exclusion of vulnerable people and groups by cutting levels of inequality and poor health

Community & Social Services Service Plan.

The Service Plan will provide a picture of how the Directorate has performed during 2001/2 and outline the objectives for the coming year.

The Plan will be supported by a Service Planning Framework (see Section 10 Delivering Change) with Commissioning Plans and Annual Service/Performance Plans, commencing in April 2002 and continuing throughout the year.

We are committed to:

- working in partnership with other statutory services and the voluntary and private sectors to develop joint or complementary services which improve standards across Community & Social Care services

- involving users, carers and local people in the planning, development, commissioning and review of services

- supporting local groups and local communities to enable them to enhance their quality of life and to enable local citizens to be involved in decisions that affect their lives

- developing needs-led services that are sensitive and responsive to the requirements of service users and carers, promoting independence wherever possible

- providing information that is accessible to all through a range of different formats and languages

- implementing a performance culture led by a robust business planning framework located within the City Council's Corporate Planning and Performance Management Model

- robust annual budget planning supported by improved financial and other management information systems

- developing and implementing a workforce planning strategy incorporating recruitment and retention policies, ensuring that staff are appropriately trained and supported

- implementing new information and communication technologies to improve services in partnership with all linked agencies.

Health Improvement Programme (HImp).

The overall aim of agencies within Salford who are concerned to improve health are to:

- improve the health of the whole population as measured by increase in life expectancy and the number of years people spend free from illness or disability

- improve the health of the worst off and narrow the health gap as measured  by reductions in the difference between the worst and best off areas

In order to tackle these overall aims, all agencies will continue to work together  to tackle the root causes of ill health and also provide access to high quality health and social care services.

All agencies with an interest in these objectives will take advantage of the additional flexibilities offered by the Health Act 1999 to jointly commission services and pool budgets, to continue to improve services.

Partnerships at the Local level.

Salford has a strong tradition of partnership working as evidenced by our Community Plan and Community Action Plans from the 9 Community Committee areas.

Securing innovation and enabling developments, delivering quality services        to the people of Salford, ensuring choice, fair access and equity, is dependent   upon Community & Social Services working in partnership with the statutory, voluntary and independent sectors.

The Directorate is the lead directorate for the key themes: 'A Healthy City',         'A City Where Children and Young People are Valued' and 'An Inclusive City with Stronger Communities'. The partnerships responsible for these themes include  the: Joint Commissioning Forum, Children's Services Planning Forum and the Social Inclusion Forum.

A number of key partnerships are currently in place and these will be further developed to facilitate and enhance the modernisation process. From a very    wide range of networks and relationships the Directorate is primarily involved     in the following:

## Health

For many years the Directorate was a key partner in the Joint Commissioning Forum, a group comprising representatives from Social Services and other Council Directorates, the Health Authority, Primary Care Groups and Hospital Trusts. This Forum was disbanded only in late 2001 with the inception and evolution of the Primary Care Trust. The Directorate is now represented on the Board of the Primary Care Trust and quarterly joint meetings of senior managers of both organisations take place.

Partnership arrangements have been further developed using new Health Act flexibilities.  For example, our Community Occupational Therapy Team, which has been in place for many years, is moving towards formal pooled budget arrangements. We also now have a new joint Learning Difficulties Service, which will also be developing pooled budgets within the forthcoming year.

Partnership working is evidenced in many other areas. The Directorate is represented on and leads some of the following:

- Local Modernisation Review Board

- Integrated Care – Management Board

- Local Implementation Strategy (LIS) Board

- Local Capacity Planning Group (LCPG)

- Drugs and Alcohol Action Team (DAT)

- Salford Health Improvement for Tomorrow (SHIFT) Project

- Local Improvement Finance Trust (LIFT) Board

- Service and Financial Framework (SAFF) Board

- Children’s Services Planning Forum

- Caldicott Steering Committee

- Teenage Sexual Health Strategy Project

- Children’s District Health Project

- Older People's Development Board

- Partnership Board for Learning Difficulties

- Local Implementation Team for Mental Health    					Mental Health Forum

- Local Implementation Team Welfare to Work

- Supporting People, etc.

Other joint areas of work include: Head of Joint Service appointed in Learning Difficulties (under a Section 31 application), the Elderly People's Integrated Care in Salford  (EPICS) project, Joint Team to manage Special Needs Housing Services (Adaptations), Neuro Rehabilitation Services Project, plans for Drugs Action Team Section 31 application etc.

For services to people with learning difficulties there is a plan to have a jointly managed community nurse/social work team by the end of 2002.  It is also planned that Supported Tenancies in health will be managed within the Social Services structure by April 2003.

In addition, the Directorate works closely with both Health and Housing Services in the implementation of the 'Better Care, Higher Standards' (BCHS) charter. This work is directed through the multi agency BCHS Steering Group.

Children’s Services.

Other partnership working within Children’s Services includes:

- Area Child Protection Committee

- Children’s Fund

- Early Years and Childcare

- Home Start

- Sure Start

There are also a range of partnership arrangements with:

Education & Leisure Directorate

Housing Directorate

Barnardos [including a Childhood Disability Team]

National Children’s Homes (NCH) [including an Aftercare Team, Family						 	Suppprt Services, Leaving Care Service etc]

Spurgeon’s

# Implementing Best Value.

Best Value places a duty on Social Services to continually improve the quality, efficiency and effectiveness of services for the public. Best Value means giving the best possible service at an affordable cost. The Best Value Performance Plan contains an overall assessment of the progress the service has been making against the targets it has set for itself. It highlights the key areas in which we want to make further improvements. The Plan sets out information to help the public judge how well we are performing.

Social Services will be expected to achieve Best Value by:

- continually improving services

- setting out performance measures and reporting results

- demonstrating the quality of services, including comparisons with other Metropolitan and service organisations

- carrying out Best Value Reviews of all our services

During 2000/01 Community & Social Services has completed the Best Value Review of Support at Home to Older People (see Section 6 for details). In addition, reviews of Procurement and Office Accommodation were also supported.

The Best Value Review programme for 2002/03 includes reviews on:

- Transport

- Support at Home to people with Disabilities

- Community Engagement

- Children’s Residential and Associated Care

The Performance Assessment Framework (PAF).

In managing a complex business environment under rapidly developing social policy and modernisation programme in both the Social Care and Health environments, the focus on quality and performance management/evaluation has been, and will continue to be, pronounced.

The PAF has provided valuable information concerning current levels of performance, and it has contributed to our understanding of where further improvements across service areas are required. We are committed to continually improving our performance and we have taken steps to introduce quantitative and qualitative monitoring but need to continue to do more.

How Are We Doing?

Community & Social Services performance is measured by the PAF data, an annual review by the SSI, specific inspections and thematic reviews by the SSI.

In 2001 the Secretary of State for Health announced that Salford Social Services was one of the best 15 performing Authorities, based on the Performance Assessment Framework rating over 3 years.

The data revealed that 35 indicators have been very good, good or acceptable; 11 indicators raise questions about performance; and in respect of 2 indicators, urgent investigations were necessary to improve performance (see Appendix 2 for details of Best Value Performance Indicators and PAF Indicator ratings).

For example:

AI	Stability of placements of looked after children

(Very Good)

C31	Adults with Mental Health problems helped to

live at home

B17	Unit cost of Home Care for adults and older people

C22	Young children looked after in foster placements or

placed for adoption					(Acceptable)

C23	Adoptions of looked after children

C26	Admissions of supported residents aged over 65

residential/nursing care

(Investigate)

C27	Admissions of supported residents aged 18-64 to		residential/nursing care

External inspection and review.

Of services have revealed real progress including:

- The autumn assessment for mental health, conducted by the SSI and Regional Executive of NHS, concluded that we were making good progress in delivering the National Service Framework in Salford in some areas, notably establishing an assertive outreach service, involvement of users and carers through the Mental Health Forum and in having a diverse range of social care providers.

They indicated that we need to do more work on health and social care integration, and on improving our services to people from ethnic minorities.

The key findings of the children's inspection conducted by the SSI, which took place during the autumn, included:

- Inspectors commented on the positive attitude and enthusiasm they found amongst staff, this not withstanding the pressure of work they saw.

- Inspectors noted the high threshold for social work involvement and the consequent uniformly high complexity of cases being handled.  Staff felt they had to be totally committed to everyday practice and did not get much time to be involved in development.  Even principal managers were heavily involved in day-to-day service delivery.  Nevertheless, inspectors found that morale amongst staff was holding up.

- Inspectors found an interest amongst staff in finding imaginative ways to deliver services and rise to the challenge of the volume and complexity of the work.

- They indicated we needed to do more work on integration of services to children with disabilities

- Inspectors also expect us to complete the implementation of the National Assessment Framework

We are working hard to maintain our level of performance and also focusing on areas for improvement (see Appendix 3 for a list of the Action Plans for the above mentioned indicators).

2002/3 is an important year for Community & Social Services in Salford as it is the year that the 5 yearly Joint Review will be carried out by the Social Services Inspectorate and Audit Commission.  The Joint Review will cover how Salford organises and delivers services to meet the needs of vulnerable people.

### Budget/Finance Issues.

During the course of 2001/02, the Community & Social Services budget   continued to experience very significant pressures and these pressures are expected to continue into the foreseeable future.

We are, therefore, working within very tight budget limitations and all of our activity is being examined with a view to cost effectiveness and Best Value principles.  For budget details see Section 9.

### Human Resources.

In order to deliver the considerable agenda placed on the Directorate, it is recognised and acknowledged that it is necessary to:

- achieve and maintain motivated and diverse workforce with the       right skills, knowledge and attitude to deliver quality services;

- have a workforce which is equipped to deliver the modernisation agenda for the Council and Government

The purpose of the Human Resources (HR) strategy is to provide a framework of the principles, which support the Directorate’s people management arrangements and to guide the HR planning process.

The objectives of the Strategy are to:

- meet the current and future skills needs of the Authority by effectively managing the recruitment, retention, training and development of all employees

- support and encourage equal opportunities in employment and promote diversity in the workplace by developing policies, guidelines and practice that meet legal requirements, promote work-life balance, and encourage applications from all sections of the community

- maximise the employment opportunities for local people through positive action initiatives

- facilitate the development of the organisation to keep pace with change through review of structures, processes and skills, through training and development, and through innovation and imagination

- maintain stable employee relations through negotiation and consultation with the recognised trade unions

- review, amend and develop Personnel policies and procedures, to ensure they are aligned with service requirements, involve users and carers where appropriate and are best practice as benchmarked against comparable organisations

- promote a work culture which is receptive to change, promotes continuous improvement and is responsive to the needs of the organisation and the community

- achieve and maintain a safe and healthy working environment for all.

Section	4

Key Service Objectives.

The following key service objectives, together with targets are designed to measure the Directorate's achievements during the year and are set out under the City Council's pledges and priorities and linked to Government priorities.

| 1 | Better Education for All |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | - To ensure that children looked after gain maximum life chance benefits from educational opportunities. | C | - The proportion of those young people leaving care aged 16 or over with at least 1 GCSE at Grades A*-G or at GNVQ - target 65% - The proportion of young people leaving care with 5 GCSEs at Grades A-C - target 9%. (Public Service Agreement (PSA) Indicator) | A2 | 50 |
| Educational attainment is an important step for young people to escape from social deprivation. These indicators measure how many looked after children are getting GCSEs. Performance is dependent on schooling and education and support but also on good planning and the provision of stability for children. |  |  |  |  |  |

* C       -   Children/Young People and Families

A       -   Adults

Com  -   Community Services

| 2 | Quality Homes for All |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | - To ensure that young people leaving care, as they enter adulthood, are not isolated and participate socially and economically as 'citizens'. - To enable adults assessed as needing social care support to live as safe, full and as normal a life as possible, in their own home wherever possible | C A A A A A A A A | The percentage of those people who were looked after on 1 April in their 17th year (aged 16), who were known to have suitable accommodation - target 75%. To use supporting people policy to support more service users in their own homes to avoid admissions into residential and nursing care, in particular to: - Learning Disability - develop supported tenancies for 78 people currently in residential care in the independent sector. To review with NHS the best management arrangements for supported tenancies. - Physical Disabilities - to provide 4 supported tenancies at Pendle Way for people previously in Willow Bank residential home. To develop with Housing Associations and Housing Directorate additional adapted supported tenancy units in the next 2 years. - As part of integrated housing, adaptation services to support 40 people in having major adaptations, or moving to more suitable property. - People with mental health problems - to develop additional 6 units of supported tenancies. - For older people - to work with Housing Directorate and Housing Associations to develop 2 more extra care sheltered housing units. - To work with NHS to repatriate/ return to Salford 17 people with learning disability/mental health needs, currently residing out of the area. - To review 242 people with preserved rights over 2002/3 to establish if their needs are best met in their current living environment. |  |  |

| 3 | A Clean and Healthy City |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | - To ensure that children in need have the opportunity to enjoy a standard of health and development as good as that which can be expected for the general population, having regard to any diagnosed disability or health condition. - To increase timeliness of assessment for community equipment services through the single assessment process, use of call centre, and efficiency in delivery - To introduce a single assessment process for older people in 2002 to ensure both health and social care needs are addressed. - To work with the NHS, users, carers and other agencies to avoid unnecessary admission to hospital and inappropriate placement on leaving hospital; and to maximise the health status and thus independence of those they support. - Develop an intermediate care strategy and develop these services to ensure that people are not unnecessarily admitted to, or remain in hospital or long term care, but focus on rehabilitation and promote independence. - To enable informal carers to care or continue to care for as long as they and the service user wish. | C A A A A A A A A A A A | - Of children looked after continuously for at least 12 months, the average of the percentages who had routine immunisations up to date, had their health checked by a dentist and had an annual health assessment during the previous 12 months - target 60% - Assessments for those requiring equipment or adaptations will be undertaken within 4 months of referral date, according to urgency of need. - To increase domiciliary care services to those in greatest need by increasing the number of households receiving intensive home care - target 16 per 1,000 - To reduce dependency on Residential/Nursing home provision by improving percentage of intensive home care as proportion of intensive home and residential care - target 26% - Through the implementation of the new Fair Access to Care Services eligibility criteria to ensure targeting of services to promote independence. New criteria to be in place 2002. - Through the implementation of revised Continuing Health Care Criteria in 2002 to ensure the NHS target those with long- term health needs. - 300 people to use intermediate care beds in 2002/3. - Reduction in growth in emergency admissions to 2% change. - Reduction in the number of delayed hospital discharges to maximum of 25. - Reduction in number of admissions to long-term care supported by local authority to 200 per thousand people over 65. - To use the powers under the Health Act to move towards integrated services in the areas of: Learning Disabilities - integrated teams start April 2002 Mental Health - Assertive Outreach team April 2002 - Community Mental Health Teams start April 2002 Intermediate Care - Summer 2002 Community Equipment Services - 2003 - To offer carers assessments and services to carers on request and as part of a long term plan - 35% of carers to receive assessment. | C19 D38 C28 B11 A5 D41 C26 D42 |  |

| 4 | A Safer Salford |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | - To ensure that children are protected from emotional, physical and sexual abuse and neglect (significant harm). - Protect communities from drug related, anti-social and criminal behaviour. | C C C A | - The proportion of children registered during the year on the child protection register who had been previously registered - target 9% - The proportion of children de-registered from the child protection register during the year ending 31 March who have been on the register for at least 2 years - target 5% - The percentage of child protection register cases which should have been reviewed, that were reviewed - target 100% - Through channelling offenders to treatment via Arrest Referral Scheme. Target: Screen 260 people; Assess 110 people; Refer 96 people to treatment services. | A3 C21 C20 | 162 |

| 5 | Stronger Communities |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | - To develop, implement and monitor a Community Action Plan for each of the 9 Community Committee Areas - To reduce crime and social exclusion of children and young people at risk - To more effectively target funding in community and voluntary sectors in line with Community Plan Themes and Pledges. To actively involve users and carers in planning services and in tailoring individual packages of care. - To update all community care information and make available to users, carers and the community to ensure assessments are targeted at those in need of services. - To ensure the needs of adults from ethnic minority communities who need services are recognised and addressed through the provision of appropriate services. - To review care packages and ensure service outcomes are in line with objectives and continue to promote independence. - To ensure service users and carers know what their care needs have been assessed as and what services have been arranged to meet these needs. - In order to extend people's independence Ensure excellent employment prospects and high job opportunities and to continue to raise aspirations and achievement by providing learning and development opportunities of the highest quality. - Through the establishment of Welfare to Work inter-agency implementation team, who will implement the Action Plan of the Welfare to Work Joint Investment Plan. | Com Com Com Com Com Com Com Com Com A A A A A A A A A | - To produce written draft by July 2002 - To have Community Committee approval by August 2002 - To have Cabinet approval by September 2002 - To develop and implement a model of local working with children and young people which links the Crime Reduction Strategy, Children's Plan and the Capacity Releasing Strategy - Joint Report to Crime and Disorder Partnership Executive, Children's Services Planning Forum, YOT Steering Group and Social Inclusion Task Group by April 2002 - Pilot model in 2 Community Committee Areas April - December 2002 - Grants database to be completed. - Review of effectiveness/ appropriateness of current pattern of investment. - Implement the draft Local Compact across the Local Strategic Partnership by March 2003. - To develop a code of practice with organisations on funding policy which will include the promotion of long term multi year funding and the process of early notification of funding arrangements by March 2003. - To develop with the Sector a code of good practice on consultations, policy approval and implementation by March 2003. - Have a single point of contact for funders and enquiries by March 2003. - To assess 150 per thousand older people. 65% of all assessments to lead to provision of service. - Users who said that matters relating to race, culture or religion were noted - target 58%. - Ethnicity of adults and older people receiving assessment - target proportion 2.66 - Ethnicity of adults and older people receiving services following an assessment - target proportion 1.29 - 90% of users to be reviewed within the year. - 90% of users to receive copies of the care plan - To ensure the timely delivery of services by increasing to 86% the number of people who said they got help quickly. - To increase the number of users on the Direct Payment Scheme to 30. - For 50 people within the learning disability services who have severe or moderate learning disabilities to move into employment or move closer to the world of work by March 2003. | E49 E50 E46 E47 E48 D40 D39 D36 |  |

| 6 | Supporting Young People |  |  | Indicators |  |
| --- | --- | --- | --- | --- | --- |
|  | Service or Project Objective | Service Area* | Target | PAF | BV |
|  | To ensure that children are securely attached to carers capable of providing safe and effective care for the duration of childhood - To reduce the number of changes of placements for looked after children. - To maximise the contribution adoption can make to providing permanent families for children in appropriate places. - To maximise the period children remain looked after before they are placed in long-term foster care. - To ensure the needs of children and families from black and other ethnic minority communities are recognised and addressed through the provision of appropriate services. - To ensure that young people leaving care, as they enter adulthood, are not isolated and participate socially and economically as citizens. - To ensure that children with specific social needs arising out of disability or a health condition are living in families or other appropriate settings in the community where their assessed needs are adequately met and reviewed. | C C C C C C | - The percentage of children looked after at 31 March with three or more placements during the year - target 13% - The number of looked after children adopted during a year as a % of children looked after at year ending 31 March - target 5% - Of children looked after at 31 March who have been looked after continuously for more than 4 years, the proportion who have been in their foster placements for at least 2 years - target 55% - The proportion of children in need from ethnic minorities, divided by the proportion of children in the local population that are from ethnic minorities - target ratio of 3 - Proportion of young people looked after on 1 April aged 16, who are engaged in education, training or employment at age 19 - target 45% - The number of disabled children looked after during the year under an agreed series of short term placements as a percentage of all children looked after at any time during the year - target 17.9% | A1 C23 D35 E45 A4 | 49 163 161 |

Section	5

Community Priorities.

An analysis of the 9 Community Action Plans has identified the following priorities related to the Community Plan themes:

| 1. | A Healthy City |  |
| --- | --- | --- |
|  | Service or Project Objective | Target |
|  | - Contributing to the development of the NHS Plan within the City. - To address health inequalities arising from food and fuel poverty. | - Ensuring full community participation in Salford Health Investment for Tomorrow (SHIFT) and Local Improvement Finance Trust (LIFT) - Consultation with 9 Community Committees to be undertaken in 2002/3. - 6 special consultation events planned for 2002/3. - Community representation on appropriate project management bodies - when project work is implemented. - To develop joint strategies to combat food and fuel poverty. - Strategies to be considered by Local Strategic Partnership by March 2003. |
| 2. | A Safe City |  |
|  | Service or Project Objective | Target |
|  | - Addressing nuisance caused by youths | - To contribute to the implementation of the Youth Strategy. |
| 3. | A Learning & Creative City |  |
|  | Service or Project Objective | Target |
|  | - Delivering appropriate training to community activists | - To deliver 3 training events for community activists during 2002/3. |

| 4. | A City where Children and Young People are Valued |  |
| --- | --- | --- |
|  | Service or Project Objective | Target |
|  | - To ensure that children and young people leaving care, as they enter adulthood, are not isolated and participate socially and economically as 'citizens'. | - Engaging children and young people creatively in each Community Committee Area - 9 Projects to be implemented across Community Committee areas by March 2003. |
| 5. | An Inclusive City with Stronger Communities |  |
|  | Service or Project Objective | Target |
|  | - Develop Business Plans for 11 Community Centres, which improve representativeness and representation on Community Committees | - Business Plans to be in place by March 2003. |
| 6. | An Economically Prosperous City |  |
|  | Service or Project Objective | Target |
|  | - To promote increased take-up of Welfare Benefits for older people and people with disabilities. | - Extra benefits secured for people through specific take-up work: target gain £450,000 in 2002/3. |

Section	6

Outcome of Best Value Reviews.

The following are the key elements from the Improvement Plan for the completed Best Value Reviews:

| 1. | Best Value Review of Support for Older People at Home |  |
| --- | --- | --- |
|  | Service or Project Objective | Target |
|  | Terms of Reference for Review To review the following services - Home Care, Day Care, Meals at Home, Sheltered Housing, Very Sheltered Housing, Mobile Warden/Community Alarm Service. Key Points from the Theme Consultation - The Review has examined and been party to a wide range of consultation exercises. - Consultation has occurred with a variety of stakeholders, with a strong focus on the views of service users. - The Review has identified a positive mix of regular ongoing consultation systems and, more specific, topic-led surveys. - It has also identified examples of 'open' consultation where views have determined policy, and also consultation on proposals. - The consultation exercises have led to identified changes in the services provided. - Consultation is an integral part of service provision. Key Outcomes from the Theme Consultation - There has been steadily increasing involvement of users and carers in the development monitoring of services. - A multi-agency Development Board for Older People's Services has been established including service user and carer representation to take forward the views expressed in the Strategy for Services for Older People. - The City Council has acknowledged that there needs to be further clarity about the future of the in-house home care service. Recommendations - Work needs to be undertaken in each of the service areas to review and extend current (regional and national) benchmarking systems where they exist, and in those areas where they do not yet exist, to undertake work to develop these. - Work needs to be undertaken to develop local performance indicators, in consultation with service users. Systems for monitoring and reporting on these performance indicators need to be developed. - That individual service areas review their current systems for service user and purchaser consultation. - That the consultation groups of users, carers and stakeholders brought together in the development of the Strategy for Services of Older People, be reconvened on a more regular basis. - The Community & Social Services Directorate needs to set a course for the in-house home care service to follow. This will need decisions to be taken to the focus of the service, coverage, availability, etc. - Action needs to be taken to develop a block contract with an independent sector provider for home care in the Irlam and Broughton areas, either on the basis of a tendering process or through a partnership arrangement. - The Community & Social Services Directorate must ensure that progress is made on its aim to focus day care provision on the most vulnerable. Once this is achieved, the Directorate needs to review the level of demand and supply of day care places in the City, in terms of centres and current days of opening. - Criteria should be developed in respect of the provision of frozen as opposed to hot meals. - Frozen meals should be made available across the whole City. - Detailed proposals should be drawn up in respect of the provision of the future hot meals service, with a timetable for implementation and targets/milestones. | - Re-examine data collected in respect of regional and national benchmarking systems by 31 March 2002. - Agree and implement benchmarking systems by 30 June 2002 in respect of: - Home Care Services - Day Care Services - Residential Services - Identify systems to be applied to ensure service users are involved in determining benchmarking systems. Link this to Better Care High Standards Charter by 31 March 2002. - Identify and review how current systems for consultation with service users, carers and purchasers is undertaken by 31 March 2002. - Identify and implement regular consultation sessions by 1 June 2002. - Set up programme of meetings with those groups previously brought together to develop strategy for services by 31 March 2002. - Develop a Commissioning Strategy for Home Care Services and agree a future direction for in-house Home Care service by commissioning a consultant to undertake specific work to be completed by 30 June 2002. - Prepare service specification and establish route to be taken by 30 June 2002. - Review present service users and day care services to ensure that they meet eligibility criteria by March 2002. - Examine waiting lists and apply eligibility criteria by March 2002. - Consult with existing users as to timeliness of service availability by 31 March 2002. - Measure present usage of Brierley House at weekends by 31 March 2002. - Review implications of Homes to Trust on day services for people with Mental Health needs by 31 March 2002. - Agree eligibility criteria for provision of frozen meals/hot meals in consultation with service users by 30 June 2002. - Implement criteria and availability of frozen meals across the City by 30 June 2002 - Determine resources required to convert existing users from hot meals to frozen by 31 July 2002. - Develop in-house hot meals service linking to welfare to work for people with disabilities strategy by 31 July 2002. |

In addition, Community & Social Services also contributed to the Best Value Reviews of:

- Procurement

- Office Accommodation

Section	7

Continuous Improvement.

The following are specific improvements arising from the application of Performance & Customer Care and Support Services.

| Pledge5. | Stronger Communities |  |
| --- | --- | --- |
|  | Service or Project Objective | Target |
|  | To continue to increase the involvement of users and carers and local people. To provide better communication and information to the public and staff about services in Salford. | - Users to participate in user reviews within Day Centres. - Ongoing development of Directorate internet site |
| Pledge6. | Support for Young People |  |
|  | Service or Project Objective | Target |
|  | - To ensure the rights and views of children and young people are heard in the development and delivery of children's social services. | - Publication and dissemination of Children & Young Persons Rights Strategy - Implementation of a training programme for staff and children and young people |
|  | Supporting the Pledges: Measuring Efficiency & Statutory Compliance |  |
|  | Service or Project Objective | Target |
|  | To ensure that resources are used efficiently and effectively for the benefit of service users and carers. | - To provide front line managers with on-line, real time access to financial information to assist with budgetary control - To train all front line managers in the use of the Authority's financial SAP systems between March 2002 and March 2003. - Development of devolved budgets during 2002/3. |

|  | Supporting the Pledges: Measuring Efficiency & Statutory Compliance |  |
| --- | --- | --- |
|  | Service or Project Objective | Target |
|  |  | - To agree, develop and implement standard reports from the CareFirst client information system. - To establish a timetable for reports. - To implement further modules of CareFirst by March 2003. - Implementation of direct Social Worker input to CareFirst: Adults and Older People Social Workers by March 2002 Children's Social Workers pilot to be completed and evaluated by December 2002 - Ongoing development of Internet/ Intranet access for staff - target completion by March 2003. - Liaison with Health partners through LIS to identify practical steps for achieving connection to NHS net system - formal report by December 2002. - Identification of all services, which could be enabled by e-government to meet Department for Transport London and Regions (DTLR) targets. |
|  | To have a workforce, which is, equipped to deliver the modernisation agenda for the Council and Government. | - Training Plan will continue to focus on the modernisation agenda for Community & Social Services Directorate and achievement of national training targets for services and prepare staff for registration - Achievement targets by 31.3.03 (Figures include some staff in independent sector) 15 staff - PQ1 7 staff - PQ Accred. Child Care Award 5 Foster Carers - NVQ3 5 staff - NVQ3 Promoting Independence 14 staff - NVQ4 - Management 7 staff - NVQ4 - Care 20 staff - NVQ3 - Working with Children and Young People 18 staff - NVQ2 – Care |
|  | To have a workforce which is equipped to deliver the modernisation agenda for the Council and Government (continued) Achieve and maintain a motivated and diverse workforce with the right skills, knowledge and attitude to deliver quality services. | - Involvement of users and carers in training - Increase number of training programmes that users/carers are directly involved in. - Address recruitment difficulties for certain groups of staff including qualified social workers, care staff, etc. - Continue being a primary partner with the Salford DipSW programme. 30 practice placement to be offered - Secure Department of Health funding and support 4 students on part-time route to DipSW - Implement a recruitment strategy to run throughout 2002 - Development of multi-agency training opportunities - Establishment of management development programme jointly with NHS trusts in Salford. - Implement a Human Resource Strategy to provide regular workforce statistics and plan accordingly - by 31.3.03 - Implement the Staff Development and Appraisal Policy by 31.3.03 |

Section	8

Consultation.

Consultation that is planned with users, carers and partners includes:

|  | Area of Consultation | Timescale | Lead Person |  |  |
| --- | --- | --- | --- | --- | --- |
| 1. | Better Care Higher Standards: Local Charter - Survey | July 2002 | Lyndon Jones/ Deborah Siddique |  |  |
| 2. | Personal Social Services Survey | January/February 2002 | Lyndon Jones/ Deborah Siddique |  |  |
| 3. | Carers Special Grant Plan: 2002/3 Workshop | April 2002 | Lyndon Jones/ Grier Thompson |  |  |
| 4. | Children & Young Persons Rights Strategy | February - July 2002 | Liz Cameron |  |  |
| 5. | User/Carer Survey: SSI/Audit Commission Joint Review | September 2002 | Alan Bunting/ Deborah Siddique |  |  |
| 6. | Ethnic Minorities questionnaire: to identify why older people with disabilities from the Indian sub-Continent do not use hospital and Social Services | August 2002 | Zahid Siddique |  |  |
| 7. | Charging Policy: To revise non-residential services charging policy in line with revisions outlined in Government guidance on 'Fairer Charging'. | February - September 2002 | Keith Darragh/ Julia Clark |  |  |
| 8. | Homes to Trust – redesign proposals. | April – September 2002 |  | Eve Murphy/ Julia Clark |  |

Section	9

Resources.

The Directorate has made the following key resource allocations within its decision-making powers:

Section	10

Delivering Change.

To meet the requirements of a rapidly developing modernising agenda, the service has a range of Plans in place. These are defined under the headings of:

- Key Joint and ‘Cross Cutting’ Plans

- Social Services Plans

- Commissioning Plans

- Annual Service/Performance Review Plans

### Key Joint and ‘Cross Cutting’ Plans

### Salford Community Plan

Community Action Plans (from the 9 Community Committee areas)

Social Inclusion Plan

Crime and Disorder Plan

Youth Justice Plan

Children’s Fund Plan

Area Child Protection Committee business plan

Early Years and Childcare Development Plan

Sure Start Development Plan

Welfare to Work Strategy

Child and Adolescent Mental Health Strategy

Teenage Sexual Health Strategy

Strategic Plan and Best Value Performance Plan

Health Improvement Plan

Joint Investment Plan for Older People

    - Rehabilitation Strategy

    - Supporting People Strategy

    - Prevention Strategy

    - Palliative Care Strategy

    - Carers Strategy

Joint Investment Plan Learning Difficulties

Joint Investment Plan for Mental Health

Joint Investment Plan for Intermediate Care

Drugs Action Team Strategy

Children’s Services Plan

Quality Protects (Management Action Plan [MAP])

Community and Social Services Planning.

The Directorate will maintain and develop a coherent and visible business

planning framework. This will provide a structured and focused approach to the

setting and monitoring of objectives, priorities and targets at directorate and

individual service levels.

Key strategies and plans will be linked together in order to build the "big picture" and will take account of cross cutting issues within the Directorate, other agencies and the Council’s corporate performance improvement plans.
A ‘whole systems approach’ will be adopted to achieve the required integration over successive business planning cycles.

Business plans will provide focus and direction for the Directorate as whole and individual service units and show a comprehensive picture of activities and priorities. They will constitute a written statement of how resources will be used and developed to meet the changing needs of our communities and thereby improve service provision.

The Service Plan is the Directorate's Strategic Plan and will be driven by:

- the Directorate's 3 Commissioning Plans:  Personal Social Services 	(sub-divided between Adults and Children & Families services) and 	Community Affairs

- National Priorities (Central Government Policy)

- Local Priorities (local needs)

The Joint Investment Plans (JIP’s), the Quality Protects Map, the 9 Community Committee Plans (Community Strategy) etc will link the external (National) and internal (Local) priorities.  For example, common themes and priorities can be pulled out of the Community Committee Plans and JIPs related to the national agenda.

The Directorate’s framework for business planning is detailed below:

Directorate

Service Plan

Strategic Plan

Community

# Plans

Children’s

Commissioning

Strategy

Community

Affairs

Commissioning

Strategy

Adults

Commissioning

Strategy

Commissioning

Plans

Grant and Specific Plans

Grant and Specific Plans

Grant and Specific Plans

Annual Service/Performance Review Plans

Service

Operational Unit

Operational

Unit

Operational

Unit

Operational

Unit

Operational

Unit

Plans

Best Value Reviews and Action Plans

Directorate Service Plan

An overarching strategic plan reviewed annually setting the overall direction, including priorities between divisions, providing specific targets for the Directorate’s service management and delivery within a Best Value framework.

The Directorate's Service Plan will need to, increasingly:

- be focused on the Performance Assessment agenda (PAF, Best Value, indicators etc)

- be supported by clear "data sets" - as a Directorate we need to be clear what data we require on an ongoing (e.g. monthly) basis and for which returns and plans

- the Principal Officer (Strategic Planning) is responsible for leading the service planning process and will link closely with the:

- Principal Officer (Management Information and Performance)

- Principal Officer (Systems and Support)

- Support and Operational Divisions through the Assistant Directors

- identify an action plan with specific outputs, outcomes and targets

- be supported by an ongoing commissioning and budget planning process

Commissioning Strategies

Annual plans setting out the Directorate’s service commissioning intentions for realising the vision of the Service Plan towards meeting identified social care needs in line with national/local priorities and service quality standards, informed by grant and other specific joint inter-agency plans. Covering:

Adults

Children and Families

Community Affairs

Annual Service/Performance Review Plans

Annual action-orientated plans for delivering services within the Directorate’s overall strategic plan and to review performance against objectives and targets.

Best Value Reviews

Information from Reviews will be utilised to produce detailed Action Plans for improvement.

Business Planning Cycle.

The Directorate’s business planning cycle will normally begin at the same time as the budget planning process (November) in order to ensure that strategic and financial planning activities are clearly linked.

(Annual Service and Performance Review Plans)

May/June/July

Each Division in partnership with key stakeholders to establish goals and targets for the following year, review performance and produce service action/delivery plans

(Directorate Service Plan)					                (Consultation)

January/February/March

Review of service plans and communication of strategic direction taking into account national and corporate development objectives. Preparation for implementation and action of service delivery plans

September/October

Service priorities agreed and the community consulted. Options for change need to be clearly described and fully costed. Service delivery targets drafted and resourcing requirements identified

The Directorate Planning Cycle

(Commissioning Strategies)

November/December

Commissioning strategies agreed for the following year. Any new partnership agreements prepared for approval. Initial budget/resource plans to be shared across whole system.

All plans will be produced by nominated lead managers with the involvement and support of staff responsible for implementation. Staff at all levels need to own the plans if they are to be effective tools for organisational development and progress.

The interface between individual teams, Divisions within the Directorate and external agencies will be addressed whilst the plans are being drawn up so that their content is discussed and agreed as part of a formal consultation process.

Each Annual Service/Performance Review Plan will be approved by the Directorate’s Management Group and monitored through a formal process.

Section	11

Monitoring Arrangements.

To ensure the range of Plans we have in place are delivering improvements and change; the service has introduced (or is introducing) a number of monitoring mechanisms for evaluating progress and accountability. Progress in meeting targets and objectives will be systematically monitored and reported as appropriate to involve staff, managers, Members and outside agencies as part of an overall performance management framework

These monitoring mechanisms include:

- Members

Cabinet

Scrutiny Committees

Non-Regulatory Panels

Social Services members:

- Members’ Visits (to homes/establishments)

- Complaints

- Quality Reviews for Children Looked After

- Partnerships

- Local Modernisation Review Board

- Integrated Care – Management Board

- Local Implementation Strategy (LIS) Board

- Local Capacity Planning Group (LCPG)

- Service and Financial Framework (SAFF) Board

- Children’s Services Planning Forum

- Older People's Development Board

- Partnership Board for Learning Difficulties

- Local Implementation Team for Mental Health

- Local Implementation Team Welfare to Work

- Supporting People

- Community Committees

In addition, the Directorate works closely with both Health and Housing Services in the implementation of the 'Better Care, Higher Standards' (BCHS) charter. This work is directed and monitored through the multi agency BCHS Steering Group.

- Area Child Protection Committee

- Sure Start Strategy

- Home Start Strategy

- Child and Adolescent Mental Health Strategy

- External

Social Services Inspectorate

including an annual review by the SSI, specific inspections and      thematic reviews

City Council overview of:

Best Value Performance Plan

(additional monitoring and evaluation via District Audit)

Best Value Reviews

Joint Review (5 yearly inspection by SSI and Audit Commission)

- Community and Social Services

Progress in meeting the objectives and targets within the Service Plans and Annual Service/Performance Review Plans will be systematically monitored and reported as appropriate to involve staff, managers, Members and outside agencies as part of an overall performance management framework.

The Directorate’s business planning cycle will normally begin at the same time as the budget planning process (November) in order to ensure that strategic and financial planning activities are clearly linked.

(Annual Service and Performance Review Plans)

May/June/July

Each Division in partnership with key stakeholders to establish goals and targets for the following year, review performance and produce service action/delivery plans

(Directorate Service Plan)					              (Consultation)

January/February/March

Review of service plans and communication of strategic direction taking into account national and corporate development objectives. Preparation for implementation and action of service delivery plans

September/October

Service priorities agreed and the community consulted. Options for change need to be clearly described and fully costed. Service delivery targets drafted and resourcing requirements identified

The Directorate Planning Cycle

(Commissioning Strategies)

November/December

Commissioning strategies agreed for the following year. Any new partnership agreements prepared for approval. Initial budget/resource plans to be shared across whole system.

Each Annual Service/Performance Review Plan will be approved by the Directorate’s Management Group (DMG) and monitored through a formal performance management process.

The process will also take cognisance of:

- contract monitoring information

- Best Value Review information

- budget plan and budget monitoring

- Human Resource Planning

In addition, DMG also monitors:

- selected performance indicators, on an ongoing basis

- budget performance

- modernisation programme

- service user/carer issues

- Service Managers

Management Groups

- Other Arrangements

Staff supervision

# APPENDIX 1

# NATIONAL OBJECTIVES FOR SOCIAL SERVICES

The following sets out the full objectives for social services, including the sub-objectives for children’s services.  There are no sub-objectives for adult services.  Note that objectives 8 to 11 are common for both children and adult services.  The associated PAF indicators are listed in italics in brackets after each objective or sub-objective.

Children’s Services

C1.0	To ensure that children are securely attached to carers capable of providing safe and effective care for the duration of childhood.

C1.1	To support children in need and their families in order wherever possible to prevent family breakdown and promote better life chances for the most vulnerable children. (Indicator E44).

C1.2	To reduce the number of changes of placement for children looked after.  (Indicator A1)

C1.3	To maximise the contribution adoption can make to providing permanent families for children in appropriate places. (Indicator C23).

C1.4	To minimise the period children remain looked after before they are adopted.

C1.5	To minimise the period children remain looked after before they are placed in long-term foster care. (Indicator D35).

C2.0	To ensure that children are protected from emotional, physical and sexual abuse and neglect (significant harm).

C2.1	To reduce the number of deaths of children, where abuse or neglect is a factor.

C2.2	To reduce the incidence of child abuse (significant harm).

C2.3	To reduce the incidence of repeated child abuse (significant harm). (Indicators A3, C20, C21).

C3.0	To ensure that children in need gain maximum life chance benefits from educational opportunities, health care and social care.

C3.1	To help improve the educational attainment of children in need.

C3.2	To ensure that children in need have the opportunity to enjoy a standard of health and development as good as that which can be expected for the general population, having regard to any diagnosed disability or health condition.

C3.3	To reduce the rate of offending of children in need.

C3.4	To ensure that children whose parents have specific needs arising out of disability or health conditions enjoy the same life chances as all other children in the locality.

C3.5	To improve the provision of appropriate, high quality care and treatment for children and young people with mental health problems in line with the Child and Adolescent Mental Health Services (CAMHS) objectives set out in the National Priorities Guidance.

C3.6	To help children in need from black and ethnic minority groups gain maximum life chance benefits from educational opportunities, health care and social care. (Indicator E45).

C4.0	To ensure that children looked after gain maximum life chance benefits from educational opportunities, health care and social care.

C4.1	To bring the overall performance of children looked after, for a year or more, in National Curriculum tests closer into line with local children generally. (Indicators A2, C24).

C4.2	To ensure that children looked after enjoy a standard of health and development as good as all children of the same age living in the same area. (Indicator C19)

C4.3	To reduce the offending rate of children looked after.   (Indicator C18)

C4.4	To ensure that children looked after from black and ethnic minority groups gain maximum life chance benefits from educational opportunities, health care and social care.

C5.0	To ensure that young people leaving care, as they enter adulthood, are not isolated and participate socially and economically as citizens.

C5.1	For young people who were looked after at the age of 16 to maximise the number engaged in education, training or employment at the age of 19.  (Indicator A4).

C5.2	To maximise the number of young people leaving care after their sixteenth birthday who are still in touch with Social Services, or a known and approved contact, on their 19th birthday.

C5.3	To maximise the number of young people leaving care on or after their 16th birthday who have suitable accommodation at the age of 19.

C6.0	To ensure that children with specific social needs arising out of disability or a health condition are living in families or other appropriate settings in the community where their assessed needs are adequately met and reviewed.

C6.1	To arrive at a complete picture of the numbers and circumstances of disabled children by ensuring that in each local authority the social services department, the education department and relevant health agencies share the information they hold.

C6.2	To increase the number of disabled children in receipt of family support services – including short term breaks and domiciliary services – and the number of hours of service provided in order to enable disabled children and their families to lead as ordinary a life as possible.

C6.3	To increase the number of children who use inclusive play and leisure services, including holiday play schemes, after school clubs and pre-school provision with appropriate support if necessary.

C6.4	To ensure that parents and disabled children are provided with information about services from the statutory and voluntary sectors on an inter-agency basis.

C7.0	To ensure that referral and assessment processes discriminate effectively between different types and levels of need and produce a timely service response.

C7.1	To ensure close and co-operative working with all relevant local agencies by developing locally agreed referral and assessment protocols and procedures.

C7.2	To reduce the proportion of repeat referrals within a 12 month period, where reason for the re-referral indicates that the response to the original referral did not appropriately address the child’s needs.

C7.3	To complete an initial assessment and put in place case objectives, within a maximum of 7 working days of referral.

C7.4	To complete a core assessment, and put in place case objectives, within a maximum of 35 working days from the day the initial assessment was completed.

C7.5	Throughout the assessment process, to put in the service response indicated by the assessment within a timescale that meets the needs of the child.

C8.0	To actively involve users and carers in planning services and in tailoring individual packages of care; and to ensure effective mechanisms are in place to handle complaints.

C8.1	To demonstrate that the views of children and families are actively sought and used in the planning, delivery and review of services.

C8.2	To demonstrate that the satisfaction of users with services provided is increasing.

C9.0	To ensure through regulatory powers and duties that children in regulated services are protected from harm and poor care standards.

C9.1	To demonstrate that regulatory requirements are complied with.  (Indicator 25)

C.10	To ensure that social care workers are appropriately skilled, trained and qualified, and to promote the uptake of training at all levels.

C.10.1	To ensure all residential childcare workers are adequately trained for the job.

C.10.2	To ensure that childcare social workers have structured opportunities to achieve the new Post Qualifying (PQ) award in childcare.

C.11.0	To maximise the benefit to service users from the resources available, and to demonstrate the effectiveness and value for money of the care and support provided, and allow for choice and different responses for different needs and circumstances.  (Indicators B7-B10, C22).

C.11.1	To ensure that the needs of children and families from black and other ethnic minority communities are recognised and addressed through the provision of appropriate services.

Adult Services

A1.0	To promote the independence of adults assessed as needing social care support arranged by the local authority, respecting their dignity and furthering their social and economic participation.  (Indicators C29-C32, D37, E48, E50).

A2.0	To enable adults assessed as needing social care support to live as safe, full and as normal a life as possible, in their own home wherever feasible. (Indictors C26-C28, D38).

A3.0	To ensure that people of working age who have been assessed as requiring community care services, are provided with these services in ways which take account of and, as far as possible, maximise their and their carers’ capacity to take up, remain in or return to employment.

A4.0	To work with the NHS, users, carers and other agencies to avoid unnecessary admission to hospital, and inappropriate placement on leaving hospital; and to maximise the health status and thus independence of those they support.  (Indicators A5, A6, C33, D41).

A5.0	To enable informal carers to care, or continue to care, for as long as they and the service users wish.  (Indicator D42)

A6.0	To plan, commission, purchase and monitor an adequate supply of appropriate, cost-effective and safe social care provision for those eligible for local  authority support.

A7.0	To identify individuals with social care needs who are eligible for public support, to assess those needs accurately and to review care packages as necessary to ensure that they continue to be appropriate and effective.  (Indicator D39, D40, D43, E47, E49).

A8.0	To actively involve users and carers in planning services and in tailoring individual packages of care: and to ensure effective mechanisms are in place to handle complaints.  (Indicators D36, E46).

A9.0	To ensure through regulatory powers and duties that adults in regulated services are protected from harm and poor care standards.  (Indicator C34).

A10.0	To ensure that social care workers are appropriately skilled, trained and qualified, and to promote the uptake of training at all levels.

A11.0	To maximise the benefit to service users from the resources available, and to demonstrate the effectiveness and value for money of the care and support provided, and allow for choice and different responses for different needs and circumstances and to operate a charging regime which is transparent, consistent and equitable; and which maximises revenue while not providing distortions or disincentives which would affect the outcomes of care for individuals.  (Indicators B11-B17).

#### APPENDIX 2

Performance Monitoring

Performance Indicators (PAF)

The Directorate's achievements in relation to the Performance Assessment Framework are demonstrated by the Performance Indicators below.  In October 2001 the Secretary of State for Health announced that Salford Social Services was one of the 15 best performing authorities in England and Wales.  This rating is based on the Directorate's performance over the three years.  The Directorate's results in three quarters of the Performance Indicators (35 indicators) have been very good, good or acceptable: 8 very good; 12 good and 15 acceptable.  11 indicators raise questions about performance and in respect of 2 indicators, urgent investigations are necessary to improve performance.

- PERFORMANCE ASSESSMENT FRAMEWORK (PAF) PERFORMANCE INDICATORS: 2000/1

| CHILDREN’S SERVICE |  |  |  |
| --- | --- | --- | --- |
| PERFORMANCE AREA | CODE |  |  |
| National Priorities and Strategic Objectives | A1 A2 A3 A4 | # Stability of placement of children looked after (1) # Educational qualifications of children looked after (joint working) # Re-registration on the Child Protection Register Employment, education & training for care leavers (joint working) | * * * * * * * * * * * * * * |
| Cost and Efficiency | B7 B8 B9 B10 | # Children looked after in foster placements or placed for adoption # Cost of services for children looked after (2) # Unit cost of children’s residential care (2) # Unit cost of foster care | * * * * * * * * * * * * |
| Cost Effectiveness of Service Delivery and Outcomes | C18 C19 C20 C21 C22 C23 C24 C25 | # Final warnings and convictions of children looked after Health of children looked after Reviews of child protection cases # Duration on the child protection register Young children looked after in foster placements or placed for adoption Adoptions of children looked after Children looked after absent from school (joint working) Inspections of children’s homes) | * * * * * * * * * * * * * * * * * * * * * * * * * * * * |
| Quality of Services for Users and Carers | D35 | # Long term stability of children looked after | * * |
| Fair Access | E44 345 | # Relative spend on family support Ethnicity of children in need (1999/00 bands and comparators) | * * * * * |

| ## ADULTS SERVICES |  |  |  |
| --- | --- | --- | --- |
| ### PERFORMANCE AREA | ### CODE |  |  |
| ### Cost and Efficiency | ### B11 B12 B13 B14 B15 B16 B17 | Intensive home care as a proportion of intensive home and residential care Cost of intensive social care for adults and older people (2) Unit cost of residential and nursing care for older people (2) Unit cost of residential and nursing care for adults with learning disabilities (2) Unit cost of residential and nursing care for adults with mental illness (2) Unit cost of residential and nursing care for adults with physical disabilities (2) Unit cost of home care for adults and older people (2) | * * * * * * * * * * * * * * * * * * * * * * * |
| ### Effectiveness of Service Delivery and Outcomes | ### C26 C27 C28 C29 C30 C31 C32 C33 C34 | Admissions of supported residents aged 65 or over to residential/ nursing care (2) Admissions of supported residents 18-64 to resid/nursing care (2) Intensive home care Adults with physical disabilities helped to live at home Adults with learning disabilities helped to live at home Adults with mental health problems helped to live at home Older people helped to live at home Avoidable harm for older people (falls and hypothermia) (1999/00 bands and comparators) Inspections of residential care for adults and older people | * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * |

| ### PERFORMANCE AREA | CODE |  |  |
| --- | --- | --- | --- |
| Quality of Services for Users and Carers | D36 D37 D38 D39 D40 D42 D43 | Users who said they got help quickly Availability of single rooms Percentage of items of equipment and adaptations costing less than £1000 delivered within 3 weeks Percentage of people receiving a statement of their needs and how they will be met Clients receiving a review Carer Assessments Waiting time for care packages | * * * * * * * * * * * * * * * * * |
| ### Fair Access | ### E46 E47 E48 E49 E50 | Users who said that matters relating to race, culture, or religion were noted Ethnicity of adults and older people receiving assessment Ethnicity of adults and older people receiving services following an assessment Assessments of older people per head of population Assessments of adults and older people leading to provision of service | * * * * * * * * * * * * * * * * * |

ADULT SERVICES:  INTERFACE INDICATORS

| National Priorities and Strategic Objectives | A5 A6 | Emergency admissions of older people (interface) Emergency psychiatric re-admissions (interface) | * * * * * |
| --- | --- | --- | --- |
| Quality of Services for Users and Carers | D41 | Delayed discharge (interface) | * * * |

Key

- 2000/1 England comparator data are calculated from SSDA903 data

- Values between years are not comparable due to changes in definition

For indicators A5, A6, B8-10, B12-17, C21, D41, D42, E44 AND E48 best performance is band 4, not 5

For indicators E45, E47 and E48 best performance is band 3, not 5

.. Not available

. Not applicable

*	Investigate urgently

* *	Ask questions about performance

* * *	Acceptable, but possible room for improvement

* * * *	Good

* * * * *	Very good

| 2. BEST VALUE PERFORMANCE INDICATORS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BVPI no. | Note | Description | BVPP Page number ref. |  | 2000/01 Outturn | 2001/02 Estimate | 2001/02 Target | 2002/03 Target (see note below) | 2004/05 Target |
|  |  | COMMUNITY & SOCIAL SERVICES |  |  |  |  |  |  |  |
| 49 | * | Stability of placements of children looked after |  |  | 13.60% |  | 14% | 13% |  |
| 50 | * | Educational qualifications of children looked after |  |  | 57.90% |  | 50% | 65% |  |
| 51 | * | Costs of services for children looked after |  |  | £598 |  | £405 | £600 |  |
| 52 | * | Cost of intensive social care for adults |  |  | £390 |  | £374.14 | £390 |  |
| 53 | * | Intensive home care |  |  | 15.4 |  | 14 | 16 |  |
| 54 | * | Older people 65+ helped to live at home |  |  | 71 |  | 104 | 90 |  |
| 55 | * | Clients receiving a review |  |  | 88% |  | 80% | 88 |  |
| 56 | * | Equipment under £1000 delivered in 3 weeks |  |  | 95% |  | 95% | 95 | 96 |
| 57 | * | Users/carers said they got help quickly |  |  | 86% |  |  | 86 |  |
| 58 | * | %age people receiving a statement of needs/how they'll be met |  |  | 88% |  | 90% | 90 | 91 |
| 59 | * | Assessments per 1000 of population of 65+ |  |  | 153 |  | 63 | 150 |  |
| 60 | * | Users said that matters re. race culture or religion were noted |  |  | 57% |  |  | 58% |  |
| 61 | * | Relative spend on family support |  |  | 14% |  | 24% | 16% |  |
| 161 | * | Employment education and training for care leavers |  |  |  |  | 60% | 45% |  |
| 162 | * | Children on CPR - cases should have been reviewed and were |  |  | 99% |  | 100% | 100% |  |
| 163 | * | Adoptions of children looked after |  |  | 3.80% |  | 5% | 5% |  |
| 176 | * | No of domestic violence refuge places per 10,000 population |  |  | 0.14 |  | 0.14 | 0.14 |  |

#### APPENDIX 3

Action Plan - Indicator A1

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Performance is noteworthy considering pressure on looked after system. Reflects stability of placement for most children looked after. Reflects work to increase capacity and enhance resources in residential and foster care. Target 2002/3 is 13%. |  |
| --- | --- |
| Barriers to Improvement: Continuing pressure on looked after numbers. Difficulty recruiting foster carers. |  |
| Current/Proposed Action: - Continue to develop range of residential resources including partnerships. - Develop preventative services to reduce pressure on looked after system. - Use some released resources to increase foster carer payments. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Paul Woltman, Assistant Director (Children's Services) |

Action Plan - Indicator C31

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Current performance is very good but the figure has reduced over the last 3 years. |  |
| --- | --- |
| Barriers to Improvement: Fewer attendees at Day Centres. The use of community support workers has become more time limited to prevent dependency - both impact negatively on the figure. |  |
| Current/Proposed Action: Review provision of Day Centre involvement and review support through Domiciliary Care Services. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Julia Clark, Assistant Director (Adult Commissioning) |

Action Plan - Indicator B17

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Performance is acceptable, but room for improvement. Salford is below regional average (Note: definition for this indicator changed in 2000/1) |  |
| --- | --- |
| Barriers to Improvement: - Unit costs are affected by the rates payable to: internal home care, independent sector home care and the balance between the services. The cost of internal home care has increased with pay increase. This should reduce with single status, but if we have used more weekend and bank holiday working, the amounts may have gone up. Independent sector care rates have increased below inflation, but increased use of pop-ins and extended pop-ins has increased the unit cost per hour. - We are targeting people with higher needs - the increased use of pop-ins impacts adversely on unit cost calculations but supports more dependent people to be maintained in their own home. |  |
| Current/Proposed Action: Review Community Support cases to ascertain whether any could be transferred to Domiciliary Care. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Julia Clark, Assistant Director (Adult Commissioning) |

Action Plan - Indicator C22

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Salford aims to have looked after children under 10 in foster care but pressure of numbers has required some use of residential care. Target for 2002/3 in 80%. |  |
| --- | --- |
| Barriers to Improvement: Difficulty in recruiting foster carers. |  |
| Current/Proposed Action: Further development of recruitment activity in family placement section. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Paul Woltman, Assistant Director (Children's Services) |

Action Plan - Indicator C23

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Current performance raises questions about performance. Salford achieves a significant number of adoptions each year but the figure is represented as a portion of the very high looked after numbers. Projection for 2001/2 is 5%, a 1.2% improvement. Mid year estimate suggests we are now performing better than the North West average. |  |
| --- | --- |
| Barriers to Improvement: Most looked after children who need adoption have had problematic lives. Recruitment of adopters is difficult. |  |
| Current/Proposed Action: One third of Quality Protects budget for 2002/3 is committed to Family Placement services. We will establish a consortium for adoption with Manchester on 1 April 2002. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Paul Woltman, Assistant Director (Children's Services) |

Action Plan - Indicator C26

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: Salford supports a high number of people in residential care - one of the top in the country. However the figure is decreasing but this may be due (in 2000/1) to beds being purchased by the NHS - not an actual decline in numbers. In addition, turnover is higher than regional average and average length of stay is below regional average. Salford has less residents staying longer than 5 or 7 years except in dual registered homes. |  |
| --- | --- |
| Barriers to Improvement: High dependency needs of population. Poor economic position of users resulting in state dependency. Lack of self funding placements. Limited continuing health care funded placements. |  |
| Current/Proposed Action: Work with NHS to reduce numbers entering residential care. Develop alternative intermediate care provision to encourage return home. Proposals: - To explore greater rehabilitation home of people in hospital assessed as needing residential care - by use of short-term intensive home care package on hospital discharge or residential assessment beds. - To use residential assessment beds prior to permanent placement in residential care. - To increase extra care sheltered housing provision. To examine use of regular respite to reduce admissions. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Julia Clark, Assistant Director (Adult Commissioning) |

Action Plan - Indicator C27

Performance Indicator Action Plan				  	       	Date:

| Comments on Current Performance: High performance in relation to other Local Authorities. There has been an increase in the use of Adult Placement, which impacts upon indicator performance. |  |
| --- | --- |
| Barriers to Improvement: High level of admissions. Lack of self funding placements. Limited continuing health care placements. |  |
| Current/Proposed Action: Work with NHS to reduce numbers of admissions to residential care. Proposals: - To increase the number of supported tenancies as an alternative to residential care. - Investigate whether other local authorities are calculating on the same basis. |  |
| Top Quartile to be Achieved By (Date): | Lead Officer: Julia Clark, Assistant Director (Adult Commissioning) |

These figures are only approximate because they are estimates of the ONS based on ’91 census

These figures are only approximate because they are estimates of the ONS Statistics based on the 1991 census.

these numbers are approximate taken from population estimates based on the ‘91 census and apportioned using a national model of demand for care.  These are the best figures available