COMMUNITY HEALTH AND SOCIAL CARE DIRECTORATE

| REPORT ON: | Major Adaptations Service Review | TITLE: DATE OF REPORT: | Dave Clemmett Assistant Director (Provider Services) 15 October 2009 |
| --- | --- | --- | --- |
| COPIES TO: | Sue Lightup, Julia Clark, Dave Galvin |  |  |
| COVERED BY | Section 75 Partnership - between Community, Health and Social Care, Primary Care Trust and Housing Connections |  |  |
| PURPOSE OF THE REPORT | To outline the customer journey and performance for minor, major adaptations and outline actions, particularly around waiting times for Occupational Therapy assessments and waiting times for major adaptations. |  |  |
| PEOPLE INVOLVED: | Dave Clemmett ;Dave Galvin;Lynn Dixon; Angela Allan, Mike Wright, Jean Colpitts |  |  |

There are several funding streams for major adaptations which are funded through the Section 75 Partnership Agreement between Community, Health and Social Care and the Primary Care Trust.  Also, Sustainable Regeneration bid for and are allocated a Disabled Facilities Grant from the Government and contribute additional capital funding.  The work is overseen by the Independent Living Partnership Board.

The customer journey from referral through to major adaptations being in place takes on average a year.  There is also evidence that customers are also not sure of what the process is and at what point they are in the process.

There are three major areas of work that affect performance that the partnership agree needs to be reviewed in light of what is currently in place and what else needs to be done.

1.	Review Service Specification for Community Occupational Therapy and communication with customers.

2.	Lower waiting times for Occupational Therapy assessments.

3.	Lower waiting times within Major Adaptations.

2.	Performance – Present Situation (see Appendix 1)

In any month there are over 2,000 requests for service provision.  Three quarters are dealt with without the need for further assessment.  A quarter result in referrals for assessment, minor adaptations or major adaptations.

As there are over 500 new referrals each month needing further action the number on the waiting list remains static.

For occupational therapy assessment the waiting time is currently 19 weeks.  Work continues on reviewing who is able to complete assessments with more community assessment officer time being used where possible (waiting time 11 weeks).

The assessment time for wheelchair clinics is 16 weeks.

Once the assessment occurs minor adaptations (anything that cost under £1000) are fitted by on average 7 weeks.

There are over 3,000 pieces of equipment issued within any month.  Within major adaptations over 60% of the work consists of requests for provision of showers.

The budget in the area of major adaptations is usually spent within 6-9 months.

This results in waiting lists towards the end of the financial year where no further work can be completed as there is no money left.  This adds up to 3 months to the waiting times.  The average waiting time for major adaptations is a year with awaiting list of nearly 200 people.

This has been a concern over many years.  Additional funding has temporarily dealt with the waiting list but the list then quickly builds up again.

The eligibility for major adaptations needs to be reviewed as without further finance the only way of dealing with the demand is through stricter criteria.

A report in 2007 by Community, Health and Social Care Scrutiny made recommendations in the area of major adaptations.  The report is subject to a staff review at the present time.

3.	Action Plan

The following action plan was developed and agreed between Community, Health and Social Care and Housing Connections.

The plan was submitted to Care Quality Commission in September.  There have been some minor date changes since this occurred.

As outlined there are three major areas of work agreed within the Section 75 Integrated Equipment Services Partnership between Community Health and Social Care, the Primary Care Trust and Housing Connections.

1.	Review Service Specification for Community Occupational Therapy and communication with customers.

2.	Lower waiting times for Occupational Therapy assessments.

3.	Lower waiting times within major adaptations.

1. Community Occupational Therapy Service Specification

| Action | Activity | Lead Officer | Timescale for Completion | Key Milestones/Targets | Completed Yes/No |
| --- | --- | --- | --- | --- | --- |
| To offer an equitable service across Salford based on level of need | Produce redraft of the Community Occupational Therapy Service Specification | L Dixon | July 2009 | Draft to be completed. | Yes, July 2009 |
|  | Consult with staff on the redraft of the Community Occupational Therapy Service Specification | L Dixon | August 2009 | Consultation process to be completed | Yes |
|  | Independent Living Partnership Board to review the redraft of the Community Occupational Therapy Service Specification | L Dixon | 14 September 2009 | Review by Partnership Board to be completed | Yes |
|  | Independent Living Partnership Board to ratify the redraft of the Community Occupational Therapy Service Specification | L Dixon | October 2009 | Partnership Board agree the revised version Ratified | Yes |
|  | Review service specification and performance against the revised specification | L Dixon | April 2010 | Review completed and learning points noted Based on equity across City |  |

2. Improve (i.e. reduce) Waiting Times for Occupational Therapy Assessments

| Action | Activity | Lead Officer | Timescale for Completion | Key Milestones/Targets | Completed Yes/No |
| --- | --- | --- | --- | --- | --- |
| Improve (i.e. reduce) Waiting Times for Occupational Therapy Assessments | Increase number of OT’s available for assessment | L Dixon | August 2010 | Increase by 2 workers for one year | Started August 2009 |
|  | Look into feasibility of Salix funding OT time | L Dixon | October 2009 | Agreed by D Clemmett Outcome focussed. November start | Yes Yes |
|  | Increase number of Community Occupational Therapy appointments: | L Dixon L Dixon | November 2009 Sept 2009 December 2009 | Number of completed assessments increased | Yes Yes Yes |
|  | Introduce flexible appointment system where customers can see the equipment in situ at Disabled Living Centre |  |  | Flexible appointment system operational One “surgery” a month occuring |  |
|  | Purchase self assessment computer software (i.e. ADL, Smart Care) |  |  | Consult on purchase Sept |  |
|  |  |  |  | Agree to purchase October 2009 |  |
|  |  |  |  | Funding secured November System introduced December 2009 |  |
|  | Undertake a review of when Occupational Therapy Assessments are needed and increase use of Community Assessment Officer time for adaptations | L Dixon L. Dixon L Dixon A Allen | November 2009 June 2009 Dec 09 | Review of necessity for Community Occupational Therapy Assessments completed Monthly reporting in place Monthly reports on performance submitted to the Performance Monitoring Group. Continued monthly/ quarterly reporting throughout 2010 | Yes |
|  | Monitor performance for minor adaptations up to £1,000 Report to be completed Review £1,000 level and look at option to increase to £2,000 |  |  |  |  |
|  | Co-develop work with Salix (where Salix staff will be the first point of contact for adaptations enquiries). | Chris Bentley | November 2009 | Pilot completed and learning points noted |  |
|  | Salix to develop leaflet in respect of revised working processes | Chris Bentley | October 2009 | Leaflet completed by October 2009 |  |
|  | Train Salix staff on new processes for being first point of contact | Chris Bentley | October 2009 | Staff training completed |  |
|  | Revised system implemented | Chris Bentley | 1st November 2009 | Revised system operational |  |

3. Lower waiting times within major adaptations

| Action | Activity | Lead Officer | Timescale for Completion | Key Milestones/Targets | Completed Yes/No |
| --- | --- | --- | --- | --- | --- |
| Increase available budget for major adaptations | Application for increased funding via Government’s Disability Facility Grant submitted July 2009 | A Allan | December 2009 January 2010 | Bid made Take up through Salford Housing Partnership Decision on funding bid expected January 2010 | Yes |
|  | Negotiation with Registered Social landlords to obtain a contribution to budget for their tenants. | A Allan | April 2010 | 3 Registered landlords agreed in principle to the funding proposals |  |
|  | Additional budget of £300,000 made available for Salix Homes tenants to address waiting list | A Allan | April 2010 | Present waiting list of 53 dealt with |  |
|  | Additional money available October from City West - £500,000 |  |  | Arrangements to commit money December |  |
| Lower cost of adaptations (so that more can be undertaken for the same money) | Agree contractor framework agreement, which includes: | A Allan | August 2009 | Contractor framework agreed. | Yes |
|  | identification of contractors; |  |  |  | Yes |
|  | timescales for works; | A Allan |  |  | Yes |
|  | budget price for works (as at June 2009) |  |  |  | Yes |
|  | Implement plan | A Allan | Oct 2009 | Work starts with agreed contractors | Yes |
|  | Save money | A Allan | April 2010 | Potential to save up to 15% on work issued via framework, post Sept 2009 . |  |
|  | Undertake a review of the framework agreement | A Allan | July 2010 | Review to be completed |  |
| Follow-up review of Housing major adaptations by Health and Social Care Scrutiny Committee | Review recommendations of housing major adaptations Scrutiny report | D Galvin \ D Clemmett | November 2009 December January | Produce a report on progress against recommendations. Scrutiny to go out again and submit an update. Scrutiny report for submission to the Independent Living Partnership Board |  |
| Review of eligibility criteria | Undertake a review of the eligibility criteria for major adaptations | D Clemmett | November 2009 | Information gathering September Complete the review and produce an options paper |  |

4. Manage Performance

| Action | Activity | Lead Officer | Timescale for Completion | Key Milestones/Targets | Completed Yes/No |
| --- | --- | --- | --- | --- | --- |
| Performance manage the customer journey | Referral times for Occupational Therapist to completion of assessment | D Clemmett | Monthly Monthly Monthly Monthly | Monitor performance levels against previous years data |  |
|  | Referral to delivery of minor adaptations |  |  |  |  |
|  | Referral for major adaptations to letting of contract |  |  |  |  |
|  | Contract to completion of work |  |  |  |  |
|  |  |  |  | Report on Progress in April |  |

October Review completed by Lynn Dixon/Angela Allen/Dave Clemmett.

OT waiting list down from 16 to 14 weeks.

Minor Adaptations 100% completed within 6 weeks.  Average 4 weeks.

Major Adaptations:

(a)	Average length of time waiting for major adaptations from assessment to work beginning:

Outturn 08-09 – 39 weeks

Plan 09-10 – 32 weeks

Please review planned target in light of current practice.

(b)	Waiting list:

08-09 – 220

09-10 – 220

Please review as number.  Should go down with all activity.  However, current figure is 330.

However, City West are planning to do their own adaptations.  This will lower the amount of work by 50% to 160.

Please review plan in light of current practice.

Appendix 1

COMMUNITY OCCUPATIONAL THERAPY SERVICES

| MONTH AUGUST 2009 |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1) | TOTAL NUMBER OF REFERRALS RECEIVED IN MONTH |  |  | 2233 |
|  | a) Number included in above for stock only |  |  | 1499 |
|  | b) All other referrals (for assessment visits and minor adaptations) including wheelchairs |  |  | 734 |
| 2) | ASSESSMENT VISITS |  |  |  |
|  | a) Waiting list for assessment at beginning of month (due to no report last mth) |  |  | not available |
|  | b) Waiting list for assessment at the end of month - reported up to 15/09 |  |  | 746 |
|  | c) Number of wheelchair assessments completed “ “ “ “ |  |  | 128 |
|  | d) Number of reviews completed |  |  | 370 |
|  | e) Number of recommendations to other agencies for major adaptations | Private | 22 |  |
|  |  | Council | 12 |  |
|  |  | ##### City West |  | ##### 15 |
|  | f) Waiting time for assessment visit |  |  |  |
|  | O.T. Weeks |  |  | 14 wks |
|  | C.A.O. Weeks |  |  | 14 wks |
|  | Wheelchair Clinic Weeks |  |  | 11 wks |
| 3) | MINOR ADAPTATIONS (Excludes grab rails and banisters) |  |  |  |
|  | Number on waiting list (includes adaptations awaiting estimates) |  |  | 60 |
|  | Number with contractors |  |  | 33 |
|  | Number completed during the month |  |  | 8 |
|  | Average time from assessment to completion |  |  | 4 wks |
|  | Average time from assessment to order |  |  | 0 wks |
|  | % from assessment to order with 6 wks |  |  | 100% |
|  | % completed within 6 weeks |  |  | 100% |
| 4) | EQUIPMENT (Includes grab rails and banisters) |  |  |  |
|  | a) Equipment issued |  |  | 2641 |
|  | b) Equipment Returned |  |  | 1380 |
|  | c) Failed deliveries |  |  | 0 |
|  | d) % Equipment delivered within 7 days |  |  | 94% |
|  | e) Sensory equipment delivered Figures for Partnership Board |  |  | 206 |
|  | f) Sensory equipment collected |  |  | 10 |
| 5) | MAJOR ADAPTATIONS |  |  |  |
|  | % of Major Adaptations done within 12 months of referral | Private |  | 29% |
|  |  | Council |  | 60% |
|  | Number on waiting list for Major Adaptations | Private | 143 |  |
|  |  | Council | 41 |  |
|  |  | City West | 157 |  |

/tmp/in/input.doc