| - PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF THE DIRECTOR OF COMMUNITY, HEALTH and SOCIAL CARE

LEAD MEMBER BRIEFING FOR :

- CULTURE and SPORT; CUSTOMER and SUPPORT SERVICES [14th April]

- LEAD MEMBER FOR PLANNING FOR INFORMATION (17th June)

TITLE:         	 Conserving and Developing Ordsall Hall – HLF Stage 2 submission

RECOMMENDATIONS:

- That Lead Members approve the submission of the Stage 2 application to the Heritage Lottery Fund.

- That Lead Members approve the continuing development of the project to enable the building works to go out to tender.

- That the Lead Member for Customer and Support Services: -

a]	approves the necessary financial resources required to complete tender documentation.

b]	approves the necessary financial resources required to underwrite the shortfall in match funding, subject to review upon tendering of the building contract.

4.  That the Lead Member for Planning notes the report for information

EXECUTIVE SUMMARY:

The report updates Lead Members on the Ordsall Hall HLF project and seeks permission to: -

- Submit the HLF’s Stage 2 development work to the HLF

- Continue to develop the project whilst waiting for the HLF’s Stage 2 decision

In addition the report requests that the shortfall in funding is underwritten by the Council whist the fund raising continues.

BACKGROUND DOCUMENTS:	/

ASSESSMENT OF RISK:	The successful implementation of this project is subject to

- Stage 2 HLF approval (low risk).

- Raising of other external funding (high risk)

- Construction cost risks (medium).

THE SOURCE OF FUNDING IS:	Capital programme, Section 106, Heritage Lottery Fund, other external funding.

LEGAL ADVICE OBTAINED: 	I Sheard – Approved

FINANCIAL ADVICE OBTAINED:	J Spink  - Approved

K Darragh – Approved

COMMUNICATION IMPLICATIONS: / VALUE FOR MONEY IMPLICATIONS: / CLIENT IMPLICATIONS: / PROPERTY: / ______________________________________________________________ HUMAN RESOURCES: / ______________________________________________________________

CONTACT OFFICER :	Robin Culpin 0161 793 2210 / Jackie Ashley   0161 779 6043

WARD(S) TO WHICH REPORT RELATE(S)   Ordsall and Langworthy

KEY COUNCIL POLICIES  Conservation Policy within the UDP, Central Salford                        Regeneration, Community Plan, Cultural Strategy

DETAILS (Continued Overleaf)

1.	INTRODUCTION

  - The purpose of the report is

- To update Lead Members on the status of the Ordsall Hall development project

- To obtain authority to submit the HLF Stage 2 application.

- To obtain authority to progress the production of tender documentation for the building works & to go out to tender in advance of the HLF’s Stage 2 decision.

- To appraise Lead members of the fund raising position.

2.	BACKGROUND

  - In March 2007 the Heritage Lottery Fund approved the council’s Stage 1 submission resulting in a grant to develop in detail all aspects of the project.  This work has been completed and the information is now ready to be submitted for Stage 2 HLF approval that would result in a Heritage Grant of £4,134,909 from the HLF.

- DETAILS

  - The project that has been developed continues to achieves its key aim of: -

“Restoring and conserving the building and develop the grounds

with the mission of providing a sustainable base to tell the

stories around the Hall from 14th to 21st centuries - and develop

it as the hub of the community that it would have been for most

of its life.”

The costs for the Stage 2 submission have been developed whilst reconciling:-

- Significant variations between Stage 1 estimates and Stage 2 final costings

- The need to meet original funding estimates without reducing the fundamental vision behind the project

- The need to maintain the support and approval of the HLF Case Officer, Project Monitoring Officer and other agencies such as English Heritage.

3.2	Project costs

The overall project consists of the following elements.

| #### Ordsall Hall - implementation costs |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item |  |  |  |  |  |  |
| 1 | Building works including building services |  | £ 3,802,137.00 |  |  |  |
| 2 | Specialist works to paint, plaster, glass, Victorian light fittings and archaeological works |  | £ 137,915.00 |  |  |  |
| 3 | Landscape scheme |  | £ 654,370.00 |  |  |  |
| 4 | Artwork project enhancing landscape scheme |  | £ 153,700.00 |  |  |  |
| 5 | Exhibition, interpretation and general fitting out works |  | £ 674,071.00 |  |  |  |
| 6 | Training & volunteer development projects |  | £ 354,238.00 |  |  |  |
| 7 | Audience development projects including community projects during closure, the outreach schools service during closure & the opening event |  | £ 116,100.00 |  |  |  |
| 8 | Professional fees and statutory approval costs |  | £ 558,453.00 |  |  |  |
| 9 | Non - cash contribution from partner organisations |  | £ 98,000.00 |  |  |  |
|  | Total |  | £ 6,548,984.00 |  |  |  |
|  | [The above figures exclude the funding provide by Salford Council to develop the HLF Stage 1 submission (£129,157) and the Stage two development works (£285,498) that were funded by the HLF (£177,008) & Salford Council (£108,490)] |  |  |  |  |  |

The Stage 1 submission estimated the value of the above works at £6,454,917.  The Stage 2 submission at £6,548,984 is £94,067 above the Stage 1 estimated budget and reflects:-

- A detailed review of the project in order to keep costs as near to the Stage 1 budget as possible.

- Significant, but not fundamental, reductions in the landscape, building and interpretation works.

- An underestimate of inflation allowances at Stage 1, largely caused by the HLF’s 3 month delay in giving its approval [estimated at around £90,000].

3.3	Project funding

3.3.1 The fund raising target has increased from £885,208 to £979,275 to reflect additional costs that has arisen due the HLF original decision taking longer than usual. Currently approximately £138K has been raised via public donations and grant bodies [see Appendix A].  Extensive efforts have been made by both council officers and the Friends of Salford’s Museums to fund raise and further bids are being developed or in the pipeline.

3.3.2 In addition the Central Salford URC is very supportive of the project at Ordsall Hall and a bid to the NWDA is being developed by officers from the URC for an amount around £350,000. This can be considered a realistic source of funding.

The table below sets out the current position

| #### Ordsall Hall - project funding |  |  | £6,548,984.00 |
| --- | --- | --- | --- |
| a | HLF capital grant |  | £ 4,134,909.00 |
| b | Council funding (Capital programme & Section 106) |  | £ 1,336,800.00 |
| c | Non- cash contribution |  | £ 98,000.00 |
| d | External grants & fund raising |  | £ 188,000.00 |
| e | Central Salford URC – verbal agreement to bid for £350,000 from NWDA |  | £ 350,000.00 |
|  | Total |  | £ 6,107,709 |
|  | Current shortfall |  | £ 441,275 |

3.3.3 This report requests that the Council agrees to write a letter to the HLF underwriting the shortfall subject to a continuing review at the time of approving the building works contract.

3.4	Short-term programme

    - The Stage 2 development work has taken longer than scheduled resulting in a potential impact on which HLF Trustee meeting the Stage 2 submission can go to for approval.  There is a good working relationship with the HLF’s case officer and there is the possibility that the project still being able to go to the June meeting as scheduled. However the later submission may mean the HLF’s decision does not occur until mid September.

    - In order to achieve the desired start on site of building works in April 2009 it is necessary, over the summer, to finalise the design work and produce tender documentation for the September tendering period.  This in effect means there will be professional fees incurred that are potentially at risk pending a September HLF decision.  The cost of this work is £211,280.00. The risk is assessed, as being low and a delay in this process will result in higher project costs as well service delivery implications.

    - Feedback from the HLF is clear that they will work with the council to achieve a Stage 2 approval and therefore, this report requests approval to continue with the design development prior to formal approval.

  - Long-term programme

    - The key dates of the project’s log-term programme are set out below.  Appendix B sets out the expenditure profile based on this programme.

- June / September 2008– HLF approves Stage 2 information

- OJEU tendering process commences for the building contract

- Dec 2008/ January 2009 – final approvals and contract let for building contract

- 13th February 2009 Ordsall Hall closes to the public

- April 2009 – building contract commences

- October 2010 – building works complete

- October 2010/ March 2011 – landscape works undertaken and building fitted out

- April 2011 Hall opened to the public

- June 2011 official opening

- Sept 2011 Learning programme starts.

4.	Conclusion

4.1	Renovation of the Hall and improvement of its grounds is an integral part of the wider regeneration of Ordsall, including the council's development partnership with LPC Living, the proposed transformation of the Ordsall Riverside Corridor and the plans for Irwell City Park.  The proposals for the Hall will enhance confidence in the area's housing market, provide new community facilities and improve the appearance of Ordsall Lane.  Complementary regeneration work in the area includes the recent completion of a new housing development, Radclyffe Mews, overlooking and framing views of the Hall, other recent and proposed environmental improvements along Ordsall Lane and the planned creation of new open space that will create a vista from the Hall to the waterfront.

  - The HLF, through their Stage1 approval of the project recognise that this project will result in Ordsall Hall having a great future to match its past.

4.3	This next phase is the continuation of the process of realising the original vision and ambition.

5.	Recommendations

5.1   That Lead Members approve the submission of the Stage 2 application to the Heritage Lottery Fund.

  - That Lead Members approve the continuing development of the project to enable the building works to out to tender.

5.3	That the Lead Member for Customer and Support Services: -

a]	approves the necessary financial resources required to complete tender documentation.

b]	approves the necessary financial resources required to underwrite the shortfall in match funding, subject to review upon tendering of the building contract.

Appendices