| Part 1 | ITEM NO. |
| --- | --- |

REPORT OF THE DEPUTY DIRECTOR OF HOUSING AND PLANNING

TO THE LEAD MEMBER FOR PLANNING

1st JULY 2008

TITLE : CARGO CRANES – ONTARIO BASIN SALFORD QUAYS

RECOMMENDATIONS :

LEAD MEMBER FOR PLANNING:-

Lead Member is asked to approve the proposal for procuring the repair of the two cranes at the head of Ontario Basin.

EXECUTIVE SUMMARY :

The two cranes located at the head of Ontario Basin in Salford Quays urgently require repair and repainting. This report outlines the options and costs and seeks approval to the proposed method of procurement.

BACKGROUND DOCUMENTS : 	Lead Member Report dated 28th November 2007

Stothert & Pitt Structural Report dated 22nd May 2007

ASSESSMENT OF RISK: Medium.

There two key risks. Firstly, that the cranes prove difficult to dismantle in such a tight ‘operational window’ and secondly, that when the cranes are dismantled and fully accessible to close inspection, they may be found to be in a worse condition than currently assessed.

SOURCE OF FUNDING:

An allocation of £400,000 is available from the 2007/08 Capital programme.

- LEGAL IMPLICATIONS: Comment on risk.  Provided by Ian Sheard tel: 3084

- FINANCIAL IMPLICATIONS: There was originally an allocation of £250,000 within the 2007/08 programme that has been carried forward to 2008/09 and increased to £400,000 to reflect the expected cost of the project.  	Provided by : Nigel Dickens tel: 2585

PROPERTY (if applicable):

HUMAN RESOURCES (if applicable):

CONTACT OFFICER :	Max Griffiths 779 4902

WARD(S) TO WHICH REPORT RELATE(S): Ordsall

KEY COUNCIL POLICIES: A learning and creative city.	A city in which it is good to live.

DETAILS (Continued Overleaf)

1	Background

1.1	The two cranes are Grade A listed on the Local List of Buildings Structures and Features of Archaeological, Architectural or Historic Interest. Located at the head of Ontario Basin, they are considered to be an important local landmark. Operational from 1966 and relocated to their current site in 1988 as a non-working feature, they represent an important link with the heritage and history of Salford Quays.

1.2	The cranes were last serviced and repainted at the time they were moved to their current position in 1988. Today the cranes are in a poor visual condition being heavily corroded and streaked with rust stains. This rust is becoming serious in nature and in places strengthening work will be required as the metal is becoming very thin and could soon be perforated in locations such as the cab roofs.

1.3	In 2006 emergency works were undertaken at night to remove loose steel hand railing and ladders in danger of falling on to pedestrians below.

1.4	The cranes were inspected by Stothert and Pitt (the manufacturers of the cranes)  in May 2007 at a cost of £1500. Prior to this the cranes were inspected in August 1999. The later S&P inspection concluded that both are capable of repair and retention subject to a range of repair measures that are outlined in the attached report.

1.5	A range of options for the cranes has been explored including relocation; however, the conclusion has been reached that they should be repaired and preserved in their current location.

    - It is proposed that the cranes will be painted to a finish in accordance with their current colour scheme.

- Details

  - The poor condition of the two cranes allied with their location presents major difficulties regarding repair and repainting works because of:-

- the proximity to Metrolink permitting only short and costly night time possessions;

- Inadequate space to erect scaffolding; and

- the jibs overhang the water in the basin

  - Given these problems, consideration has been given to the relocation of the cranes to an alternative permanent site where future repair and maintenance to the cranes could be carried out in-situ. However, no alternative sites were located and the proposal is therefore to retain them in their current location.

  - The methodology for repairing the cranes is as follows:-

  - Each crane is estimated to weigh around 60 tonnes and will be dismantled in four sections. This will be complicated because each piece will require careful separation from the others and will then require to be lifted over the tramway tracks using a 300 tonne capacity mobile crane.

  - In order to position the crane and low loader transport vehicles, the dock road will require to be temporarily closed during working hours. During the day when no work can take place, one-way movement of traffic will be possible.

  - It is estimated that the mobile crane will be temporarily in position for up to 12 days in order to dismantle the cranes and subsequently for a similar period when the cranes are returned to their current location following refurbishment off site.

  - Although in principle the mobile crane can be positioned on a daily basis, the works to mobilise and demobilise the crane using a smaller crane are time consuming and a crane hire company has confirmed that moving the cranes on a daily basis would add to the cost of the project.

  - Power to the tramway overhead electrical equipment  must be isolated during the nightly lifting operations and the dismantling operation approved and monitored by Metrolink engineers.

- Procurement

  - It will be appreciated that the operation to remove such heavy, aged and inoperable cranes poses certain programming and financial risks. The cranes may prove difficult to dismantle or weather may become problematical. Access to the original fabrication drawings and details for the cranes would therefore be invaluable with respect to the dismantling operation.

  - It was therefore initially considered wise to utilise the services of Stothert and Pitt, the crane manufacturer, to arrange for refurbishment of the cranes at one of their fabrication yards in accordance with their original design details held in their archives.

  - Whilst this still remains a logical option the use of a single tender poses certain problems should the arrangement run into difficulty late in the tendering process. Also Stothert and Pitt may require assistance with respect to arranging road closures and traffic management, as this is not their normal area of expertise.

  - The alternative of utilising a conventional tendering process carries disadvantages because the tenderer may not be familiar with the cranes, may need to employ the services of a specialist crane engineer and may also need to commission Stothert and Pitt with respect to the original crane design specification and other technical advice.

  - During the feasibility stage United Cranes Ltd were contacted and it was ascertained that they also specialise in the refurbishment of cranes and recently transported a large crane from Europe to their Sheffield works for refurbishment.

  - During discussions on the repair cost during the feasibility phase, Stothert and Pitt revised their estimate several times before reaching the current  £394,000 target. Although this quotation included several sums for risk contingencies that may not be required, this will become clear only when the cranes can be inspected at close quarters.

  - Unfortunately, although Stothert and Pitt are a major international specialist crane contractor they are not currently accredited by construction line or CHAS and therefore could not be employed as the Principal Contractor by the City Council.

  - Taking into account the above considerations it is therefore proposed that the project is detailed and a conventional target based contract produced by Urban Vision Partnership Ltd and sent to Galliford Try, Birse Civils, Manchester and Cheshire Construction Ltd and A E Yates.

  - Stothert and Pitt and United Cranes will be named within the documents as specialist subcontractors able to carry out work under the main contractor’s site supervisory team or in a technical advisory role. This will ensure that the breadth of technical capability is assured from the beginning whilst also securing a competitive tender target sum.

  - Should the contractors have sufficient in-house expertise, they will not be contractually obliged to seek the services of Stothert and Pitt or United Cranes.

4. 	Financial

4.1	An allocation of £400k is available from the 2007/08 Capital Programme.

5	Conclusion

5.1	The two cranes currently present a poor appearance particularly in the context of the general Salford Quays environment.

5.2	A failure to repair and maintain the cranes will inevitably lead to further deterioration and eventually there would be no other cost effective solution but to remove them from site permanently when they become unsafe.

5.4	The cranes must be dismantled and removed from site for repair as there is no practicable means of undertaking this work whilst they remain in position.

5.5	The work is of a specialist nature and contractors contacted during the feasibility stage have been cautious in their expressions of interest. Feedback from these contractors confirms that that the work is considered to pose certain risks that will require careful management.

Bob Osborne

Deputy Director of Housing and Planning

Appendices