# Recycling/ Refuse Collection/ Street Cleansing/ Themed Issues/ Dog Wardens Improvement Plan

## Progress Update, September 2003

RECYCLING

| ## INDICATOR | 2001/2 BASELINE | 2002/3 TARGET | 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| BVPI 82 a Percentage of domestic waste arisings recycled | 5.47% | 7% | 4.89% The failure to achieve target was due to a change in Government definitions as to what could be counted as waste actually recycled by the local authority. Waste collected by the local authority in the general waste stream and sorted out at the plant by GMWDA on behalf of the City (e.g. tins) could not be claimed as recycled material by the City, as it had not collected it separately for recycling. This issue is currently being discussed with Defra. |

| ### OBJECTIVE | ### ACTION | ### TIMESCALE | ### POSITION MAY 03 | ### COMMENTS |
| --- | --- | --- | --- | --- |
| Issue 500 compost bins per annum from 2002/03 – 2006-07 | Home compost bins are made available to the public at subsidised rates. | #### April 2002 – March 2007 | ##### Ongoing | The provision of home composters is a central element to promoting domestic waste recycling. The Directorate has just received funding from Landfill Tax credits, to carry out a community composting scheme, involving distribution of home composting equipment and the carrying out of research and educational programmes about composting. In addition as a result of a successful DEFRA bid several home compost bin sales will be taking place in 2003/04 in partnership with a private sector company. |
| Create a budget to support recycling programme | Following a successful DEFRA bid, financial commitment has been given by the City Council to provide revenue support for the recycling programme | #### April 2003 | ##### Achieved |  |

| OBJECTIVE | ACTION | #### TIMESCALE | #### POSITION MAY’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Establish a kerbside multi-material collection scheme | NDC and DEFRA funding will allow at least half the city to receive kerbside collection of recyclables. | #### April 2003 | #### Achieved | As a result of a successful bid to DEFRA via GMWDA, all eligible properties in the City have now been offered kerbside recycling collection services. To date c. 30,000 properties have agreed to take part. |
| Increase awareness of recycling and waste minimisation initiatives | A Greater Manchester wide publicity campaign will be introduced due to funding received from DEFRA | 2003- Onwards | Achieved GMWDA joint initiative with all GM local authorities and run by Beattie Media. | A publicity/communications strategy is currently being developed and is due to be rolled out this year. |
| Increase the number of sites by one per annum, year commencing 2002/03 | 2 sites have been introduced during 2002/03 | ##### Ongoing | ##### Achieved | Following a successful LPSA bid 21 mini-recycling sites will be created at the city’s high rise blocks over the next 2 years. To date (May ’03) 28 sites have been agreed, and 4 multi-material recycling sites established |
| Through partnerships with GMWDA improve civic amenity sites recycling activities. | A bid has been submitted to DEFRA to improve all civic amenity sites in Greater Manchester in relation to improving their ability to increase domestic recycling levels | 2003/04 | Funding acquired improvements to civic amenity sites will take place during 2003-04 | As part of the successful DEFRA bid all civic amenity sites in Greater Manchester will be re-designed to promote greater levels of recycling. This work is due to begin mid 2003. £70k has been assigned for Lumns Lane |
| Enhance corporate recycling schemes | A report has been prepared by the Environmental Services Directorate on how to increase corporate recycling levels | 2003/04 | Report presented to Cabinet. The recycling of toners/cartridges and mobile phones will begin in May 2003 | Cabinet have instructed that corporate recycling be a priority. Discussions are underway to identify materials for recycling and markets. The Environmental Officers Working Party is still to be resurrected to monitor progress, and develop other environmental issues which affect the City Council. |
| Develop wider range of partners to increase recycling rates | As part of the tendering process to identify potential providers of kerbside collection schemes, new contacts will be made | ##### April 2003 | Achieved | A successful contractor has been appointed – Greater Manchester Waste Ltd. Links have been established with Shotton Paper Mill and Greater Manchester Waste Ltd to increase recycling levels via the introduction of kerbside collections of recyclables. |
| Consider offering reduced rates for Commercial Recycling by end April 2003 | A report is being produced to identify a differing scale of charges for customers who recycle their waste | ##### April 2003 | ##### Ongoing | This issue is still under discussion. |

| OBJECTIVE | ACTION | ##### TIMESCALE | ##### POSITION MAY’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Increase recycling of domestic waste to 10% by 2003/04 to Government targets | The e target for domestic recycling has now been changed to 8% The kerbside collection scheme to all of The City’s eligible properties is currently being implemented. It is expected these collections will help achieve the required recycling rate. | ##### April 2003 | ##### Partly Achieved | The City’s current recycling rate of 5.47% will form the foundation for the 8% target which needs to be met. The 8% target has been included as a contract requirement for GM Waste Ltd to achieve as part of the provision of the kerbside collection of recyclables service, which they have successful tendered for |
| Increase investment in recycling operations by bringing about changes in current waste disposal and operational methodologies by April 2004 | The Environmental Services Directorate has produced a report for Cabinet which outlines a series of options to achieve more economical waste disposal changes. This was presented to cabinet in October 2002. | ##### April 2004 | ##### Partly Achieved | Cabinet have had meeting with GMWDA to outline their position in relation to future waste management service provision. GMWDA now have to deliver economic and environmentally sustainable waste management services if The City is to remain within the GMWDA – discussions are still taking place as Manchester are concerned about the financial impact a full tonnage-based levy would have on their waste disposal costs. |
| Increase recycling of domestic waste to 15% by 2005/06 to meet Government targets and City Council pledges. It should be noted that the revised target of 15% has yet to be confirmed. | The development of kerbside collections together with existing recycling sites, and home composters should help reach the required target | ##### March 2006 | ##### Ongoing | It is anticipated that with improvements to civic amenity sites and increased recycling via kerbside collections, this target will be achievable. |
| Update the City’s Recycling Plan to take account of the National Waste Strategy 2000. | Updated information has been added to the city’s recycling plan. | 2002 | ##### Achieved |  |

STREET CLEANSING

| ## INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/03 ACTUAL TO DATE |
| --- | --- | --- | --- |
| LPI 16% of highways that are of a clean- acceptable standard This local PI will be replaced in 2003/04 by BVPI 199, a mandatory PI. | 91.86% | 93% | 94.4% (year end result) |

| OBJECTIVE | ACTION | TIMESCALE | ### POSITION MAY 03 | COMMENTS |
| --- | --- | --- | --- | --- |
| To implement BVPI 199 in order to comply with the requirements and to begin to collect data which will allow future targets to be set. | Monitoring of service performance both operationally and statistically is carried out | ##### March 2004 | ##### Ongoing | An independent cleanliness survey carried out by ENCAMS has shown an improvement in cleanliness levels in The City. 2003/04 has seen the introduction of a new Best Value Performance Indicator (BVPI 199) which has replaced the local performance indicator currently used. Targets will need to be established to allow benchmarking to take place from 2004/05 onwards. |
| Develop calendar to inform public of specified dates of cleansing in their areas | Printing and distribution to all households of street sweeping calendar | 2002 | Achieved (May 2002) |  |
| Increase city-wide sweeping frequency to a minimum of every 3 weeks | All residential areas now receive a three-weekly sweep as a minimum. | 2002 | Achieved (May 2002) |  |
| Undertake a customer survey by telephone on revised/improved street cleansing | To be carried out by Contract Services administration and operational staff | ##### December 2002 | Ongoing | The next customer survey exercise is planned to take place in November 2003. The Quality of Life survey to be carried out in September 2003 will also provide valuable information on customer’s perceptions. |
| Introduce a Geographical Monitoring Service | Trials of tracking system completed, now need to identify source of finance. | ##### September 2002 | ##### Achieved | Tracking system has been purchased and was fitted to vehicles in April 2003. |
| Establish a litter enforcement programme. | A litter enforcement programme was launched in August 2003 to allow authorised officers to administer Fixed Penalty Notices For littering. | ##### August 2003 | ##### Achieved | Officers are now actively enforcing the anti-litter message by publicity and Fixed Penalty Notices. |

| OBJECTIVE | ACTION | TIMESCALE | POSITION MAY’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Improve removal time of abandoned vehicles | Partnership with Greater Manchester police has given responsibility to police to remove vehicles on behalf of the City Council. | 2002 | ##### Achieved | Response time now within 25hours. |
| To improve standard of street cleansing to within top quartile of Metropolitan Authorities | Increased level of mechanical sweeping operation and increased frequency of sweeping across the city | 2004/05 | ##### Ongoing | Due to Encams no longer carrying out Metropolitan cleanliness surveys there will be a need to develop new methods of benchmarking performance – this is currently being looked into with other interested authorities, such as other Metropolitan Authorities and Sister Authorities. |
| Develop formal strategy for the allocation and siting of litter bins | Formal internal policy adopted as to siting of litter bins across the city | 2001 | ##### Achieved |  |
| To achieve Charter Mark status for Street Cleansing | Preparations underway | 2005/06 | ##### Not Achieved | New criteria being developed by Chartermark which will need to be assessed – this is currently being undertaken. |
| To reduce cost per head of population for provision of street cleansing services | Due to recent investment in greater levels of machinery to improve cleanliness levels this has proved difficult to achieve as quality comes at a cost. | 2001 | ##### Not Achieved | Remains an ongoing target |
| Ensure 100% service delivery through alternative employment practices/partnerships | Partnerships developed which allows use of agency staff to cover sickness and holidays ensuring 100% cover | 2001 | ##### Achieved |  |
| Improve customer consultation | Increased level of customer consultation via ENCAMS survey | 2001 | ##### Ongoing | The Environmental Services has developed a consultation strategy which identifies levels of consultation required. |
| Increase the number of litter bins | Partnership with GMPTE has allowed over 200 additional bins to be sited at bus stops across the city | Ongoing | ##### Achieved/Ongoing | It is intended to site a further 120 litter bins during 2002/03. |
| Seek external funding/sponsorship for litter bins | Partnership with Trash Media has resulted in almost 100 extra bins across the city. | Ongoing | ##### Achieved/Ongoing |  |

| OBJECTIVE | ACTION | TIMESCALE | POSITION MAY ’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Increased level of mechanisation to deliver better quality street cleansing | 14 New mini sweepers have been introduced, which have led to higher frequencies of street cleansing | ##### Begin in 2001 | ##### Achieved |  |

REFUSE COLLECTION

| ### INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/03 ACTUAL TO DATE |
| --- | --- | --- | --- |
| The cost of waste collection per household | £19.95 | £19.59 | £23.63 The apparent failure to achieve target is not due to increasing service costs, but rather a reflection of the addition of new service provision i.e. city-wide kerbside collection of recyclables. As such there will be a need to adjust future year’s targets to reflect this change. |
| The number of collections missed per 100,00 collections | 98 | 70 | 23.5 year end result 2002/03 |

| OBJECTIVE | ACTION | TIMESCALE | POSITION MAY’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Reduce the cost of service provision by £150k per annum | By amalgamating teams, reducing relief staff and team numbers savings of £150k per annum have been achieved | ##### May 2002 | ##### Achieved |  |
| To collect all bulky waste within 5 days of receiving the request | All bulky waste is now collected as part of the normal domestic waste collection round | ##### May 2002 | ##### Achieved |  |
| Carry out customer surveys by telephone | Survey questionnaires have been prepared and contact has been made with customers | ##### December 2002 | ##### Achieved | 96% satisfaction recorded |
| Improve reliability and image of vehicle fleet | New vehicle leasing programme has resulted in 3-year replacement programme for all RC Vehicles. 11 new vehicle received 1/7/02 | ##### July 2002 | Achieved |  |
| Achieve Charter Mark Status | Preparations currently underway | ##### January 2004 An application is currently being prepared. | ##### Ongoing |  |
| Ensure profitability of commercial refuse collection service | New partnership has allowed use of agency staff to cover sickness & holidays |  | ##### Ongoing |  |
| Ensure 100% service delivery through alternative employment practices/partnerships. | New partnerships has allowed use of Agency staff to cover sickness and holidays | ##### May 2001 | ##### Achieved |  |
| Introduce 4 day working on a zoned basis | 4 day working week introduced to resolve issue of non-collection on Bank Holidays | May 2001 | #### Achieved |  |
| Improve rectification rates of missed bins | Better quality of monitoring by Environmental Co-ordinators has significantly reduced levels of missed bins | ##### August 2001 | ##### Achieved | The current rectification rate for missed bins is, 100% rectification within 1 full working day. |

| OBJECTIVE | ACTION | ##### TIMESCALE | POSITION MAY ’03 | COMMENTS |
| --- | --- | --- | --- | --- |
| 100% removal of excess waste | All refuse placed out by residents is now removed | ##### August 2001 | Achieved |  |
| Resolution of non-collection on Bank Holidays | The introduction of the 4-day working week (Tues-Fri has now resolved the issue of non-collection on Bank Holiday Monday | August 2001 | Achieved |  |
| Improve customer relations | All front-line staff receive customer care training | Ongoing | Achieved/Ongoing |  |
| Introduce service between Christmas and New Year | The service between Christmas and New Year was introduced in December 2001 | December 2001 | Achieved |  |
| Reduce the number of missed bins to within the top quartile of Metropolitan Authorities | Significant reductions in missed bins have occurred through improved monitoring by Environmental Co-ordinators | ###### March 2002 | ###### Achieved ###### (based on previous national PI returns 2001/02) | This aimed to be benchmarked against other Metropolitan Authorities as part of the PI system. However this PI has now been abolished, therefore alternative benchmarking procedures will need to be devised Levels of missed bins has fallen from 98 per 100,00 (2001/02) to 9.6 per 100,000 (December 2002) |
| Improve customer consultation | A survey is to be undertaken in October 2002. An Encams survey for street cleansing will also have reference to refuse collection | Ongoing | Achieved | The Environmental Services Directorate has developed a consultation strategy which identifies the amount of consultation each service area needs to carry out. |

## DOG WARDENS

| ### INDICATOR | ### 2001/02 BASELINE | ### 2002/03 TARGET | ### 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| Indicators for this service have only been recently developed and therefore no performance data can be provided, however those proposed are as follows |  |  |  |
| Number of fixed penalties issued | Not Applicable | 50 Successful prosecutions p.a. | Not Available |
| Response time in dealing with a stray dog | Not Applicable | Within 24 hours | Not Available |
| Educational visits per annum | Not Applicable | 13 visits p.a. | Not Available |

| OBJECTIVE | ACTION | TIMESCALE | POSITION MAY’ 03 | COMMENTS |
| --- | --- | --- | --- | --- |
| Implement Dog (Fouling of Land Act) 1996 | The consultation period was begun in April 2002 and following this period, the use of enforcement measures will begin in October 2002 | ##### June 2002 | ##### Achieved |  |
| Establish effective private sector service provision. | The Dog Warden Service was initially placed out to tender and was awarded to Leigh Animal Sanctuary Home. However the contract has now changed provider to Animal Wardens who currently operate the service on behalf of the Directorate. | ##### September 2002 | ##### Achieved |  |

THEMED ISSUES

| INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| Due to this area of the implementation plan still being the subject of inter-Directorate discussions no performance date can at present be provided. |  |  |  |

| OBJECTIVE | ACTION | TIMESCALE | POSITION MAY’ 03 | COMMENTS |
| --- | --- | --- | --- | --- |
| To Remove large amounts of fly-tipping which needs specialist equipment within 10 days of notification. | Such material is either moved via the Directorate itself using heavy plant or an outside contractor when more specialised equipment is needed. e.g. bulk carriers | ##### Ongoing | ##### Achieved Over 90% of all occurrences dealt with within 10 days. |  |
| To remove fly-tipped materials that do not require specialist equipment within 3 days | The directorate removes all such materials using either Refuse Collection or Street Cleansing vehicles and staff. | ##### Ongoing | ##### Achieved Over 90% of all occurrences dealt with within 3 days. |  |
| Re-locate gully emptying crew from Environmental Services Directorate to Development Services. | Discussions are currently being progressed | ##### December 2002 | Achieved |  |
| Relocate drainage crew from Environmental Services Directorate to Development Services | Discussions are currently being progressed | December 2002 | Achieved |  |
| Place weed control under the Environmental Services Directorate by transferring function from Development Services | Discussions are currently being progressed | ##### December 2002 | Achieved |  |