APPENDIX B

POST OFSTED ACTION PLAN MONITORING REPORT

OCTOBER 2000

City of Salford, Education & Leisure Directorate

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 1 In order to provide schools with greater financial autonomy: a) Consultation with schools on fair funding should lead to a greater level of delegation of resources. Aggregate Inspection Grade 4 | Lead Person/s Monitoring Mark Carriline, Director Of Education and Leisure, Edwina Grant, Deputy Director, Education and Leisure, Bob McIntyre, Head Of Finance. |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Termly meetings of the School Funding Review Group (comprising representatives of primary, secondary and special school Headteachers, Governors, Councillors, and Trade union officials) to consider services currently delegated to schools and the proposed delegation of further services. - Monitoring of Section 52 budget statements by the School Funding Review Group. - Wider evaluation of proposals agreed at the School Funding Review Group to take place through programmed meetings with Headteachers. - Review of delegation of resources via Leadership Team and Scrutiny Committee meetings. - Monitoring and Evaluation through the Education Development Plan. |
| Strengths A commitment has been made to raise the level of delegation in the next financial year (Para 32) |  |
| Weaknesses Spending not entirely linked with Council/LEA priorities. Concern about level of delegation and effectiveness of deployment of funds (Para 32). However this judgement does not standout when compared with other LEA's inspected. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Increased delegation of resources. Consideration of delegation of resources for community use. Reduction of small schools factor in the funding scheme. | April 2001 - March 2002 | Level of delegation 86% by April 2000. (1999/2000 figure was 77% for comparison) | Delegation from 77% 1999 to 86% 2000 which exceeds the target for 85% for 2001. Community budget still held centrally. Policy decision needed to determine what is to be done with this budget. Aiming for 2002. The Fair Funding review group has reviewed Small Schools Allowance since April 2000. All schools have received written consultation. Two replies have been received. Schools involved have had a separate consultation meeting and have had a three year transitional plan explained. They have been offered budget planning advice and support for Governing Body meetings. | DfEE Guidance on the Financing of Maintained Schools. Best Value Performance Plan Directorate Service Plan. |
| 1.2 | Further review of delegated areas in the light of the SEN Commission report. | SEN Commission report in July, Action Plan September 2000. Funding consultant September 2000. | Agreement on funding options for SEN by 2001. Implementation of options requiring no policy change March 2001. Those requiring policy change March 2002. | Consultation with schools and other stakeholders, Summer 2000. Links with budget Performance Indicators and Fair Funding, August 2000. Partnership Board in place October 2000. Project groups commence work, October 2000. Looking at proposals for SEN funding. Will work up formulas for one year and will report to the Fair Funding group. | SEN Commission Report Behaviour Support Plan Education Development Plan Best Value Performance Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 2 To raise standards of attainment: - Maximise the delegation of the IAS budget to schools, particularly in relation to training and curriculum support; - Target support and challenge schools to raise the quality of teaching at Key Stage 3, particularly in relation to literacy and numeracy; - Develop a vision and strategy for ICT which is shared with schools and; - Focuses on curriculum support to schools to raise standards of attainments in ICT and other subjects through ICT: - Provides a clear training strategy which enables teachers to meet the government's targets for skill and expertise. Aggregate Inspection Grade 4 | Lead Person/s Monitoring Edwina Grant, Deputy Director, Education and Leisure, Anne Hillerton, Acting Assistant Director, Inspection-Advisory Service, Richard Dodd, Senior Inspector-Advisor, Jane Austin, Excellence in Cities Co-ordinator |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Monitoring via level of buy-back by schools, and level of participation by teachers - Monitoring via the requirements of DfEE and the LEA Key Stage 3 Pilot Plan - Evaluation of strategy development via schools/officers forum - Monitoring via OFSTED report and Inspector-Adviser visits - Annual review of pupil attainment in ICT - Review of progress against EDP targets - Monitoring via EiC strand group - Monitoring and Evaluation through the Education Development Plan. |
| Strengths The LEAs support for Literacy is sound with training rated as satisfactory to good. Progress in raising standards in Numeracy is good. There are pockets of good practice in ICT. |  |
| Weaknesses Results at Key Stage 3 and 4 are below the national average. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Training and additional curriculum support and guidance to be offered to schools on an individual buy back basis specified annually. This will include support for the development of ICT. | September 2000 | Positive evaluation and feedback from headteachers | 86 Primary schools have bought into the LEA's Inservice Training Package. Only 2 Secondary schools have bought into the package. 24 Primary schools have purchased the services of ICT consultant. | Education Development Plan, Standards Fund Information Booklet for Schools, ICT Development Plan |
| 2.2 | Secondary schools will take part in the national pilot for KS3 in literacy and numeracy and have been invited to take part in the Science and Thinking skills extension. All schools will have specific Key Stage 3 targets. Excellence in Cities has specific targets which are indicated in the EDP. Attention will be given to bridging the transition from primary to secondary schools. | September 2000 | Excellence in Cities targets reached. Outcomes linked to evaluation framework for national KS3 project. Successful outcomes from KS3 project pilot schools. IAS will focus on Key Stage 3 in all schools during review visits. | 12 secondary schools are taking part in the Key Stage 3 Pilot in Literacy and Numeracy. The Science and Transforming Teaching and Learning strand is on line to start January 2000. Salford has asked to be one of the 5 Pilots for the ICT strand and is awaiting the result of the application. Inspection-Advisory Service will have completed school level target setting at Key Stage 3 by December 2000. There are 34 primary schools in EiC extension improving technology links with secondary schools Links are being developed with Digital World. | Education Development Plan, Excellence in Cities Implementation Plan |
| 2.3 | A framework for evaluation of ICT practice will be developed. This will be in discrete subject areas and across the curriculum. Links will be made between schools via lead teachers, City Learning Centres and Beacon schools. | Implement Action during Academic year 2000/01 | Service Level Agreement with schools on curriculum support. Focus review by Inspection Advisory Service on school visits. | A framework for evaluation of ICT practice is being developed for use in Autumn 2001. This is linked with recently launched Broadband technology and incorporated with the EiC platform. | Education Development Plan, Excellence in Cities Implementation Plan ICT Development Plan. |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 3 To improve the management and governance of schools: - Share school evaluation reports with governors to assist them in their role of evaluating the work of schools; - Complete and distribute an audit instrument for governing bodies to enable them to complete a self-evaluation of their effectiveness as detailed in the Education Development Plan; - Act swiftly to fill LEA governor vacancies within a stated timescale and encourage all Governors to play a full and equitable role. Aggregate Inspection Grade 4 | Lead Person/s Monitoring Judy Edmonds, Assistant Director, Support Services, Anne Hillerton, Acting Assistant Director, Education and Leisure, Inspection - Advisory Service |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Feedback from termly governing body meeting via minutes and Link Officer attendance - Evaluation of the training provided for governors - Evidence of effectiveness provided via OFSTED reports - Review of progress via Leadership Term and Scrutiny Committee processes - Feedback from school visits by Inspector-Advisers and OFSTED, and from termly governing body meetings via minutes and Link Officer attendance - Direct feedback for governors identifying gaps in their knowledge/expertise - Evaluation of the training programme for governors - Review of progress via Leadership Team and Scrutiny Committee processes. - Monitoring of vacancy levels on a weekly basis by Lead Member and Deputy Lead Member for Education - Monitoring and evaluation through the Education Development Plan |
| Strengths Governors are generally well supported by the LEA, over 95% of schools buy into Governor Training. (Para 67). |  |
| Weaknesses Governors do not as yet receive all the information available on their school's effectiveness. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Revised schools governors' self-evaluation Framework. | July 2000 | New Schedules implemented during academic year 2000/2001 | Framework is being amended again to take account of the new Terms of Reference regulations. Revised framework to be issued November 2000. | Managing for Success, Education Development Plan |
| 3.2 | Inspection and Advisory Service reports to Governors to be revised to take account of the new Ofsted model. | Autumn terms 2000 | New Schedules implemented during academic year 2000/2001 | An annual statement incorporating General Inspector-Adviser visits over the school year September 1999 - August 2000 has been produced for all primary schools. This will be shared with chairs of Governors during the term of Autumn 2000. It will be an agenda item on full Governing Body meetings Spring 2000 and ongoing. The 'Managing for Success' framework is being amended in the light of the new Ofsted model. | Managing for Success, Education Development Plan |
| 3.3 | Training to be offered to governors on the use of the revised models | September 2000 | Training modules receive positive evaluation | Training in the Autumn term has had to focus almost exclusively on Governors' new Performance Management responsibilities. Future programmes will be developed to include self-evaluation. | Managing for Success, Education Development Plan |
| 3.4 | Marketing and Communications exercise to be undertaken to promote the filling of vacancies with a target of less than 7.5% of post vacant overall during the year. | September 2000 | Target to be met by September 2001 Monitoring of attendance and follow up action. | New system in place for making LEA turnover appointments (as a result of council structure). Discussions taking place with Deputy Lead Member (Cllr Sheehy) on marketing strategies. Vacancy levels being monitored on a weekly basis by Director of Education and Leisure, Lead Member and Deputy Lead Member. | Managing for Success, Education Development Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 4 In order to improve levels of service management: - Service team plans should be reviewed to state clearly their contribution to targets in key corporate and educational fields and include costs and measurable and realistic success criteria: - Schools should be provided with a clear definition and specification for each service; details of costs; and methods by which the service is to be monitored and evaluated. Aggregate Inspection Grade 4 | Lead Person/s Monitoring Edwina Grant, Deputy Director, Education and Leisure, Judy Edmonds, Assistant Director, Education and Leisure, Anne Hillerton, Acting Assistant Director, Education and Leisure Directorate, Inspection - Advisory Service, Assistant Director, Pupil Services (to be appointed). |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Annual Review of the Directorate's service planning process by the Strategy Team - Regular review of service plan via Scrutiny Committee - Half yearly monitoring of progress against service team plans by Leadership Team - Monthly review of progress by individual service teams. - Review of approach to service specification by School Funding Review Group, the Services to Schools Group, and the Best Value Review of 'Services to Schools' - Monitoring and evaluated through the Education Development Plan |
| Strengths The monitoring of performance relating to service plans is well managed (Para 78) |  |
| Weaknesses Although team plans adopt a common format, they vary considerably in quality. Some are poor. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Team plans and Service Level Agreement with schools to include information on costs and to clearly state their contribution to Corporate and Directorate Objectives. | September 2000 onwards | A robust planning process. Subject to evaluation by Best Value Review. | Assistant Directors are charged with ensuring their Teams planning and review processes and mechanisms have appropriate links with Corporate and Directorate objectives and that costs to schools information is clear. Best Value Review of Services to Schools includes costs to schools. It will look at Service Level Agreements and information given to schools. Service specifications and costs will be completed by May 2001. Ofsted will inspect the review in Summer 2001. Service Level Agreements with schools need further refinement and detail. Monitoring and evaluation of the quality of Service to Schools needs to be developed and the cost of the infrastructure to support this needs to be considered. | Corporate Plans. Directorate Plans, Best Value Review Plan, All Team Plans |
| 4.2 | Review the Services to Schools Directory to include targets and evaluation criteria. Where services are not delegated, a set of standards will be published. | September 2000 | Evaluation by schools showing improvement on a year by year basis. | The SLA group is taking steps to co-ordinate service marketing and delivery. Some service dealing in a non-traded basis need to be brought into a similar format and discipline. | Corporate Plans. Directorate Plans, Best Value Review Plans, All Team Plans |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 5 In order to improve the effectiveness of special educational provision: - Develop an SEN and Inclusion Policy which is underpinned by the principles of early identification and intervention; - Draft, in consultation with schools, a detailed, long-term SEN strategy - Develop transparent and equitable criteria for allocating resources to pupils and develop monitoring and evaluation arrangements for stages 3-5 of the Code of Practice. Aggregate Inspection Grade 5 | Lead Person/s Monitoring Assistant Director, Pupil Services, (To be appointed). |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Develop an SEN and Inclusion Policy which is underpinned by the principles of early identification and intervention; - Draft, in consultation with schools, a detailed, long term SEN strategy - Review SEN funding with a view to increasing the amounts delegated or devolved to schools; - Develop transparent and equitable criteria for allocating resources to pupils and develop monitoring and evaluation arrangements for stages 3-5 of the Code of Practice. |
| Strengths There are examples of very good initiatives, for example, the development of barrier free and language provision I primary schools with enhanced resources provides excellent examples of inclusive education. |  |
| Weaknesses There is no up to date SEN policy or overall strategy for the development of Special Education. (Para 87). SEN provision is expensive: too much money is spent on a highly centralised service resulting in low cost provision. (Para 98). |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Act upon the outcomes of the SEN Commission. Draft policy document subject to consultation September 2001. | Commission's report due July 2000 | Recommendations of SEN Commission effectively implemented and positively evaluated. Draft Policy document in place. | Team convened November 2000 Terms of Reference agreed. Programmes and schemes of work began. First draft to Leadership Team January 2001. Consultation on new Policy by July 2001. Policy ready for implementation by September 2001. Partnership Board met 25 September. Project Groups Draft Policy with Heads and Senco's, Summer 2000. Modelled Spring 2001. Consultation with schools and other stakeholders Summer Term 2001. | Best Value Performance Indicators Education Development Plan Behaviour Support Plan |
| 5.2 | Consultation with schools regarding further delegation of SEN resources. | April 2001 | Recommendations of SEN Commission effectively implemented and positively evaluated. | Funding Groups meet October 2001. Consultation completed, aiming for April 2002 budget. Links with Budget Performance Indicators and Fair Funding, August 2001. Action Plan ready for delivery and implementation September 2001. Larger changes in delegation to be implemented September 2002. | Best Value Performance Indicators Education Development Plan Behaviour Support Plan |
| 5.3 | To review the Education Welfare Service and implement to outcomes of the review. | Review to be completed May 2000 and implementation of outcomes May 2000 - March 2001 | Effective implementation of the outcomes and positive evaluation. | Working practices in place for September 2000. Structure costs. Interim structure to be implemented January 2001. Working practices changed and awaiting consensus. To go to Cabinet December 2000. New structure for some, January 2000. | Best Value Performance Indication Education Development Plan Behaviour Support Plan Crime and Disorder Strategy Quality Protects Management Action Plan Best Value Performance Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 6 In order to maximise the resources allocated to education: - In consultation with the Dioceses, complete the review of primary places as a matter of urgency; - Take urgent action to significantly reduce the number of surplus places in the secondary sector; - Reduce the level of support provided by the small school protection factor. Aggregate Inspection Grade 6 | Lead Person/s Monitoring Mark Carriline, Director of Education and Leisure, Judy Edmonds, Assistant Director, Support Services |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Monitoring of performance against Best Value Performance indicators relating to surplus places: - Evaluation of the outcomes of the School Review which is currently taking place - Analysis of places by denomination - Monitoring and evaluation of strategies by the School Organisation Committee - Evaluations of funding proposals by Cabinet and Council - Ongoing analysis of school places - Ongoing analysis of school funding and how it is directed. - School Funding Review Group and feedback from consultation with schools on development of the financial scheme. - Monitoring and evaluation through the Education Development Plan. |
| Strengths In the primary sector, a two-part review of surplus places has taken place and is now being implemented. (Para 100). |  |
| Weaknesses There is an unacceptable level of surplus places in Salford schools. (Para 99). |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Agree with the Dioceses a commitment to publish a consultation document leading to a School Review | Publish set of proposals by January 2001. Options from Diocese by September 2000 and proposals by January 2001. | Reduction in the number of surplus places year on year, so contributing to the City's target (see below). | We have jointly looked at some basic premises rationalisation to lead to Standard Number reduction proposals to the School Organisation Committee by January 2000. Federated schools model presently being tested for feasibility. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan |
| 6.2 | Consult upon a review of secondary schools | Produce draft proposals in June 2000. Formal proposals September 2000. Implementation on September 2001. | Reduction in the number of secondary schools. | Draft proposals produced June 2000. Council has agreed to a set of proposals to reduce surplus places. Presently looking at capital funding and other proposals. Proposals to School Organisation Committee at the end of March when funding is secured. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan. |
| 6.3 | Monitor schools with surplus places greater than 16% moving to action at 20% | Ongoing | Reduction in surplus places to an overall level of 8% in the City as at September 2003. | Proposals to reduce surplus places (except RC sector) from 18% to 7%. Primaries to be re-visited. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan. |
| 6.4 | Consult upon the reduction of the small school factor in funding formula | Phased reduction over three years. | Reduction in the small schools factor incrementally over three years. | Consultation has taken place re the reduction of the small school factor in funding formula. A three year transitional plan has been offered to schools as a proposal. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 7 In order to improve the condition of school buildings: - Increase the level of investment in school building maintenance, including the use of public-private partnerships; - Make the priorities for investment transparent and agree them with schools; - Review procedures to ensure that health and safety issues in schools are dealt with within an appropriate timescale. Aggregate Inspection Grade 6 | Lead Person/s Monitoring Mark Carriline, Director of Education and Leisure, Judy Edmonds, Assistant Director, Support Services |
| --- | --- |
|  | Monitoring and Evaluation Strategy - Monitoring of performance against Best Value Performance indicators relating to surplus places: - Evaluation of the outcomes of the School Review which is currently taking place - Analysis of places by denomination - Monitoring and evaluation of strategies by the School Organisation Committee - Evaluations of funding proposals by Cabinet and Council - Ongoing analysis of school places - Ongoing analysis of school funding and how it is directed. - School Funding Review Group and feedback from consultation with schools on development of the financial scheme. - Monitoring and evaluation through the Education Development Plan. |
| Strengths Condition surveys of schools have been carried out and have identified a need for investment of £37 million in the top two priority categories and £48 million in the third. (Para 106). |  |
| Weaknesses The history of poor stewardship has had a serious impact on schools. There are substantial problems with the condition of a number of school buildings. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Using the outcome of the school places review and the evidence of the Asset Management Plan, develop positive responses to reduce the number of schools with accommodation difficulties | Linked to the School places review. | Measures of accommodation suitability show improvement year on year. | AMP condition snapshot data identified maintenance backlog in excess of £111 million. Suitability issues will increase this figure. In response we have secured funds and are investing: - £8 million plus under all NDS rounds which can now address most category 1 works. - Replacement of 3 existing special schools by 1 new special school. - Replacement of 2 high schools with 1 new high school. - 1 primary school amalgamation - PRG approval of 15.1 million points of PFI credits to replace 3 special high schools. In total this will remove over £20 million from the £111 million backlog and a large number of suitability issues. | Asset Management Plan. School Organisation Plan. Education Development Plan |
| 7.2 | PFI initiatives to be continued alongside other bidding strategies the process of bidding to be subject to consultation with schools. | Annual bidding round. | Measures of accommodation suitability show improvement year on year. | See 7.1 re PFI initiative. Further submission for first stage support for PFI credits. Recently submitted a bid for £38.5 million to support secondary school review. Awaiting Government response in November. In principal agreement with schools has been gained. | Asset Management Plan. School Organisation Plan. Education Development Plan. |
| 7.3 | Develop a more robust system to identify health and safety issues and timescales for response. | Revised system by September 2000 | Monitoring shows health and safety issues are identified and dealt with within agreed timescales. | Revised system in Place. All schools contacted and supported regarding production and maintenance of Risk Assessments with target to ensure all schools have appropriate set of Risk Assessments in place by mid November. Health and Safety Officer group established. Meet bi-monthly to review issues arising in schools, Group includes Education Officers, Health and Safety Officers and Health and Safety Officer for the Inspection & Advisory Service. School Security group reviewing Health and Safety issues with Headteachers. System established with Inspection & Advisory Service where Inspector-Advisers pick up Health and Safety issues on their visits and report these to the Inspector-Adviser for Health and Safety. | Asset Management Plan. School Organisation Plan. Education Development Plan. |