## Salford City Council - Record of Decision

I, Councillor Warmisham, Lead Member for Children’s Services, in exercise of the powers conferred on me by Paragraph J(a)(v), of the Scheme of Delegation of the Council do hereby approve

1.	Funding the fit out of the TEN Centre by early August 2009, to maximise the use of the current Morgan Ashurst site set up / continuity of staff, and minimise the cost of:

- Prelims at approx £5,000 per week;

  - Compensation Event claim of approx £30,000; and

  - Re-connection costs of approx £35,000.

2.	the issue of the necessary Authority Notices of Change (ANC) under the PFI 2 	contract.

3.	the wrap up of the FM element as part of Deed of Variation 2.

4.	an Authority Notices of Change (ANC) to allow the screed to be laid over the summer holidays 2009 at a cost of approx £26,000 (budget cost).

The Reasons are to facilitate the fitting out the new TEN Centre.

Options considered and rejected were not to proceed with this decision.

Assessment of Risk - High - The implications for delaying the instruction for fitting out the TEN Centre could result in significant financial penalties to the council, as detailed further in the report.

The source of funding is - Unsupported borrowing as agreed with the City Treasurer.  .

Legal Advice obtained - The full arrangements for the creation and maintenance of the TEN Centre will be subject to a future Deed of Variation under the PFI 2 Contract which will be undertaken via Ian Sheard, Assistant Director, Legal Services.

Financial Advice supplied by Chris Mee, Group Accountant (BSF / PFI)

The following documents have been used to assist the decision process.

(if the documents disclose exempt or confidential information, they should not be listed, but the following wording shall be inserted : "(The relevant documents contain exempt or confidential information and are not available for public inspection)":-

BSF Outline Business Case

Report to Cabinet February 2007

Contact Officer: Kevin Wolstencroft 	Tel No 0161 778 0440

| * The appropriate Scrutiny Committee to call-in the decision is the Children, Young People and Families Scrutiny Committee. |  |
| --- | --- |

Signed:  JD Warmisham  	Dated:  17 July, 2009  .

Councillor Warmisham

Lead Member for

Children’s Services

FOR COMMITTEE SERVICES USE ONLY

*	This decision was published on 17 July, 2009                                               .

*	This decision will come in force on 27 July, 2009 unless it is called-in in 	accordance with the Decision Making Process Rules.