## Salford City Council - Record of Decision

I, Councillor Morris, Lead Member for Children’s Services in exercise of the powers conferred on me by Paragraph J(a)(v), of the Scheme of Delegation of the Council do hereby

Approve the omission of the works to the value of £32,500 to the new playgroup as part of the Lower Kersal Children’s Centre capital contract with Cruden and to approve the addition of the same works to the new playground as a direct order from Children’s Service (Salford City Council) to Hultons (groundworks contractors).

The Reasons are to enable Cruden (contractor) to vacate site sooner and provide cost saving to the Client through the omission of the additional preliminary cost, overheads and profits.

Assessment of Risk: There is minimal risk associated with this matter. In allowing the works to the new playground to be undertaken by another contractor the principal contactor will be off site sooner allowing an earlier project completion.

The source of funding is  Sure Start Capital Grant

Legal Advice obtained  No

Financial Advice obtained  Yes – Michelle Perry,

The following documents have been used to assist the decision process.

(if the documents disclose exempt or confidential information, they should not be listed, but the following wording shall be inserted : "(The relevant documents contain exempt or confidential information and are not available for public inspection)":-

………………………………………………………………………………………………

………………………………………………………………………………………………

……………………………………………………………………………………………….

Contact Officer: Paul Walsh				Tel No 0161 604 7685

PTO

| * This decision is not subject to consideration by another Lead Member |  |
| --- | --- |
| * The appropriate Scrutiny Committee to call-in the decision is the Children Young People and Families Scrutiny Committee. |  |

Signed: …Councillor Morris		Date 21 June, 2010

FOR COMMITTEE SERVICES USE ONLY

*	This decision was published on 22 June, 2010

*	This decision will come in force on 30 June, 2010 unless it is called-in in accordance with the Decision Making Process Rules.