SALFORD CITY COUNCIL - RECORD OF DECISION

I Councillor Bill Hinds Lead Member for Customer and Support Services

in exercise of the powers conferred on me by Paragraph of the Scheme of Delegation of the

Council do hereby

Authorise the progression of the second package of work for the Higher

Broughton Hub Scheme in respect of

- Foundations

- Steel frame

- Pre-cast concrete elements

- Ground floor & toppings

- The Guaranteed Maximum Price for the second package of works is £593,950.63

- The planned start for this package is June 2010, continuing to November 2010.

The reasons are:

- In respect of the Higher Broughton Hub capital project 5 packages of work are

- planned and as agreed Lead Member for Customer and Support Services authorisation

- is required for each package prior to their implementation. The 5 packages are:

- Package 1 Ground Works – [previously approved].

- Package 2 Plateau/Foundations, steelframe and associated items –[current package]

- Package 3 Watertight envelope/Mechanical & Electrical

- Package 4 Fit out works

- Package 5 Demolition/External landscaping/Carpark

Assessment of Risk Low

Legal advice obtained

Financial advice obtained

The following documents have been used to assist the decision process.

(If the documents disclose exempt or confidential information, they should not be listed, but the following wording shall be inserted :"(The relevant documents contain exempt or confidential information and are not available for public inspection)" : -

Contact Officer Andy Howitt……………………………..	Tel. No. 0161 793 2243

PTO

| * This matter is also subject to consideration by the Lead Member for Customer and Support Services |  |
| --- | --- |
| Childrens Services and, accordingly, has been referred to the Lead Member for Childrens Services |  |
| * This decision is not subject to consideration by another Lead Member/Director |  |
| * This document records a key decision, but the matter was not included in the Council's |  |
| Forward Plan and it has been dealt with under the emergency procedure |  |
| * This decision is urgent and is not subject to call-in, in accordance with paragraph 5 |  |
| of the Decision Making Procedure Rules. |  |
| * The appropriate Scrutiny Committee to call-in the decision is the ……………………………….. Scrutiny Committee. |  |

Signed Councillor Bill Hinds		Dated 15 March 2010.

Lead Member for Customer and Support Services.

____________________________________________________________________________________

FOR COMMITTEE SERVICES USE ONLY.

*	This decision was published on 15 March 2010.

*	This decision will come into force on 23 March 2010

unless it is called-in in accordance with the Decision Making Process Rules