SALFORD CITY COUNCIL - RECORD OF DECISION

I Councillor Bill Hinds Lead Member for Customer and Support Services

in exercise of the powers conferred on me by Paragraph of the Scheme of Delegation of the

Council do hereby

Authorise the progression of package 4a of work for the Higher Broughton Hub Scheme in respect of works to the internal fabric of the building comprising of such items as:

  - Fixtures, Fittings & Equipment

  - Sanitary ware

  - Ceiling Finishes (excluding decoration which is contained in package 4b)

  - Floor Finishes (skirting only remainder is contained in package 4b)

  - Internal Doors (excluding decoration which is contained in package 4b)

  - Internal Walls (excluding decoration & tiling which is contained in package 4b)

  - Lift

  - Provisional Sums

- The Guaranteed Maximum Price for the package 4a of works is £565,609.75

- This package of work will commence in November 2010 going through to completion of the main works of the building in June 2010.

The reasons are:

- In respect of the Higher Broughton Hub capital project 5 packages of work are planned and as agreed Lead Member for Customer and Support Services authorisation is required for each package prior to their implementation. Due to the longer procurement & lead – in periods for some of the building fit-out items these works have been priced in advance as package 4a. The 5 packages are:

- Package 1 Ground Works – [previously approved].

- Package 2 Plateau/Foundations, steelframe and associated items – [previously approved].

- Package 3 Watertight envelope/Mechanical & Electrical – [previously approved].

- Package 4 Fit out works – [current package]

- Package 5 Demolition/External landscaping/Carpark

Assessment of Risk Low

Legal advice obtained

Financial advice obtained

The following documents have been used to assist the decision process.

(If the documents disclose exempt or confidential information, they should not be listed, but the following wording shall be inserted :"(The relevant documents contain exempt or confidential information and are not available for public inspection)" : -

Contact Officer Andy Howitt……………………………..	Tel. No. 0161 793 2243

PTO

| * This matter is also subject to consideration by the Lead Member for Customer and Support Services |  |
| --- | --- |
| Childrens Services and, accordingly, has been referred to the Lead Member for Childrens Services |  |
| * This decision is not subject to consideration by another Lead Member/Director |  |
| * This document records a key decision, but the matter was not included in the Council's |  |
| Forward Plan and it has been dealt with under the emergency procedure |  |
| * This decision is urgent and is not subject to call-in, in accordance with paragraph 5 |  |
| of the Decision Making Procedure Rules. |  |
| * The appropriate Scrutiny Committee to call-in the decision is the ……………………………….. Scrutiny Committee. |  |

Signed Councillor Bill Hinds		Dated: 18 October 2010.

Lead Member for Customer and Support Services.

____________________________________________________________________________________

FOR COMMITTEE SERVICES USE ONLY.

*	This decision was published on 18 October 2010.

*	This decision will come into force on 26 October 2010

unless it is called-in in accordance with the Decision Making Process Rules