SALFORD CITY COUNCIL - RECORD OF DECISION

I Councillor Bill Hinds

Lead Member Customer & Support Services

in exercise of the powers conferred on me by Paragraph J(a)(i) of the Scheme of Delegation of the Council do hereby approve

(insert details, continuing overleaf if necessary) ………………………………………….

1.	That the contract for the construction of a MUGA at Beechfarm/Moorside Park, Swinton is awarded to:

Russell Leisure Ltd to the value of £82,560.98

2.	That the contract for the supply and installation of floodlights and associated electrical works to the MUGA at Beechfarm/Moorside Park, Swinton is awarded to

WT Jenkins Ltd to the value of  £21,000

3.	That approval is given for the works to proceed subject to authorization being given by the  Lead Member Customer & Support Services to waive Standing Order Part 4, section 7 and in addition approve the revised capital expenditure forecast.

The reasons are

1.	The contractor previously employed to carry out the works is in voluntary liquidation and has ceased to trade.

2.	Re-authorisation of capital expenditure is required from the Lead Member Customer & Support Services

Options considered and rejected were N/A

Assessment of Risk Low

The source of funding is New Opportunities Fund Fairshare Programme

Legal advice obtained	Yes, JCLI Form of Contract approved for use

Financial advice obtained Yes, additional authorisation required for Capital expenditure from Lead Member Customer & Support Services

The following documents have been used to assist the decision process.

(If the documents disclose exempt or confidential information, they should not be listed, but the following wording shall be inserted :"(The relevant documents contain exempt or confidential information and are not available for public inspection)" : -

The relevant documents contain exempt or confidential information and are not available for public inspection

Contact Officer; Ian Worsley……………………………..	Tel. No 925 1089

PTO

| * This matter is also subject to consideration by the Lead Member Environment |  |
| --- | --- |
| and, accordingly, has been referred to that Lead Member for a decision |  |
| * This decision is not subject to consideration by another Lead Member/Director |  |
| * This document records a key decision, but the matter was not included in the Council's |  |
| Forward Plan and it has been dealt with under the emergency procedure |  |
| * This decision is urgent and is not subject to call-in, in accordance with paragraph 5 |  |
| of the Decision Making Procedure Rules. |  |
| * The appropriate Scrutiny Committee to call-in the decision is the Budget |  |
| Scrutiny Committee. |  |

Key

*	Tick boxes at end of these lines, as appropriate.

Signed  Bill Hinds		Dated 3rd March, 2005.

Lead Member

____________________________________________________________________________________

FOR COMMITTEE SERVICES USE ONLY.

*	This decision was published on 3rd March, 2005...

*	This decision will come into force on 11th March, 2005,……….,

unless it is called-in in accordance with the Decision Making Process Rules

Key

#	Insert date five working days after decision notice is to be published.

REPORT OF: 	DIRECTOR OF ENVIRONMENT

TO: 	LEAD MEMBER FOR CUSTOMER & SUPPORT SERVICES

SUBJECT: 		CONSTRUCTION OF A MULTI-USE GAMES AREA AT 			MOORSIDE PARK/BEECHFARM, SWINTON 

DATED: 		24 February 2005

PURPOSE OF REPORT

1.1 	To seek approval to waive Part 4, Section 7 of the Council’s Constitution 	and continue with the above works. 

BACKGROUND

2.1 	Further to the report submitted to the Customer and Support Services 	Lead Member Briefing on the 18th October 2004 Cotterill Landscapes 	Ltd were employed to undertake the construction of a MUGA at Moorside 	Park/Beechfarm, Swinton in November 2004. Following concerns 	regarding the lack of progress, in accordance with the JCLI Agreement 	for Landscape Works approved by the Head of Law and Administration, 	a default notice was issued on 11th February. On 16th February we 	received a phonecall from Robert Cotterill, the Managing Director of  	Cotterill Landscapes Ltd informing us that he had been placed the 	company into voluntary liquidation. In accordance with the agreement the 	contract was terminated on 18th February.

2.2 	The £105,800 capital budget for the works has been provided by the 	NOF Fairshare Programme and is linked to the achievement of 	milestones within an agreed timescale. It is acknowledged that a re-	tendering process for completion of the works would prevent the works 	being completed within the timescale and will result in a serious 	inconvenience to the users of Beechfarm/Moorside Park.

2.3 	The following quotations have been received for completion of the works:

	Russell Leisure Ltd (Manufacturer of the MUGA) 	£ 82,560.98
	WT Jenkins Ltd (Electrical contractors) 			£ 21,000.00

TOTAL							£ 103,560.98

		Given that the total cost of completion is lower than the original lowest 		tender for the works (submitted and won by Cotterill Landscapes Ltd) 		these prices are clearly competitive.

	2.4	Appendix 1 confirms that if the Council agree to waive Standing Orders 		(in accordance with clause 2.1(a) of part 4 construction works can 			continue with minimum delay.

3.0 	RECOMMENDATIONS

	3.1 	Approval is given to waive clause 2.1(a) of Part 4, Section 7 of the 			Council’s Constitution and proceed with the above works subject to Lead 		Member Customer & Support Services approval of the revised capital 		expenditure forecast

- TENDER APPROVAL - PROFORMA

- For use in seeking the approval of the Lead Member for Customer & Support Services to proceed with a capital proposal

| REPORT TO LEAD MEMBER FOR CUSTOMER & SUPPORT SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Title of Scheme : Multi-Use Games Area Beechfarm/Moorside Park, Swinton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommendations (please append report to Lead Member for Directorate only if preferred) Approval is given to proceed with the above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scheme Details (please append report to Lead Member for Directorate only if preferred) Construction of a multi-use games area at Beechfarm (Moorside Park, Swinton) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender Details (please append report to Lead Member for Directorate only if preferred) N/A Please see attached report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated - Start Date : 1/03/05 Estimated - End Date : 20/05/05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FINANCIAL DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Please see attached report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Breakdown of Scheme Cost : |  |  |  |  |  |  | 03/04 £000‘s |  |  | 04/05 £000‘s |  |  | 05/06 £000‘s |  | Later £000‘s |  | Total £000‘s |  |  |
| Contract |  |  |  |  |  |  |  |  |  |  |  |  | 103,561 |  |  |  |  |  |  |
| Fees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other (Specify) contingency |  |  |  |  |  |  |  |  |  |  |  |  | 2,239 |  |  |  |  |  |  |
| Total Cost |  |  |  |  |  |  |  |  |  |  |  |  | 105,800 |  |  |  |  |  |  |
| 2005/06 only - Phasing of Expenditure (£000‘s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May | June | July | Aug | Sept |  |  | Oct |  |  | Nov |  |  | Dec |  | Jan |  | Feb | Mar |
|  |  | 105,800 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note : The monthly cash flow above should be consistent with the contract start and end dates shown above and should allow for normal time lapses which will occur between work being done, claimed for, certified and paid, as well as retentions. Please consult your Capital Accountant if you need assistance with this or any other part of this proforma. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is Scheme In The Current Approved Capital Programme ? Yes / No |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding Identified : |  |  |  |  |  | 03/04 £000‘s |  |  | 04/05 £000‘s |  |  | 05/06 £000‘s |  |  | Later £000‘s |  | Total £000‘s |  |  |
| Supported Borrowing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unsupported Borrowing (see note 1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grant (Specify) NOF Fairshare |  |  |  |  |  |  |  |  |  |  |  | 105,800 |  |  |  |  | 105,800 |  |  |
| Capital Receipts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other (Specify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Financial Implications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Decision Lead Member Customer & Support Services Approved/Not Approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |